# Attachment 3: California Community Schools Partnership Program Draft Timeline

| **Grant/Contract Type** | 2021–22 | 2022–23 | 2023–24 | 2024–25 | 2025–26 | 2026–27 | 2027–28 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2020–21: Round 1$45,000,000\*Elementary and Secondary School Emergency Relief Fund (COVID) | 20 local educational agencies (LEAs)1 contract | Close Round 1 | N/A | N/A | N/A | N/A | N/A |
| Planning Grants10% = $287,416,400(Up to 1,347 grants available at $200,000 per qualifying entity [QE])Matching – 1/3 | Round 1: Year 1(Up to $200,000 per QE for up to 2 years) | Round 1: Year 2Round 2: Year 1 (Up to $200,000 per QE for up to 2 years) of Planning Grant funds remaining from Round 1 | Round 2: Year 2 | N/A – Only 2 rounds | N/A – Only 2 rounds | N/A – Only 2 rounds | N/A – Only 2 rounds |
| Implementation Grants70% = $2,011,914,800 (Up to $500,000 annually per QE)Matching – 1/3Need to reserve funds for Planning grantees  | Round 1: - QEs (e.g. LEAs) that currently operate Community Schools | Round 2: -QEs that currently operate Community Schools -Round 1 Planning grantees that completed the Planning Grant requirements | Round 3: -QEs that currently operate Community Schools-Round 1 or 2 Planning grantees that completed the Planning Grant requirements | Round 4:-QEs that currently operate Community Schools-Round 2 Planning grantees that completed the Planning Grant requirements | Round 1 and 2 Planning grantees to receive funds | Round 1 and 2 Planning grantees to receive funds | Round 1 and 2 Planning grantees to receive funds |
| Coordination Grants20% = $574,832,800 (Up to $100,000 annually for QEs)Matching – 1:1 | N/A – Starts in 2024–25 | N/A – Starts in 2024–25 | N/A – Starts in 2024–25 | $143,708,200Funds available to QEs | $143,708,200Funds available to QEs | $143,708,200Funds available to QEs | $143,708,200Funds available to QEs |
| Lead Technical Assistance Center (LEAs)$24,000,000 | N/A | $4,000,000 | $4,000,000 | $4,000,000 | $4,000,000 | $4,000,000 | $4,000,000 |
| Regional Technical Assistance Centers (LEAs)$141,833,000 | N/A | $19,638,833At least 5 Technical Assistance Center (TAC) contracts | $19,638,833At least 5 TAC contracts | $19,638,833At least 5 TAC contracts | $19,638,833At least 5 TAC contracts | $19,638,833At least 5 TAC contracts | $19,638,833At least 5 TAC contracts |

Created by the California Department of Education, October 2021. Updated May 2022.