California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

Enclosure - Ravenswood City School District (03-15-10)

Page 1 of 26

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. |  |
| English/Reading-language Arts | Core R/ELA instructional materials (Open Court & Prentice Hall - 2002 SBE-Adoption) continue to be used daily in the overwhelming majority of classrooms across the district. However, there is a need to continue to build teacher capacity with universal access ("workshop" or "UA" in secondary classes) as well as amore robust use of the ancillary materials R/ELA Intensive Intervention (Inside) are being used in the classes identified as Intervention classes for ELA across the district. In order to ensure full implementation, greater support and training is required in an ongoing way. This is being provided by site and district based professional development and coaching (as needed) ELD materials (Avenues [K-5] and Santillana [6-8]) continue to be used in re-grouped classes (by proficiency levels at common times during the school day) with English Learners during designated ELD blocks at all schools Instructional pacing (as indicated in district pacing guides) continues to be followed district-wide (K-8) in the majority of classes with both core and intervention materials The district continues to emphasize student attainment of high-leverage standards and attendant school-wide/classroom data-monitoring practices prompted by a new partnership with Strategic Schooling. This focus has energized site leadership and teachers regarding standards-based instruction and, more importantly, learning among students in R/ELA . |

| Mathematics | Core mathematics instructional materials (Everyday Mathematics (K-5)& Pearson Prentice Hall Mathematics (6th-8th), 2007 Adoption) continue to be used daily in the overwhelming majority of classrooms across the district Mathematics Intensive Intervention (Momentum Mathematics) materials are being used in the appropriate classes across the district where students were identified working 2 years or more below grade level. In order to ensure full implementation, greater support and training is required in an ongoing way. At the semester, students who scored at the "benchmark" level were carefully reviewed by a team (made up of principal, teacher, district coach and staff) to determine 2nd Semester placement. Some students were returned to the core math program and others remain in the intervention to continue to develop math proficiency levels for the remainder of the year. All students in the intervention curricula continue to have their progress closely monitored (every six weeks) by the review team. Instructional pacing (as indicated on district pacing guides) continues to be followed district-wide (K-8) with core and intervention materials District-wide emphasis on student attainment of high-leverage standards continues via attendant school-wide/classroom data-monitoring practices are being prompted by a new partnership with Strategic Schooling and this has energized site leadership and teachers regarding standards-based instruction and, more importantly, learning among students in mathematics/ |
| --- | --- |

| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | Schools continue to generally implement the Nine Essential Program components as monitored by both district, school and DAIT teams. What follows is a specific statement of progress related to each EPC: Schools are implementing the core instructional materials and continue monitoring of implementation of the core materials for fidelity. Universal Access (K-8) is an area of focus for continued growth in most classrooms. The implementation of English Language Development materials in the appropriate classrooms is markedly improved since the last report, with evidence of the use of the district-adopted materials as well as schedules that reflect appropriate time allocations. This component requires constant monitoring for fidelity. The intensive intervention classes in the district in ELA and math have been stabilized and are closely monitored by site administrators, district math coach and literacy coordinator. Student progress checks have been put in place to review student outcomes and placement. All students in the intervention programs are tagged as having participated in these programs so as to track ongoing growth. All schools continue to allocate appropriate amounts of time for R/ELA, Math and ELD, as well as for intensive interventions in R/ELA and Mathematics. District pacing guides continue to be used district-wide (K-8) in the majority of classes with both core and intervention materials. In addition, these pacing guides are reviewed and adjusted as teachers work through the first years of the new curricula. ELD pacing guides must be developed as soon as possible. Administrators have attended materials based professional development in R/ELA and Math core curricula and some have attended training in R/ELA interventions As indicated above (previous section of this report) teachers have attended materials based professional development in R/ELA and Math core curricula as well as interventions. Another team of teachers (25-30) have attended mathematics training during this quarter (bringing the total K-5 to about 50% district-wide). In addition, teachers will begin to work with other San Mateo County K-5 teachers (March-April) to calibrate and collaborate on ongoing implementation concerns that have arisen with initial implementation of the Everyday Math program. The district has academic coaches at the district level in place at all grade levels and for the three core areas to be deployed as needed. In addition, the District has deployed the coaches to the most needy/high-leverage teachers in the schools. Finally, district staff work with site level teachers at "Monday night clinics" to support ongoing instructional planning (lessons) with teachers. Each school in the district The district continues to use the Reading Lions Assessment for monitoring program implementation and student progress (grades K-5) as well as a district-wide standards-aligned benchmark in secondary language arts. Meanwhile, the district also implements mathematics benchmarks three times throughout the year. All of this data is manipulated/ analyzed using the EduSoft data management system. Principals use the data from district benchmark and Reading Lions assessments with teachers in collaborative settings so as to continuously improve the implementation of the core instructional programs. However, continued refinement of these protocols is warranted. Although some schools convene longer interactions among teachers to use data to inform long-term instructional planning, this practice is not evident at all schools sites and must be. Schools continue to engage in goals-based budgeting overall as documented in each school's SPSA. In addition, the district seeks grants and other resources to support the academic program of each school. As an example each school site has a privately funded Reading Recovery teacher assigned to each first grade classroom to intervene early and ensure that more students enter second grade reading on grade level. In addition the Ravenswood Foundation has raised resources to provide an extended day in three of the seven schools whose focus is to provide more time for student support and intervention |
| --- | --- |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | This chart has re-submitted with this report, but has not changed since December 15, 2009 report as the CST has not (obviously) been completed for this academic year. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance District leaders, including local governing board, superintendent, and administrators, will participate in professional development on governance issues District will adopt policies to fully implement Response to Intervention (RtI model) Local governing board will adopt policies for teacher recruitment and retention and for providing and monitoring professional development | Ed Porter (DAIT member) has worked with Board on norms and protocols for meetings. Master's in Governance trainings still need to be scheduled for spring 2010 completion District will convene full-day strategic planning session with all relevant stakeholders on March 17, 2010 to review and revise current (expiring) strategic plan. The outcome of this process will outline focus the district on its major initiatives for the next three years 9000 (C & I-related items) policy review has gone to Board for first reading (used CSBA guidance to inform basic policies) recommendations) with other elements to follow throughout remainder of school year Began the work on RtI, in collaboration with DAIT and RSIP, although not yet in policy - this is an ongoing item There is a need to revisit draft policy on RtI, in particular those related to serving the needs of ELs and SWDs Teacher recruitment is in an item in the RSIP and has been codified into district policy by the board Teacher recruitment and hiring process was revised in Spring 2009 with DAIT support - there are far fewer potential non-re-elect teachers in district thus far this year than there were last year at this time. Further revision to this process will occur this spring, but hiring is expected to be minimal this year, due to budget reductions | Supt. Maria de la Vega and Board president | 2/2009 3/2010 2/2009 Ongoing 2009-10 Ongoing 2009-10 3/2010 5/2010 | ( ( ( ( ( ( ( ( | ( ( ( ( ( ( ( ( |  |  | Some things in draft, some in committees, but progress is moving forward |

| Alignment of Curriculum and Instruction to State Standards The district will adopt and implement SBE instructional materials for all students, including interventions, for all students diagnosed as in need. The district will ensure that schools implement core English language arts (E/LA) and mathematics standards-based instruction The district will implement all Reading First program requirements. | Per Williams audit and verified during visits by SMCOE textbooks are in place in all schools - in core programs as well as interventions. This includes new programs in: Core mathematics programs (K-8) ELA Intensive Intervention grades 4-8 Math Intervention (4-8) Based on formal walkthroughs conducted by district and site leadership as well as DAIT (Jan. and March 2010), core and intervention programs have been verified as being implemented district-wide in all schools and classrooms Although the District lost Reading First funding in the Fall of 2009, district and school leadership continue to pursue high-fidelity implementation & continuous improvement of the core curricula in R/ELA via implementation of the Reading Lions and benchmarks assessment systems | Assistant Superintendent Rosa Molina | 10/2009 9/2009 & ongoing through 6/2009 9/2009 | ( ( ( | ( ( ( |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| The district will provide a tiered intervention system for all students (RtI) based upon multiple measures, including diagnosis for placement, programmatic assignment and criteria for exit. Interventions will be provided for ELs and SWD in ELA and mathematics, consistent with the adopted RtI model, diagnosed language needs and requirements of the Special Education SAM model. The district will provide uninterrupted instructional time in E/LA, mathematics, and interventions | The district has conducted a preliminary in-service of all principals and teachers to understand where interventions lay in RtI pyramid. Additionally, the district has conducted (1/2010) mid-year evaluation meetings with school teams to review each intervention student’s progress and make the necessary program changes as needed. Intensive interventions are in place in every school in ELA and math and are being monitored closely by district and school leadership regarding implementation of instructional materials and acceleration of student progress The district is working with SES providers to focus and improve math support Benchmark assessments are in place, with kindergarten assessments and report cards needing to be re-written and calibrated with new student reporting system (Infinite Campus) Instructional time: core programs are using sufficient time - this has been verified by the DAIT. Variation in time allocations for interventions across schools has been improved since December progress report and now appropriate time is in place at schools The district has extended the day at 3 sites with "soft' money, and will extend to other schools in future (all sites are scheduled to have extended day in the Fall of 2010 if the budget downturn does not negatively impact the budget) | Asst. Supts. Rosa Molina & Adam Escoto | 9/2009 & Ongoing 1/2010 10/2009 2/2009 In prorgress 2/2010 and ongoing 12/2010 in progress and to be completed based on implementation of Infiinte Campus | ( ( ( ( ( | ( ( ( ( ( ( |  |  |  |

| Interventions The district will implement Title III Year 4 requirements as documented on the on-line system to ensure that EL students are appropriately assessed and provided with English language development support. The district will continue to implement and monitor IEP goals that are linguistically appropriate to address the language proficiency needs of EL students, based on the individual student’s disabilities. | Formal Title III monitoring ended last year and received official letter stating that district had met compliance in their Title III plan (which is aligned with LEA Plan). IEP goals: This is an RSIP item, and is monitored by court monitor monthly. Details of compliance with this expectation can be found in those reports | Asst. Supts. Rosa Molina and Adam Escoto | 9/2009 and 10/2009 8/2009 and Ongoing | ( ( | ( ( |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| The district will implement the Ravenswood Self Improvement Plan (RSIP) model with fidelity ensuring that all student interventions are appropriately assigned within the IEP process. | Many, but not all benchmarks are being met in this area at this time. New commitments have been made by staff and CDE and will continue to be tracked by Court Monitor | Asst. Supts. Rosa Molina & Adam Escoto | 8/2009 and ongoing | ( | ( |  |  | It should be noted that it was a number of historically problematic areas were significantly improved in the most recent report from the Court Monitor. The RSIP report can be made available upon request |
| Fiscal Operations Budget revisions will be made on a timely basis and efforts will be made to reduce long-term debt, charter school costs and long term workers compensation claims. Fiscal policies that support sound resource management will be adopted, e.g., carryover, staffing allocations and school budget distributions Fiscal policies will be adopted that align with measurable student achievement outcomes and instructional goals. | RCSD approved and hired a new CBO December 1, 2009 and principals have received their latest budget revisions as of 12/15/09. In the process of reviewing the categorical balances to plan for summer Professional Development (PD), program institutes for students and parent trainings. All of this is predicated on having sufficient budget for completing initiatives | CBO: Meagan Curtis | 11-12/2009 | ( | ( |  |  |  |

| Parent and Community Involvement The district will form a parent involvement committee that meets regularly to identify the needs of parents and community and organize parent functions across the district. | Each school has both School Site Council in accordance to state and federal law as well as a Site English Learner Advisory Committee. The District holds parent meetings on a monthly basis as part of the District English Learner Advisory Committee work. District will convene full-day strategic planning session with all relevant stakeholders on March 17, 2010 to review and revise current (expiring) strategic plan. The outcome of this process will outline focus the district on its major initiatives for the next three years District is convening First RCSD Community Conversation with parent and teacher leadership groups from every site to share the district strategic plan, grade the progress of each school's academic program and parent governance components. This will include completion of a "360- degree" review and action plan for the 2010-11 school year. | Sup. De La Vega | 9/2009 3/17/10 4/17/10 | ( ( | ( ( ( |  |  | It should also be noted that the district held, in conjunction with Supervisor Rose Jacobs and SMCOE at Community Call to Action to continue the process of coordinating community resources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Human Resources The district will ensure that it employs highly qualified teachers and has a plan for the recruitment and retention of these teachers. The district will adopt policies for the recruitment, retention and support of school principals. | Last year at this time, potential non-re-elects numbered 50 teachers; this year, the list has 9 names - this is because of new hiring and evaluation practices implemented in the spring of 2009 Selection and interview of possible new principals will begin at end of March among relevant sites The district has moved toward full implementation of new student information system, Infinite Campus which will be fully operational by July 1, 2010. The system will link with the State’s Cal Pads and also the high schools into which the district feeds Core classes, in order to be compliant with new NCLB HQT requirements, have a May 30 deadline to rename and reschedule every course. This has an impact on RCSD teachers. | James Lovelace, Director of HR | Ongoing 3/31/10 Ongoing | ( ( ( | ( ( ( |  |  |  |

| Data Management and Student Achievement Monitoring The district will implement a student data management system using EduSoft and Reading Lions Assessments The district will develop, implement and monitor benchmark assessments, analyzing data for use in instructional delivery and teacher collaborative meetings. The district will continue to implement ongoing classroom observations used as part of teacher collaboration meetings alongside student achievement data. | The District continues to implement benchmark assessments K-8 (Reading Lions) - this data is used by district leadership, principals and teachers to varying degrees of effectiveness to adjust programs and practices. The district will pursue a new standards-aligned benchmark in the spring 20101 Principals are scheduled to conduct daily and weekly walk-throughs of their teacher’s classrooms while reviewing the implementation of core program. Each principal has been asked to create their own systems for data collection and monitoring feedback. Program Improvement Leads, DAIT team members, New Teacher Mentors and coaches also join the school site principal as they review teacher practices through a walkthrough program monitoring process. District and DAIT have monitored implementation of these walkthroughs and found that principal implementation of this practice is mixed across the district The district has collaborated with the DAIT on implementation of a District Alternative Governance Team (DAGT) protocol on a bi-monthly basis during which site implementation of the district Corrective Action plan is monitored (using observation and achievement data) and feedback is given regarding areas for growth | Assistant Superintendent Rosa Molina | 9/2009 and ongoing 9/2009 and ongoing 10/200912/2009 2/2010 | ( ( ( | ( ( ( |  |  | #1 and 2 is completed and continues. #3 is continues in an ongoing way |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Professional Development Classroom teachers will participate in SB 472 and materials-based professional development on the instructional materials in mathematics and RLA and mathematics interventions in use in their classroom. Eighty hour practicum will be supervised by the DAIT or DAIT-approved staff. Principals will receive coaching from a DAIT-approved instructional provider on standards-based teaching and learning and the principal’s role in supporting it. All site and district administrators will complete the Administrator Training Program. New Teacher Center will continue to provide BTSA support. | 50% of math teachers have attended materials based mathematics professional mathematics from SBE-approved provider All teachers of Inside R/ELA Intensive intervention have been SB-472 trained in the program materials Materials-based PD in OCR is being conducted for OCR for teachers new to the district during winter/spring afterschool sessions There is not currently an SB472 training for Momentum Math, and this has created a problem regarding teacher preparation for this program There are lesson-planning clinics taking place for INSIDE, OCR, and ELD and Every Day Math on a weekly, voluntary basis All math and ELA intervention teachers were convened for 1/2 day sessions in March 2010 to calibrate work and align standards/effort in preparation for the upcoming assessment cycles OCR catch-ups: Literacy coordinators are doing "side by side" work with new teachers in clinics. Teachers get a week's worth of lesson plans every time they attend clinic. In addition, teachers will begin to work with other San Mateo County K-5 teachers (March-April) to calibrate and collaborate on ongoing implementation concerns that have arisen with initial implementation of the Everyday Math program AB430: many principals attended last year or in the past years and are compliant with this require-ment. The new principal to Green Oaks will need to attend this training. ELD The district is folding PD into principal meetings and some additional teacher trainings: Standards Plus, Strategic Schooling (supervision of standards-based approaches), INSIDE, Positive Behavior Support, and RtI | Assistant Superintendents Rosa Molina | 3/15/10 | ( ( ( ( ( ( ( ( | ( ( ( ( ( ( ( ( |  |  |  |
| Other None |  |  |  |  |  |  |  |  |