California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. |  |
| English/Reading-language Arts | Core R/ELA instructional materials (Open Court & Prentice Hall - 2002 SBE-Adoption) continue to be used daily in all (100%) of classrooms across the district as evidenced by district and DAIT team walkthroughs conducted bi-monthly throughout the spring at all school sites. However, there is a need to continue to build teacher capacity with universal access ("workshop" or "UA" in secondary classes) as well as a more robust use of the ancillary materials in over 50% of classes. District personnel continue to hold all principals accountable for monitoring implementation of these curricular programs through walkthroughs and formal/informal feedback to all teachers on a weekly basis. R/ELA Intensive Intervention (Inside) are being used 100% of the classes identified as Intensive Intervention classes for ELA across the district. Teachers met with district-level reading coordinator quarterly to ensure fidelity and alignment of the instruction through the various levels. 100% of the Inside teachers have attended SB-472 (materials-based) training. Site and district based professional development and coaching continue as needed. At the end of the first semester, students who scored at the "benchmark" level were carefully reviewed by a team (made up of their respective school principal, teacher, district coach and SPED staff) to determine 2nd Semester placement. Some students (15%) were returned to the grade-level reading program (if appropriate) and others remain in the intensive intervention to continue to develop ELA proficiency levels for the remainder of the year. ELD materials (Avenues [K-5] and Santillana [6-8]) continue to be used in re-grouped classes (by proficiency levels at common times during the school day) with 100% of English Learners during designated ELD blocks at all schools. New pacing guides were completed in the Spring quarter and will be distributed district-wide in August 2010. Instructional pacing for Reading-Language Arts (as indicated in district pacing guides) continues to be followed district-wide (K-8) in 100% of classes with both core and intensive intervention materials with the exception of the administration of the STAR tests during the testing window in May. The district continues to emphasize student attainment of high-leverage standards and attendant school-wide/classroom data-monitoring practices prompted by a new partnership with Strategic Schooling. This focus has energized site leadership and teachers regarding standards-based instruction and, more importantly, learning among students in R/ELA. Implementation of the "12 Bread and Butter Strategies" prompted by this relationship was enacted at 100% of schools district-wide. |

| Mathematics | Core mathematics instructional materials (Everyday Mathematics (K-5) & Pearson Prentice Hall Mathematics (6th-8th), 2007 Adoption) continue to be used daily in 100% of classrooms across the district. District personnel continue to hold all principals accountable for monitoring implementation of these curricular programs through walkthroughs and formal/informal feedback to all teachers on a weekly basis. Mathematics Intensive Intervention (Momentum Mathematics) materials are being used in 100% of the appropriate classes across the district where students were identified working 2 years or more below grade level. In order to ensure full implementation, greater support and training is required in an ongoing way. At the semester, students who scored at the "benchmark" level were carefully reviewed by a team (made up of principal, teacher, district coach and staff) to determine 2nd Semester placement. Some students were returned to the core math program and others remain in the intervention to continue to develop math proficiency levels for the remainder of the year. All students in the intervention curricula continue to have their progress closely monitored (every six weeks) by the review team. Instructional pacing (as indicated on district pacing guides) continues to be followed district-wide (K-8) in 100% of classes with core and intervention materials in mathematics The district continues to emphasize student attainment of high-leverage standards and attendant school-wide/classroom data-monitoring practices prompted by a new partnership with Strategic Schooling. This focus has energized site leadership and teachers regarding standards-based instruction and, more importantly, learning among students in Mathematics. Implementation of the "12 Bread and Butter Strategies" prompted by this relationship was enacted at 100% of schools district-wide. |
| --- | --- |

| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | All (100%) schools continue to generally implement the Nine Essential Program Components as monitored by district, school and DAIT leaders. What follows is a specific statement of progress related to each EPC: All schools (100%) are implementing the core instructional materials and continue monitoring of implementation of the core materials for fidelity. Universal Access (K-8) is an area of focus for continued growth in many (over 50%) of classrooms. The implementation of English Language Development materials in the appropriate classrooms is markedly improved since the last report (increased from less than half of classrooms in use, to now 90% of relevant classroom use), with evidence of the use of the district-adopted materials as well as schedules that reflect appropriate time allocations. This component requires constant monitoring for fidelity and instructional delivery quality by site administration. The intensive intervention classes in the district in ELA and math have been stabilized and are closely monitored by site administrators, district math coach and literacy coordinator. Student progress checks have been put in place to review student outcomes and placement. All students in the intervention programs are tagged as having participated in these programs so as to track ongoing growth. All (100%) schools continue to allocate appropriate amounts of time for R/ELA, Math and ELD, as well as for intensive interventions in R/ELA and Mathematics. District pacing guides continue to be used district-wide (K-8) in all classes with both core and intervention materials. In addition, these pacing guides are reviewed and adjusted as teachers work through the first years of the new curricula. ELD pacing guides will be drafted in the summer, refined early in the school year and dispensed by the end of Sept. 2010. All administrators have attended materials based professional development in R/ELA and Math core curricula and some (50%) have attended training in R/ELA interventions As indicated above (previous section of this report) all (100%) R/LA teachers have attended materials based professional development in R/ELA core curricula (2002 Adoptions) as well as the intensive intervention (Inside). 75% of teachers district-wide have attended this materials-based professional development in mathematics (2008 Adoptions) as well as interventions. Teachers will be invited to R/ELA & ELD Summer Institutes to continue their professional growth The total number of teachers attending The remaining 25% of teachers of mathematics and any new teachers will be trained in the Fall of 2010. The district has academic coaches at the district level in place at all grade levels and for the three core areas to be deployed as needed. Each of these coaches has been trained in the materials-based PD for which they have content expertise. In addition, two of them are also officially sanctioned/certified trainers of the district's adopted R/LA curricula. In addition, the District has deployed the coaches to the most needy/high-leverage teachers in the schools. The district is writing new grants to secure coaching positions for 2010-11. New funding sources must prioritize coaching support for the schools covered in these grants. The district continues to use the Reading Lions Assessment for monitoring program implementation and student progress (grades K-5) as well as a district-wide standards-aligned benchmark in secondary language arts. Meanwhile, the district also implements mathematics benchmarks three times throughout the year. All of this data is manipulated/ analyzed using the EduSoft data management system. Principals use the data from district benchmark and Reading Lions assessments with teachers in collaborative settings so as to continuously improve the implementation of the core instructional programs at all (100% of schools). However, continued refinement of these protocols is warranted at all schools. Although some schools (three of seven, fewer than 50%) convene longer interactions among teachers to systematically analyze and use data to inform long-term instructional planning, this practice is not evident at all schools sites and must be. The district will purchase a new standards-aligned benchmark assessment system for implementation in the Fall of 2010 along with attendant analysis protocols. Schools continue to engage in goals-based budgeting overall as documented in each school's SPSA. In addition, the district seeks grants and other resources to support the academic program of each school. The district is actively working with the school sites, especially the Schools designated as Persistently Low Performing, to write both a SIG grant and CMSP grant to secure the funding to continue the reform work into the following school year. |
| --- | --- |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | This chart has re-submitted with this report, but has not changed since December 15, 2009 report as the CST has not (obviously) been completed for this academic year. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance District leaders, including local governing board, superintendent, and administrators, will participate in professional development on governance issues District will adopt policies to fully implement Response to Intervention (RtI model) Local governing board will adopt policies for teacher recruitment and retention and for providing and monitoring professional development | Master's in Governance trainings (provided by CSBA) are scheduled for all Board of Trustees members for July 2010. District convened a full-day strategic planning session with all relevant stakeholders on March 17, 2010 to review and revise current (expiring) strategic plan. The outcome of this process was to outline the major initiatives for district-wide implementation for the next three years 9000 (C & I-related items) policy review has gone to Board for first reading (used CSBA guidance to inform basic policies) recommendations) with other elements to follow throughout remainder of school year. The district began the work to better implement the RtI framework throughout the district this spring, in collaboration with DAIT and RSIP, although not yet in policy - this is an ongoing item. There is a need to revisit draft policy on RtI, in particular those related to serving the needs of ELs and SWDs Teacher recruitment is in an item in the RSIP and has been codified into district policy by the board Teacher recruitment and hiring process was revised in Spring 2010 with DAIT support. There are far fewer potential non-re-elect teachers in district thus far this year than there were last year at this time. Further revision to this process will occur this spring, but hiring is expected to be minimal this year, due to budget reductions. Interview teams were formed at the district level for the small number of teacher vacancies, administrative positions and district level administration. There is an improved and more organized hiring process that has yielded 50% fewer non- re-elected teachers. Policy regarding teacher retention and recruitment was revised in the Spring 2010 to reflect current practice. | Supt. Maria de la Vega and Board president | 7/2009 3/2010 2/2009 Ongoing 2009-10 Ongoing 2009-10 | ( ( ( ( ( | ( ( ( ( ( | ( ( ( ( ( |  | Some things in draft, some in committees, but progress is moving forward |

| Alignment of Curriculum and Instruction to State Standards The district will adopt and implement SBE instructional materials for all students, including interventions, for all students diagnosed as in need. The district will ensure that schools implement core English language arts (E/LA) and mathematics standards-based instruction The district will implement all Reading First program requirements. | Per Williams audit and verified during visits by SMCOE textbooks are in place in all schools - in core programs as well as interventions. This includes new programs in: Core mathematics programs (K-8) ELA Intensive Intervention grades 4-8 Math Intervention (4-8) Based on formal walkthroughs conducted by district and site leadership as well as DAIT (Jan. and March 2010), core and intervention programs have been verified as being implemented district-wide in all schools and classrooms. Three formal walkthroughs were scheduled and completed by the Spring of 2010. And weekly walkthroughs are completed and documented by 75% of principals. Although the District lost Reading First funding in the Fall of 2009, district and school leadership continue to pursue high-fidelity implementation & continuous improvement of the core curricula in R/ELA via implementation of the Reading Lions and benchmarks assessment systems. This continues through the 3rd quarter. | Assistant Superintendent Rosa Molina | 10/2009 9/2009 & ongoing through 6/2009 9/2009 | ( ( ( ( | ( ( ( ( | ( ( ( ( |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| The district will provide a tiered intervention system for all students (RtI) based upon multiple measures, including diagnosis for placement, programmatic assignment and criteria for exit. Interventions will be provided for ELs and SWD in ELA and mathematics, consistent with the adopted RtI model, diagnosed language needs and requirements of the Special Education SAM model. The district will provide uninterrupted instructional time in E/LA, mathematics, and interventions | The district has conducted a preliminary in-service of all principals and teachers to understand where interventions lay in RtI pyramid. Beginning June 16, 2010, the district will conduct program evaluation meetings with school teams to review each intervention student’s progress and make the necessary program changes as needed. Intensive interventions are in place in every school in ELA and math and are being monitored closely by district and school leadership regarding implementation of instructional materials and acceleration of student progress. The district is working with SES providers to focus and improve math support Benchmark assessments are in place, with kindergarten assessments and report cards needing to be re-written and calibrated with new student reporting system (Infinite Campus). The student reporting system will be fully operational by August 2010. Instructional time: core programs are using sufficient time - this has been verified by the DAIT. The district plans to extend the day at four sites in 2010. State and local budgetary shortfalls will not allow the schools to extend their days throughout the district. | Asst. Supts. Rosa Molina & Adam Escoto | 9/2009 & Ongoing 1/2010 10/2009 2/2009 In progress 2/2010 and ongoing 05/2010 in progress and to be completed based on implementation of Infinite Campus | ( ( ( ( ( | ( ( ( ( ( ( | ( ( ( ( ( ( |  |  |

| Interventions The district will implement Title III Year 4 requirements as documented on the on-line system to ensure that EL students are appropriately assessed and provided with English language development support. The district will continue to implement and monitor IEP goals that are linguistically appropriate to address the language proficiency needs of EL students, based on the individual student’s disabilities. | Formal Title III monitoring ended last year and received official letter stating that district had met compliance in their Title III plan (which is aligned with LEA Plan). IEP goals: This is an RSIP item, and is monitored by court monitor monthly. Details of compliance with this expectation can be found in those reports The district was prompted by CDE Special Education staff and the DAIT in the fall of 2009 to inform and gain consent from the parents/guardians of students with disabilities who have been included in the intensive intervention courses. District legal counsel and leadership crafted the consent letter and completed this activity (and any warranted follow-up meetings with families/guardians who requested formal meetings) during Feb. 2010 and this process will be done again in the fall of 2010 by Oct. 1. | Asst. Supts. Rosa Molina and Adam Escoto | 9/2009 and 10/2009 8/2009 and Ongoing | ( ( | ( ( |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| The district will implement the Ravenswood Self Improvement Plan (RSIP) model with fidelity ensuring that all student interventions are appropriately assigned within the IEP process. | Many, but not all benchmarks are being met in this area at this time. New commitments have been made (initiated at the Jan. 2010 court appearance) by staff and CDE and will continue to be tracked by Court Monitor. | Asst. Supts. Rosa Molina & Adam Escoto | 8/2009 and ongoing | ( | ( | ( |  | It should be noted that it was a number of historically problematic areas were significantly improved in the most recent report from the Court Monitor. The RSIP report can be made available upon request |
| Fiscal Operations Budget revisions will be made on a timely basis and efforts will be made to reduce long-term debt, charter school costs and long term workers compensation claims. Fiscal policies that support sound resource management will be adopted, e.g., carryover, staffing allocations and school budget distributions Fiscal policies will be adopted that align with measurable student achievement outcomes and instructional goals. | RCSD approved and hired a new CBO December 1, 2009 and principals have received their latest budget revisions as of 12/15/09. In the process of reviewing the categorical balances to plan for summer Professional Development (PD), program institutes for students and parent trainings. All of this is predicated on having sufficient budget for completing initiatives | CBO: Meagan Curtis | 11-12/2009 | ( | ( | ( |  |  |

| Parent and Community Involvement The district will form a parent involvement committee that meets regularly to identify the needs of parents and community and organize parent functions across the district. | Each school has both School Site Council in accordance to state and federal law as well as a Site English Learner Advisory Committee. The District holds parent meetings on a monthly basis as part of the District English Learner Advisory Committee work. District convened full-day strategic planning session with all relevant stakeholders on March 17, 2010 to review and revise current (expiring) strategic plan. The outcome of this process will outline focus the district on its major initiatives for the next three years. District convened its First RCSD Parent Institute parent and teacher leadership groups from every site to share the district strategic plan, grade the progress of each school's academic program and parent governance components. This will include completion of a "360- degree" review and action plan for the 2010-11 school year. | Sup. De La Vega | 9/2009 3/17/10 4/17/10 | ( ( | ( ( ( | ( ( ( |  | It should also be noted that the district held, in conjunction with Supervisor Rose Jacobs and SMCOE at Community Call to Action to continue the process of coordinating community resources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Human Resources The district will ensure that it employs highly qualified teachers and has a plan for the recruitment and retention of these teachers. The district will adopt policies for the recruitment, retention and support of school principals. | Last year at this time, the district chose to non-re-elect 50 teachers; this year, the list has 17 names - because of improved hiring and evaluation practices. Selection and interview of possible new principals will begin at end of March among relevant sites and is on-going. The district anticipates hiring three new site principals. The district has moved toward full implementation of a new student information system, Infinite Campus which will be fully operational by July 1, 2010. The system will link with the State’s Cal Pads and also the high schools into which the district feeds. | James Lovelace, Director of HR | Ongoing 3/31/10 | ( ( | ( ( | ( ( |  |  |

| Data Management and Student Achievement Monitoring The district will implement a student data management system using EduSoft and Reading Lions Assessments The district will develop, implement and monitor benchmark assessments, analyzing data for use in instructional delivery and teacher collaborative meetings. The district will continue to implement ongoing classroom observations used as part of teacher collaboration meetings alongside student achievement data. | The district will purchase and implement a new standards-aligned benchmark system in the spring 2010. Principals were required to conduct and document daily and weekly walk-throughs of their teachers’ classrooms while reviewing the implementation of core program. Each principal has been asked to create their own systems for data collection and monitoring feedback. Principals need continued training on how to provide corrective feedback to teachers needing support. Program Improvement Leads, DAIT team members, New Teacher Mentors and coaches continue to join the school site principal as they review teacher practices through a walkthrough program monitoring process. The district conducted four formal DAGT reviews in conjunction with its DAIT team. Principals were required to share their student progress data and receive feedback from the members of the DAGT team. | Assistant Superintendent Rosa Molina | 9/2009 and ongoing 9/2009 and ongoing | ( ( | ( ( | ( ( |  | #1 and #2 are completed and continue. #3 is continues in an ongoing way |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: San Mateo		Local Educational Agency: Ravenswood City Elementary		Note: Third Quarter Material in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Professional Development Classroom teachers will participate in SB 472 and materials-based professional development on the instructional materials in mathematics and RLA and mathematics interventions in use in their classroom. Eighty hour practicum will be supervised by the DAIT or DAIT-approved staff. Principals will receive coaching from a DAIT-approved instructional provider on standards-based teaching and learning and the principal’s role in supporting it. All site and district administrators will complete the Administrator Training Program. New Teacher Center will continue to provide BTSA support. | 75% of math teachers have attended materials based mathematics professional mathematics from SBE-approved provider All (100%) teachers of Inside R/ELA Intensive intervention have been SB-472 trained in the program materials Materials-based PD in OCR is being conducted for OCR for teachers new to the district during summer. All math and ELA intervention teachers were convened for 1/2 day sessions in March 2010 to calibrate work and align standards/effort in preparation for the upcoming assessment cycles OCR catch-ups: Literacy Coordinators are working with all reading teachers as part of a Summer Institute. ATP: one-two of the three new principals will need to take this training in the Fall of 2010. ELD –One day institute will be provided in August to roll out the new pacing guides to all teachers. The district will continue to incorporate PD into principal meetings and some additional teacher trainings: Standards Plus, Strategic Schooling (supervision of standards-based approaches), INSIDE, Positive Behavior Support, and RtI. | Assistant Superintendents Rosa Molina | 3/15/10 | ( ( ( ( ( ( ( | ( ( ( ( ( ( ( | ( ( ( ( ( ( ( ( |  |  |
| Other None |  |  |  |  |  |  |  |  |