California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

County: Fresno	Local Educational Agency: West Fresno Elementary School District	Third Quarter Additions in Bold

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials, ensuring full implementation in every classroom. | The LEA adopted and purchased SBE adopted core and intervention materials for all classrooms in Mathematics during the 2008-09 school year and replacement materials were purchased for 2009-10. All classrooms have all materials. Report 3: ELA K-5 TREASURES ELA 6-8 HOLT ELA Intervention K-3 TREASURES imbedded and READING FIRST ELA 4-8 READ 180 ELD K-5 TREASURES ELD component 6-8 INSIDE and INSIDE USA Math K-5 HARCOURT California Math 6-8 MCDOUGAL LITTELL, Algebra Course 1,2 Math Intervention Grades 4-5 FAST FORWARD MATH Grades 6-8 FAST FORWARD MATH; AMERICAS CHOICE ALGEBRA READINESS Principal walk through data and academic coach reports indicated core materials are being used in 100% of classrooms The LEA adopted and purchased SBE adopted core and intervention materials for all classrooms in English/Reading-language Arts for the 2009-10 school year and is in process of receiving all materials. Partial orders, late orders, and backorders resulted in “substantially” implemented, with “full” implementation expected by January 2010. Report #2: Full implementation in every classroom, including English/Reading-language arts, ELD, RLA Intervention in grades 4-8, Mathematics, Mathematics intervention in 4-7, and Algebra Readiness for grade 8 |
| English/Reading-language Arts | Report #3: Based on interview feedback from teachers, ongoing reports from academic coaches, and end of the year implementation report from each grade level indicates a high degree of satisfaction with the new materials. Data show higher outcomes than with previous adoption. Preliminary CST data shows significant increase in the number of students scoring proficient in grades 2, 4, 5, 6, and 8. Grade 3 showed a decline and grade 7 showed no change |
| Mathematics | Report #3: With the second year of implementation and instructional coaching, implementation is nearing “fully.” |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | All teachers have participated in the 40 hours of materials-based P.D. for both Mathematics, English/Reading-language arts and English learners during either the 2008-09 or 2009-10 school year. Teachers are in the process of completing the 80 hours of structured follow-up. Report #3: All teachers (except the music teacher) participated in the 80 hour follow up and 86 % of the teacher have turned in documentation 1 of 2 principals been trained been in the new ELA adoption: New teachers and the elementary principal will be trained by submission of the next DAIT report. K-5 TREASURES 6-8 HOLT |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | The 9 EPCs are revisited annually to measure growth towards full implementation. Most areas are “Substantially” implemented with specific steps in place for any area that is “Partial.” Reaching “Full” implementation in most areas is expected by the end of the 2009-10 school year. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | The LEA met 18/21 criteria for AYP (86%) in 2009 compared to 14/25 (56%) in 2007. The LEA has improved by 92 API points in two years (2007 = 572 and 2009 = 664). Both schools are still in PI, but have made similar growth to the LEA. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Fresno	Local Educational Agency: West Fresno Elementary School District	Third Quarter Additions in Bold

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance Continue Board of Trustee training and support by CSBA and state administrator two years beyond permanent superintendent appointment. | Implement FCMAT recommendations CSBA training Implement recommendations and guidance of state appointed trustee | TBD |  |  | X | X |  | Report #3 West Fresno has been under the leadership of a state appointed Trustee since 2003. After the election in 2008, two new Board members were offered training by CSBA which they declined. In 2008, some local powers were returned to the Board, however, in December 2009, a letter from Jack O’Connell rescinded those powers. Currently the Board functions in an advisory capacity only and the state appointed trustee has full authority. CDE and the Fresno County Office of Education assigned a superintendent who handles the day to day operations of the district. The Superintendent from FCOE will continue in that capacity through 2010-11. |
| Alignment of Curriculum, Instruction, and Assessments to State Standards Promote effective instruction through: Pacing guides reflecting essential standards Classroom observations and feedback on effective routines Student motivation and involvement in achievement of standards Effective and timely intervention programs Improve coordination of services: After School and academic intervention Ensure ELs are provided with effective English Language Development (ELD) instruction. | Principal will collect, review, and maintain a copy of all pacing guides. (EPC 3) Principal will maintain a log of classroom observations and feedback provided to ensure effective implementation of the instructional program. (EPC 1) Principal will implement motivation strategies and student involvement practices and provide evidence. Principal will provide evidence of interventions provided for each grade level according to Academic Program Survey. (EPC 1-2) Principal will provide evidence of the coordination of afterschool with academic intervention. Principal will provide evidence of effective ELD instruction and ELD classroom assessment data. (EPC 1-2) | Armando Ayala, Elementary Principal Joey Adame, Middle School Principal | Nov 2009 | X | X | X |  | The principals provided Lead Teachers with release time in May to review the essential standards, update the pacing guides for all courses, and create a benchmark blueprint identifying which standards will be the focus of each trimester. The principals met with the Superintendent for an annual review; specific performance goals were set for 2010-11. Report #3: b. A district classroom observation tool was developed and will be adopted - both principals will use the same tool in 2010-1011. The superintendent has directed the principals to be in the classrooms at least one hour per day, and to provide timely feedback about the effectiveness of instruction. c. Both the elementary and middle school provide motivation and involvement in the achievement of standards. Goal setting and student review of assessments, assemblies, certificates, monthly recognitions, academic dances, student lead conferences and field trips are in place. d. The district has developed a Tiered Intervention Program. Assessment are ongoing and calendared. Grades K-3 use Reading First materials TREASURES imbedded intervention materials. Grade 4-8 use READ 180. The district employs three Interventions teachers to address the need of students failing to score proficient on chapter tests, unit assessments and district benchmarks. Students are identified for intervention using CST, CELDT, and publisher pre and post assessments, as well as teacher recommendation. Intervention classes are fluid and student identification in and out of intervention takes place at the end of each theme, unit, standard, or benchmark. |
| Fiscal Operations The district will establish a process to determine budget priorities based on data (including student achievement data) that will assist staff in making expenditure decisions that will support student learning. | The Business Office will provide a timeline for budget review and decision-making process. (EPC 9) Principals will update SPSA annually | Chris Vaz Joey Adame, Armando Ayala | Dec 2009 | X | X | X |  | The Business Office continues to communicate with principals, district office staff, and the DAIT lead on the budget. Expenditures are monitored to ensure alignment with priorities. |

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Parent and Community Involvement None |  |  |  |  |  |  |  | Report #3: The district has all required parental involvement policies in place per compliance requirements for parental involvement in site councils and advisories. Translation is available at all school/district meetings as per CPM compliance. Opportunities exist at all sites for parents to receive information and participate in school activities. Progress reports, report cards and conferences are in place to inform parents of their child’s academic progress. Communications to parents are provided in their home language. All staff have been trained how to communicate with parents through the district TELL-A-PARENT phone system. |
| Human Resources Improve teacher quality through proven recruitment and retention strategies | Business office will review all teacher credentials to ensure HQT. (EPC 5) | Irma Regalado | Aug 2009 | X | X | X |  | Report #3: Three openings for the 2010-11 school year have been filled with fully credentialed teachers. Both schools are fully staff for the 2010-11 school year with no Intern credentialed teachers. |
| Data Systems and Achievement Monitoring Make effective use of the Data Monitoring system and establish timelines to monitor student progress Monitor the progress of ELs and other significant subgroups | Teachers and principals will be trained on how to use Data Director. (EPC 7) Principals will maintain a progress-monitoring assessment calendar. (EPC 7) Principals will monitor student progress by reviewing disaggregated benchmark results with each grade level and individual teacher. (EPC 7) | Tanya Goosev, FCOE Armando Ayala Joey Adame | Aug 2009 Oct 2009 Nov 2009 Feb 2010 | X | X | X |  | Report #3: 2010-2011 Staff Development days prior to school beginning included training in the use of Data Director-as a review for returning teachers and a introduction for new staff. All teachers K-8 have become much more adept at using Data Director to monitor student progress. In addition, the elementary principal is using Access (database) to track interventions for each student K-5. Principals continue to monitor student progress. |
| Professional Development Provide professional development in SB 472 to implement new instructional programs Provide coaching, job-embedded professional development Provide training on effective collaboration protocols and data analysis | All teachers will complete SB472 in ELD, Math, and ELA. (EPC 5) All teachers will complete the 80 hour practicum. (EPC 5) Staff will be training in effective collaboration protocols (PLCs) and data analysis. (EPC 8) Principals will monitor the products of collaboration to ensure effective implementation. (EPC 8) Principal will facilitate student performance meetings (Teacher Chats) at the end of each Trimester. (EPC 7) Math and ELA coaching will be provided to ensure effective implementation of new instructional materials. (EPC 6) | Tanya Goosev, FCOE Armando Ayala Joey Adame | Sept 2009 Oct 2009 Nov 2009 Feb 2010 All year | X | X | X |  | Report #3: 86% of teachers have completed their 80 hours of follow-up have submitted their portfolios to the district office. The remaining teachers will continue to log their PD activities and will submit completed portfolios by December 2010. New contracts have been signed with FCOE for coaching support in 2010-11. Training for collaboration is scheduled for the staff during the first & last start days in September 2010. Principals will increase monitoring of collaboration to ensure change in classroom practice as the result. |
| Other None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Fresno		Local Educational Agency: West Fresno Elementary

|  | 2007 AYP | 2009 AYP | Difference in % Proficient | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide | 16.4 | 22.1 | 25.5 | 42.0 | 9.1 | 19.9 | Curriculum-imbedded ELA and MATH (combination of publisher’s and teacher-created using Data Director Item bank) | Every 6-8 weeks | District and State data results | End of the year assessments show an increase of about 10% in the number of students scoring proficient and above in Mathematics and an increase of 12% in English-Language arts as compared to end of year assessments in 2008-09. A very positive indicator! | Teachers analyze data in teams, principals conduct “student performance meetings” with each teacher; teachers share data schoolwide, interventions are developed based on results of assessments. |
| African American or Black (not of Hispanic origin) | 8.4 | 12.0 | 22.0 | 28.1 | 13.6 | 16.1 |  |  |  |  |  |
| Asian | 18.3 | 29.4 | 31.3 | 53.8 | 13.0 | 24.4 |  |  |  |  |  |
| Hispanic or Latino | 18.9 | 23.9 | 25.7 | 44.8 | 6.8 | 20.9 |  |  |  |  |  |
| Socioeconomically Disadvantaged | 16.2 | 22.0 | 25.5 | 42.0 | 9.3 | 20.0 |  |  |  |  |  |
| English Learners | 17.3 | 25.9 | 27.9 | 49.4 | 10.6 | 23.5 |  |  |  |  |  |