California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. English/Reading-language Arts Mathematics | The Local Education Agency (LEA) is implementing the 2001-2002 SBE adopted core instructional programs and materials in English Language Arts, including strategic intervention materials. The district is currently using Houghton Mifflin (2001-02) for all K-5 teachers and Prentice Hall for grades 6-8, including ancillary materials for universal access. The district is implementing systematic intensive level intervention to grades 4-8 students indentified as two or more years below grade level. Currently, these students are using High Point by Hampton Brown. All students in grades 4-8, including ELs and SWDs, are given a grade level diagnostic assessment at the end of each school year to screen for intervention needs. Those students that place below 65% on this assessment are placed in intensive intervention, where they take the High Point Diagnostic Placement Inventory to determine placement level in the program. Students scoring 80% or higher on the end of level assessment are exited or regrouped into the strategic intervention program. To qualify for strategic intervention, students that score below 79%, but greater than 65% on the Diagnostic Placement Inventory will receive 30 additional, targeted minutes of instruction using Universal Access. Students are eligible to exit strategic intervention if they score benchmark or above on the 6-8 week theme assessments. Currently there are 79 students in High Point Intervention at grade 4, at grade 5. At grade 6, there are 123 students in High Point. At grade 7, there are 93 students, and grade 8 has 94 students. Selection of the new 2007-08 state adopted ELA textbooks for grades K-8 was completed in December of 2009 and will go to the Board for approval on December 15, 2009. The selected textbooks are as follows: RLA K-6 California Treasures by Macmillan-McGraw-Hill RLA 7-8 California Treasures by Glencoe-McGraw-Hill RLA Intervention 4-8 Inside Language, Literacy and Content Implementation of new materials to begin as early as August of 2010, providing that funds are available. The Local Education Agency (LEA) has implemented the 2007-08 SBE adopted core instructional programs and materials in mathematics, which is Harcourt Brace for K-6 teachers and McDougal-Littell Course 2 for grade 7 and Algebra 1 or Algebra Readiness for grade 8. Teachers fully implement the Kaplan Momentum Math-SBE adopted intensive level intervention program, along with core, for students identified as being two or more grade levels below in grades 4-8. Core ancillary materials are used for strategic intervention. There are 400 grade 4-8 students in Momentum Math, along with their core textbook. The following includes the entry and exit criteria for the intensive intervention program: All students in grades 4-6, including ELs and SWDs, take the diagnostic assessment (Momentum Math Volume 1 Pre-Test) For intensive intervention: Students scoring below 65%, scoring FBB or BB on the CST math test and placing into intensive on the End of Year Benchmark or by teacher recommendation, are placed according to their Momentum 1 Volume 1 analysis. Math intervention for grades 4-6 is an additional 15 minutes beyond core instruction To exit intensive intervention, students must score 51% or higher on the Momentum Math exit test. Students who score between 66-79% on the diagnostic assessment and are BB or B on the CST and strategic on the End of Year benchmark, and/or by teacher recommendation, qualify for strategic math intervention. These students receive targeted instruction using the Momentum Math program for 15 additional minutes above the core program. The results of the placement test are used to determine the correct level of student placement into the program. Students may exit strategic intervention by scoring 81% or higher on the Momentum Math Volume 1 post-test. Students who score 80% or higher on the diagnostic assessment and are proficient or advanced on the CST, and benchmark on the End of Year assessment, use the core textbook with those assessments and work on problem solving skills and enrichment activities using the core ancillary materials for an additional 15 minutes beyond the core. At grades 7-8, all students, including ELs and SWDs, take the Math Diagnostic Testing Project Readiness Assessment (MDTP). For grade 7, students who score below 25% and are FBB or BB on the CST, and are intensive on the End of Year Benchmark or by teacher recommendation, are identified for Momentum Math. Those students then take the Momentum Math entry assessment and are placed in the program by the inventory analysis. Students must score 41% or higher on the Momentum Math exit assessment to exit the intensive intervention program. Intensive math intervention for grade 7 is an additional 30 minutes beyond core math instruction. In grade 7, students who score 26-49% on the Readiness Test and are BB or B on the CST and strategic on the End of Year Benchmark, and/or by teacher recommendation, are placed in math intervention elective for an additional 30 minutes beyond the core curriculum, using the extra support ancillary materials. Students who score 50% or higher on the Readiness Test, exit strategic intervention. Benchmark math students in grade 7 that score 50% or higher on the Readiness Test and are proficient or advanced on the CST, are placed in the McDougal-Littell Course 2 core program. For students entering grade 8, an algebra readiness test is given in the spring. The results of this assessment, along with three years of CST Math scores, and the End of Year benchmark scores, are used to place students in the appropriate math class. Students scoring 75-100%, are in core Algebra. Students scoring 50-74% are in Algebra and receive an extra period of core instructional support every other day. Students scoring 26-49% are in Algebra Readiness, with an extra period of instruction every other day, using the ancillary basic skills support books. There are currently 130 students in strategic intervention. Students below 26% are in Algebra Readiness with an extra period of math instruction daily using the ancillary basic skills support books. There are currently 60 students in intensive intervention. |
|  | MARCH 15, 2010 PROGRESS REPORT The Arvin Union School Board approved the selected state adopted RLA materials for grades K-8 listed in the previous document (see above) on December 15, 2009. At the January 19, 2010 School Board meeting, board members approved to purchase the RLA textbooks for grades 6, 7 and 8 and the Intervention materials for grades 4 through 8 for implementation in August of 2010. These textbooks will include RLA California Treasures by Macmillan-McGraw-Hill for grade 6, to align with the K-5 series, and RLA California Treasures by Glencoe-McGraw-Hill for grades 7 and 8. For Intervention at grades 4-8, the district will purchase Inside Language, Literacy and Content. Due to budget constraints, K-5 California Treasures purchase and implementation is planned for the following school year of 2011. |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | The district has a Professional Development Master Plan for teachers and administrators. It includes a professional development matrix that records all trainings completed by district staff. The matrix is updated by the ELD and math coordinators and reviewed monthly by the Director of Student Services. The matrix is posted on the district SharePoint site for all staff to view. The matrix includes approved activities for the SB 472 practicum hours. The district uses a Professional Development Goal Plan to meet with teachers that have not shown progress in professional development trainings. A course of action is developed betweeen individual teachers and the Director of Student Services to increase attendance in these trainings. The LEA offered three 5-day sessions of both SB 472 math for the 2007-08 state adopted series and ELPD training in summer of 2009. These sessions were open to both administrators and teachers. Currently, the following trainings have been completed: Site Administrators: AB 75/430: 100% SB 472/ RLA or Instructional Materials Based Professional Development: 100% (Houghton-Mifflin) ELPD: 100% SB 472/Math: 90% (2007-08 adoption series) Teachers: SB 472/ RLA or Instructional Materials Based Professional Development: 72% ELPD: 31% SB 472/Math: 32% The LEA is working with the DAIT Lead team to provide further sessions of training during the 2009-2010 school year. To address the need for increased teacher attendance, the district is working with the county schools office to provide 3-day SB 472 training sessions in all the curricular areas. This will include a two day follow-up, in collaboration with the district and the DAIT provider and provided by a knowledgeable and experienced provider. MARCH 15, 2010 PROGRESS REPORT Publishers will train teachers and site administrators in the new RLA series for grades 6, 7 and 8 during the week prior to the opening of the student school year. Grades 4-8 will also receive training from the publishers for Inside, Literacy and Content. This will include all teachers at grades 4-6, and RLA and Intervention teachers at grades 7 and 8. Training for SB 472 in the new RLA series will begin with all teachers in grades 6-8 who teach reading language arts as soon as the training is offered to districts. |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | Standards aligned Curriculum: RLA/ELD Instruction The district provides to all K-5 students, including ELs and SWDs, the Houghton Mifflin SBE 2001-02 state adopted core instructional programs and materials for English/Reading Language Arts, including ancillary materials for strategic interventions. For the students in grades 6-8, the Prentice Hall SBE 2001-02 state adopted core instructional program materials in English/Reading Language Arts, including strategic interventions are used. Universal access is used to differentiate instruction for strategic and benchmark students as part of the core instructional minutes. To incorporate universal access time, an additional 30 minutes of ELA uninterrupted time was added to the daily schedule. Ancillary materials are used during universal access time to focus on individual student needs. Any student, including ELs and SWDs identified for intensive intervention (2 or more years below grade level) in grades 4-8, is placed in the High Point program for RLA for core instruction. SWDs in grades 4-8 as appropriate and required by their IEPs, may use Corrective Reading for core instruction. ELs use the EL ancillary support book from the core program to support English Language Development, as well as daily ELD instruction. For K-5 students, the ELD program is Avenues by Hampton/Brown and for students in grades 6-8, High Point by Hampton/Brown is used. For K-5 SWDs, Avenues is used for ELD instruction. For SWDs in grades 6-8, English Now by Litt-Conn. is used. Students are placed in an appropriate ELD program using data from the CELDT test and Avenues and High Point Placement tests, as appropriate. Selection of new 2007-08 adopted ELA textbooks for grades K-8 was completed in December, 2009 and will be taken to the Board on December 15, 2009. Implementation of new materials will begin as early as August, 2010, provided funding is available. Mathematics Instruction The district provides to all K-6 students, including ELs and SWDs, the Harcourt Brace 2007-08 SBE state adopted core instructional programs and materials for mathematics, including ancillary materials for strategic interventions. The Momentum Math program is used for students in grades 4-8 for intensive intervention support. For the teachers in grade 7, the McDougal-Littell Course II 2007-08 SBE state adopted core instructional program materials in mathematics, including ancillary materials for strategic interventions are used. At grade 8, the McDougal-Littell Algebra I or Algebra Readiness is used. The district developed an intervention program to include both intensive and strategic options based on student need. The plan was disseminated to all staff, and all instructional personnel were trained in early January, 2009. Interventions were implemented at the end of January, 2009. MARCH 15 PROGRESS REPORT The Arvin School Board adopted the selected textbooks for RLA and Intervention at the December 15, 2009 Board meeting. At the January Board meeting, the Arvin School Board approved an implementation schedule for phasing in the RLA and Intervention textbooks beginning with 2010-11. Grades 6-8 will receive the new RLA textbooks and grades 4-8 will receive the Intervention textbooks by August, 2010. Grades K-5 will receive the new state adopted RLA textbooks beginning in August, 2011. Instructional Time: The district has school schedules that ensure all grades have the appropriate time allocation, including universal access and strategic intervention time for their respective grade level, as outlined in the 2007 California State Framework for English RLA. Grade K: 1.5 hours daily including 30 minutes of UA for strategic/ benchmark/enrichment students Grades 1-3: 3.0 hours daily including 30 minutes of UA for strategic/ benchmark/enrichment students Grades 4-6: 2.5 hours daily including 30 minutes of UA for core/strategic/benchmark/enrichment students Grades 4-6: 2.5 hours daily including 30 minutes of UA for out of core intensive intervention students Grades 7-8: 1 to 2.0 hours daily including 30 minutes of UA for core/strategic/benchmark/enrichment students Grades 7-8: 1 to 2.0 hours daily, including 30 minutes of UA for out of core intensive intervention students ELD Instructional time: Grades K-8: 30-45 minutes daily of ELD instruction based on placement tests in ELD curriculum. The district has school schedules that ensure all grades have the appropriate time allocation, including strategic intervention time for their respective grade level, as outlined in the 2007 California State Framework for mathematics Grade K: 30 minutes daily Grades K-3: 15 additional minutes daily using core ancillary materials for benchmark/strategic students Grades 1-8; 60 minutes daily or one period daily Grades 4-6: 15 additional minutes daily in Momentum Math for intensive intervention students Grades 7-8: 30 additional minutes daily for intensive intervention students Grades 7-8: 30 additional minutes every other day for strategic intervention students. MARCH 15, 2010 PROGRESS REPORT Beginning in January, 2010, an additional third hour of intensive intervention was added to the RLA program for grades 7 and 8 for a total of 3 hours of RLA. Instructional Leadership: The district validates that site administrators have completed the following trainings: AB 75/430: 100% SB 472/ RLA or Instructional Materials Based Professional Development: 100% ELPD: 100% SB 472/Math: 90% RTI: 92% of all district administrators All current site administrators will complete the SB 472 Instructional Materials Based Professional Development 40 hour training for the newly adopted 2007-08 RLA textbooks, once they are purchased and implemented and the trainings are available. The one remaining site administrator will complete the SB 472 Instructional Materials Based Professional Development 40 hour training for the newly adopted and implemented 2007-08 mathematics textbooks by August, 2010. MARCH 15 PROGRESS REPORT All district administrators (100%) have received training in the Response to Intervention, (RTI) Model for instruction. Teacher Professional Development: The Arvin Union School District currently employs 100% of Highly Qualified Teachers in the district under Title II. Teachers have received training in the following: SB 472/ RLA or Instructional Materials Based Professional Development for Houghton Mifflin 2001-02 adoption: 72% ELPD: 31% SB 472/Math or Instructional Materials Based Professional Development for the 2007-08 adoption for K-8: 32% The LEA is working with the DAIT Lead team to provide further sessions of training during the 2009-2010 school year. To address the need for increased teacher completion, the district is working with the county schools office to provide 3-day SB 472 training sessions in all the curricular areas, including ELPD. This will include a two day follow-up collaboratively organized by the district and the DAIT provider, to ensure the required hours are met. The district provides the following to support professional development: Bi-weekly collaboration time is provided to teachers to review and discuss student achievement results to plan and adjust instruction. Special education teachers meet one time per month with one another and also with grade level or content area teachers. b. Teachers have been trained in the use of universal access including the use of ancillary support materials. c. Teachers have received training in specific researched based strategies appropriate for SWDs and ELs, including content and language objectives, linguistic frames, graphic organizers, and academic language scaffolding. d. Due to budget restraints and the reduction of one coach per site, the district has made the following adjustments to support staff: Use the coaching cycle to provide in-classroom support In addition to the coaching cycle, teachers or site administrators, through their classroom observations, may request additional support The district fully implements the BTSA support provider program for all new staff that qualify The district uses the UCLA Teacher Observation Protocol to support in-classroom instruction with sites debriefing to learn together and make instructional adjustments The ELD and math coordinators provide model lessons and present professional development trainings on district priorities Two days of professional development is given each August prior to the beginning of school e. The district consolidated its data reporting system, OARS, to include grades K-8. All staff has received training in this district wide data system f. The district offers support to sites requesting further assistance in the use of prescriptive tools for modeling of best practices. MARCH 15, 2010 PROGRESS REPORT The district has continued to make progress toward the completion of 100% of staff trained in ELPD. As of March, 2010, 60% of the staff have received this training. District-wide grade level articulation was scheduled beginning in January, 2010, for grade levels and site administrators to share best practices with their grade level peers across the school sites. Coordinator and site coaches have been working with targeted grade levels to complete lesson studies and increase the use of appropriate instructional strategies in areas of need as identified by benchmark data. All lesson studies will be completed by June. Currently, two of the six targeted grade levels have completed their lesson studies. A follow-up OARS training, (district wide data system) was completed in February by the math coordinator for all middle school staff. Student Achievement Monitoring System: In August of 2009, the district implemented OARS, an electronic, district-wide data management system to uniformly administer, score and analyze student achievement data in a timely manner. The common curriculum embedded/formative assessments are given every 6-8 weeks as defined by the grade level pacing guides. Teachers have been trained on the use of the data system, and are able to collect, disaggregate and determine student placement and diagnosis of student needs. All assessment data, including formative, curriculum embedded, and summative, is available to district and site administrators, coordinators and teachers. Time is scheduled on a bi-monthly basis for teachers to collaborate and identify student needs, and to design instruction and intervention lessons. MARCH 15, 2010 PROGRESS REPORT The follow up OARS training was held in February, 2010. Instructional Assistance: Instructional assistance to support teachers is provided by academic coaches, coordinators and site administrators. The instructional assistance includes training in best practices, teacher planning and collaboration, student goal setting, progress monitoring, data analysis and intervention placement and monitoring. The coaches and experts assist with the full implementation of the district’s current SBE-adopted RLA/ELD and intensive intervention instructional programs to improve student achievement. The district coaches are trained in and knowledgeable about all current adopted curricular programs in the district and work with teachers of all students including SWDs and ELs. The coaches provide in classroom coaching support through modeling of lessons as needed, based upon teacher request or recommendation of the site administrator. The ELD and math coordinators are also available to model lessons and present trainings in use of data for instructional design, and academic coaches use the coaching cycle which includes modeling a lesson, debriefing with teachers, observing a lesson and a second debrief, to train teachers in modifying instruction to meet the needs of all students. District administrators provide leadership professional development to all site administrators ensuring they have the skills to monitor and support the full implementation of the EPCs. This is done on a bi-monthly basis through the Administrative Cabinet meetings. The UCLA Teacher Classroom Walkthrough Protocol has been introduced this year. The protocol is used by the sites to develop a targeted focus and observe and debrief together for developing improved instruction. By consolidating the district’s data system in K-8 to OARS, ease of use and interpretation of results has been simplified for all teachers. The district also employs the BTSA program to support new staff. MARCH 15 PROGRESS REPORT No new actions to report at this time Teacher Collaboration: Teachers meet collaboratively to strengthen the implementation of the district’s current SBE-adopted instructional programs for all students, including ELs and SWDs. These bi-monthly collaboration meetings by grade level or by program cover the following: Review placement and exit criteria for intervention programs Provide differentiated lesson design Progress monitoring which includes frequently analyzing formative and curriculum embedded benchmark assessments Teachers have been trained in the components for Professional Learning Communities. A team from each site in the district is currently attending a 5-day PLC Training through KCSOS as a follow-up to the initial training. Prior to the bi-monthly Collaboration meetings held at the sites, grade level teams or program teams submit an agenda to their Principal for approval or suggestions. Site administrators further review all minutes and notes following the PLC meetings, to ensure the effectiveness of data analysis and lesson design. MARCH 15, 2010 PROGRESS REPORT Site Administrators are requiring each grade level to revisit or revise established norms for their professional learning communities, (PLC’s). Site Administrators monitor the effective functioning of their PLC’s through grade level agendas, minutes, smart goals and use of data. All agendas are pre-approved by the site administrator and results are shared at the conclusion of the meeting. Pacing and Scheduling: The LEA has reviewed all school schedules to ensure that all grades have the appropriate time allocation, including universal access and strategic intervention time for their respective grade level as outlined in the 2007 California State Framework for RLA and ELD: Grade K: 1.5 hours daily Grades 1-3: 2.5 hours daily Grades 4-6: 2.0 hours daily Grades 7-8: 1 to 2.0 hours daily Grades K-8: 30-45 minutes daily for ELD Appropriate time allocation for mathematics is as follows: Grade K: .5 hours daily Grades 1-6: 1.0 hours daily Grades 7-8: 50-60 minutes daily There is a standards-based, district-wide pacing guide that includes curriculum-embedded, formative and summative assessments, for each grade level and each adopted program, including intervention. All teachers are systematically using their grade-level pacing guides to administer common formative, curriculum-embedded assessments in RLA and mathematics, a minimum of every 6-8 weeks. Pacing guide use is monitored by classroom observations, daily site administrator visits recorded on a walk-through log, and district visits recorded through observation notes and next steps. MARCH 15, 2010 PROGRESS REPORT Beginning in January, 2010, an additional third hour of intensive intervention was added to the RLA program for grades 7 and 8 for a total of 3 hours of RLA. Fiscal Support: The LEA has a fiscal policy and a resource allocation plan to fully implement the 9 EPC’s in regards to RLA and mathematics instruction. Site administrators receive and review their site budgets with the District Accountant on a monthly basis. The LEA annually reviews the LEA plan and single school plans to verify that the budgets align with the goals of the district. The LEA ensures that the most restricted funding is appropriately expended in accordance with federal and state guidelines, prior to using unrestricted funds. MARCH 15, 2010 PROGRESS REPORT The single plans for student achievement (SPSA’s) for all four school sites were approved by the Arvin Union School Board in January, 2010. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | In 2009, Sierra Vista Elementary and El Camino Real Elementary met their AYP in ELA, and Bear Mountain Elementary met their AYP in mathematics. The chart below displays an overview of district and individual site scores for API and AYP for 2008 and 2009. 2009 AYP Status At a Glance Targets Met Title I Program Improvement AYP ELA AYP Math District 12 of 21 Yes Yes No No Sierra Vista Elementary 13 of 17 Yes Yes Yes No Bear Mountain Elementary 13 of 17 Yes Yes No Yes El Camino Real Elementary 12 of 17 Yes Yes No No Haven Drive Middle School 9 of 17 Yes Yes No No 2006-07 Through 2008-09 District and Schoolwide API Overviews 2006-07 Base API 2006-07 Growth Met 2006-07 API 2007-08 Base API 2007-08 Growth Met 2007-08 API 2008-09 Base API 2008-09 Growth Met 2008-09 API District 613 624 (11 points) Yes 624 650 (26 points) Yes 653 658 (5 points) Yes Sierra Vista Elementary 639 647 (8 points) Yes 645 649 (4 points) No 647 650 (3 points) No Bear Mountain Elementary 607 617 (10 points) Yes 618 626 (8 points) No 629 653 (24 points) Yes El Camino Real Elementary N/A N/A N/A N/A 708 N/A 707 700(-7 points) No Haven Drive Middle School 600 616 (16 points) Yes 615 642 (27 points) Yes 648 642 (-6 points) No |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance Develop and implement a plan to provide systematic intervention in reading/language arts and mathematics until the 2007 math and 2008 reading/language arts adoptions are selected and implemented. This plan will include district policies related to the instructional materials to be used and the assessment, identification, placement and monitoring of strategic and intensive-level intervention for all students in grades 4-8 in reading/language arts and mathematics. 2. Create a plan to systematically implement the 2007 mathematics adoption and the 2008 reading/language arts adoption so that all students will be served appropriately, including English learners (ELs), students with disabilities (SWD) and those identified as needing strategic or intensive-level intervention. 3. Develop and implement policies related to instructional materials, instructional time and the use of pacing guides to fully implement the related Essential Program Components (EPCs). 4. Develop and implement an instructional monitoring plan to align district polices with school-site practices and procedures to ensure that the nine EPCs are fully implemented. This plan should include, at a minimum: Daily classroom observations by site administrators as well as bi-monthly targeted classroom walk-throughs of district and site staff. A district protocol for providing teachers feedback after classroom observations. A district protocol to ensure implementation of professional development activities to support on-going classroom application. A district protocol for progress monitoring of data, at least quarterly, that would also include a semi-annual review of student placement into or movement out of intervention programs. A district protocol for monitoring the grade-level/department-level collaborative meetings. | 1. The district’s leadership team (DLT) developed and disseminated a written plan outlining polices and protocol for the identification, placement, instruction and monitoring in RLA and mathematics of all strategic and intensive-level students. The DLT is composed of the superintendent, the assistant superintendent and the Director of Student Services. The DLT met with the district/site leadership team, (DSLT) to review and finalize the intervention plan. Training sessions were held at the sites prior to implementation. The District Board approved the LEA plan which included the systematic intervention in RLA and mathematics. MARCH 15 PROGRESS REPORT In January, 2010, the intervention plan was revised in both RLA and math to include the following: The Assistant Superintendent and DAIT Lead met with each site principal individually to review their school’s disaggregated benchmark data and develop next steps for their staff. The district will ensure that site administrators monitor strategic and intensive intervention in RLA and math by walk-through logs, debriefing of collected evidence and evaluating benchmark and diagnostic data to ensure that all students receive targeted intervention as determined by district entrance and exit criteria. Principals will monitor and update intervention class lists to guarantee accurate student placement. 2. The DLT developed action steps within the LEA Plan to fully implement the 2007 mathematics adoption. The action steps include systematic implementation of strategic and intensive intervention as well as instruction for ELs and SWDs. The DLT also developed a process, outlined in the action steps of its LEA Plan, to review the 2008 SBE-adopted RLA materials for implementation. The process to adopt included the collaboration of district/site administrators, teacher teams, instructional leaders and coaches from all schools in the district. 3. The DLT collaboratively developed an Instructional Materials Usage Policy for RLA and mathematics. This policy included district expectations and procedures related to instructional materials, instructional time and the use of pacing guides. This policy was reviewed in depth with site leadership and disseminated to all staff. MARCH 15 PROGRESS REPORT No new actions to report at this time. The DLT developed a written plan for monitoring of instructional programs. The plan was reviewed with the DSLT and disseminated to all staff. The monitoring plan included the following: Daily classroom observations by site administrators Bi-monthly District Walk-throughs A protocol for providing teachers feedback A professional development master plan details student placement into or out of intervention programs. District protocol for progress monitoring of data. District protocol for monitoring collaborative meetings. | Superintendent, Assist. Supt., Director of Student Support Services, Site Administrators Superintendent Assist. Supt., Director of Student Support Services, Site Administrators Superintendent, Assist. Supt., Director, Principals, Coordinators, and Coaches SuperintendentAssist. Supt., Director, Principals, Coordinators, and Coaches Superintendent, Assist. Supt., Director, Principals, Coordinators, and Coaches Superintendent, Assist. Supt., Director, Principals, Coordinators, and Coaches Superinten-dent, Assist. Supt., Director, Principals, Coordinators, and Coaches | 1/09 1/10- 6/10 8/09 Math 8/10 RLA 8\/09 8/09 1/10- 6/10 | X X 12/09- 8/ 10 X X | X X X x |  |  | Steps for implementation were written in the LEA plan. This plan was Board approved on September 16, 2008. Implementation of the intervention programs for RLA and mathematics in strategic and intensive intervention began on January 12, 2009. The plan was revisited and revised in January, 2010. The revision is currently being implemented. The 2007 SBE-adopted math instructional materials for core, strategic and intensive intervention are being fully implemented. SBE-adopted ancillary materials are used daily for ELs and SWDs. 32% of teachers have completed the instructional materials professional development for the 2007 adoption. A plan is in place to complete training by August, 2010,for the remaining teachers. The 2008 RLA materials have been selected and will be adopted by the local board on December, 15, 2009. The purchase and implementation timeline will be based upon available funding and the goal is to fully implement in August, 2010. MARCH 15 PROGRESS REPORT RLA and Intervention textbooks were approved by the Local School Board on Dec. 15, 2010. At the Jan. 19 Board meeting, the plan for implementation was Board approved. California Treasures for grades 6-8 will be purchased and implemented by August, 2010 for grades 6-8, and Inside, Literacy and Content for grades 4-8 will be purchased and implemented by August, 2010. Grades K-5 will be purchased and implemented for the following year, beginning in August, 2011. The district updates the Instructional Materials Use Protocol periodically, as needed. The last update was done on April 1, 2009. The district disseminated the Instructional Materials Usage Protocol to staff in August, 2009 at the time the District Course of Study is posted on the district website. District and site administration monitors this protocol by lesson plan review, observations and the annual Williams Review. Principals submit classroom walk-through logs as evidence of daily observations on a monthly basis to the Director of Special Services for review. District walk-throughs were calendared for all sites in August, 2009. Teachers are provided written feedback after classroom observations by Principals and district staff. The Professional Development Master Plan includes a matrix outlining training activities for each teacher. The matrix is reviewed monthly by district administrators. District coordinators and site coaches provide support for ongoing classroom application of professional development activities by teacher request or site administrator recommendation. Benchmark data is reviewed every 6-8 weeks by teachers as well as district and site administrators. The district monitors teacher collaborative meetings through site administrator review of agendas and minutes from each meeting. MARCH 15 PROGRESS REPORT In January, 2010, additional monitoring protocols were added to the LEA Plan as listed below: 1.Trainings, using the FRISK model, have been provided to site administrators in having necessary conversations with teachers at administrative cabinet meetings held twice a month. Non-negotiable expectation talks have begun with site principals, as well as talks to discuss non-negotiable expectations for teachers. Working sessions have been scheduled with individual site administrators to improve areas of strength in individual leadership skills. 2. Site administrators are identifying and supporting teachers with the greatest need based on class visits and student data. 3. Site administrators will ensure that required student data is input into the district data system by the specified due date. Monitoring protocol for collaborative meetings has been increased by the following: 1.Assistant Superintendent and DAIT Lead have met with site principals on an individual level to review data and set up next steps for the teacher collaborative meetings. 2. District wide articulation meetings by grade levels have been held to discuss best instructional practices with grade level peers. (Mining for Pockets of Gold) 3. Interim Smart Goals have been set to monitor student progress between student assessments. 4. Principals have stepped up the monitoring of the professional development matrix to have individual teacher conversations in planning their professional development. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Alignment of Curriculum, Instruction, and Assessments to State Standards Provide a continuum of program options in reading/language arts, English Language Development and mathematics to meet the needs of all students, including SWD, ELs and students in need of strategic and intensive-level intervention. The continuum should include: A master plan for the identification, placement and instruction of all strategic and intensive-level intervention students with specific entrance and exit criteria for flexible grouping and assessments for progress monitoring. Providing all teachers, including special education teachers and teachers of ELs, with all board-adopted core and district-approved ancillary materials for their respective instructional programs, including intervention. Providing all teachers with professional development in their respective materials as appropriate to their assignment. The use of standards-aligned academic assessments as well as diagnostic assessments in making initial placement decisions and for continuously monitoring the performance of students with disabilities. Providing standards-aligned instructional materials as appropriate to students’ present levels of performance and the goals and objectives in student individualized educational plans (IEPs). | The district developed a comprehensive master plan for intervention for all students in RLA and mathematics. The plan includes a continuum of program options for all students by grade level, including EL’s and SWD’s. The plan details specific entrance and exit criteria for flexible grouping in RLA and mathematics. All teachers, including EL and SWD teachers, have and use Board adopted core and district approved ancillary materials, for their respective instructional programs, including intervention. These materials are detailed in Part A, Section 3, #1, Standards Aligned Curriculum. Teachers are provided Instructional Materials Professional Development as outlined in the Professional Development Master Plan. Students with disabilities, (SWDs) are provided a continuum of program options based on need as identified by standards-aligned, academic and/or diagnostic assessments. Standards-aligned instructional materials are provided to SWDs based on student IEP goals and objectives. | Superintendent, Assist. Supt., Director, Principals, Coordinators | 1/09 | X | X |  |  | A continuum of program options and instructional materials is in place in RLA and mathematics for all students, including ELs and SWDs. The options are outlined in the Board approved LEA plan. These options for RLA include SBE adopted core and ancillary materials, including intervention and ELD from the 2001-02 adoption. For SWDs, standards aligned Corrective Reading materials may be used, based on student needs. For mathematics, the continuum of program options includes 2007-08 SBE adopted core, ancillary and intervention materials. MARCH 15 PROGRESS REPORT No new actions to report at this time. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Ensure that site administrators and all teachers of special education students participate in the development of IEPs and IEP meetings for students to whom they provide services Provide biweekly grade level/department collaboration time for general education and special education teachers to review assessment data and plan reading/language arts and mathematics instruction to meet the needs of all students. | The district developed a process to ensure that all teachers of SWDs and site administrators participate in the development of student IEPs. MARCH 15 PROGRESS REPORT No new actions to report at this time The district established bi-weekly collaboration time for all teachers. The district also developed a protocol for teachers to review assessment data and plan RLA and mathematics instruction during the collaborative meetings to meet the needs of all students. MARCH 15 PROGRESS REPORT No new actions to report at this time | Director of Student Services, Principals, District Psychologists Supt, Assist. Supt., Director of Student Services | 8/08 8/08 | X X | X X |  |  | The IEP process includes IEP goals being developed collaboratively amongst all stakeholders with all required participants attending IEP meetings. The District’s psychologists monitor each IEP upon its completion to ensure that all required participants were in attendance. Special Education teachers meet one time per month together, and one time per month with grade level general education teachers. Assessment data is reviewed at all collaborative meetings. Academic coaches have provided training on the use of data. Site teams from Sierra Vista Elementary and Bear Mountain Elementary attended the Data Team Training provided at KCSOS in Fall, 2009. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Fiscal Operations The district will create fiscal policies and a resource allocation plan to fully implement the nine EPCs in regard to reading/language arts and mathematics that includes the following actions: Provide site administrators with monthly budget reports. Require site administrators to review the budget reports on a monthly basis. Annually review the LEA Plan and the Single School Plans for each school site to verify that the budgets align with the goals in the LEA DAIT Plan. Ensure that the most restricted funding is expended in accordance with federal and state guidelines prior to using unrestricted funds. | a.The district accountant meets monthly with site administrators to review monthly budget reports. b.The superintendent developed a protocol to ensure site administrators review their monthly budget reports with the district accountant. c. The district reviews the single school site plans to ensure alignment with the LEA plan. The District Board annually approves all district and school site plans. d. The district accountant reviews practices regarding distribution of funds to ensure all expenditures are in accordance with federal and state guidelines. | Supt, District Accountant Assistant Superinten-dent | 8/09 1/10 | X | X |  |  | The district accountant provides site administrators with monthly budget reports which are reviewed collaboratively. The district accountant consults with Kern County Superintendent of Schools Department of Fiscal Services to stay current with all funding guidelines. The local Board is scheduled to approve the revised district and school site plans in January, 2010. MARCH 15 PROGRESS REPORT All single plans for school achievement (SPSA’s) were approved at the January 19, 2010 Arvin School Board meeting. |
| Parent and Community Involvement None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Human Resources Ensure that all site administrators complete the Senate Bill (SB) 472 training for any future reading/language arts and mathematics adoptions implemented at their school. Ensure that all site administrators hired in the future complete the Assembly Bill (AB) 430 principal’s training, including practicum hours. Ensure that all site administrators attend and complete the English Learner Institute for Administrators and the SB 472 English Learner Professional Development program. Ensure that all site administrators are trained on the implementation of programs for students with disabilities and Response to Intervention. | 1. The DLT developed a protocol to monitor the professional development of site administrators 2. The protocol includes steps to train all future site administrators in AB 430 Principal training as part of the job criteria 3. This protocol includes the Professional Development Master Plan and a matrix for tracking the completion of professional development activities for site administrators. 4. The master plan includes instructional materials professional development training including practicum hours as well as ELPD and Response to Intervention. | Supt., Assist. Supt., Director of Student Services Supt., Assist. Supt., Director of Student Services | 8/08 12/09 | X | X |  |  | Currently, 100% of the site administrators have completed professional development training in ELPD and the 2001-02 RLA adoption. Of the site administrators, 90% have completed the instructional materials based professional development for the 2007-08 mathematics adoption as appropriate to their assignment. The master plan outlines how the remaining and future professional trainings will be completed. See Part A, Section 2 for reference. MARCH 15 PROGRESS REPORT As of December, 2009, all site administrators (100%) have been trained in the Response to Intervention (RTI) model. |
| Data Systems and Achievement Monitoring None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Professional Development 1.Develop and implement a professional development plan that will include: a. A matrix detailing SB 472 trainings in reading/language arts, mathematics and English Learner Professional Development (ELPD), with a system for tracking the completion of the various professional development activities for all teachers in the district. b. A listing of approved activities for practicum hours and district documentation of completion. c. Individual goals/plans for teachers who have not completed the SB 472 initial and practicum hours in reading/language arts, mathematics and ELPD. d. A detailed description of how the district will support and train new teachers in the curriculum materials they will be using. Site administrator training in adopted reading/language arts and mathematics programs in use at the respective school site. f. Site administrator training in research-based practices for English language learners and ELPD training. g. Site administrator training in Response to Intervention. h. A district-level monitoring process for the professional development plan. | a. The DLT met collaboratively with teachers to review current and future professional development needs for all staff. Each site completed the Academic Program Survey to determine current status. In addition, priorities were established, based on the goals in the LEA plan for RLA, mathematics, and for ELs and SWDs. Action steps for professional development were written into the LEA plan based upon determined priorities. b. The DLT developed a monitoring protocol for professional development of teachers and site administrators. The monitoring protocol includes a listing of approved activities for practicum hours. c. Teachers who have not completed trainings meet with district and site administrators to establish goal plans for completion. d. To support beginning teachers, the district determined that the BTSA program and the Coaching cycle would be used. e.-g. The DLT developed a protocol to monitor the professional development of site administrators which includes SB 472 in RLA mathematics and ELPD. RTI training is included as well. h. District administration update and review the professional development matrix on a monthly basis in order to determine further training needs and follow up. | Supt., Assist. Supt., Director of Student Services, Principals Supt., Assist. Supt., Director of Student Services, ELD Title III Coordinator | 8/08 3/10 | X | X |  |  | The Professional Development Matrix was created to include instructional materials based professional development in ELPD, RLA and mathematics as well as other research based professional development. The matrix is reviewed monthly by district administrators. Individual Professional Development Goal Plans are developed with teachers who have not completed required trainings. MARCH 15 PROGRESS REPORT A sign-up sheet was sent to all staff listing the available ELPD training dates with the expectation that all teachers needing training will attend either county or district sessions by August, 2010. Emphasis has been placed on site principals to closely monitor the training matrix and speak with staff individually to set up goal plans for future training needs. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Arvin Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Provide a continuum of professional development for teachers in ELA and mathematics, including intervention that will include: SB 472 trainings. Training in research-based instructional strategies appropriate for all students. Training on Universal Access support materials, including English learner support. In-classroom coaching support. 3. Provide a continuum of support to teachers delivering specialized instruction to students with disabilities and to teachers of English language learners, including: Training in specific research-based strategies for students with disabilities and English language learners. All appropriate SB 472 trainings. In-classroom coaching support from staff with expertise in teaching English language learners and students with disabilities. Training on all district-approved curriculum materials with which they instruct. | The district developed a Professional Development Master Plan which includes the following: /c.Percentage and identification of teachers who have attended or need to complete the trainings in SB 472, including universal access and support for ELs. Percentage and identification of teachers who have attended or need to complete district sponsored professional development in researched based instructional strategies. d. A coaching cycle monitoring log to identify teachers in need of support. The Professional Development Master Plan includes a continuum of support for teachers delivering specialized instruction for SWDs and ELs. Examples include: Corrective Reading, SB 472, ELPD, RTI (See implementation notes for item 2 above) MARCH 15 PROGRESS REPORT-No new actions to report at this time. | Supt., Assist. Supt., Director of Student Services, Principals, Coordinators, Coaches Supt., Assist. Supt., Director of Student Services, Principals, Coordina-tors, Coaches Supt., Assist. Supt., Director of Student Services, Principals, Coordinators, Coaches | 8/08 1/10 8/08 | X X | X X |  |  | a/c. The following list details the percentage of teachers who have completed the SB 472 Trainings: 72% for RLA 32% for math 31% for ELPD b/c.The following trainings in research based strategies have been provided: Explicit Direct Instruction Content and Language Objectives Focused Approach to Houghton Mifflin and Systematic ELD (Dutro) English Learner Institute for coaches and administrators Universal Access training through Reading First d.Coaches consult with the teachers, model lessons, and debrief with the teachers on a scheduled basis. This is recorded through logs that are turned in to the Principal on a monthly basis. MARCH 15 PROGRESS REPORT As of January, 2010, an additional 30 teachers were enrolled in ELPD 5 day training. The district now reports a 60% completion rate of district teacher in ELPD. As written in the revised January LEA Action Plan, Principals will only assign teachers who have been trained in High Point to instruct an intensive intervention class. Beginning in February, 2010, Title III Coordinators for math and ELD began meeting with grade levels to offer extra coaching support in lesson study, lesson planning and delivery. Further training has been provided to staff in lesson modeling and debriefing. Support for long term substitutes will be provided by the coordinators and coaches to ensure continuity of classroom instruction. Need is determined by site principals. As appropriate to their assignment, Special Education teachers receive training in Corrective Reading. All special education teachers were included in percentages for SB 472 in item # 2 noted above. RLA |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Kern			Local Educational Agency: Arvin Union Elementary

|  | 2007 AYP | 2009 AYP | Difference in % Proficient | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide | 21.2 | 26.0 | 29.1 | 33.9 | 7.9 | 7.9 | Curriculum embedded district benchmarks, skills assessments | 6 weeks 9 weeks | Programs measured by student movement out of intervention, and student growth to higher instructional levels. | Skills assessment tests given first week of Dec., 2009 | Used during PLC meetings for instructional planning to determine strategic or intensive intervention students and to move students in or out of these programs. |
| Hispanic or Latino | 20.8 | 25.5 | 28.7 | 33.9 | 7.9 | 8.4 | Same as above | Same as above | Same as above | Same as above | Same as above |
| Socioeconomically Disadvantaged | 20.5 | 25.3 | 28.5 | 33.4 | 8.0 | 8.1 | Same as above | Same as above | Same as above | Same as above | Same as above |
| English Learners | 17.0 | 23.9 | 26.6 | 32.8 | 9.6 | 8.9 | Same as above, plus curriculum embedded benchmark ELD and Language Assessments | 4-8 weeks | Movement of students between instructional levels and by movement on the CELDT | language assessment given last week of November, 2009 | Used for instructional planning to determine language instruction strategies and lessons. |
| Students with Disabilities | 6.7 | 11.9 | 15.1 | 17.5 | 8.4 | 5.6 | District curriculum embedded assessments, or Corrective Reading placement and assessments as stipulated by student IEPs | 4-8 weeks 2-4 weeks | Programs measured by student movement out of intervention, and student growth to higher instructional levels. | First week of December, 2009 | Used for instructional planning and differentiation and to determine movement to higher instructional levels |
| Statewide Targets | 24.4 | 26.5 | 46.0 | 47.5 | 21.6 | 21.0 | CST and CELDT | annually | Overall and subscores | CST-Spring of 2009 CELDT-mid-Sept., 2009 | Summative, used to look at target growth, set goals, measure trends, patterns and set staff professional developmt training |