California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

County: Riverside		Local Educational Agency: Coachella Valley Unified

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. English/Reading-Language Arts Mathematics | English/Reading-language Arts CVUSD adopted in June 2002 and immediately implemented these SBE programs for all students grades K-12 including special education and English Learners: K-6 Houghton Mifflin Reading and High Point; 7-12 McDougal Littell Language of Literature, High Point 7-8, and Language! 9-12. In 2005 they adopted these SB1113 Supplemental Programs for English Learners: K-6 Rigby Harcourt Achieve, On Our Way to English; 7-12 Hampton Brown ELD Level Libraries and Rosetta Stone for ELD. In December 2007 they adopted and implemented SBE Voyager CA Passport for 4-6 reading intervention to replace High Point at those grades. High school implements High Point for ELD and Voyager reading intervention for special day class students. High school no longer uses the previously adopted Language! program and, along with middle school, has first priority to adopt a new 2008 E/RLA reading intervention/ELD program as funds are available. Adoptions are fully implemented through annual replacement of all needed materials including ancillary resources, classroom observations for fidelity to program implementation and instructional time, and mandated standards-based district benchmark assessments aligned to grade/course level pacing schedules. Administrators and teachers are required to participate in AB 430 and SB 472 respectively for professional development to fully monitor and implement adopted programs. Principals, coaches, and site teams use a district Learning Walk-Through Matrix for classroom observations to monitor E/RLA implementation that is also reviewed by the district team of administrators and DAIT members twice a year. Principals use this district process to receive feedback on program implementation, hold teachers accountable by addressing specific areas of need, and provide support through classroom coaching. Mathematics In spring 2008, CVUSD adopted and then implemented that fall these 2007 SBE-approved mathematics programs for all students, including special education and English Learners: grades K-6, Scott Foresman-Addison Wesley enVisionMath California; grade 7, Prentice Hall Pre Algebra; grades 8-12, Prentice Hall CA Algebra I; grades 8-12 Intervention, Prentice Hall Mathematics California Algebra Readiness; grades 9-12 Prentice Hall Mathematics Geometry, Algebra 2, Precalculus, and Wiley Calculus. In spring 2009, they adopted and implemented that fall Kaplan’s Momentum Math intervention program for grades 4-7. The adoption process included purchasing all teacher, student, and ancillary materials including those to for use with technology. Adopted programs are fully implemented through annual replacement of all needed materials including ancillary resources, classroom observations for fidelity to program implementation and instructional time, and mandated standards-based district benchmark assessments aligned to grade/course level pacing schedules. Administrators and teachers are required to participate in AB 430 and SB 472 respectively for professional development to fully monitor and implement adopted programs. Principals, coaches, and site teams use a district Learning Walk-Through Matrix for classroom observations to monitor mathematics implementation that is also reviewed by the district team of administrators and DAIT members twice a year. Principals use this district process to receive feedback on program implementation, hold teachers accountable by addressing specific areas of need, and provide support through classroom coaching. |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | SB 472 RLA Teachers Professional Development (Completion) 2008 K-6 Teachers: 84% 2009 K-6 Teachers: 93% 2008 7-8 Teachers: 41% 2009 7-8 Teachers: 92% 2008 9-12 Teachers: 59% 2009 9-12 Teachers: 76% SB 472 Mathematics Teachers Professional Development (Completion) 2008 K-6 Teachers: 93% 2009 K-6 Teachers: 96% 2008 7-8 Teachers: 97% 2009 7-8 Teachers: 88% 2008 9-12 Teachers: 92% 2009 9-12 Teachers: 95% ELPD Professional Development (Completion) 2008 K-6 Teachers: 60% 2009 K-6 Teachers: 86% 2008 7-8 Teachers: 92% 2009 7-8 Teachers: 95% 2008 9-12 Teachers: 76% 2009 9-12 Teachers: 86% 2009 K-12 Principals Completed 100% SB 430 Administrator Training (Completion) 2009 RLA K-6 Principals 71% 2009 Math K-6 Principals 100% 2009 RLA 7-8 Administrators 83% 2009 Math 7-8 Administrators 50% (Asst. Prin. to be trained 2010) 2009 RLA 9-12 Administrators 60% 2009 Math 9-12 Administrators 33% (Asst. Prin. to be trained 2010) |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | During October-November 2009, all sites reviewed progress using the Revised APS. While exact correlations cannot be made due to changes on the revised APS in numbering of EPCs, added criteria, and new rating scale, the following EPCs show improvement from minimal or partial implementation in 2008 to substantial or full implementation in 2009. Implementation of core RLA/ELD programs K-12 Implementation of intensive reading intervention programs 4-8 Implementation of core mathematics programs K-12 Implementation of intensive math intervention program 4-7 Implementation of Algebra readiness program 8-10 Instructional time for strategic support of core R/ELA programs K-12 Instructional time for additional adopted ELD programs K-12 Instructional time for intensive intervention RLA 4-8 Instructional time for strategic support of core math programs 7-10 Instructional time for strategic support of Algebra program 8-10 Instructional time for intensive intervention RLA 4-8 Instructional time for intensive intervention math 4-7 Instructional time for Algebra Readiness 8-10 Lesson pacing guides for strategic and intensive math intervention 4-7 Lesson pacing guides for strategic Algebra support 8-10 Administrator professional development math K-12 Credentialed and Highly Qualified Teachers: K-6 from 91% to 97% Credentialed and Highly Qualified Teachers: 7-8 from 79% to 85% Credentialed and Highly Qualified Teachers: 9-12 from 85% to 89% Authorization to teach English Learners: K-6 from 99% to 97% Authorization to teach English Learners: 7-8 from 91% to 94% Authorization to teach English Learners: 9-12 from 86% to 90% Authorization to teach Special Education: K-6 from 60% to 96% Authorization to teach Special Education: 7-8 from 55% to 93% Authorization to teach Special Education: 9-12 from 70% to 96% Ongoing assessment and monitoring RLA K-12 Ongoing assessment and monitoring mathematics K-12 Monthly collaboration for R/ELA and mathematics K-12 Support for teachers by coaches in R/ELA and mathematics K-12 This EPC remains at substantial or full implementation. Fiscal support for R/ELA and math |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | 2007 AYP Targets Met: 20/26 2009 AYP Target Met: 17/26 2007 Percentage Title I non PI Schools: 1% 2009 Percentage Title I non PI Schools: 0% 2002 API Base: 507 2009 API Growth: 664 (+157 from 2002) 2009 API: 664 CVUSD ranks 30 out of 44.on SBE’s Nov. 2009 “Cohort 1 LEAs in Corrective Action.” |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Riverside		Local Educational Agency: Coachella Valley Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance The district will strengthen policies to hold teachers, site administrators and district personnel accountable for student achievement. This includes a structure to monitor implementation of the EPCs and implementation of a K-12 Response to Intervention model at all sites to identify, place, and support students in intensive and strategic RLA/ELA and mathematics interventions. | Implement policies for greater accountability by district administrators to monitor principals’ supervision of classroom instruction and data teams Develop and implement Classroom Observation Matrix of key district instructional strategies for ELs and SWDs in ELA and math | Superintendent Asst. Supt. Ed Services | 08-09 09-10 | Yes Yes | Yes Yes |  |  | Beginning Fall 2009, twice a year district administrators monitor principals’ supervision of instruction through Learning Walk-Throughs (LWTs) using District Matrix and rubric for rating implementation. Principals use data to develop SMART Plans. Supt. monitors principals’ weekly visits of all classes using Matrix through data collected on district system (EADMS). |
|  | Annually conduct APS review to monitor implementation of EPCs especially those for RLA and math interventions | Asst. Supt. Ed Services | 08-09 09-10 | Yes Yes |  |  |  | Revised APS was administered in Fall 2009 to determine areas of growth and weakness for district additional support. |
|  | Train principals in RtI model and process Implement and monitor RtI at district and site level Retrain principals and coaches in Universal Access Implement additional classes where special education teachers team/collaborate with regular education teachers as part of the RtI model | Asst. Supt. Ed Services Director Special Education | 08-09 Fall 09 09-10 Jan 10 Mar 10 8/09 09-10 | Yes Yes Yes | Yes Yes Yes |  |  | Principals attended two trainings 08-09 with an additional training Fall 2009. District and sites are developing plans.. RCOE and district admin. conducted training. Inclusion of SWDs in regular ed. classes and team teaching/ collaboration increased at 7-12 sites by about 40%. |
| Alignment of Curriculum, Instruction, and Assessments to State Standards Implement SBE Corrective Action 6. Full implementation of the curriculum will be met through full implementation of the nine Essential Program Components (EPCs) for instructional success. New 2007 mathematics programs are currently implemented in all K-12 classrooms by SB472-trained teachers who have new district pacing guides with aligned benchmark assessments. Monitoring of this new adoption’s implementation especially for English Learners and Students with Disabilities will be completed by district and site administrators. A number of the new RLA programs will be piloted K-12 in 2009-10. Under an SBE-approved waiver, new RLA programs will be board adopted no later than June 2011 for implementation by August 2011. | Monitor site and classroom implementation of EPCs for ELA and math instructional programs using district Classroom Matrix. | Superintendent Asst. Supt. Ed Services | 08-09 09-10 | Yes Yes | Yes Yes |  |  | District and DAIT members monitor classroom instruction through LWTs. Directors support principals and their site SMART Plans. |
|  | Train principals to monitor teacher use of new math program materials, pacing guides and assessments | Asst. Supt. Ed Services | Aug 08 Oct 09 09-10 | Yes Yes | Yes |  |  | All K-12 principals trained in new math adoptions through AB 430 from RCOE. RCOE DAIT assists principals and teachers in implementation of new math adoptions. |
|  | Monitor all sites’ grade level and class implementation of 2007 math adoptions | Asst. Supt. Ed Services | 08-09 09-10 | Yes Yes | Yes Yes |  |  | Principals and district monitor math implementation through LWTs. |
|  | Provide teachers of ELs and SWDs support to implement math adoptions using Thinking Maps, acad. language, and cooperative grouping strategies | Asst. Supt. Ed Services Director ELs | 08-09 09-10 | Yes Yes | Yes Yes |  |  | Ongoing training provided in these strategies for ELs and SWDs. Middle school math teachers retrained in Adv.Thinking Maps. Site coaches provide teachers additional training and support for thinking maps, academic language, and cooperative grouping strategies. |
|  | Use the district adoption policy to identify new RLA adopted programs to pilot and recommend to the board for purchase | Asst. Supt. Ed Services | 5/09 9/09 1/10 5/10 | Yes Yes Pilot Rec. to Bd. | Yes |  |  | K-12 is piloting two core ELA with ELD adoptions, K-6 three and 7-10 two reading intervention programs for EL. DAIT recommends priority for adoption a 7-12 reading intervention program with ELD (Program 5). |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Riverside		Local Educational Agency: Coachella Valley Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Provide all students full access to the core curriculum in reading/English language arts (ELD) and mathematics including strategic intervention for all students within two years of grade level and intensive intervention for all students two or more years below grade level. This includes using assessments to appropriately place and exit ELs, SWD, and all underperforming students in interventions by providing specific additional instructional time (EPC 2) and fully using adopted intervention programs. At high school, strategic intervention with two periods will be provided in RLA for students at 6th grade level but unable to pass or failing California High School Exit Exam (CAHSEE) ELA, and in mathematics for students at 7th grade level but unable to pass or failing CAHSEE Math. At high school, intensive intervention with two periods will be provided in RLA for students below sixth grade level but unable to pass or failing CAHSEE ELA, and in mathematics for students below seventh grade level but unable to pass or failing CAHSEE Math. | Identify and implement placement assessments/criteria for students needing intensive and strategic intervention in ELA and math. | Asst. Supt. Ed Services | 8/08 5/09 5/10 09-10 | Yes Yes | Yes |  |  | Assessments for new math intervention program 4-7, Momentum Math, used for placement fall 2009 and 2010 as well as to monitor ongoing progress. |
|  | Monitor K-6 instructional time and appropriate strategies for strategic and intensive interventions (grades 4-6) ELA and math. | Director Elementary Ed Principals | 08-09 09-10 | Yes Yes | Yes Yes |  |  | K-6 teachers provide additional time for Universal Access with core adoption and reading and math interventions. LWTs monitor implementation. |
|  | Monitor implementation of two-period classes for all students needing strategic and intensive intervention in ELA and math. | Director Secondary Ed Principals | 8/09 9/09 09-10 | Yes Yes Yes | Yes |  |  | High schools only provide reading intervention to ELs at Levels 1 & 2 and SDC students. |
|  | Train secondary site teams to build master schedules with two-period interventions in ELA and math. Monitor master schedules. | Director Secondary Ed | 6/09 9/09 09-10 | Yes Yes | Yes |  |  | 7-12 master schedules provide sufficient two-period classes for interv. for ELA and math. CAHSEE within school day. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Riverside		Local Educational Agency: Coachella Valley Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Fiscal Operations The district work with the DAIT on aligning its budget and priorities for improving student achievement. The reallocation process will occur at least annually as the district budget for the next fiscal year is developed. | DAIT and Cabinet will meet to review district budget and funding for High Leverage Actions in LEA Addendum. | Superintendent Asst. Supt. Fiscal Services | Jan 09 10 | Yes | Yes |  |  | Asst. Supt. Fiscal Services works closely with RCOE fiscal administrators to prepare annual budget. |
| Priority will be given to funding the new RLA adoption and site instructional coaches. | Fund at least one full time instructional coach at each site. Determine possible funding for new RLA adoptions. | Board of Education Superintendent | May 09 10 May 10 | Yes | Yes |  |  | District and DAIT will work to prioritize funding first for new RLA 7-12 adoptions in intensive reading intervention and ELD. |
| Parent and Community Involvement None |  |  |  |  |  |  |  |  |
| Human Resources Teacher implementation of key components of professional development will be monitored by administrators and principals using a common observation tool. | Provide principals training to monitor instruction and teachers’ use of key district strategies for ELs and SWDs as listed on District Matrix for Learning Walk- Throughs (LWTs). Schedule district/site LWTs 3 times a year 08-09 and 2 times 09-10. Train principals to use LWT data to support teachers with added coaching assistance. | Asst. Supt. Ed. Services Asst. Supt. Ed. Services | 08-09 09-10 08-09 09-10 Fall 09 | Yes Yes Yes Yes Yes | Yes Yes Yes |  |  | DAIT participates in district LWTs. Data showing level of implementation of key strategies by teacher and grade/course level are compiled in a report using EADMS. Principals work with district to develop action plans for site instructional coach to address needs of teachers and grade/course levels. |
| Principals will be provided training, support, and monitoring to better supervise and evaluate teachers’ use of data. | Provide principals ongoing training in monitoring teachers’ use of data to determine appropriate instructional response. Hold principals accountable to monitor data teams. | Asst. Supt. Ed. Services | 08-09 09-10 Fall 09 09-10 | Yes Yes Yes Yes | Yes Yes |  |  | District conducts observations of site grade/course level teams and how principals monitor teams’ data analysis three times a year providing “just in time” training as appropriate. |
| Secondary principals need training and support to correctly assign teachers according to their credentials for appropriate classes. | Provide training and monitor secondary principals to correctly assign teachers to courses according to their credentials. | Executive Director Personnel Director Secondary Ed. | 08-09 09-10 | Yes Yes |  |  |  | Principals attend training on hiring and assigning Highly Qualified Teachers annually in spring. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Riverside		Local Educational Agency: Coachella Valley Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Data Systems and Achievement Monitoring Strengthen district data system and use to increase teacher/principal system navigation, report generations, data disaggregation and scoring of standards-aligned assessments | Provide training to principals and sites in effectively using EADMS (Educator’s Assessment Data Management System) data collections system. | Director of Assessment | 08-09 09-10 | Yes Yes | Yes |  |  | Staff provided over 130 district and site trainings to use system and develop reports; provided over 300 site visits for technical assistance. |
| Implement mandatory district benchmark and curriculum-embedded assessments to ensure full alignment to grade level RLA/ELA and mathematics standards and pacing guides. | Implement and monitor use of K-6 district standards-based ELA and Math benchmark assessments aligned to pacing guides. | Asst. Supt Ed. Services Director of Assessment | Aug 08 09-10 | Yes | Yes |  |  | K-6 ELA, math, and ELD trimester benchmarks are required/monitored by district for K-12. |
|  | Implement 7-12 district standards-based ELA and Math benchmark assessments aligned to pacing guides. | Asst. Supt Ed. Services Director of Assessment | Aug 09 09-10 | Yes | Yes |  |  | K-12 ELA, math, and ELD trimester benchmarks are required/monitored by district. |
|  | Implement ongoing formative short-cycle K-12 assessments in ELA and Math. | Asst. Supt Ed. Services Director of Assessment | 09-10 | Yes | Yes |  |  | Schools are beginning to develop/implement assessments. |
| Provide structured, systematic professional development in the analysis of assessment data for use in instructional improvement, monitored by site and district administrators. | Train principals to analyze data through error analysis of standard-based items. Train principals to use data analysis for instructional improvement. District and site administrators will monitor data analysis through EADMS reports. | Director of Assessment and Testing Asst. Supt Ed. Services Director of Assessment | 08-09 09-10 08-09 09-10 08-09 09-10 | Yes Yes Yes Yes Yes | Yes Yes Yes |  |  | District administrators and principals hold district PLCs to analyze district grade level data and use results to assist site level analysis.. Principals monitor results of data teams. District monitors site data teams with visits using list of expectations for effective PLCs. |
| Professional Development Provide professional development for all district staff including: |  |  |  |  |  |  |  |  |
| Teacher and site administrator participation in professional development (SB 472, ELPD, and AB 430) designed to support Corrective Action 6 implementation of 2007 Mathematics and 2008 RLA adoptions, | Provide SB 472, ELPD, and AB 430. (See completion rates page 2) | Asst. Supt Ed. Services Exe. Director Personnel | Aug 08 08-09 Aug 09 09-10 Aug 10 10-11 | Yes Yes Yes Yes |  |  |  | Teachers and administrators are required to complete SB 472, ELPD, and AB 430: staff new to district attends professional development during school year. |
| RLA, ELD, and math EPC implementation and site coaching for teachers and site principals, and | Provide ELD training in Thinking Maps, academic vocabulary, Think/Pair/Share. | Asst. Supt. Ed. Services | 08-09 09-10 | Yes Yes | Yes |  |  | 90 MS Teachers completed training for Adv. Thinking Maps summer 2009. |
|  | Provide ELA, Math, and ELD Coaching and Coaches’ Network ongoing professional development. | Asst. Supt. Ed. Services | 08-09 09-10 | Yes Yes | Yes |  |  | All sites have full time Instructional Coaches. DAIT assists with Coaches’ Network for monthly training. |
|  | Provide training for Momentum Math. | Asst. Supt. Ed. Services | Aug. 09 09-10 | Yes | Yes |  |  | 112 teachers grades 4-7 attend intervention math training with follow-up with coaches and site visits. Follow-up training ongoing. |
|  | Provide Summer Institute math training. | Asst. Supt. Ed. Services | July 09 | Yes | Yes |  |  | 72 teachers from grades 4-8 attended. |
|  | Provide principal coaching to implement adoptions. | Asst. Supt. Ed. Services/DAIT | 08-09 09-10 | Yes Yes | Yes |  |  | 09-10 principal coaching provided at some K-6 sites. |
| Support for principals to supervise implementation of professional development learning communities at all sites. | Train principals to implement data analysis and PLCs using district Data Analysis Worksheet. | Asst. Supt. Ed. Services/DAIT | Aug. 08-09 09-10 | Yes Yes | Yes |  |  | Principals attended 5 Leadership workshops to implement district Data Team Guide Book and effective PLCs. |
|  | Develop district standards for PLC implementation. | Asst. Supt. Ed. Services | 08-09 | Yes |  |  |  | Principals implement District PLC Logistics. |
|  | Support and monitor principals implementing data analysis teams. | Asst. Supt. Ed. Services | 09-10 | Yes | Yes |  |  | District developed and implemented Data Analysis Observation tool with specific expectations for team members and principals. Monitoring of site data teams and principals occurs three times a year. |
|  | Ensure that special education teachers are part of site data teams and PLCs. | Asst. Supt. Ed. Services | 08-09 09-10 | Yes Yes | Yes |  |  | The PLC Network for special education teachers meets monthly to additionally train data analysis to deliver the appropriate instructional response. |
| Other None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Riverside		Local Educational Agency: Coachella Valley Unified

|  | 2007 AYP | 2009 AYP | Difference in % Proficient | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide LEA-wide | 19.0 | 26.4 | 30.0 | 41.8 | 11.0 | 15.4 | K-6 K-6 ELA and Math District Benchmarks* K-6 DIBELS* K-6 BPST* K-6 Writing Benchmark* K-1 enVision Math Place and End* 2-6 ELA/Math KDS Blueprint 4-6 Voyager DIBELS 4-7 Momentum Math 7-12 7-12 ELA and Math Course District Benchmarks 7-12 ELA Pre Test 7-8 ELA CST Review 7-8 ELA Post Benchmark 7-8 Highpoint | Trimester Trimester 3 Times Trimester Sept. June Sept. and March Bi-weekly Aug. Weekly Quarter, Block, or Trimester Sept. April May Weekly | Progress monitoring Diagnostic Diagnostic Progress monitoring Placement Diagnostic Diagnostic Intervention Placement Intervention Progress monitoring Placement Diagnostic Diagnostic Next year placement Intervention | District Bnchmrks % Proficient ELA Grade 1st 61% 2nd 44% 3rd 38% 4th 22% 5th 31% 6th 29% Math Grade 2nd 54% 3rd 48% 4th 47% 5th 46% 6th 46% District Bnchmrks % Proficient ELA Grade 7th 36% 8th 39% 9th 40% 10th 36% Math 7th 47% 7th Int 30% 8th AlgRd 32% Alg. 34% 9th AlgRd 23% Geom. 51% | K-6 Grade level Data Teams meet twice monthly to analyze both ELA and Math data, monitor student and grade level progress, modify lessons, and intervene. Principals provide added support to teachers using data. Same as above only teachers meet as course level teams. |
| Hispanic or Latino Hispanic or Latino | 18.6 | 26.2 | 29.5 | 41.6 | 10.9 | 15.4 | Same as above | Same as above | Same as above | District Bnchmrks % Proficient ELA Grade 1st 60% 2nd 44% 3rd 37% 4th 22% 5th 30% 6th 28% Math Grade 2nd 54% 3rd 48% 4th 47% 5th 46% 6th 46% District Bnchmrks % Proficient ELA Grade 7th 35% 8th 40% 9th 35% 10th 42% Math 7th 47% 7th Int 30 8th AlgRd 32% Alg. 34% 9th AlgRd 23% Geom. 51% | Same as above |
| White White | 42.4 | 37.0 | 52.3 | 54.7 | 9.9 | 17.7 | Same as above | Same as above | Same as above | District Bnchmrks % Proficient ELA Grade 1st 94% 2nd 62% 3rd 72% 4th 28% 5th 54% 6th 45% Math Grade 2nd 65% 3rd 52% 4th 35% 5th 54% 6th 53% District Bnchmrks % Proficient ELA Grade 7th 61% 8th 55% 9th 50% 10th 67% Math 7th 38% 7th Int 100 8th AlgRd NA Alg. 35% 9th AlgRd 40% Geom. 57% | Same as above |
| Socioeconomically Disadvantaged | 17.6 | 25.4 | 29.7 | 41.8 | 12.1 | 16.4 | Same as above | Same as above | Same as above | District Bnchmrks % Proficient ELA Grade 1st 55% 2nd 36% 3rd 29% 4th 18% 5th 24% 6th 24% Math Grade 2nd 49% 3rd 44% 4th 45% 5th 43% 6th 42% District Bnchmrks % Proficient ELA Grade 7th 31% 8th 37% 9th 40% 10th 37% Math 7th 46% 7th Int 31% 8th AlgRd 31% Alg. 32% 9th AlgRd 23% Geom. 52% | Same as above |
| English Learners English Learners | 16.0 | 24.4 | 24.6 | 39.2 | 8.6 | 14.8 | Same as above with * tests also in Spanish CELDT (handscored) K-8 ELD District Benchmarks | Same as above Sept.-Oct. Jan. May | Same as above Diagnostic Placement Diagnostic | District Bnchmrks % Proficient ELA Grade 1st 55% 2nd 41% 3rd 34% 4th 13% 5th 16% 6th 11% Math Grade 2nd 54% 3rd 46% 4th 42% 5th 37% 6th 36% ELD K-1st 46% 2nd 26% 3rd-5th 46% 6th-8th 53% District Bnchmrks % Proficient ELA Grade 7th 13% 8th 16% 9th 20% 10th 14% Math 7th 34% 7th Int 29 8th AlgRd 38% Alg. 19% 9th AlgRd 21% Geom. 27% | Same as above Teachers use data to regroup and intervene. |
| Students with Disabilities | 11.1 | 12.1 | 32.0 | 31.4 | 20.9 | 19.3 | Same as above PreK-6 CAPA students FAST (RCOE published assessment) 12% scored proficient on FAST Pre-Test | Same as above Sept., Jan. | Same as above Diagnosis | District Bnchmrks % Proficient ELA Grade 1st 38% 2nd 33% 3rd 13% 4th 6% 5th 6% 6th 5% Math Grade 2nd 29% 3rd 25% 4th 24% 5th 17% 6th 19% District Bnchmrks % Proficient ELA Grade 7th 12% 8th 11% 9th 25% 10th 20% Math 7th 33% 7th Int 17% 8th AlgRd 50% Alg. 17% 9th AlgRd 7% Geom. 33% | Same as above Teachers use data for lesson planning and to intervene. |
| Statewide Targets | 23.0 | 23.7 | 45.0 | 45.5 | 22.0 | 21.8 |  |  |  |  |  |