California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6 (Keppel)

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. | English Language Arts—Have been using the 2002 Open Court and McDougall-Little for 7th and 8th grade. We are in the process of piloting adoptions for K-8. For K-6 we have completed two pilots and will be making a decision based on student needs and pilot results. For 7th-8th we have piloted one program and are in the process of the second pilot. Mathematics—We are in the second year of our newly adopted program Envision. Middle school is working with math DAIT team member on restructuring the Algebra path for greater student success in Algebra. |
| English/Reading-language Arts | English Language Arts—The district worked with all stakeholders to garner feedback for adopting a SBE approved English Language Arts program. The recommendation was given to the Board and the Board voted to approve the adoption of MacMillan/McGraw-Hill/Glencoe for grades K-8. |
| Mathematics |  |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | English Language Arts—We planned summer training for the teachers at the conclusion of the 2009-10 school year to train them in the newly adopted language arts program. Mathematics— All but one teacher has been trained on our math series Envision. The district is looking at both internal and external options for getting the last person trained. Training was set-up for March but due to an emergency the person was unable to attend. This training will be completed before the end of the school year. |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | The instructional minutes are strictly adhered to for appropriate minutes; principals and teachers have been trained in AB30 and SB472; 6 week benchmarks in place and an on-line assessment reporting system for staff to access data to utilize for instruction; we have a combination of district wide system for coaching support at all schools with a specific focus on PI+ Schools, the content experts are building capacity by building the expertise of the coaches; professional learning community training summer, 2009 for all teachers; each site allocated three meetings a month to professional learning community collaboration at the grade levels; the master schedule was developed for interventions in both mathematics and language arts; all grades use lesson and course pacing schedules that were developed by the district in conjunction with publishers pacing guides. The district has 6 instructional coaches. Two of the coaches have expertise working with English learners however; the focus for all coaches is on the implementation of SDAIE strategies in a differential manner throughout the district. The District has also developed an inclusion model for students with disabilities. Training for principals, general and special educators has been conducted. Schools are working on developing a pyramid of interventions that reflect the needs of the students at each school. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | Progress was made in AYP and API from Spring, 2008 to Spring, 2009. Two schools froze in their program improvement status in this one year span. All other schools made growth in the percentage of targets met and API except for one. That one middle school underwent major restructuring in the structures and systems necessary to make students successful. This school is being monitored monthly to insure goals for success are being met for growth in both AYP and API through data monitoring of benchmark data every 6 weeks. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Los Angeles		Local Educational Agency: Keppel Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance The district will develop procedures and protocols that will allow for clear, transparent communication and feedback in all processes across the district for clarity and focus in academic alignment, fiscal, human resource and governance. | Revise EL Master Plan—a committee has been working on this revision District formed DAC and established a written bulletin with the actions of the DAC Ongoing meetings with union leadership Meeting with teacher leadership to identify barriers, obstacles and challenges Meeting with classified leadership to identify barriers, obstacles and challenges Develop a plan with specific responsibilities outlined in the district org chart and communicate to all stakeholders Articulation will occur between the district and high school district regarding math Meetings will occur with after school program provider for alignment to district curriculum | Randall Jolin Steve Doyle Steve Doyle Steve Doyle Steve Doyle Steve Doyle Bart Hoffman Bart Hoffman | 1/2010 11/2009 Ongoing Dec 8 Jan 19 June 1 Ongoing Ongoing | X | X X X |  | X | District established a committee process to review and monitor Meetings are occurring with both classified and certificated Follow up meetings have been held with both classified and certificated leadership union reps. To develop an action plan; all certificated and classified staff have been advised of the outcomes of meetings District attends months AVCAC meetings and participated in math meetings District is in the process of changing an after school provider and has established regular meetings |
| Alignment of Curriculum, Instruction, and Assessments to State Standards The district will address the needs of all students by utilizing a variety of data sources to focus instruction and interventions. The district will utilize the newly implemented mathematics adoption as the focus for access to core curriculum and standards for all students, professional development, administrative walkthroughs, hiring practices and fiscal decisions. | Criteria will be established in the 7th and 8th grade to determine how students access Algebra 1 classes Data team meetings will be calendared at each school site for summative and formative assessments Each school will participate in an accountability summit with data There will be a purposeful use of time, student engagement and energized environment, professional collaboration and articulation, communication and goal setting Teachers will have student friendly objectives posted Establish math benchmarks every 6 weeks Focused professional development in Algebra and Math intervention provided at middle school level Teachers will meet the needs of English Learners by using strategies necessary to access core Coaching will occur at all schools | Bart Hoffman Bart Hoffman Site Admin Cabinet Bart Hoffman Bart Hoffman Bart Hoffman Bart Hoffman Bart Hoffman Bart Hoffman | Mar 2010 Monthly Oct, 2009 Ongoing Ongoing Sept, 2009 Sept & Oct, 2009 Ongoing Ongoing | X X X |  | X |  | The district is embarking on a reconfiguration plan that will impact all of our sites. A more detailed explanation and plan will follow on our next report. The district uses a walkthrough tool to monitor instruction monthly through the DSLT and AGB process The District continues to conduct monthly classroom visits using a consistent walk through tool. Data and minutes are kept of each walk through District is systematically training, coaching and holding accountable the implementation of specific SDAIE strategies District has developed a coaching plan with follow-up |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Los Angeles		Local Educational Agency: Keppel Union Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Parent and Community Involvement The district will develop a district wide and school based parent involvement plan. | Develop a parent involvement plan Parent academy on Saturday in conference style Parent survey to inform plan Monitor the number & type of parents involved at the schools and district through data Have community forums with specific agenda topics ( for example, in December on proposed ELA adoption) Train parents to support their students learning at home through understanding the system and services available to them The district will involve parents in a transparent process through DELAC and DAC | Bart Hoffman Randall Jolin Bart Hoffman Randall Jolin Bart Hoffman Randall Jolin Bart Hoffman Randall Jolin Bart Hoffman Randall Jolin | Feb, 2010 Jan, 2010 Ongoing Ongoing Ongoing ongoing |  |  | X |  | District-Parent team formed-updated parent involvement policy work and plans underway for Family Academy April 24, 2010 Board scheduled every other month |
| Human Resources See Governance #1, Alignment #2, and Professional Development #1 | See actions in these areas |  |  |  |  |  |  |  |
| Data Systems and Achievement Monitoring See Alignment #1 and Fiscal #1 | See actions in these areas |  |  |  |  |  |  |  |
| Professional Development The district will establish professional learning community principles across the district in order to increase student achievement. | PLC meetings at each school site 3 times a month for review of data for student achievement Cabinet PD Monthly PD with DAIT Administrative walks with debriefing Cabinet coaching with site administration Monthly meeting with executive cabinet to review progress with board goals DuFour PLC training for cabinet DuFour PLC training for site administration DuFour Common Assessment training for principals and leadership teams 4 days LACOE PLC training for all teachers and administrators Kansas University training for general ed and special education teachers for instructional strategies with follow-up coaching. | Site Administrators Executive cabinet Steve Doyle Steve Doyle Administration Bart Hoffman Linette Hodson | Ongoing Ongoing Nov, 2009 Summer 2010 March/May 2010 Summer 2009 Nov, 2009 & March, 2010 |  | X X X | X | X X | Training on the use of common assessments to supports effective first instruction within PLC |
| Other None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Los Angeles		Local Educational Agency: Keppel Union Elementary

|  | 2007 AYP | 2009 AYP | Difference in % Proficient | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide | 27.0 | 28.3 | 36.6 | 41.5 | 9.6 | 13.2 | * | ** | *** | **** | ***** |
| African American or Black (not of Hispanic origin) | 24.7 | 19.1 | 34.5 | 29.8 | 9.8 | 10.7 | * | ** | *** | **** | ***** |
| Hispanic or Latino | 23.4 | 25.9 | 32.6 | 39.7 | 9.2 | 13.8 | * | ** | *** | **** | ***** |
| White | 38.4 | 37.9 | 49.6 | 50.7 | 11.2 | 12.8 | * | ** | *** | **** | ***** |
| Socioeconomically Disadvantaged | 24.0 | 25.4 | 33.2 | 39.2 | 9.2 | 13.8 | * | ** | *** | **** | ***** |
| English Learners | 14.7 | 19.3 | 26.2 | 33.8 | 11.5 | 14.5 | * | ** | *** | **** | ***** |
| Students with Disabilities | 3.9 | 4.8 | 13.2 | 18.1 | 9.3 | 13.3 | * | ** | *** | **** | ***** |
| Statewide Targets | 24.4 | 26.5 | 46.0 | 47.5 | 21.6 | 21.0 |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Los Angeles		Local Educational Agency: Keppel Union Elementary

The data you are being provided is formative assessment data. You may not see growth from formative assessment to formative assessment because data is based on standards taught during the period assessed. It is not cumulative data. The formative assessment that is being presented in the data provides percentage of students proficient on standards taught during that specific period of time.

*District  Assessments Used:

Benchmark Assessments

**Frequency of Use:

Every 6 weeks

***How Programs are Measured:

Unit assessments and common assessments based on core in English Language Arts and Mathematics

****Latest Data Summary:

See attached charts

*****Use of Data by Principals and Teachers:

Teachers have professional learning communities three times a month. Data is reviewed and SMART goals are developed. Also common assessments are made. Both SMART goals and common assessments are completed every 1-3 weeks by grade levels. Principals review data after the assessments and work with leadership teams and grade level teams to create goals at the grade level. Every 6 weeks the principals review the progress of the schoolwide SMART goals with the leadership team.

Latest Data Summary

Keppel Union Elementary

Mathematics Benchmark 4

Percent Proficient

|  | K | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Algebra |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LEA-wide | 84 | 64 | 68 | 43 | 43 | 22 | 13 | 42 | 21 |
| African-American | 79 | 52 | 67 | 33 | 30 | 27 | 5 | 37 | 13 |
| Hispanic/Latino | 84 | 62 | 67 | 42 | 42 | 17 | 13 | 41 | 20 |
| White | 86 | 65 | 71 | 45 | 47 | 26 | 16 | 43 | 22 |
| Socioeconomically Disadvantaged | 86 | 64 | 69 | 53 | 41 | 18 | 12 | 43 | 21 |
| English Learners | 85 | 59 | 63 | 33 | 23 | 4 | 1 | 22 | 11 |
| Students with Disabilities | 71 | 50 | 25 | 28 | 19 | 6 | 6 | 22 | 7 |

Latest Data Summary

Keppel Union Elementary

English-Language Arts Benchmark 4

Percent Proficient

|  | K | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LEA-wide | 75 | 75 | 56 | 83 | 21 | 26 | 30 | 31 | 33 |
| African-American | **Subgroup data unavailable | 67 | 50 | 96 | 11 | 19 | 15 | 31 | 25 |
| Hispanic/Latino |  | 75 | 56 | 79 | 19 | 22 | 28 | 29 | 31 |
| White |  | 74 | 58 | 85 | 28 | 29 | 32 | 35 | 38 |
| Socioeconomically Disadvantaged |  | 74 | 54 | 84 | 24 | 21 | 25 | 32 | 34 |
| English Learners |  | 71 | 51 | 71 | 4 | 7 | 5 | 11 | 18 |
| Students with Disabilities |  | 60 | 13 | 61 | 9 | 7 | 6 | 11 | 7 |

**Data not available—working on data system