Attachment 6

Item 12.D.1

May 3–4. 2012

Mathematics SMC

Timeline for the 2013 Revision of the

Mathematics Framework for California Public Schools:

Kindergarten Through Grade Twelve

| Event | Schedule |
| --- | --- |
| Focus Group recruitment letter and application distributed to LEAs, mathematics and stakeholder organizations, and institutes of higher education | Mid November 2011 |
| Recruitment of Focus Group members, pursuant 5 CCR, §9511(c) and Ed Code Section 44013(a) | Mid November 2011 to Early January 2012 |
| State Board of Education (SBE) action on a timeline and Curriculum Framework and Criteria Committee (CFCC) application form | January 11-12, 2012 |
| Superintendent appoints Focus Group members | Mid January 2012 |
| CFCC recruitment letter and application distributed to LEAs, mathematics stakeholder organizations, and institutes of higher education | Mid January 2012 |
| Recruitment of CFCC members (at least 90 days pursuant to 5 CCR, §9513). | January to April 2012 |
| Focus Group meetings in four locations, pursuant to 5 CCR, §9511(c), San Bernardino County Office of Education, February 23 California Department of Education, Sacramento, February 28 San Diego County Office of Education, March 1 San Mateo County Office of Education, March 6 | Late February and early March 2012 |
| Instructional Quality Commission (IQC) meets, establishes Mathematics Subject Matter Committee (Math SMC), reviews Focus Group Report, and recommends CFCC members and guidance for revision of the framework to the SBE | May 2012 |
| SBE appoints CFCC members, receives Focus Group Report, and approves guidance for revision of the framework | July 18-19, 2012 |
| CFCC meets, five or six 2-day meetings in Sacramento, to develop draft Mathematics Framework The CFCC meetings are tentatively scheduled for the following dates: September 6–7, 2012 October 4–5, 2012 November 1–2, 2012 December 6–7, 2012 January 16–17, 2013 February 13–14, 2013 | September 2012 to February 2013 |
| Math SMC reviews draft Mathematics Framework in preparation for full IQC review | March 2013 |
| IQC approves draft Mathematics Framework for initial 60-day public review period | March 2013 |
| 60-day public review period prior to IQC recommendation to SBE, pursuant to 5 CCR, §9515(a)(3) | April to May 2013 |
| Math SMC reviews public review results and staff recommendations for edits to draft Mathematics Framework | Late May 2013 |
| IQC analyzes public review results and revises draft Mathematics Framework, approves draft Mathematics Framework for second 60-day public review period | June 2013 |
| Staff incorporates IQC changes to draft Mathematics Framework per IQC action | June 2013 |
| Required 60-day public review and comment on IQC’s recommended Mathematics Framework Section §95159(c) | July to August 2013 |
| SBE action on IQC’s recommended Mathematics Framework includes public hearing. | November 2013 |
| LEA implementation of Mathematics Framework | 2013–14 |
| Smarter Balanced Assessments | 2014–15 |
| Instructional Materials Adoption | November 2016 |

© California Department of Education

January 2012

# Footnotes

This timeline assumes that the SBE appoints members of the IQC in March 2012 and the IQC holds its first meeting in May 2012.