# CALIFORNIA STATE PLAN FOR CAREER TECHNICAL EDUCATION Working Timeline

Posted by California Department of Education  
November 2019

This document is a working timeline for the submission of the federal *Strengthening Career Technical Education for the 21st Century Act* (Perkins V) State Plan including an extended timeline to complete the full California State Plan for Career Technical Education (CTE).

## 2019

### Completed:

*May 29 California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting*

*July 12 CWPJAC Meeting*

*Aug. 7 Virtual Stakeholder Meeting*

*Aug. 13 Stakeholder Meeting #1*

*Sept. 13 CWPJAC Meeting*

*Sept. 17 Stakeholder Meeting #2*

*Oct. 2-4 Advance CTE – Perkins Implementation Meeting, Washington DC*

*Oct. 11 CWPJAC Meeting*

*Oct. 16 California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback*

*Oct 17 K­–12 Teacher Feedback Virtual Meeting*

*Nov. 08 CWPJAC Meeting – Present the full Draft responses to the Perkins V State Plan and timeline for the California State Plan for CTE*

*Nov. 20-22 Association of Career and College Readiness Organizations (CAROCP) CTE Conference, Rancho Mirage, CA*

### In Progress:

Nov. 25 CWPJAC Meeting – Second review of the California Perkins V State Plan

Nov. 26-27 Incorporate CWPJAC edits for posting/public comment

Dec. 02 Public Meeting #1 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference [ACTE] in Anaheim on December 4-7, 2019).

* 10:00 A.M.–12:00 P.M.
* 1:00–3:00 P.M.

Dec. 2 Open the California Perkins V State Plan Public Feedback Survey

Dec. 2 SBE Staff to share the Federal Perkins V State Plan with the Governor

Dec. Public Meeting #2 in Sacramento, date is to be determined (TBD)

Dec. 11-13 Joint Special Populations Advisory Committee (JSPAC) Conference – Opportunity for Receiving Public Feedback

## 2020

Jan. 3 Close the California Perkins V State Plan Public Feedback Survey   
(32 days)

Jan 4-10 Analyze California Perkins V State Plan Public Feedback Survey results

Jan 6-17 Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into the Final California Perkins V State Plan

Jan. 8 SBE Meeting, the Draft California Perkins V State Plan is presented

\*The version presented to the CWPJAC on November 25, 2019

Jan. 13 BOG Meeting, the Draft California Perkins V State Plan is presented

\*The version presented to the CWPJAC on November 25, 2019

Jan. 17 March SBE Item due to the EAB

* Need a delayed submission date (February 7, 2020) for posting the final California Perkins V State Plan to allow a week to incorporate the edits from the January 31, 2019 CWPJAC meeting

Jan. 21 CWPJAC Agenda Posting Date for the January 31, 2020 meeting

Jan. 31 CWPJAC Meeting – Review the final California Perkins V State Plan

Feb. 1-5 Incorporate CWPJAC feedback on the California Perkins V State Plan to present to the SBE in March

Feb. 6 Final California Perkins V State Plan complete for SBE approval/March meeting

March 3 CWPJAC Agenda Posting Date for the March 13, 2020 meeting

March 11-12 SBE Meeting – the Final California Perkins V State Plan approved

March 13 CWPJAC Meeting – Review Chapter Three of the complete California State Plan for CTE

March 13 The Final California Perkins V State Plan is sent to the Governor for approval

March 16 BOG Meeting, the Final California Perkins V State Plan is presented (informational item)

April 12 Governor Approval of the California Perkins V State Plan Complete   
(30 days)

April 15 Submit the California Perkins V State Plan to the United States Department of Education

### Extension of Timeline to complete California State Plan for CTE

April 28 CWPJAC Agenda Posting Date for the May 8, 2020 meeting

May 8 CWPJAC Meeting – Present Chapter Four and Five of the California State Plan for CTE

June 30 CWPJAC Agenda posting date for the July 1, 2020 meeting

July 1 Receive the United States Department of Education’s response to California’s submitted California Perkins V State Plan

July 10 CWPJAC Meeting – Present final draft of the California State Plan for CTE

Aug.-Sept. Public Feedback on draft of the California State Plan for CTE

TBD CWPJAC Agenda Posting Date (Sept.)

September CWPJAC Meeting –

TBD CWPJAC Agenda Posting Date (Nov.)

November CWPJAC Meeting – Approval of final draft of the California State Plan for CTE