- Appendix A: Local CCSS Systems Implementation Plan Template

California Department of Education

April 2014

(This appendix appears in the California CCSS Systems Implementation Plan available on the CDE CCSS Web page.)

Each of California’s local educational agencies (LEAs) should develop its own local plan for Common Core State Standards (CCSS) systems implementation based on local needs and resources. To facilitate the process of local plan development, this section offers a template organized around the significant milestones of CCSS systems implementation. The template denotes full implementation of CCSS systems by the 2014–15 school year. LEAs may wish to augment their local plans with elements from the Suggestions and Opportunities for LEAs charts distributed throughout this document or delete elements as appropriate to create a plan that is tailored to local needs.

| 2011–12 | CDE/SBE Activity | LEA Activity |
| --- | --- | --- |
| Fall | - A Look at Kindergarten Through Grade Six in California Public Schools released | - Begin development of local implementation plan based on full implementation of the CCSS system in 2014–15 - Conduct local needs assessment to identify needs and set priorities for professional learning and develop local professional learning plan based on identified needs and full implementation in 2014–15 - Suggested Area of Focus: - Working in grade-level teams, compare/contrast the CCSS with the 1997 content standards and begin to incorporate new skills from the CCSS into instructional planning - Subscribe to the CDE CCSS Resources and Smarter Balanced Web page listservs to remain apprised of the latest developments and resources related to CCSS systems implementation - Review and utilize professional learning resources available on CDE-hosted or sponsored Web portals including archived webinars and presentations on CDE on iTunes U - Utilize CCSS professional learning resources offered by professional organizations, California Subject Matter Projects, and your county office of education - Identify CCSS that current materials do not support (use supplemental instructional materials review evaluation criteria for grades K–8) and develop lessons using resources from the library and internet and primary source documents |
| Winter | - Establish design team to develop guidelines for professional learning modules (January) - Evaluation criteria for supplemental instructional materials review approved by SBE* (January) - Timeline and general plan for revision of the mathematics curriculum framework approved by the SBE* (January) | - Provide opportunities for professional learning to develop understanding of difference between interim assessments and formative practices - Visit Standardized Testing and Reporting (STAR) Web site for released test questions and constructed responses. Mirror the format into quiz/test questions and weekly writing prompts |

* Indicates activity which requires State Board of Education (SBE) action

| 2011–12 | CDE/SBE Activity | LEA Activity |
| --- | --- | --- |
| Spring | - Online technology readiness tool available (March) - Convene education experts to update the ELD standards (March–August) - Timeline and general plan for revision of the English language arts curriculum framework approved by the SBE* (May) - A Look at Grades Seven and Eight in California Public Schools released (May) | - Utilize online technology readiness tool to evaluate current technology and infrastructure |
| Summer |  |  |
| 2012–13 | CDE/SBE Activity | LEA Activity |
| Fall | - 5 professional learning modules released (September/October) - Revised ELD standards adopted* (November) - Assessment transition plan presented to the Legislature (November) | - Review new professional learning modules from the CDE and incorporate new strategies into unit/lesson plans for 2012–13 - Support ongoing professional learning to promote transition to the CCSS based upon priorities established in local plan - Suggested Areas of Focus: - Mathematics: the standards for mathematical practice - ELA: text complexity, text-based questions and tasks - General: develop structures for interdepartmental collaboration to improve student literacy across the content areas, - Participate in professional learning opportunities to deepen understanding and support implementation of the ELD standards - Continue to assess existing instructional materials and supplement them with resources from the library and internet and primary source documents to develop CCSS-aligned lessons |
| Winter | - Revised CTE Model Curriculum Standards adopted* (January) - List of recommended supplemental instructional materials posted online* (February) - Plan and deliver professional learning opportunities for all components of the assessment system | - Participate in local professional learning opportunities designed to deepen understanding and support implementation of the revised CTE standards - Review and utilize the CDE’s supplemental instructional materials list to supplement existing instructional materials - Revise existing quizzes, unit exams, and end-of-course exams to assess higher-level thinking, constructed responses, synthesis, and collaboration as indicated in the CCSS |

* Indicates activity which requires SBE action

| 2012–13 | CDE/SBE Activity | LEA Activity |
| --- | --- | --- |
| Spring | - Pilot testing of Smarter Balanced summative and interim assessments | - Utilize online technology readiness tool to evaluate current technology and infrastructure |
| Summer | - Smarter Balanced Practice Test available (May) - Additional professional learning modules released (September) | - Utilize Smarter Balanced Practice Test to familiarize stakeholders with new assessments - Review new professional learning modules from the CDE and incorporate new strategies into unit/lesson plans for 2013–14 |
| 2013–14 | CDE/SBE Activity | LEA Activity |
| Fall | - Mathematics curriculum framework released* (November) | - Support ongoing professional learning to promote transition to the CCSS based upon priorities established in local plan - Suggested Areas of Focus: - Mathematics: modeling - ELA: collaborative conversations - General: revised ELD standards, revised CTE Model Curriculum Standards , effective utilization of technology and media - Communicate information regarding the CCSS and what they mean for students to parents and guardians - Utilize the mathematics curriculum framework as a blueprint for implementation of the mathematics CCSS - Promote local awareness of the assessment transition plan, Smarter Balanced assessments, and purposes of assessment |
| Winter | - Instructional materials for mathematics adopted* (January) - Promote mathematics curriculum framework | - Review list of SBE-adopted instructional materials for mathematics - Revisit end-of-chapter/unit questions and quizzes in existing materials and elevate them to higher level critical thinking - Include performance task assessments for end of unit/chapter assessment - For mathematics, utilize word problems to provide students with opportunities to apply mathematical reasoning to real-world challenges |
| Spring | - Field testing of summative assessments | - Visit Smarter Balanced Web pages for information about field tests - Utilize online technology readiness tool to evaluate current technology and infrastructure |

* Indicates activity which requires SBE action

| 2013–14 | CDE/SBE Activity | LEA Activity |
| --- | --- | --- |
| Summer | - ELA/ELD curriculum framework released* (July) - Promote ELA/ELD curriculum framework | - Promote awareness of the new ELA/ELD curriculum framework and utilize in professional learning opportunities as appropriate - Utilize the ELA/ELD curriculum framework as a blueprint for implementation of the CCSS for ELA and the CA ELD standards - Implement local technology plan |
| 2014–15 | CDE/SBE Activity | LEA Activity |
| Fall | - Provide professional learning opportunities and technical assistance to support full implementation of the CCSS | - Provide professional learning to support full implementation of the CCSS - Suggested Areas of Focus: - Mathematics: support content shifts in K–8 - ELA: writing informational text - General: transition to Smarter Balanced assessments |
| Winter |  |  |
| Spring | - Operational summative assessment administered | - Debrief with staff and students all elements of the Smarter Balanced summative assessment - Using feedback from debriefing, start planning adjustments to instruction and curriculum, formative practices, site-based assessments, expectations, learning goals, student/parent involvement, and all stakeholders’ roles for improvement next year |
| Summer |  | - Create site-based plan for professional learning to ensure continuous improvement of instruction and a higher level of academic achievement for all students |
| 2015+ | CDE/SBE Activity | LEA Activity |
|  | - Provide professional learning opportunities and technical assistance to support full implementation of the CCSS based upon needs assessment - Instructional materials adoption* (ELA/ELD November 2015) | - Implement site-based plan with regular progress monitoring and reflection |

* Indicates activity which requires SBE action