California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

With Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

County: Fresno		Local Educational Agency: Parlier Unified

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. | English/Reading-language Arts Currently the district is using the 2002 Houghton Mifflin ELA materials. As per the DAIT recommendations, the District intends to adopt new ELA curriculum and intervention materials to be in place by the Fall of 2010. The ELA tool Kit process was calendared and scheduled to take place from November through May with the assistance of Fresno County Office of Education. However, the District Leadership Team decided to implement its own internal adoption process and indicated it will make a decision about the new program selection by March 2010. |
| English/Reading-language Arts | Mathematics The district adopted new Math instructional materials in the 2007-2008 school year along with Holt Algebra readiness materials. As of November 2009, some classrooms still do not have instructional materials for all students (Williams notification) |
| Mathematics |  |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | To date 62 teachers have been trained in SB 472 Math Approximately 100 teachers have been trained in SB 472 ELPD 3 of 6 principals have completed the SB472 ELPD training 3 of 6 principals have completed SB472 Math training An ELPD “refresher” session was presented in October 2009 to keep current the use of instructional strategies to ensure that EL students have access to grade level content A district wide classroom observation checklist was developed and includes monitoring the use of EL strategies presented in the SB 472 ELPD trainings. |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | Nine EPC Level of implementation as per DAIT #1 Instructional/Intervention Materials (ELA, Math, ELD) The district currently uses the 2002 ELA adoption materials and anticipates the purchase of a new ELA curriculum to be in place by Fall 2010. Math instructional materials are in place in the majority of classrooms. SBE approved Intervention materials are not in place district wide. SBE approved ELD materials are not in place district wide. Teachers of students with disabilities have materials they need to fully implement their students IEPs. #2 Instruction Time The majority of High school, middle school, and elementary schedules reflect proper instructional minute’s requirements including time for ELD. Instructional minutes for SWD are as per student IEPs. #3 Lesson Pacing Guide Pacing guides for ELA and Math for the first semester only are in place at all sites and used by the majority of teachers. Pacing calendars for the second half of the year are being developed. #4 School Administrator Instructional Leadership Training Three elementary school principals have completed AB430. However, the High School and Middle School principals and one elementary school principal have NOT completed the initial 40 hour training at their assignment level. #5 Credentialed Teachers and Professional Development Opportunity The district has a current CMIS plan. However, not all teachers of EL students possess proper EL certification and not all teachers of SWD are considered to be highly qualified as per designated requirements. #6 Professional Development/Teacher Support The district has done an exemplary job of restructuring to provide each site with an academic coach. Not all positions have been filled due to a lack of qualified applicants at the High School Level. Ongoing Professional Development is in place to train the new academic coaches. #7 Student Achievement Monitoring System The District uses Data Director as a student achievement monitoring system. Multiple training sessions have been provided in order to ensure site level staff has access to information and reports. The district has recently purchased a new system that will be piloted at two sites and in the After School Program. ELA and Math benchmarks for grades 2-8 were purchased through ALS. High School benchmarks were developed by departments. No benchmarks or district wide assessments for K or 1 are in place. Teachers have access to curriculum embedded assessment but there is no district wide uniform plan to administer them or use their results. Data analysis of student achievement CST data is disaggregated to include EL students and students with disabilities. #8 Monthly Collaboration by Grade Level or Program Level for Teachers Facilitated by the Principal The district has a common weekly early release time but no district wide protocol or format exists for how that time will be used or monitored. Teachers of EL students and Students with disabilities are included in collaboration activities. #9 Fiscal Support The district categorical funds are coordinated, prioritized, and allocated to align with student need. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | AYP Targets: District Information 2008-2009 13 of 22 AYP targets met 2007-2008 13 of 22 AYP targets met 2006-2007 10 of 18 AYP targets met 2005-1006 11 of 22 AYP targets met Title I Schools not in PI All schools except for San Joaquin Valley Continuation High School are in program improvement API Growth 2008-2009 API Growth +22 2007-2008 API Growth +17 2006-2007 API Growth +3 2005-2006 API Growth +12 API performance Current API 620 |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

With Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Fresno		Local Educational Agency: Parlier Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance The district will hold teachers, site administrators, and district personnel accountable for student achievement through the development of a district assessment results review process. | The DAIT team, district cabinet and leadership team created a common district wide calendar that outlines assessments, cycle of inquiry follow-up, Principal Summits, presentations to the Board, as well as DAIT Diners to present achievement data to the public. | District Cabinet District Leadership Team DAIT Team Site administrators | Ongoing Aug-June | Partially Implemented |  |  |  | Challenges to full implementation include: 1. district wide benchmarks are inconsistent 2. alignment of benchmarks with current adoption and pacing guides is underway but has not been completed 3. district staffing to ensure ongoing rostering is inadequate (the district has recently hired a consultant to assist with technology needs. 5. Site staff is often unable to access test results due to data system problems. - |
| Alignment of Curriculum, Instruction, and Assessments to State Standards The district will develop a plan to fully implement at all sites the nine EPCs as outlined in the Academic Program Survey. Prior to the implementation of a Dual Immersion Program, the district will develop a research based, fully articulated plan that is detailed in the Master Plan for ELs. The district administration will hold site administrators responsible for daily classroom observations, observation logs, reflective questioning/ feedback with teachers, and reports to the district Cabinet to improve the quality and consistency of classroom instruction. | Create a plan that details SMART goals for implementation of the DAIT recommendations 1. Revise the existing EL Master Plan 2. Develop criteria for Dual Immersion classes 3. Parent and community input 4. Develop student identification and placement criteria 5. Create teacher job description to include responsibilities, qualifications and expectations 6. Develop and select criteria for instruction 7. Develop student achievement goals 8. Create assessment targets for all EL, SEI, and EI student groups. 9. Monitor academic progress in relations to other school sites (CST, STS, CELDT, benchmarks, and curriculum embedded assessments. 1. Communicate district superintendent expectation for site administrators to be in classrooms 2. Collaboratively create a district walkthrough protocol. 3. Provide protocol for collection of observation data (log) 4. Submit walk through data log to superintendent and DAIT Team on a monthly basis 5. Develop Principal Summit three times per year to report classroom instruction and student achievement progress. 6. Present data to district stakeholders at each trimester. | DAIT Team District Leadership Team District Director of Curriculum and Instruction FCOE Bilingual Coordinator District Cabinet and Leadership Team District Leadership Team Director of C & I Site administrators DAIT Team | 2009-2011 Ongoing August 2009 Aug-June ongoing | Minimally Implemented Substantially Implemented Minimally Implemented |  |  |  | A more concrete and systemic plan has recently been developed to ensure that the DAIT recommendations are implemented in a prioritized and systemic manner. The district and DAIT team EL coordinator developed a plan and criteria to collapse the Dual Immersion programs at three of the four elementary schools and to transfer all students whose parents requested a DI placement to one elementary site. Criteria for DI, SEI, and EI instructional materials and instruction was created, published and communicated to all K-12 teachers. Monitoring of student achievement is ongoing. The DAIT recommendation and superintendent’s directive for site administrators to conduct daily observations in classrooms is yet at an optimal level of implementation. Two of six principals submitted their observation log as requested by the DAIT team. Principals report that the district wide observation tool that was collaboratively developed does not meet their needs. It is currently being revised. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations (Cont.)

County: Fresno		Local Educational Agency: Parlier Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Fiscal Operations The LEA Plan will detail fiscal plans and expenditures as tied to achievement goals and priorities. (EPC 9) | Update LEAP to include DAIT recommendations and align fiscal resources | District Leadership Team District CBO Director of C&I DAIT Team | February 2009 | Fully Implemented |  |  |  | The District LEAP was revised to reflect current practice, goals, and DAIT recommendations. It was accepted without need of change and received a commendation by the SBE. |
| Parent and Community Involvement The district will implement family and parent involvement policies and programs at all schools in order to provide multiple opportunities for parents and family members to access school programs. | 1. Review and/or revise current district policy regarding parental involvement. 2. Establish opportunities to ensure two clear, timely, and two-way communication with parents about student achievement, academic, and other expectations, accountability requirements, and support of student success. 3. Create and distribute a parent survey. 4. Communicate to parents student expectations in core academic areas. 5. Establish transition opportunities from grade 6 to 7 and Grade 8 to 9. | District Leadership Team DAIT Team | Aug-June Ongoing | Substantially Implemented |  |  |  | The district has all required parental involvement policies in place as per compliance requirements for parental involvement in site councils and advisories. However, proper implementation at all sites is not evident. Translation is available at all school/district meetings as per CPM compliance. Opportunities exist at all sites for parents to receive information and participate in school activities. Progress reports, report cards and conferences are in place to inform parents of their child’s academic progress. Communications to parents are provided in their home language. A parent survey was conducted in May 2009. Results indicate that a large majority of parents feel welcome at school, feel they have a voice, and that their children are well taken care of, supervised, and encouraged to do their best. |
| Human Resources The district will restructure existing resource teacher positions and responsibilities to develop site content specialist positions (academic coach) to best provide flexibility, classroom coaching and modeling, and intervention opportunities. | 1. Create a job description for academic coaches. 2. Interview and hire 3. Assign coaches to individual sites 4. Provide weekly professional development for academic coaches | District Leadership Team DAIT Team | Aug-Sept 2009 | Substantially Implemented |  |  |  | The district has done an exemplary job of restructuring to provide each site with an academic coach. Not all positions have been filled due to a lack of qualified applicants at the High School Level. Professional Development is in place to train the new academic coaches. Steps to fully communicate the role of the academic coaches was needed and addressed by the superintendent. A district wide expectation was clarified and communicated to all sites as to the coaches main focus, time spent in classrooms, and ongoing professional development. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

With Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations (Cont.)

County: Fresno		Local Educational Agency: Parlier Unified

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Data Systems and Achievement Monitoring The district and site staff will analyze data from multiple sources (California Standards Tests, California English Language Development Test scores, benchmarks assessments, curriculum imbedded assessments) and develop action plans to improve instructional practices. (EPC 5) | 1. Develop Principal Summits three times annual to review CST, benchmark progress, language acquisition (CELDT) behavior, discipline, extra curricular involvement, attendance in the areas of Language Arts and Math to include interventions and next steps for insure student progress. | District Leadership Team DAIT Team | Ongoing | Partially Implemented |  |  |  | Site teacher Chats. Principals’ Summits and DAIT Dinners are in place to analyze and report data to all stakeholders. A systemic district wide plan for interventions is not yet in place. However, there is little evidence that the use of data is currently used to develop action plans to improve instructional practices. |
| Professional Development The district will calendar and provide professional development activities that reflect research-based strategies for improved student achievement with a focus on standards-based content knowledge and English Language Development. (EPC 4) | 1. Develop a PD calendar the instruction of English Learners | District Leadership Team DAIT Team | Aug-Jan Ongoing | Partially Implemented |  |  |  | Approximately 100 teachers have participated in SB472 ELPD during the past year. However, the majority of those teachers are in grades K-8. Fewer High School teachers have participated in the training. Only 3 of 6 principals have completed the training. Additional trainings are still available if participation numbers are adequate. |
| Other None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

With Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Fresno		Local Educational Agency: Parlier Unified

|  | 2008 AYP | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |
| LEA-wide | 21.5 | 26.3 | CST, STS, CMA ALS or teacher created benchmarks Curriculum embedded assessments | Annually Three times per year | Other than universal access, data is not used to determine program effectiveness. No district intervention program is in place at this time. Any before school, after school or Saturday school tutoring is site specific. Systemic criteria for entry into or exit from tutoring has been determined and data is not used other than as a predictor of CST. | 2009 AYP data indicate that the following percent of students scored proficient of above: ELA 23.6 Math 31.9 Benchmarks data. Cut points in Data Director were changed to better predict student 2010 AYP progress. First benchmarks results show that | To chart student progress, report to parents, inform stakeholder, prepare Principal Summit and DAIT Dinner presentations. Math and English scores are used for placement in High School and math classes. |
| Hispanic or Latino | 21.3 | 25.7 | CST, STS, CMA ALS or teacher created benchmarks Curriculum embedded assessments | Annually Three times per year Ongoing as per site/grade level/department discretion | See above | 2009 AYP data indicate that the following percent of students scored proficient of above: ELA 23.7 (+2.3 increase from 2008) Math 31.8 (+6.1 increase from 2008) 93% of the students are Hispanic with other student ethnic groups at 4% or less. Benchmark data is not disaggregated by ethnicity. | To chart student progress, report to parents, inform stakeholder, prepare Principal Summit and DAIT Dinner presentations. |
| Socioeconomically Disadvantaged | 21.6 | 26.3 | CST, STS, CMA ALS or teacher created benchmarks Curriculum embedded assessments | Annually Three times per year Ongoing as per site/grade level/department discretion | See above | 2009 AYP data indicate that the following percent of students scored proficient of above: ELA 23.6 (+2 increase from 2008) Math 31.9 (+5.6 since 2008) 81% of the students qualify for free or reduced lunch. Benchmark data is not disaggregated by student group at this time. | To chart student progress, report to parents, inform stakeholder, prepare Principal Summit and DAIT Dinner presentations. |
| English Learners | 17.1 | 23.6 | CELDT CST, STS, CMA ALS or teacher created benchmarks Curriculum embedded assessments | Annually Three times per year Ongoing as per site/grade level/department discretion | See above | 2009 AYP data indicate that the following percent of students scored proficient of above: ELA 22.9 (+5.8 since 2008) Math 32.6 (+9 since 2008) 50.4% of the students are identified as English Learners. AMAO goals: 2008 YES NO NO 2007 NO NO NO 2006 NO NO NO 2005 YES NO NO New configuration to the district’s Dual Immersion program took place for the 2009-2010 school year. Progress of those students enrolled in the DI program will be monitored to determine program effectiveness using AMAOs, CLEDT, CST progress, as well as benchmark data. Benchmark data is not disaggregated by language at this time. | CEDLT and CST data is used to determine ELD placement as well as to identify those students who qualify to be redesignated. CELDT scores are also used to determine placement in Dual Immersion or Structured English Immersion classes (along with parent waiver). |
| Students with Disabilities | 11.8 | 18.4 | CST, STS, CMA ALS or teacher created benchmarks Curriculum embedded assessments Placement assessments | Annually Three times per year Ongoing as per site/grade level/department discretion As per IEP | See above | 2009 AYP data indicate that the following percent of students scored proficient of above: ELA 15.2 (+3.4 since 2008) Math 13.0 (-5.4 since 2008) 331 students are identified as students with disabilities and received services at their elementary, middle or high school sites. Benchmark data is not disaggregated by student groups at this time. | To chart student progress, report to parents, inform stakeholder, prepare Principal Summit and DAIT Dinner presentations. To determine progress toward IEP goals. |