California Comprehensive Center Overview of Proposed Activities

The Project Plan for WestEd’s California Comprehensive Center proposal is organized around the following areas:

- Quality Schooling Framework to Guide, Motivate, and Support Effective Instruction and Student Outcomes

- Planning and Successful Implementation of Common Core State Standards

- Educator Excellence

- Increased Capacity to Support Productivity, Effectiveness, and Efficiency

Following is a description of key activities and the approach proposed to address each of the above listed areas.

Project Area: Quality Schooling Framework to Guide, Motivate, and Support Effective Instruction and Student Outcomes

YEAR 1 Finalize development of Quality Schooling Framework (QSF) Develop tools and resources to facilitate use of Quality Schooling Framework Create a process to collect and share emerging and promising practices aligned to Quality Schooling Framework domains Support creation of policies, guidance, and procedures within CDE that facilitate local implementation and use of Quality Schooling Framework Build local awareness of the QSF through outreach and convening

YEAR 2 Finalize organizing emerging and promising practices aligned to Quality Schooling Framework domains Continue to update tools Launch emerging, promising practice interactive web site Organize Quality Schooling Framework Symposium to highlight effective practice and promote resource sharing Review impact of policies, guidance, and procedures within CDE that facilitate local implementation and use of Quality Schooling Framework and work to improve as necessary

YEARS 3-5 Refine and improve QSF Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience Convene and disseminate information about QSF to promote use and participation in expanding resources associated with the QSF Assess impact of QSF on local implementation and outcomes for students

Project Area: Planning and Effective Implementation of Common Core State Standards

YEAR 1 Provide assistance and support to CDE’s CCSS Implementation Team (project managers and integrated action team) Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) Support development and use of professional development modules supportive of CCSS implementation Support development and integration of English Language Development (ELD) standards into revised English/Language Arts framework Promote understanding of purpose and usefulness of revised ELD standards Develop resources for schools and districts to provide access and learning opportunities related to CCSS for students with disabilities Develop resources for schools and districts to build awareness and prompt attention to equity concerns (e.g., teacher distribution, outcomes for students) related to CCSS Collaborate with the California Preschool Instructional Network to articulate CCSS to preschool and support objectives of Race to the Top Early Learning Imitative Incubate and support development and identification of promising and emerging practices Create a process to collect and share promising and emerging practices for CCSS implementation Contribute to CDE’s knowledge regarding local practice and pathways to career and college readiness

YEAR 2 Continue to assist and support CDE’s CCSS Implementation Team (project managers and integrated action team) Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) Promote professional development modules supportive of CCSS implementation Launch emerging, promising practice interactive web site Collaborate with the California Preschool Instructional Network to articulate CCSS to preschool and support objectives of Race to the Top Early Learning Imitative Incubate and support development and identification of promising and emerging practices Share effective examples of pathways to career and college readiness aligned to CCSS

YEAR 3-5 Continue to assist and support CDE’s CCSS Implementation Team (project managers and integrated action team) Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) Assess impact of CCSS on local implementation and outcomes for students Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience

Project Area: Educator Excellence

YEAR 1 Support development of plan to implement recommendations from the Educator Excellence Task Force Support development of Professional Learning Standards and related quality indicators Identify models of effective evaluation practice for development and support of classroom and site leadership with tools and resources to support application Convene and support teacher and principal evaluation design team Create a process to collect and share promising and emerging practices related to teacher and administrator recruitment, induction retention, professional learning, and evaluation Provide support related to teacher and principal evaluation to School Improvement Grant districts and schools Provide support related to teacher evaluation to Teacher Incentive Fund grantees

YEAR 2 Continue to provide support to implement recommendations from the Educator Excellence Task Force Facilitate development of tools that support application of Professional Learning Launch emerging, promising practice interactive web site Continue providing support related to teacher and principal evaluation to School Improvement Grant districts and schools Provide support related to teacher evaluation to Teacher Incentive Fund grantees

YEAR 3-5 Continue to assist and support implementation of Educator Excellence recommendations Assess impact of Educator Excellence initiatives on local implementation and outcomes for students Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience

Project Area: Increased Capacity and Support Productivity, Effectiveness, and Efficiency

YEARS 1-5 Develop and coordinate professional growth series for CDE and CDE-affiliated networks of support Support ongoing use of the California Accountability and Improvement System (CAIS) to streamline reporting and monitoring and increase efficiency Develop tools and resources to facilitate efficient and effective program and fiscal monitoring and offerings of technical assistance Develop creative approaches to using available data from CDE, IHEs, and others to inform local decisions impacting student outcomes.

Prepared by WestEd California Comprehensive Center | October 2012