| California Department of Education Executive Office SBE-003 (REV. 09/2011) ilsb-plsd-mar13item01 | ITEM #04 |
| --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION March 2013 AGENDA |
| SUBJECT Update on the public process to revise the Science Content Standards for California Public Schools, Kindergarten through Grade Twelve based upon the nationally developed Next Generation Science Standards as required by Education Code 60605.85. |  | Action |
|  |  | Information |
|  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

This agenda item provides the State Board of Education (SBE) and the public information on the public process that the California Department of Education (CDE), in collaboration with the California Comprehensive Center (CA CC) at WestEd, intends to utilize to revise the Science Content Standards for California Public Schools, Kindergarten through Grade Twelve based upon the nationally developed Next Generation Science Standards as required by Education Code (EC) Section 60605.85.

RECOMMENDATION

The CDE recommends that the SBE take action as deemed necessary and appropriate but recommends no specific action at this time.

BRIEF HISTORY OF KEY ISSUES

EC Section 60605.85 required the State Superintendent of Public Instruction (SSPI) to submit a set of revised Science Content Standards for California Public Schools, Kindergarten through Grade Twelve to the SBE in March 2013.  Due to the number of responses received during the first public release, Achieve, Inc. announced a delay in the release of the final draft of the NGSS in order to adequately address the public feedback.  Due to this delay, the State Superintendent of Public Instruction (SSPI) sponsored Senate Bill (SB) 1200 to extend the time to present new California Science Standards to the SBE. On September 27, 2012, SB 1200 was signed into law. This bill extended the time for new science standards to be presented to the SBE from March 30, 2013, to July 31, 2013, and the adoption, rejection, or modification of those standards by the SBE from July 30, 2013, to November 30, 2013. The revised science standards for California must be based upon the nationally developed Next Generation Science Standards (NGSS).

The development of the NGSS is based on a national framework commissioned by the National Research Council (NRC).The national framework was developed by an 18 member nationally recognized science committee. The NRC framework committee was chaired by Dr. Helen Quinn, a professor of Physics at Stanford University. The complete framework is available on the National Academies Web site at http://www.nap.edu/.

Twenty-six Lead State Partners are guiding the standards writing process, providing feedback from state-level committees, and coming together to address common issues and challenges. On September 20, 2011, Achieve, Inc. officially announced that California is one of the Lead State Partners who are participating in the development of the NGSS. The state’s efforts in this endeavor are lead by Phil Lafontaine, Director of the Professional Learning Support Division and his staff. As a Lead State Partner, California also agreed to commit staff time to the initiative and, upon completion, give serious consideration to adopting the NGSS.

To provide input from California, the SSPI commissioned the State Review Team (SRT), consisting of 80 science experts representing kindergarten through grade twelve (K–12) science teachers, administrators, county science consultants, college and university professors, and business and industry. Facilitated by the CDE, the first meeting of the SRT was held on November 30, 2011, where members reviewed a sampling of draft science standards. The team was also given the opportunity to review the complete set of standards in February 2012, May 2012, October 2012, and January 2013. While the review process is confidential and the standards are still under review, the SRT generally agrees with the direction of the standards and that these standards will improve science education for our students.

Public drafts of the proposed NGSS were made available to the public for input twice during the development process. The first public draft was available for review and feedback for three weeks in May 2012, and the second public draft was available for three weeks in January 2013. During each public release, Achieve, Inc., released several supporting documents to provide additional information as to the background and organization of the standards. During these public releases, numerous members of the SRT, including classroom science teachers and county science consultants, facilitated group review sessions and submitted group feedback to Achieve, Inc.

The NGSS is scheduled to be completed in March 2013. Should the NGSS not be released in time, the proposed timeline will need to be revised.  Additional information is available on the NGSS Web site at http://www.nextgenscience.org/.

A few editorials and reports have been generated based on the second draft of the NGSS.  The CDE, SBE, and SBE liaisons have been in communication with Achieve to address these issues.

Once the final draft of the NGSS is released, the CDE, with support of the CA CC of WestEd, will embark on a process to recommend the Science Content Standards for California Public Schools, Kindergarten through Grade Twelve to the SBE (see attachment three for proposed timeline). The process will encompass several steps involving the SRT and a panel of science experts who are representative of the SRT, referred to as the Science Expert Panel (SEP). Additionally, the process will allow for public comment at three Regional Public Forums.

As a first step, in January 2013, the CDE, in collboration with science specialists from the SRT and the CA CC, conducted a preliminary analysis of the alignment of California’s existing science standards with the NGSS. The second public draft of the NGSS was utilized for the analysis. A final analysis will be conducted once the final draft of the NGSS is released.

Once the final draft is released, the CDE, with support from the CA CC, will conduct a survey of SRT members to seek input regarding the final draft of the NGSS and the working group analysis.

In March 2013, the SEP will convene to review: (a) the final draft of the NGSS; (b) the analysis of California standards to NGSS; and (c) survey input from members of

the full SRT. By the end of March 2013, the SEP will produce a first draft Science Content Standards for California Public Schools, Kindergarten through Grade Twelve for public review.

Regional Public Forums will be conducted in Northern, Southern, and Central California in late March and April 2013. Exact locations and dates of the events are curently being scheduled. The public will be noticed once all logistics are confirmed. At these meetings, public stakeholders will receive background on the NGSS and the proposed California Science Standards. They will have an opportunity to provide input for consideration by the SEP. The CDE and CA CC staff will document public input and share it with the SEP.

As a final step, the SEP will reconvene to make any revisions based on public input and share a new draft of the California Science Standards with the SRT by early May 2013.

Once this group has conducted its final review, the SEP will incorporate revisions and submit this version to the SSPI, the CDE, and the SBE for consideration in July 2013.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

November 2012: The CDE updated the SBE through an Information Memorandum on the development of NGSS.

May 2012:  At its May 2012 meeting, The CDE staff presented on the progress and timeline of the development of the NGSS along with Dr. Stephen L Pruitt, Vice President for Content, Research, and Development at Achieve, Inc.

November 2011: The CDE’s presentation also provided information on the requirements of Senate Bill 300. Specifically, the SSPI was required to recommend science content standards–utilizing the NGSS as their basis–to the SBE by March 30, 2013. The SBE was required to adopt, reject, or modify those standards by July 30, 2013. Information regarding the state’s involvement in the national process for the development of the NGSS was discussed.

FISCAL ANALYSIS (AS APPROPRIATE)

Projected estimated costs for participating in the development of the NGSS are approximately $186,000. CDE is seeking foundation funding to cover the costs of required trips to Washington, convening the California teams, and for staff to coordinate the logistics associated with the development of the standards.

ATTACHMENT(S)

Attachment 1: Timeline for the Development of the Next Generation of Science Standards (1 Page).

Attachment 2: CDE Timeline of Next Generation Science Standards Development

Process (1 Page).

Attachment 3: California Science Standards Review and Adoption Process (2 Pages).

Timeline for the Development of the Next Generation Science Standards

The information provided below outlines the general development process and timeline and it is replicated from the Next Generation Science Standards (NGSS) Development Process Web page at http://www.nextgenscience.org/development-process.

The NGSS has been through several rounds of review with multiple stakeholder groups. Each group received draft standards at least twice throughout the development process.

# Next Generation Science Standards Development Process

California Science Standards Review and Adoption Process

Context

The Next Generation Science Standards (NGSS) are designed to serve as high quality college and career-ready K-12 standards ready for state adoption. Twenty-six states, including California, have participated in the national development process facilitated by Achieve, Inc. The NGSS are based on the July 2011 National Research Council’s A Framework for K-12 Science Education: Practices, Crosscutting Concepts, and Core Ideas.  The development process has engaged numerous stakeholders, including nationally-recognized leaders in science, science education, higher education, and industry. The NGSS have undergone multiple reviews, including two public drafts. As required by this national process, California selected a group of 80 science experts, known as the State Review Team (SRT) to conduct confidential reviews of the various drafts of the NGSS. The final version of the NGSS will be available in March 2013.

Purpose

For the NGSS to be used by California, they must be reviewed and adopted by the State Board of Education (SBE). Senate Bills 300 and 1200 require that by July 2013, the Superintendent of Public (SSPI) Instruction submit new science standards to the SBE for review and consideration. Given that the NGSS are not scheduled to be released in their final format until March 2013, this means that California must initiate a fast-paced process to engage key stakeholders in reviewing the NGSS and recommend set of standards for consideration and adoption in July 2013. Given the compressed timeline, the CDE will enlist the help of select members of the SRT, referred to as SEP, to review and analyze the NGSS, and develop a first draft for public review and comment.  Below is the proposed process and timeline for engaging subject-matter experts and other science, education, business, and community stakeholders in this review.

Proposed Review Timeline:

Late January 2013

- Subject-area analysis groups analyze NGSS and current CA standards

By Late February 2013

- Survey of SRT members regarding NGSS and workgroup analysis

March 2013

- SEP reviews the NGSS work group analysis and survey input

- SEP develops first draft of the CA Science Standards

Early April 2013

- Regional public stakeholder forums and compilation of public input

By Early May 2013

- SEP reviews public input from stakeholder forums

- SEP develops second draft of CA Science Standards

Mid-May 2013

- SRT reviews the latest draft of the CA Science Standards and submits comments to the SEP

By late May 2013

- SEP reviews SRT comments and prepares final proposed CA Science Standards

June 2013

- Proposed CA Science Standards prepared for submission to the SBE

July 2013

- SBE review of proposed CA Science Standards for consideration of adoption

# Text boxes

2014*: Implementation of New Science Standards

October 2012: Third Meeting of SRT

March 2013: Final Draft of NGSS Released

February 2012: Second Meeting of SRT

* Pending SBE’s action in November 2013

September 2011: California Selected as Lead State in the Development of NGSS, Based on Framework

Spring 2013: Three Regional Public Forums

November 30, 2013: California SBE Adopts, Rejects, or Modifies Recommended Science Standards

July 31, 2013: SSPI Presents to California SBE Recommended Science Standards Based on the NGSS

2011: Promotion of the NGSS and Conceptual Framework at Conferences and Workshops

January 2013: Second Public Draft of NGSS Released

May 2012: First Public Draft of NGSS Released

November 2011: First Meeting of SRT comprised of Science Experts

| 2011 | 2012 | 2013 | 2014 |
| --- | --- | --- | --- |

July 2011: Framework for K-12 Science Education Released by National Research Council