| California Department of Education Executive Office SBE-003 (REV. 09/2011) pptb-adad-nov17item02 | ITEM #09 |
| --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION NOVEMBER 2017 AGENDA |
| SUBJECT California Assessment of Student Performance and Progress: Determination of the Release of Up to 10 Percent Withheld for the 2016–17 Educational Testing Service Contract. |  | Action |
|  |  | Information |
|  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

The California Assessment of Student Performance and Progress (CAASPP) contract with Educational Testing Service (ETS), approved by the State Board of Education (SBE), specifies that on or before the annual November SBE meeting, the California Department of Education (CDE) shall present to the SBE a recommendation regarding the performance of ETS in complying with the terms and conditions of the contract for the prior-school-year test administration.

Per California Education Code (EC) Section 60643, the CDE must withhold 10 percent from progress payments invoiced for each component task. The CAASPP contract establishes the process and criteria by which the CDE recommends, and the SBE approves, the annual release of the 10 percent withheld from progress payments.

The completion criteria for the CAASPP contract component tasks are provided in Attachment 1, and the approved contract provisions regarding the annual determination of successful completion of component tasks are outlined in Attachment 2.

RECOMMENDATION

The CDE recommends releasing a total of $7,689,266.60 from funds withheld during the 2016–17 test administration. The CDE further recommends not releasing $170,000 to the contractor specific to component task 9. The amounts per task are listed in Attachment 3.

BRIEF HISTORY OF KEY ISSUES

The CDE has reviewed the performance of ETS in complying with the contract and determined that ETS has satisfactorily performed contract component tasks 1 through 8 for both the CAASPP computer-based assessments and the paper-pencil tests during the 2016–17 test administration to date, pending completion of all contract requirements through December 2017. Therefore, the CDE is recommending approval of the 10 percent release for those tasks. The contract task descriptions are listed in Attachment 3.

However, in the CDE’s review of ETS’s compliance with contract component task 9, it was determined that ETS did not satisfactorily perform a portion of that contract component included in the outline below. The CDE and ETS have met to resolve errors in the 2016–17 test administration and ETS has put into action corrections that are intended to ensure success in the future.

Task 9: Reporting

The CDE recommends the release of $98,088.10 of the 10 percent withhold for task 9 related to reporting to local educational agencies (LEAs), performing secure file transfers protocols, and completing additional analyses.

The CDE also recommends the non-release of $170,000 of the 10 percent withhold for task 9, as related to the Smarter Balanced Summative Assessments, because ETS did not satisfactorily follow CDE-approved aggregation rules for the display of assessment data on the public CAASPP Results Web site and delivered a file with incomplete test administration window information for multitrack schools, as specified in the contract. Neither of these issues had an impact on the accuracy of individual student scores. Details for each of the component tasks within Task 9 include:

9.1. Reporting to Local Educational Agencies

ETS satisfactorily implemented a comprehensive and secure online reporting system for interactive reporting at the LEA, school, and student levels. Although an error was identified on the Student Score Reports, ETS implemented a successful remediation plan and absorbed the costs of resolving the error.

9.2. Reporting to the CDE—Public Reporting Web Site

ETS satisfactorily designed, developed, and implemented the CDE’s public reporting Web site, complied with student privacy rules, provided summary data, and provided research files. However, ETS neglected to properly implement the CDE-approved aggregation rules when creating public reporting files. This error was corrected but, because the deliverable did not meet the specifications of the contract, the error is reflected in the non-release amount.

9.3. Data Files

ETS satisfactorily maintained a student database to house all student demographic data and assessment results. ETS made an error in the student data files delivered for state and federal accountability program calculations. This error was also corrected but, because the deliverable did not meet the specifications of the contract, the error is reflected in the non-release amount.

9.4. Secure File Transfer System

ETS satisfactorily maintained secure file transfer protocol because of the confidential nature of student information and test results, meeting the requirements of this subtask.

9.5. Technical Report

ETS satisfactorily produced technical reports for each administered summative assessment, including pilot and field test assessments, meeting the requirements of this subtask.

9.6. Other Analyses or Reports

ETS was a responsive and beneficial partner with the CDE and SBE staff/liaisons in identifying and expanding on research questions, meeting the requirements of this subtask.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

In July 2017, the SBE gave the CDE the authority to begin the process of approving a renewal of ETS’s administration contract for an additional two years (https://www.cde.ca.gov/be/ag/ag/yr17/documents/jul17item04.doc).

In May 2017, the SBE approved the proposed contract amendment with ETS for the CAASPP contract (https://www.cde.ca.gov/be/ag/ag/yr17/documents/may17item02.doc).

In March 2017, the SBE gave the CDE the authority to begin negotiations with ETS to amend the existing Scope of Work for the CAASPP contract (https://www.cde.ca.gov/be/ag/ag/yr17/documents/mar17item06.doc).

FISCAL ANALYSIS (AS APPROPRIATE)

The funds to be released were withheld during 2016–17 from invoices paid with existing CAASPP System contract funding, shown in Attachment 3. The CDE recommends the release of $7,689,266.60. The CDE recommends not releasing $170,000 specific to task 9. Any portion of the funds withheld during 2016–17 will revert back to the state General Fund and cannot be used for any other purpose. The reversion date for fiscal year 2016–17 funding is June 30, 2019. The amounts per task are listed in Attachment 3.

ATTACHMENT(S)

Attachment 1: California Assessment of Student Performance and Progress Completion Criteria (3 Pages)

Attachment 2: California Assessment of Student Performance and Progress Process for Determination of Successful Completion of Component Tasks (2 Pages)

Attachment 3: California Assessment of Student Performance and Progress Contract 2016–17 Test Administration Component Task Budget (1 Page)

# Educational Testing Service

CDE Agreement # CN150012

Exhibit E

California Assessment of Student Performance and Progress

Completion Criteria

The criteria by which the California Department of Education (CDE) will recommend and the State Board of Education (SBE) will determine the successful completion of each separate and distinct component task for payment of the final 10 percent is set forth in the following table for each test administration covered in Exhibit A, Scope of Work (SOW) of the Agreement.

If it is determined by the CDE that a certified deliverable submitted to the CDE by the contractor does not meet all of the criteria in Exhibit E, the CDE reserves the right to use this information as part of the criteria by which the CDE will recommend, and the SBE will determine, successful completion of each separate and distinct component task for payment of the final 10 percent for each applicable test administration as set forth in the California Assessment of Student Performance and Progress (CAASPP) completion criteria shown in the following table:

Criteria for Successful Completion of Component Tasks

| Component Task | Criteria |
| --- | --- |
| Task 1 Comprehensive Plan and Schedule of Deliverables | The contractor provided all reports, plans, and schedules required in the task as specified in the SOW. All materials, documents, and/or deliverables developed in conjunction with this contract were submitted to the CDE for approval. The contractor provided the local educational agency (LEA) coordinators with all data, forms, and agreements as outlined in the SOW. The contractor provided and maintained a secure Web-based CAASPP administration management system as specified in the SOW. The contractor delivered all electronic data files and documentation as specified in the SOW. |
| Task 2 Program Support Services | The contractor provided all trainings, focus groups, workshops, and Webcasts as specified in the SOW. The California Technical Assistance Center provided assistance to LEAs as specified, and within the response times specified, in the SOW. The CDE received electronic files and other reports as specified in the SOW. |
| Task 3 Technology Services | The Assessment Delivery System meets all system requirements as specified in the SOW. The contractor provided a single sign-on as detailed in the SOW. Contractor provided and maintained a Project Management Plan as detailed in the SOW. The Assessment Delivery System supported up to 500,000 concurrent users as specified in the SOW. The Assessment Delivery system supported at least 99.982 percent availability as specified in the SOW. |
| Task 4 Test Security | All test items, test materials, electronic files, and data (including student-identifiable data) were developed, used, transferred, delivered, and maintained in a secure manner as specified in the SOW. The contractor completed all monitoring (including, but not limited to, on-site visits, social media monitoring, and inventorying of materials) of schools before, during, and after testing as specified in the SOW. The contractor conducted security breach investigations as specified in the SOW. The contractor provided the CDE with summary reports of the results of each security breach investigation. |
| Task 5 Accessibility and Accommodations | The contractor provided all universal tools, designated supports, and accommodations as required in the SOW. All items developed (as specified in Task 6) include all the embedded accessibility supports and functionality and render within the test delivery system as specified in the SOW. |
| Task 6 Assessment Development | The contractor developed for all grades and subjects the number and types of items specified in the SOW. The contractor pilot tested or field-tested the minimum required number of items as specified in the SOW. The contractor provided blueprints for new assessments as specified in the SOW. A review of the scaling and equating processes showed items to meet or exceed industry standard. The performance level settings generated results for all content areas, and performance levels were reported to LEAs and the CDE. |
| Task 7 Test Administration | All test materials required in the SOW were produced on time and in sufficient quantities. All test materials were delivered to and retrieved from LEAs as specified in the SOW. The contractor hosted the Assessment Delivery System as specified in the SOW. The hosting systems (Test Operations Management System; Appeals, and Assessment Delivery System) were operational and functioned as specified in the SOW, including the authentication of users. Smarter Balanced Interim Assessments were hosted and scoring was provided as specified in the SOW. |
| Task 8 Scoring and Analysis | All tests were correctly processed and scored within timelines specified in the SOW. All data analyses were completed as specified in the SOW. The contractor delivered all electronic data files and documentation as specified in the SOW. |
| Task 9 Reporting | The contractor provided accurate and complete reports of test results to LEAs that met all reporting requirements as specified in the SOW. The contractor provided accurate and complete reports of test results for the public reporting Web site that met all reporting requirements as specified in the SOW. The contractor met all reporting requirements to the CDE as specified in the SOW. The annual technical reports were received by the CDE as specified in the SOW. |

California Assessment of Student Performance and Progress

Process for Determination of Successful Completion of Component Tasks

California Education Code (EC) Section 60643 requires the following:

- The California Department of Education (CDE) is to withhold no less than 10 percent of the amount budgeted for each separate and distinct component task provided for in the California Assessment of Student Performance and Progress (CAASPP) contract pending final completion of all component tasks.

- The CAASPP contract is to establish the process and criteria by which the successful completion of each component task will be recommended by the CDE and approved by the State Board of Education (SBE).

The approved CAASPP contract is the result of a collaborative process involving SBE staff, the CDE, and Educational Testing Service. It includes the following contract provisions regarding the annual determination of successful completion of component tasks:

CN150012, Exhibit B, Section IX, Process for Release and Payment of Withhold:

Pursuant to EC 60643, the following establishes the process and criteria by which the successful completion of each component task shall be recommended by the CDE and approved by the SBE.

A. Process

1. 	SBE Determination: During the term of the Agreement, based on the criteria set forth below, the SBE will determine at its November Board Meeting, or the next meeting thereafter if a November meeting is not held, whether the contractor has successfully completed each component task for the prior fiscal year. If the SBE determines the contractor has not successfully completed each component task for the prior fiscal year, it shall, within 10 days of its determination, notify the contractor and the CDE in writing which component tasks the SBE has determined that the contractor has failed to successfully complete. The contractor shall have 10 days from receipt of the notice to respond in writing, and the response shall be promptly delivered to the CDE Contract Monitor.

At the following SBE meeting, the CDE and the contractor will have an opportunity to discuss the issues before the SBE. The SBE will, at the same meeting, make its final determination, based on the criteria set forth below, as to whether the contractor has successfully completed each task or component of a task for the prior fiscal year and releases the withholding for those component tasks.

2. 	Release: Once the SBE has determined that the contractor has successfully completed a component task, the 10 percent withheld from invoices for the component task for the prior fiscal year may be released by the CDE. The contractor must submit an invoice to CDE for the withheld amounts for each component task which SBE authorized release. The contractor must identify the prior invoice from which the money was withheld and the applicable component task in its invoice for the released withholding.

B. 	Criteria: The criteria by which CDE will recommend and the SBE will determine successful completion of each component task for payment of the final 10 percent will be set forth in Exhibit E.

California Assessment of Student Performance and Progress Contract

2016–17 Test Administration Component Task Budget

The California Department of Education recommends releasing a total of $7,689,266.60 to Educational Testing Service from funds withheld during the 2016–17 California Assessment of Student Performance and Progress (CAASPP) test administration.

| Component Task Scope of Work A | Total 2016–17 Test Administration Budget | Amount Paid/ To Be Paid from Progress Payments* | 10 Percent Withheld (Pending Release) | Recommended (Release) | Recommended Withhold (Non-Release) |
| --- | --- | --- | --- | --- | --- |
| Task 1: Comprehensive Plan and Schedule of Deliverables | $4,799,100 | $4,319,190.00 | $479,910.00 | $479,910.00 |  |
| Task 2: Program Support Services | $7,892,150 | $7,102,935 | $789,215.00 | $789,215.00 |  |
| Task 3: Technology Services | $4,701,024 | $4,230,921.60 | $470,102.40 | $470,102.40 |  |
| Task 4: Test Security | $100,577 | $90,519.30 | $10,057.70 | $10,057.70 |  |
| Task 5: Accessibility and Accommodations | $100,491 | $90,441.90 | $10,049.10 | $10,049.10 |  |
| Task 6: Assessment Development | $8,519,029 | $7,667,126.10 | $851,902.90 | $851,902.90 |  |
| Task 7: Test Administration | $28,719,157 | $25,847,241.30 | $2,871,915.70 | $2,871,915.70 |  |
| Task 8: Scoring and Analysis | $21,080,257 | $18,972,231.30 | $2,108,025.70 | $2,108,025.70 |  |
| Task 9: Reporting | $2,680,881 | $2,412,792.90 | $268,088.10 | $98,088.10 | $170,000 |
| Totals: | $78,592,666 | $70,733,399.40 | $7,859,266.60 | $7,689,266.60 | $170,000 |

*Pending completion of all contract component tasks for the 2016–17 CAASPP test administration through December 2017.