# Attachment 2: CALIFORNIA STATE PLAN FOR CAREER TECHNICAL EDUCATION Working Timeline

This document is a working timeline for the submission of the Federal *Strengthening Career Technical Education for the 21st Century Act* (Perkins V) State Plan, including an extended timeline to complete the full California State Plan for Career Technical Education (CTE).

## Completed:

### 2019

*Jan. 11 The California Workforce Pathways Joint Advisory Committee (CWPJAC) received a presentation on the requirements for the state’s 2019–20 transition plan for the Federal Strengthening Career and Technical Education for the 21st Century Act (Perkins V)*

*Feb. 19 CWPJAC reviewed the 2019–20 Federal Perkins V Transition Plan for the Federal Strengthening Career and Technical Education for the 21st Century*

*March 11 CWPJAC reviewed and provided input to the Draft Federal 2019–20 California Perkins V State Transition Plan*

*May 8 The State Board of Education (SBE) approved the Draft Federal Perkins V State Transition Plan*

*May 24 Federal Perkins V Transition Plan submitted to the United States Department of Education (ED)*

*May 29 CWPJAC received an update on the 2019–20 Federal Perkins V Transition Plan, and the progress of the development of the 2020–23 Federal Perkins V State Plan*

*July 1 Federal Perkins V Transition Plan approved by the ED*

*July 12 CWPJAC received an update on the development of the California State Career Technical Education Plan, including requirements for the Federal Strengthening Career and Technical Education for the 21st Century Act (Perkins V)*

*Aug. 7 Virtual Stakeholder Meeting*

*Aug. 13 Stakeholder In-Person Meeting #1 – 10:00 A.M. to 3:00 P.M. at the Sacramento County Office of Education’s Conference Center*

*Sept. 13 CWPJAC reviewed portions of the Draft Federal Perkins V State Plan*

*Sept. 17 Stakeholder In-Person Meeting #2 – 10:00 A.M. to 5:00 P.M. at the California Community Colleges Chancellor’s Office (CCCCO)*

*Oct. 2–4 Advance CTE – Perkins V Implementation Meeting, Washington DC, five team members attended representing the SBE, CDE and CCCCO*

*Oct. 11 CWPJAC reviewed portions of the Draft Federal Perkins V State Plan*

*Oct. 16 California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Gather Feedback*

*Oct 17 Kindergarten through grade twelve (K–12) Teacher Feedback Virtual Meeting*

*Nov. 7 CWPJAC reviewed the first complete Draft Federal Perkins V State Plan*

*Nov. 20–22 Association of Career and College Readiness Organizations (CAROCP) CTE Conference, Rancho Mirage, CA – Gather feedback*

*Nov. 25 CWPJAC reviewed a second version of the complete Draft California Perkins V State Plan*

*Dec. 2 In-Person Public Input Meeting #1 - North Orange County Community College District’s Boardroom (prior to the national Association for CTE Conference [ACTE] in Anaheim on December 4–7, 2019):*

* *10:00 A.M.–12:00 P.M.*
* *1:00 P.M.–3:00 P.M.*

*Open the Draft Federal Perkins V State Plan Public Feedback Survey*

*SBE staff to share the Draft Federal Perkins V State Plan with the Governor’s Office*

*Dec. 6 Virtual Public Web Meeting*

*Dec. 9 In-Person Public Input Meeting #2 - Christopher Center Building, WestEd Offices, Capitol Room, Sacramento:*

* *10:00 A.M.–12:00 P.M.*
* *1:00 P.M.–3:00 P.M.*

*Dec. 11–13 Joint Special Populations Advisory Committee (JSPAC) Conference – Opportunity for obtaining public feedback*

### 2020

*Jan. 3 Close the Federal Perkins V State Plan Public Feedback Survey   
(32 days)*

*Jan. 6 Virtual Accountability Stakeholder Input Session*

## In Progress:

Jan 6–10 Analyze Federal Perkins V State Plan Public Feedback Survey results

Jan 6–17 Combine feedback (January SBE Meeting, January Board of Governors (BOG) of the California Community Colleges Meeting, and the Public Feedback Survey results) into the final Draft Federal Perkins V State Plan

Jan. 8 SBE Meeting – Draft Federal Perkins V State Plan is presented

Jan. 31 CWPJAC Meeting – Final Review of the revised Draft Federal Perkins V State Plan and approval

Feb. 1–5 Incorporate CWPJAC feedback into the Federal Perkins V State Plan, including all public input, to present to the SBE in March

March 11–12 SBE Meeting – Revised Draft Federal Perkins V State Plan approved

March 13 CWPJAC Meeting

March 13 The Final Draft Federal Perkins V State Plan is forwarded to the Governor for approval

March 16 BOG Meeting, the final Federal Perkins V State Plan is presented (informational item)

April 12 Governor Approval of the Federal Perkins V State Plan Complete   
(30 days)

April 15 Submit the Federal Perkins V State Plan to the ED

## Extension to complete the comprehensive California State Plan for CTE

May 8 CWPJAC Meeting

July 1 Receive ED’s response to the Federal Perkins V State Plan

July 10 CWPJAC Meeting

Aug.–Sept. Public Feedback on draft of the comprehensive California State Plan for CTE

September CWPJAC Meeting

November CWPJAC Meeting

### 2021

January SBE and BOG approval of the comprehensive California State Plan for CTE