# Schedule of Significant Events for the 2020 Revision of the *Visual and Performing Arts Framework for California Public Schools, Kindergarten Through Grade Twelve (VAPA Framework)*

Not Yet Approved by the State Board of Education

| **Event** | **Schedule** |
| --- | --- |
| Focus Group recruitment letter and application distributed to districts, visual and performing arts (VAPA) stakeholder organizations, and institutes of higher education | **March 2018** |
| Recruitment of Focus Group members, pursuant to *California Code of Regulations,* Title 5 (5 *CCR)* §9511(c) | **March–April, 2018** |
| Instructional Quality Commission (IQC) approves Schedule of Significant Events and Curriculum Framework and Evaluation Criteria Committee (CFCC) Application | **May 17, 2018**  |
| State Board of Education (SBE) approves Schedule of Significant Events and CFCC Application (pursuant to 5 *CCR* §9513) | **July 11–12, 2018** |
| State Superintendent of Public Instruction appoints Focus Group members | **July 2018** |
| Four Focus Group meetings (pursuant to 5 *CCR* §9511[c]):* August 16, 2018: San Diego County Office of Education(4–6 p.m.)
* August 22, 2018: Santa Clara County Office of Education(4–6 p.m.)
* August 30, 2018: California Department of Education and via videoconference at Humboldt and Tulare County Offices of Education (4–6 p.m.)
* September 12, 2018: Los Angeles County Office of Education (4–6 p.m.)
 | **August–September 2018** |
| Minimum 90-day recruitment of CFCC (from date application posted through SBE appointment of CFCC) pursuant to 5 *CCR* §9513 | **August–October 2018** |
| IQC receives Focus Group input and recommends CFCC members and guidelines for the revision of the framework to the SBE | **November 15–16, 2018** |
| SBE receives Focus Group input, approves guidelines for the revision of the framework, and appoints CFCC | **January 9–10, 2019** |
| CFCC Meetings are scheduled for the following dates:* February 28–March 1, 2019
* April 4–5, 2019
* May 2–3, 2019
* June 13–14, 2019
* July 18–19, 2019
* August 15–16, 2019
 | **February–August 2019** |
| IQC approves draft framework for initial 60-day public review period | **September 19–20, 2019** |
| Required 60-day public review of draft *VAPA Framework* prior to IQC recommendation (pursuant to 5 *CCR* §9515[a][3]) | **October–November 2019** |
| IQC analyzes field review results and revises draft *VAPA Framework* | **January 2020** |
| IQC action on draft *VAPA Framework* | **January 2020** |
| Required 60-day public review of document after IQC recommendation (pursuant to 5 *CCR* §9515[c]) | **February–March 2020** |
| SBE action to adopt *VAPA Framework* | **May 2020** |
| Date of adoption of instructional materials | **November 2021** |

This timeline is subject to change. The SBE will only take action on changes to the approved timeline if they affect IQC or SBE action dates.

California Department of Education May 17, 2018