# Schedule of Significant Events for the *2020 Revision of the World Languages Framework for California Public Schools, Kindergarten Through Grade Twelve (WL Framework)*

Not Yet Approved by the State Board of Education

| **Event** | **Schedule** |
| --- | --- |
| Focus Group recruitment letter and application distributed to districts, world language stakeholder organizations, and institutes of higher education | **March 2018** |
| Recruitment of Focus Group members, pursuant to *California Code of Regulations,* Title 5 (5 *CCR)* §9511(c) | **March–April, 2018** |
| Instructional Quality Commission (IQC) approves Schedule of Significant Events and Curriculum Framework and Evaluation Criteria Committee (CFCC) Application | **May 17, 2018** |
| State Board of Education (SBE) approves Schedule of Significant Events and CFCC Application (pursuant to 5 *CCR* §9513) | **July 11–12, 2018** |
| State Superintendent of Public Instruction appoints Focus Group members | **July 2018** |
| Four Focus Group meetings (pursuant to 5 *CCR* §9511[c]):   * August 16, 2018: San Diego County Office of Education  (4–6 p.m.) * August 22, 2018: Santa Clara County Office of Education  (4–6 p.m.) * August 29, 2018: California Department of Education  (4–6 p.m.) and via videoconference at Humboldt and Tulare County Offices of Education * September 12, 2018: Los Angeles County Office of Education (4–6 p.m.) | **August–September 2018** |
| Minimum 90-day recruitment of CFCC (from date application posted through SBE appointment of CFCC) pursuant to 5 *CCR* §9513 | **August–October 2018** |
| IQC receives Focus Group input and recommends CFCC members and guidelines for the revision of the framework to the SBE | **November 15–16, 2018** |
| SBE receives Focus Group input, approves guidelines for the revision of the framework, and appoints CFCC | **January 9–10, 2019** |
| CFCC meetings are scheduled for the following dates:   * February 7–8, 2019 * March 7–8, 2019 * April 11–12, 2019 * May 30–31, 2019 * June 13–14, 2019 * August 1–2, 2019 | **February–August 2019** |
| IQC approves draft framework for initial 60-day public review period | **September 19–20, 2019** |
| Required 60-day public review of draft *WL Framework* prior to IQC recommendation (pursuant to 5 *CCR* §9515[a][3]) | **October–November 2019** |
| IQC analyzes field review results and revises draft *WL Framework* | **January 2020** |
| IQC action on draft *WL Framework* | **January 2020** |
| Required 60-day public review of document after IQC recommendation (pursuant to 5 *CCR* §9515[c]) | **February–March 2020** |
| SBE action to adopt *WL Framework* | **May 2020** |
| Date of adoption of instructional materials | **November 2021** |

This timeline is subject to change. The SBE will only take action on changes to the approved timeline if they affect IQC or SBE action dates.

©California Department of Education, May 2018.