# 2025 California Mathematics Adoption of Instructional Materials Schedule of Significant Events

Draft—pending State Board of Education approval

| Event | Date |
| --- | --- |
| State Board of Education (SBE) adoption of the Mathematics Framework for California Public Schools: Kindergarten Through Grade Twelve (California Education Code (EC) Section 60200[b][1]) | July 12, 2023 |
| Instructional Quality Commission (IQC) recommends: - Schedule of Significant Events - Reviewer application questions - Evaluation criteria map and standards maps | November 15, 2023 |
| SBE approves: - Notice of Intent to Hold Adoption (Title 5, California Code of Regulations (5 CCR) Section 9517.3) - Schedule of Significant Events (5 CCR Section 9517.3) - Reviewer application questions (5 CCR Section 9513[a]) - Evaluation criteria map and standards maps (5 CCR Section 9510[u]) | January 18–19, 2024 |
| Reviewer application period (5 CCR Section 9513[a]) | April–September 2024 |
| Small publisher fee reduction requests due (EC Section 60213) | November 1, 2024 |
| IQC recommends reviewers (5 CCR Section 9512[b]) | November 20–21, 2024 |
| SBE appoints reviewers (5 CCR Section 9512[a]) SBE considers small publisher fee reduction requests (EC Section 60213[d][1]) | January 2025 |
| Publisher Invitation to Submit meeting (5 CCR Section 9517) | January 2025 |
| Publisher intent to submit forms due (5 CCR Section 9517.3[a][3]) | February 4, 2025 |
| Publisher submission forms due (5 CCR Section 9517[c]) | March 12, 2025 |
| Publisher fees due (EC Section 60213) | April 9, 2025 |
| Reviewer training week (5 CCR Section 9512[h]) | April 14–18, 2025 |
| Publisher complete instructional programs due (5 CCR Section 9517[e]) | May 7, 2025 |
| Reviewer deliberations week one; review panels make program adoption recommendations (5 CCR Section 9519[i]) | July 21–25, 2025 |
| Reviewer deliberations week two; review panels make program adoption recommendations (5 CCR Section 9519[i]) | July 28–August 1, 2025 |
| IQC holds public meeting to receive comment (5 CCR Section 9524[a][1]) | August 2025 |
| IQC makes program adoption recommendations (5 CCR Section 9524[a][5]) | September 2025 |
| SBE holds public meeting to receive comment SBE takes action on program recommendations (EC Section 60200) | November 2025 |

This timeline is subject to change. The State Board of Education will take action on changes to the approved timeline only if they affect Instructional Quality Commission or State Board of Education action dates.

California Department of Education, November 2023