Revised: 2015 English Language Arts/English Language Development

Instructional Materials Adoption

Schedule of Significant Events

(Revision to be Approved by SBE at November 13-14, 2014 Meeting)

| Event | Date(s) |
| --- | --- |
| Instructional Quality Commission (IQC) approves reviewer application and Schedule of Significant Events (Timeline) | November 21–22, 2013 |
| Survey of publisher interest | November 2013 |
| State Board of Education (SBE) approves reviewer application and adoption Timeline | March 12–13, 2014 |
| Recruitment of reviewers (at least 90 days per 5 CCR §9513) | April 1 August 1 – October 1, 2014 [Note that the date of August 1 has strikeout and was replaced with the date of April 1] |
| SBE action on IQC’s recommended ELA/ELD Framework, includes public hearing | July 9-10, 2014 |
| Publisher Briefing: Overview of 2015 ELA/ELD Adoption Evaluation Criteria | July 30, 2014 |
| IQC recommends reviewers and revised Timeline to SBE | September 18–19, 2014 |
| Publisher Briefing: In-Depth Review of 2015 ELA/ELD Adoption Evaluation Criteria | October 23, 2014 |
| SBE appoints reviewers and approves revised Timeline | November 13–14, 2014 |
| IQC recommends reviewers and approves training materials (§9512h) | November 20–21, 2014 |
| SBE appoints reviewers and approves training materials (§9512h) | January 14-15, 2015 |
| Invitation to Submit Meeting (Sacramento) | January 28, 2015 |
| Small publisher fee reduction requests due | February 11, 2015 |
| SBE takes action on publisher fee reduction requests | March 11-12, 2015 |
| Submission List for programs (and other forms) due by 3:00 p.m. PST | March 2, 2015 |
| Non-refundable publisher participation fees due | April 8, 2015 |
| Reviewer Training (2 sessions) | Session I: Facilitator Training: April 13, 2015 Reviewer Training: April 14–17,2015 Session II: Facilitator Training: April 27, 2015 Reviewer Training: April 28–May 1, 2015 |
| Publishers provide samples of instructional materials to reviewers and Learning Resource Display Centers | Session I: May 1, 2015 Session II: May 15, 2015 |
| Independent Review | Session I: May 1–July 12, 2015 Session II: May 15–July 26, 2015 |
| Reviewer Deliberations (2 sessions) | Session I: July 13–17, 2015 Session II: July 27–31, 2015 |
| IQC holds public meeting to receive comment (5 CCR §9524(a)) | August 20, 2015 |
| IQC makes recommendation | September 24-25, 2015 |
| SBE holds public hearing to receive comment (Education Code 60203 and 5 CCR §9524(b)) | November 19-20, 2015 |
| SBE takes action on recommendation | November 19-20, 2015 |

© California Department of Education, September 3, 2014