| California Department of Education Executive Office SBE-002 (REV. 01/2011) | memo-ssssb-sfsd-oct11item01 |
| --- | --- |
| memorandum |  |

| Date: | October 4, 2011 |
| --- | --- |

| TO: | MEMBERS, State Board of Education |
| --- | --- |

| FROM: | TOM TORLAKSON, State Superintendent of Public Instruction |
| --- | --- |

| SUBJECT: | Substantial Progress Report and the Development of a Specific School Building Plan to Provide Adequate Pupil Capacity regarding the Elimination of the Multi-track Year-Round Education Concept 6 calendar by Los Angeles Unified School District Pursuant to California Education Code sections 37685 and 37687, Chapter 901, Statutes of 2004 (Assembly Bill 1550). |
| --- | --- |

Summary of Key Issues

California Education Code (EC) sections 37685 and 37687, which were added pursuant to the Eliezer Williams, et al. vs. State of California, et al. settlement, prohibits the use of Concept 6 calendars after July 1, 2012, and requires any district that is operating a school on a Concept 6 multi-track year round calendar submit evidence in writing each July to the State Superintendent of Public Instruction (SSPI). The SSPI in turn is required to report to the State Board of Education (SBE) on the substantial progress made in reaching the annual numerical goals as established in the districts’ comprehensive action plan (CAP) and on the specific school building plan to provide adequate pupil capacity to eliminate the Concept 6 program no later than July 1, 2012.

Concept 6 is a multi-track year round calendar that divides a school’s student population into three tracks of which two tracks attend the school at one time. The Concept 6 calendar provides the ability to serve the maximum number of students, but limits the number of instructional days to 163 instead of the required 180 (EC Section 37670). Daily instructional minutes are increased in this model to meet the equivalent amount of instruction time required for a 180-day schedule.

The SBE approved the Los Angeles Unified School District (LAUSD) CAP on July 6, 2005. This information memorandum summarizes the District’s report to the SSPI on the substantial progress made in the elimination of the Concept 6 multi-track year-round calendar as required by EC Section 37685 and on the specific school building plan as required by EC Section 37687.

As of July 1, 2011, the District has made substantial progress in the elimination of the use of Concept 6 as established in the district’s CAP. The LAUSD’s 2010–11 goal was to have 117,341 resident enrollees attending a total of 46 Concept 6 schools. As of July 1, 2011, the LAUSD has resident enrollment of 25,943 (Attachment 1) attending a total of eight Concept 6 schools. This exceeds the resident enrollment goal by 91,398. Resident enrollment is the number of pupils who live in a school’s attendance area and attend that school, participate in a transportation program (other than magnet), or participate in the open enrollment program. In this case, students attending a school on a permit are counted in their neighborhood school, but not magnet students who chose to attend a magnet school instead of their local neighborhood school.

Additionally, the District has developed a specific school building plan to eliminate the Concept 6 program and provide adequate pupil capacity. During the 2011–12 school year there will be four existing schools scheduled on a Concept 6 calendar (Attachment 2). The District has identified preferred sites to build new schools and has approved buildings needed to satisfy the pupil capacity projected on the comprehensive action plan (Attachment 3). The District has also identified and obtained the funding necessary to complete the particular projects identified.

Attachment(s)

Attachment 1: List of 2010–11 Concept 6 Schools in the Los Angeles Unified School District (1 page)

Attachment 2: List of 2011–12 Concept 6 schools in the Los Angeles Unified School District (1 page)

Attachment 3: Los Angeles Unified School District Specific School Building Plan

(1 page)

Attachment 4: California Education Code sections 37670, 37685, and 37687 (1 page)

List of 2010–11 Concept 6 schools in the Los Angeles Unified School District

Below is a list of 2010–11 Concept 6 schools in the Los Angeles Unified School District, showing the projected resident enrollment and actual enrollment as certified in the 2010–11 California Longitudinal Pupil Achievement Data System (CALPADS). The projected resident enrollment was the number that was submitted on the District’s comprehensive action plan and is used here, as provided by the District, to maintain consistency with the original report.

| School | 2010–11 Projected Resident Enrollment | 2010–11 CALPADS |
| --- | --- | --- |
| Bell Senior High | 5,966 | 4,286 |
| Carver Middle | 3,377 | 1,590 |
| Fremont Senior High | 6,862 | 4,337 |
| Gage Middle | 3,647 | 2,686 |
| Huntington Park Middle | 5,742 | 4,080 |
| Los Angeles Academy Middle | 3,338 | 2,082 |
| Manual Arts Senior High | 5,954 | 3,460 |
| Marshall Senior High | 4,727 | 3,422 |

List of 2011–12 Concept 6 Schools in the Los Angeles Unified School District

| Location Code | School | 2011–12 Calendar | 2012–13 Calendar |
| --- | --- | --- | --- |
| 8536 | Bell Senior High | X | √ |
| 8650 | Fremont Senior High | X | √ |
| 8151 | Gage Middle | X | √ |
| 8700 | Huntington Park Middle | X | √ |
| Total Number of Schools on Concept 6 |  | 4 | 0 |

	Concept 6

	Not Concept 6

Los Angeles Unified School District Specific School Building Plan

| Project Name | Board Approval Date of Preferred Site | California Environmental Quality Act/Project Approval | School Occupancy | Schools Relieved | 2011 – 12 Calendar | 2012 – 13 Calendar |
| --- | --- | --- | --- | --- | --- | --- |
| Southeast HS (Southeast Area New HS #2) | 10/25/00 | 02/26/02 | 09/06/05 | Huntington Park HS, Bell HS |  |  |
| Maywood Academy HS (Southeast Area New Learning Center) | 05/06/01 | 03/31/02 | 09/05/06 | Huntington Park HS, Bell HS |  |  |
| South Region HS #2 | 07/22/04 | 05/23/06 | 09/06/11 | Fremont HS |  |  |
| South Region HS #9 | 06/21/05 | 06/30/09 | 09/04/12 | Huntington Park HS, Bell HS |  |  |
| South Region HS #12 | 02/14/06 | 02/26/08 | 09/04/12 | Fremont HS |  |  |
| South Region MS #3 | 04/22/08 | 12/09/08 | 09/04/12 | Gage MS |  |  |
| South Region HS #8 | 05/28/09 | 12/31/09 | 09/02/14 | Bell HS |  |  |

   Not Concept 6

    Un-shaded schools are not yet opened

Note: School names in brackets were the original names submitted on the Comprehensive Action Plan.

CALIFORNIA EDUCATION CODE SECTIONS 37670, 37685, AND 37687

37670. (a) Except as provided in Article 2 (commencing with Section 37680), a school district may operate a program of multi-track year-round scheduling at one or more schools within the district. A program of multi-track year-round scheduling may operate at a schoolsite for as few as 163 days in each fiscal year if the governing board of the school district adopts a resolution at a regularly scheduled board meeting certifying that both of the following criteria are met at the schoolsite:

- The number of annual instructional minutes is not less than that of schools of the same grade levels utilizing the traditional school calendar.

- It is not possible for the school to maintain a multi-track schedule containing the same number of instructional days as are provided in schools of the district utilizing the traditional school calendar given the facilities, program, class sizes, and projected number of pupils enrolled at the schoolsite.

(b) A certificated employee working under a program described in this section, except one serving under an administrative or supervisorial credential who is assigned full time to a school in a position requiring qualifications for certification, shall work daily on a uniform basis.

(c) A program conducted pursuant to this section is eligible for apportionment from the State School Fund.

37685. (a) A district that plans to operate a Concept 6 program after June 30, 2006, shall, by July 1, 2006, and by July 1 of any succeeding year in which it plans to operate a Concept 6 program, as a condition of operating that program, submit evidence in writing to establish to the satisfaction of the Superintendent of Public Instruction that substantial progress has been made toward meeting its annual numerical goals as stated in its comprehensive action plan.

(b) The superintendent shall evaluate the written submission to determine whether the district has made substantial progress toward meeting its goals and shall submit a report to the state board.

37687. (a) A district that plans to operate a Concept 6 program after June 30, 2009, shall, by July 1 of 2009, and by July 1 of any succeeding year in which it plans to operate a Concept 6 program, submit evidence in writing to establish to the satisfaction of the Superintendent of Public Instruction that it has developed a specific school building plan to provide adequate pupil capacity to eliminate the Concept 6 program by the earliest practicable date and no later than July 1, 2012.

(b) The superintendent shall evaluate the written submission to determine whether the district has developed a specific school building plan and shall submit a report to the state board.