California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (A): Template for Documentation of Implementation of Corrective Action 6

County: Kern     Local Educational Agency: Fairfax Elementary School District

Note: Bold indicates new information, with the exception of headings.

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. | December 15, 2009: |
| - English/Reading-language Arts | - The district continues to provide to all K-5 grade level teachers the 2002 Houghton Mifflin SBE-adopted core instructional programs and materials in Reading/Language Arts (R/LA), including strategic interventions, ensuring full implementation as documented through the review of inventories, invoices, pacing calendars, schedules, lesson plans, and classroom observation data. - The district continues to provide to all 6-8 grade level teachers the 2002 Prentice Hall SBE-adopted core instructional programs and materials in R/LA, including strategic interventions, ensuring full implementation as documented through the review of inventories, invoices, pacing calendars, schedules, lesson plans, and classroom observation data. - The district continues to provide the SBE-approved Hampton Brown High Point intensive level intervention program for grades 4-8, as approved for identified students, based on need. The district ensures full implementation as documented through the review of inventories, invoices, pacing calendars, schedules, lesson plans, and classroom observation data. The district is in the process of phasing in the 2008 SBE-adopted reading/language arts curriculum and has developed a plan to do so systematically. The district has identified a representative committee comprised of R/LA teachers and site and district administrators to facilitate the 2008 R/LA adoption process. Committee members are reviewing and analyzing data from the district's 2002 SBE-adopted reading/language arts adoption and full implementation in 2005-06, utilizing the “Toolkit” provided by the Curriculum and Instruction Steering Committee (CISC) and are considering all options including adopting in stages by identifying areas of need, including reading/language arts intervention and ELD programs. March 15, 2010 update: The district continues to provide the current 2002 SBE-adopted basic core instructional programs, including ancillary materials for universal access, for Reading/Language Arts/English Language Development. The school/district also provides the current 2002 SBE-adopted intensive interventions for Grades 4-8 in R/LA. These R/LA programs are implemented as designed and documented to be in daily use in every classroom with materials for every student. The district has identified a representative committee comprised of R/LA teachers and site and district administrators to facilitate the 2008 R/LA adoption process and to determine the phase-in process for the 2008 SBE-adopted R/LA curriculum. The district has scheduled dates for this committee to review the 2008 SBE-adopted curriculum materials for R/LA and ELD. The first meeting to investigate R/LA Intervention program options was scheduled for Feb. 25, 2005, where the committee members met with KCSOS Reading Language Arts Coordinator for R/LA Tool Kit training and to begin the evaluation of 2008 SBE-adopted R/LA Intervention curriculum that will be purchased by June 30, 2010 and implemented in August 2010 for grade levels 4-8. July 15, 2010 update: The district is phasing in the 2008 SBE-adopted R/LA curriculum for intensive intervention, grades 4-8, with the Scholastic READ 180 California Enterprise Edition program that was adopted by the Fairfax Board of Trustees on May 13, 2010 that will be purchased and fully implemented district wide in August 2010. READ 180 publisher district training is scheduled for August 16-17, 2010. The district continues to provide the 2002 Houghton Mifflin SBE-adopted core instructional program, grades K-5, and the 2002 Prentice Hall SBE-adopted core instructional program, grades 6-8, including the use of ancillary materials for strategic intervention and Universal Access for all students. December 15, 2009: |
| - Mathematics | - The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education adopted Houghton-Mifflin California Math (K-6), the Pearson Prentice Hall Mathematics California (7-8), and the Pearson Prentice Hall Mathematics California Algebra Readiness (8th) ensuring full implementation as documented through the review of inventories, invoices, pacing calendars, schedules, lesson plans, and classroom observation data. - The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education intensive level intervention program and materials in mathematics for students working more than 2 years below grade level standards in grades 4-7 using the Kaplan K-12 Learning Services Momentum Math intervention program and in grade 8 using the Pearson Prentice Hall Mathematics California Algebra Readiness, ensuring full implementation as documented through the review of inventories, invoices, pacing calendars, schedules, lesson plans, and classroom observation data. March 15, 2010 update: The district continues to provide the current 2007 SBE-adopted basic core instructional programs, including ancillary materials the mathematics 2007 SBE-approved adoption. The district also provides the current 2007 SBE-adopted intensive interventions for Grades 4-7 and Grade 8 Algebra Readiness in mathematics. These mathematics programs are implemented as designed and documented to be in daily use in every classroom with materials for every student. July 15, 2010 update: The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education adopted Houghton-Mifflin California Math, grades K-6 and the Pearson Prentice Hall Mathematics California, grades 7-8, ensuring full implementation, including the use of ancillary materials for strategic intervention and Universal Access for all students. The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education intensive level intervention program and materials in mathematics for students working more than 2 years below grade level standards in grades 4-7 using the Kaplan K-12 Learning Services Momentum Math intervention program and in grade 8 using the Pearson Prentice Hall Mathematics California Algebra Readiness program. |
| LEA implementation of materials-based professional development for teachers and administrators in the adopted materials in use in schools. | December 15, 2009: All K-5 grade level teachers have completed the initial 40-hour materials-based professional development training for the 2002 SBE-adopted Houghton Mifflin Reading program. All teachers have completed the R/LA 80 hour practicum follow-up as well. All 6-8 grade level teachers have completed the initial 40-hour materials-based professional development training for the 2002 SBE-adopted Prentice Hall Reading program. All teachers have completed the R/LA 80 hour practicum follow-up as well. March 15, 2010 update: 100% of all K-8 grade level teachers have completed the initial 40-hour materials-based professional development training for the 2002 SBE-adopted Houghton Mifflin Reading program. All teachers have completed the R/LA 80 hour practicum follow-up as well. July 15, 2010 update: One hundred percent of the district’s current Reading/Language Arts teachers and site administrators have completed the initial Instructional Materials-Based Training in Reading/Language Arts for the 2002 Houghton Mifflin SBE-adopted core instructional program, grades K-5, or the 2002 Prentice Hall SBE-adopted core instructional program, grades 6-8. One hundred percent of R/LA teachers and site administrators have completed the 80 hour follow-up practicum in Reading/Language Arts. The Scholastic READ 180 California Enterprise Edition publisher training is scheduled for August 16-17, 2010 for R/LA intensive intervention teachers, grades 4-8 and the district will also schedule the Instructional Materials-Based Training for READ 180 during the 2010-11 school year. Twenty-four percent of teachers have completed the Instructional Materials Based Training for English Learners and 63 elementary and secondary teachers are currently attending the July 12-16, 2010 5-day Instructional Materials-Based Training for English Learners that will increase the district Instructional Materials Based Training for English Learners completion percentage rate to ninety-four percent. Fifty percent of site administrators have completed the Instructional Materials Based Training for English Learners, 25% of site administrators are currently attending the Instructional Materials Based Training for English Learners on July 12-16, 2010, and the district will schedule 25% of site administrators to complete the Instructional Materials Based Training for English Learners in 2010-11. December 15, 2009: 51% of all mathematics teachers have completed the initial 40-hour materials-based professional development training for the SBE-adopted mathematics programs for Houghton-Mifflin California Math (K-6) and the Pearson Prentice Hall Mathematics California (7-8). The district has scheduled the remaining teachers of mathematics to attend the instructional materials-based professional development training before the fall of 2010. March 15, 2010 update: The percentage of all mathematics teachers in the district that have completed the initial 40-hour materials-based professional development training for the SBE-adopted mathematics programs for Houghton-Mifflin California Math (K-6) and the Pearson Prentice Hall Mathematics California (7-8) has increased from 51% to 60%, as of March 15, 2010. Five teachers in the district have completed the KCSOS SB472 training from Jan. 22, 2010-Feb. 20, 2010. The district will schedule summer mathematics instructional materials-based professional development training for the teachers who have not yet completed that training in mathematics. July 15, 2010 update: Ninety-two percent of all mathematics teachers have completed the initial 40-hour materials-based professional development training for the SBE-adopted mathematics programs for Houghton-Mifflin California Math, grades K-6, or the Pearson Prentice Hall Mathematics California, grades 7-8. All teachers who have completed the initial forty hour instructional materials based training in mathematics will complete the 80 hour follow-up practicum hours that will include inservice on mathematics strategic intervention, grades K-8 and the 2007 State Board of Education intensive level intervention program and in grades 4-7 for the Kaplan K-12 Learning Services Momentum Math intervention program. The district will schedule instructional materials-based professional development training for intensive intervention 8th grade mathematics teachers for the Pearson Prentice Hall Mathematics California Algebra Readiness program in 2010-11. Fifty percent of site administrators have completed the instructional materials-based professional development training in the adopted mathematics materials in use at their school sites and the district will schedule 50% of site administrators to complete the mathematics training for their school site adoption in 2010-11. |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | 1. Instructional Program: December 15, 2009: The district provides the current SBE-adopted basic core instructional programs in reading/language arts, English Language Development (ELD) and mathematics programs, including ancillary materials for universal access and the strategic and intensive intervention instructional materials as well. These programs are implemented as designed and documented to be in daily use in every classroom with materials for every student through the review of pacing calendars, class schedules, lesson plans and classroom observation data. March 15, 2010 update: Principals participate in daily site-level observations and review lesson plans weekly to ensure that the current SBE-adopted basic core instructional programs in reading/language arts, English Language Development (ELD) and mathematics are implemented as designed and documented to be in daily use in every classroom with materials for every student. In addition, district-level teams that include principals and vice-principals from other school sites in the district and district administrators participate in classroom observations every quarter to monitor the use of instructional materials district wide. July 15, 2010 update: The district is phasing in the 2008 SBE-adopted R/LA curriculum for intensive intervention, grades 4-8, with the Scholastic READ 180 California Enterprise Edition program that was adopted by the Fairfax Board of Trustees on May 13, 2010 that will be purchased and fully implemented district wide in August 2010. The district continues to provide the 2002 Houghton Mifflin SBE-adopted core instructional program, grades K-5, and the 2002 Prentice Hall SBE-adopted core instructional program, grades 6-8, including the use of ancillary materials for strategic intervention and Universal Access for all students. The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education adopted Houghton-Mifflin California Math, grades K-6 and the Pearson Prentice Hall Mathematics California, grades 7-8, ensuring full implementation, including the use of ancillary materials for strategic intervention and Universal Access for all students. The district selected, adopted, purchased, and continues to provide the 2007 State Board of Education intensive level intervention program and materials in mathematics for students working more than 2 years below grade level standards in grades 4-7 using the Kaplan K-12 Learning Services Momentum Math intervention program and in grade 8 using the Pearson Prentice Hall Mathematics California Algebra Readiness program. The district has implemented placement and assessment policies and practices for English learners, including the reclassification criteria. The district provides at least 30 minutes of leveled English Language Development instruction daily for all English Learners utilizing Hampton Brown Avenues for grades K-5 and Hampton Brown High Point for grades 6-8. 2. Instructional Time: December 15, 2009: The district complies with and monitors daily implementation of instructional time for the current SBE-adopted basic core programs for reading/language arts, English Language Development (ELD) and mathematics, including strategic and intensive intervention programs in R/LA and mathematics. The district modified the instructional schedule to accommodate core instructional requirements and to allow for professional development in the area of data analysis. This time is given priority and protected from interruptions and the full implementation of instructional time for the current SBE-adopted basic core programs for reading/language arts, English Language Development (ELD) and mathematics, including R/LA and mathematics intervention programs, is monitored at all school sites through the review of pacing calendars, class schedules, lesson plans and classroom observation data. March 15, 2010 update: Principals participate in daily site-level observations and review lesson plans weekly to monitor the daily implementation of instructional time for the adopted R/LA and mathematics basic core programs, the intensive interventions as well as additional time for strategic support and ELD for identified English Learners. In addition, district-level teams that include principals and vice-principals from other school sites in the district and district administrators participate in classroom observations every quarter to monitor the implementation of instructional time district wide. School principals ensure that instructional time is given priority and is protected from interruptions including office and intercom announcements. Parents are notified annually in the parent handbook to make appointments for their children before and after school to avoid interruption during instructional time. July 15, 2010 update: All grade levels/classrooms have the appropriate time allocations, including the additional strategic and intensive intervention time for their respective grade levels as outlined in the Academic Program Survey (APS) for R/LA, mathematics and ELD. 3. Lesson Pacing Guide: December 15, 2009: The district prepares, distributes, and monitors the use of an annual district instructional/assessment pacing guide documented to be in use for each grade level for the current SBE-adopted reading/language arts, English Language Development (ELD) and mathematics programs, including intervention programs in order for all teachers to follow a common sequence of instruction and assessment. The full implementation of lesson pacing guides for the current SBE-adopted basic core programs for reading/language arts, English Language Development (ELD) and mathematics is monitored at all school sites through the review of lesson plans and classroom observation data. March 15, 2010 update: Principals participate in daily site-level observations and review lesson plans weekly to monitor the use of an annual district-instructional/assessment pacing guide documented to be in use for each grade level (kindergarten through grade eight) for the SBE-adopted basic core RLA/ELD, strategic support and intensive intervention programs and SBE-adopted mathematics basic core, strategic, and Grades 4-7 and Algebra Readiness intensive intervention. In addition, district-level teams that include principals and vice-principals from other school sites in the district and district administrators participate in classroom observations every quarter to monitor the implementation of pacing schedules district wide. July 15, 2010 update: The district implements grade level pacing calendars and benchmark assessment schedules in R/LA, mathematics and ELD that have been updated and revised for 2010-11 by lead teachers in grade level teams. All teachers are scheduled to participate in pacing calendar and benchmark assessment training in August 2010 in order to ensure that teachers follow a common sequence of instruction and assessment in R/LA and mathematics. 4. School Administrator Training: December 15, 2009: The district provides and all school site administrators have completed the 40-hour administrative training through a knowledgeable, experienced provider and have completed a 40-hour structured practicum based on the implementation of the current SBE-adopted basic core program instructional materials and the Essential Program Components (EPC’s). All school site administrators are scheduled to update the mathematics curriculum module component for their respective 2007 SBE-adopted mathematics materials before the fall of 2010. March 15, 2010 update: The district has provided 100% of the principals and vice-principal(s) with an 80-hour instructional materials-based administrative training, Module I in leadership, support and monitoring needed for the full implementation of the SBE-adopted RLA/ELD and mathematics basic core and intervention program materials. Principals are currently updating their AB430 Principal's training for the 2007 SBE-adopted mathematics basic core and intervention program materials as available. One principal has completed the AB430 mathematics training in Feb. 2010 and all others are scheduled to complete the AB430 mathematics training in summer 2010. In addition, the district offers targeted professional development and support for instructional leaders to ensure the full implementation of the district adopted program and the Essential Program Components (Collect, Connect, Coach-C3 Training, ELD Training). July 15, 2010 update: One hundred percent of site administrators have completed the AB 430 training. One hundred percent of the district’s site administrators have completed the initial Instructional Materials-Based Training in Reading/Language Arts and one hundred percent have completed the follow-up practicum hours in Reading/Language Arts. Fifty percent of site administrators have completed the materials-based professional development training in the adopted mathematics materials in use at their school sites and the district will schedule 50% of site administrators to complete the mathematics training for their school site adoption in 2010-11. Fifty percent of site administrators have completed the Instructional Materials Based Training for English Learners, 25% of site administrators are currently attending the Instructional Materials Based Training for English Learners on July 12-16, 2010, and the district will schedule 25% of site administrators to complete the Instructional Materials Based Training for English Learners in 2010-11. 5. Credentialed Teachers and Professional Development: December 15, 2009: 100% of the teachers in the district are fully credentialed and highly qualified. The district provides teachers of reading/language arts, English Language Development (ELD) and mathematics programs, with a 40-hour instructional materials professional development training through a knowledgeable and experienced provider for the current SBE-adopted instructional programs in use at all school sites. 100% of K-8 R/LA teachers have completed the 40-hour instructional materials professional development training for the 2002 SBE-adopted R/LA programs and have completed the 80-hours of structured practicum that is aligned with the effective implementation of the adopted of the adopted program and the goals of the district professional development plan. 51% of K-8 mathematics teachers have completed the 40-hour instructional materials professional development training for the 2007 SBE-adopted mathematics programs and have completed the 80-hours of structured practicum that is aligned with the effective implementation of the adopted of the adopted program and the goals of the district professional development plan. The district has scheduled the remaining teachers of mathematics to attend the instructional materials-based professional development training before the fall of 2010. March 15, 2010 update: 100% of the teachers in the district are fully credentialed and highly qualified per the requirements of the Elementary and Secondary Education Act (ESEA) and Requirements for No Child Left Behind The district provides teachers of RLA/ELD (K-8) and mathematics K-8 through Algebra I (in all grade levels and programs, including special education and ELD) with a 40-hour instructional materials professional development program provided by a knowledgeable and experienced provider for the SBE-adopted basic core RLA/ELD and mathematics programs and/or SBE-adopted reading or mathematics intensive intervention instructional programs in use at the school. The district also validates that each teacher completes an 80-hour structured practicum based on the implementation of the instructional materials and the EPCs. July 15, 2010 update: One hundred percent of the district's teachers are highly qualified. One hundred percent of the district’s current Reading/Language Arts teachers have completed the initial Instructional Materials-Based Training in Reading/Language Arts for the 2002 Houghton Mifflin SBE-adopted core instructional program, grades K-5, or the 2002 Prentice Hall SBE-adopted core instructional program, grades 6-8 and one hundred percent have also completed the 80 hour follow-up practicum in Reading/Language Arts. Ninety-two percent of all mathematics teachers have completed the initial 40-hour materials-based professional development training for the SBE-adopted mathematics programs for Houghton-Mifflin California Math, grades K-6, or the Pearson Prentice Hall Mathematics California, grades 7-8. The district has developed a protocol for the 80-hour follow-up professional development practicum that lists the district-approved activities for the follow-up instructional materials training in mathematics. All teachers who have completed the initial forty hour instructional materials based training in mathematics will complete the 80 hour follow-up practicum hours that will include inservice on mathematics strategic intervention, grades K-8 and the 2007 State Board of Education intensive level intervention program and in grades 4-7 for the Kaplan K-12 Learning Services Momentum Math intervention program. The district will schedule instructional materials-based professional development training for intensive intervention 8th grade mathematics teachers for the Pearson Prentice Hall Mathematics California Algebra Readiness program in 2010-11. Twenty-four percent of teachers have completed the Instructional Materials Based Training for English Learners and 63 elementary and secondary teachers are currently attending the July 12-16, 2010 5-day Instructional Materials-Based Training for English Learners that will increase the district Instructional Materials Based Training for English Learners completion percentage rate to ninety-four percent. 6. Ongoing Instructional Assistance and Support for Teachers: December 15, 2009: The district provides ongoing, targeted support and instructional assistance to all teachers of reading/language arts through the use of district reading specialists assigned to each school site who are knowledgeable about the content and delivery of instruction for the current SBE-adopted reading/language arts program. The district currently has identified lead teachers in mathematics who provide instructional assistance and ongoing support to teachers of mathematics to support teachers and to deepen their knowledge about the content and the delivery of instruction. The district is scheduled to identify mathematics specialists within the district in fall 2010 to provide ongoing instructional assistance and to support all teachers of mathematics and deepen their knowledge about the content and delivery of instruction. March 15, 2010 update: The district continues to provide instructional assistance and ongoing support to all teachers of Reading/Language Arts through the use of district reading specialists assigned to each school site who are knowledgeable about the content and delivery of instruction for the current SBE-adopted reading/language arts program. The district is currently developing job descriptions and working with the bargaining unit to identify the requirements and process for hiring lead teachers in mathematics who will provide instructional assistance and ongoing support to teachers of mathematics and to deepen their knowledge about the content and the delivery of instruction beginning in the fall of 2010. July 15, 2010 update: The district provides ongoing, targeted support and instructional assistance to all teachers of Reading/Language Arts through the use of district reading specialists assigned to each school site who are knowledgeable about the content and delivery of instruction for the current SBE-adopted Reading/Language Arts program. The district is planning in the 2010-11 school year to identify one lead teacher in mathematics at each school site who will provide grade level specific instructional assistance and support through the data analysis process and through ongoing assistance in identifying targeted instructional strategies to support improved student achievement in mathematics. 7. Student Achievement Monitoring System: December 15, 2009: The district uses an ongoing assessment and monitoring system that provides timely data from common assessments based on the current SBE-adopted instructional programs. Curriculum embedded assessments in reading/language arts and mathematics are administered quarterly according to the pacing calendars at each grade level. Assessment results inform teachers and principals on student placement, diagnosis, progress, and effectiveness of instruction in the current SBE-adopted programs in reading/language arts, English Language Development (ELD) and mathematics. Edusoft, an electronic data system, is utilized district wide and provides timely data to teachers and principals to assist with identifying patterns of performance and appropriate instructional modifications to meet the needs of all students in order to improve instruction and student achievement. March 15, 2010 update: The district continues to use Edusoft, an ongoing assessment and monitoring system that provides timely data from common assessments based on the SBE-adopted RLA/ELD and mathematics basic core and intensive intervention programs. Student achievement results from assessments are used to inform teachers and principals on student placement, diagnosis, progress, and effectiveness of instruction. Teachers and principals have been trained and currently use the Teacher and Tools component of Edusoft to provide additional information on student placement, diagnosis, progress, and effectiveness of instruction. July 15, 2010 update: The district uses an ongoing assessment and monitoring system that provides data from benchmark assessments based on the current SBE-adopted instructional programs. Edusoft, an electronic data system, is utilized district wide and provides timely data to teachers and principals to assist with identifying patterns of performance and appropriate instructional modifications to meet the needs of all students in order to improve instruction and student achievement. District wide data analysis forms have been developed by the District Leadership Team for R/LA and mathematics that will be utilized at all school sites in grade level collaboration in 2010-11. The district has also developed English Language Development (ELD) data analysis forms that will be utilized in grade level collaboration and data analysis in 2010-11 for all English Learners. 8. Monthly Collaboration for Teachers Facilitated by Principal: December 15, 2009: The district schedules at minimum two, one hour department/grade level structured collaboration meetings per month at all school sites, facilitated by the principals. Teachers analyze, discuss and utilize district assessment results to guide student placement, instructional planning and delivery, and progress monitoring, for the current SBE-adopted programs in reading/language arts, English Language Development (ELD) and mathematics. March 15, 2010 update: The district has increased grade level collaboration to three, 50-minute to one hour department/grade level structured collaboration meetings per month at all school sites, facilitated by principals. In addition, the district also schedules one monthly district wide one-hour meeting for teachers to analyze, discuss, and utilize the results of the school/district assessment system to guide student placement, instructional planning and delivery, and progress monitoring, within the SBE-adopted RLA/ELD and mathematics programs. The district will continue to explore options for the 2010-11 school year to provide additional structured collaboration meeting time for all teachers. July 15, 2010 update: The district schedules at least two department/grade level structured collaboration meetings and two staff development meetings per month at all school sites, facilitated by the principals. Teachers analyze, discuss and utilize district assessment results to guide student placement, instructional planning and delivery, and progress monitoring, for the current SBE-adopted programs in Reading/Language Arts and mathematics. The district has also developed English Language Development (ELD) data analysis forms that will be utilized in grade level collaboration and data analysis in 2010-11 for all English Learners. 9. Fiscal Support: December 15, 2009: The district provides and ensures that all general and categorical funds are coordinated, prioritized and allocated to align with the full implementation of the EPC's and the Single plan for Student Achievement (SPSA) to support the reading/language arts, ELD and mathematics program goals in the LEA plan. March 15, 2010 update: The district continues to align, coordinate and prioritize general and categorical funds with the full implementation of the EPCs in RLA/ELD, mathematics, and the Single Plan for Student Achievement (SPSA) to achieve the district goal of improved student achievement. July 15, 2010 update: The district continues to implement fiscal policies that appropriately allocate general and categorical funds to support the R/LA and mathematics program goals listed in the LEA Plan and all school sites' Single Plan for Student Achievement. Administrators review budgets regularly to ensure that all available funds are allocated to high leverage actions. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | The district has demonstrated improvement across the following measures according to state assessment results: - LEA-wide AYP targets have improved over a 3 year period by 7.5 in ELA and 5.0 in mathematics. AYP targets for subgroups including Hispanic or Latino, White, Socioeconomically Disadvantaged, English Learners, and Students with disabilities have all increased in ELA and mathematics over a 3 year period. - The district met 19 of 25 AYP criteria with a 76 percentage of AYP targets met. Virginia Avenue School met 17 of 17 AYP criteria with a 100 percentage of AYP targets met. Shirley Lane Elementary School met 17 of 17 AYP criteria with a 100 percentage of AYP targets met. Fairfax Middle School met 11 of 17 AYP criteria with a 65 percentage of AYP targets met. - Two of the three school sites in the district met AYP targets in 2009 in ELA and mathematics, both school wide and in all significant subgroups, however, the percentage of Title I schools in the LEA that are not in Program Improvement (PI) has not changed. - The relative growth in the Academic Performance Index (API) over time indicates continuous growth over a three year period. The relative API performance indicates that 100% of all school sites have met API growth targets for 2008-09. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Fairfax Elementary

Note: Bold indicates new information, with the exception of headings.

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance - Develop clear, written district policies and procedures for a comprehensive continuum of intervention services in Reading/Language Arts and mathematics to meet the needs of benchmark, strategic and intensive learners to be fully implemented at all sites in the district, to include: - Clear entry and exit criteria for intensive level intervention based on multiple measures and prioritization based on level of student need - Multiple assessment measures, both curriculum embedded and diagnostic, for assessing student need for intervention services - Specific required time allocations for strategic and intensive level intervention services - State Board of Education (SBE)-adopted curriculum for intervention instruction - Develop clear, written district policies related to aligned assessments, instructional time and the use of pacing guides so as to fully and effectively implement the correlated EPCs. | 1. 11/5/08-Collaborative meeting with Superintendent to draft the district wide Reading Intervention master plan. The development of the intervention plan includes identification, placement and instruction components for benchmark, intensive and strategic level intervention in R/LA for all grade levels, including clear entry and exit criteria, multiple measure cut points, time allocations and SBE-adopted curriculum. 12/5/08- Collaborative meeting with Superintendent to draft the district wide Mathematics Intervention master plan. The development of the intervention plan includes identification, placement and instruction components for benchmark, intensive and strategic level intervention in Mathematics for all grade levels, including clear entry and exit criteria, multiple measure cut points, time allocations and SBE-adopted curriculum. 1/09- District presents intervention plan at all school sites. 1/09- All school sites pilot the district wide strategic and intensive intervention program in R/LA and mathematics 8/09- All school sites fully implement the district wide strategic and intensive intervention program in R/LA and mathematics March 15, 2010 update: All at risk students have been identified in grades K-8 in R/LA and Math to participate in the 45- minute extended day at risk program from Feb-April, 2010 July 15, 2010 update: The District Leadership Team updated the district R/LA and mathematics intervention master plan in May 2010 and all staff will receive district intervention protocol training in August 2010. 2. 8/08- District pacing calendars are developed and disseminated by grade level leads for R/LA and mathematics. Grade level teams meet monthly to discuss and collaborate on the pacing, instructional time and aligned assessment implementation. July 15, 2010 update: The grade level pacing calendars and benchmark assessment schedules in R/LA and mathematics have been revised and updated for 2010-11 by lead teachers in grade level teams. All teachers are scheduled to participate in pacing calendar and benchmark assessment training in August 2010 in order to ensure that teachers follow a common sequence of instruction and assessment in R/LA and mathematics. | Program Coordinator, Principals Program Coordinator, Principals, Grade Level Leads | Pilot-1/09 Fully 8/09 8/08 | X X | X X | X X |  | 1. For students in grades 4-8 the SBE approved Hampton Brown High Point has been adopted and is utilized as appropriate for intensive intervention. For students in grades 4-7 the SBE approved Mathematics intensive intervention Momentum Math has been adopted and is fully implemented. Students in grade 8 use the Pearson Prentice Hall Mathematics California Algebra Readiness as appropriate. District wide collaborative meetings include representation from all school sites (principal and teachers), bargaining groups, Board of Trustees, and district administrators. 2. School site administrators monitor pacing calendar implementation on a regular basis through the review of lesson plans and classroom observation data. |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Fairfax Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| - Develop and fully implement an instructional monitoring plan to align district policies with school site practices and procedures that ensures full implementation of the EPCs at all school sites, classroom application of professional development and consistent use of student performance data to guide and plan instruction. This system should include, at minimum, daily classroom observations by site administrators and monthly classroom observations by district level teams. Develop district protocol for providing feedback to teachers following classroom observations and develop district protocol for site and district administrative review and participation in grade level/department collaboration. | 3. 2/24/09- District Administrative Cabinet meeting with Superintendent to develop a district wide monitoring tool utilizing the C3 (Collect, Connect, Coach) web based instrument. The tool was developed and customized to the district needs and a calendar was set for classroom observation walk throughs for both the district and site level teams through the remainder of the school year. The administrative team identified areas of importance in each one of the following classroom observation topics: - Lesson Design Elements - Organization for Learning and Management of Instruction - Content Standards - Instructional Strategies - Interactive Learning - Assessment/Progress Monitoring - Bloom’s Taxonomy Level - English Learners-Instruction - English Learners-Content - Teacher Behavior - Student Behaviors 8/09- An observation schedule and rubric for each focus area was developed for 2009-10. Administrators currently utilize the C3 observation tool for both district and site level observation teams. Meetings are scheduled following classroom observations to provide feedback to teachers. March 15, 2010 update: 12/09- Principals have received C3 Training on the district adopted observation tool 2/10- Superintendent participates in CCSESA Asilomar Conference Dynamic Leadership for Sustainable Improvement: Building on our Assets July 15, 2010 update: Full Collect, Connect, Coach (C3) implementation for monitoring will continue in 2010-11. The administrative team will identify areas of importance and develop rubrics for each focus area and schedule quarterly observations for both district and site level administrative teams in 2010-11. All site and district administrators have received C3 training during this quarter. | Program Coordinator, Principals, CWT team members | 2/09 | X | X | X |  | 3. Quarterly focus in the following areas utilizing the C3 web based tool for 2009-10 has been scheduled: - Classroom management - Content standards - English Learner instruction - Teacher behavior |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Fairfax Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Alignment of Curriculum, Instruction, and Assessments to State Standards 1. Develop, implement, and monitor implementation of a district-wide, consistent, systematic English language development program for ELs. Ensure that the program is aligned with the adopted standards based Reading/Language Arts instructional program. Provide teachers with instructional materials and with on-going professional development that supports the effective use of the materials. Monitor English language development progress regularly through the use of a progress monitoring assessment tool to guide and direct instructional planning and delivery for all ELs. 2.Ensure that students with disabilities have access to the SBE adopted core curriculum through a comprehensive continuum of special education services and instructional program options that accommodate and support the standards based goals and objectives in the IEPs. Provide standards aligned instructional materials in Reading/Language Arts and mathematics as appropriate to the students’ present level of performance. Utilize diagnostic and curriculum based assessments for initial placement and for continuously monitoring student performance. - Establish district-wide procedures to provide instructional assistance and support to all teachers of Reading/Language/Arts and mathematics through the use of coaches/content experts and/or specialists who will provide direct support in the classroom and model effective instructional practice. | 1. 4/09- Administrative meeting with Superintendent - discussion to plan and schedule school site specific KCSOS inservice on EL strategies in alignment with the DAIT and Title III plans during preservice meetings on August 19, 20, 2009. Configuration of inservice will be discussed as well as additional support, including district wide KCSOS vocabulary development inservice, as appropriate. Upcoming summer 2009 ELPD and High Point trainings were discussed as well. 8/09- District wide and grade level specific English Learner strategy inservice provided to all teachers for the full implementation of district wide English Learner student structured interaction activities strategies. EL progress is monitored and district and site level administrators confirm utilization of EL strategies through regular classroom observations and walk throughs. Teachers are provided with feedback and collaborate monthly to discuss effective EL instructional strategies as outlined in the district EL Master Plan. 10/09- Classroom walkthrough observations scheduled that focus on the implementation of English Learner strategies at each school site. March 15, 2010 update: 1/10- Principals and district administrators complete classroom observations with a focus on English Learner strategies 1/10- Principals and Teacher Leads attend Pyramid Response to Intervention 2-day training w/ Mike Mattos 2/10- English Learner Administrator Training to address specific ELD curriculum delivery and implementation strategies, grades K-8. 3/10- Professional Development opportunity for teachers and administrators on Vocabulary Instruction and Language Development for English Language Learners July 15, 2010 update: The district has implemented placement and assessment policies and practices for English learners, including the reclassification criteria. The district provides at least 30 minutes of leveled English Language Development instruction daily for all English Learners utilizing Hampton Brown Avenues for grades K-5 and Hampton Brown High Point for grades 6-8. The district has provided professional development training to assist teachers in providing structured student interactions and differentiated approaches for English Learners with follow-up training scheduled for grade level groups in fall 2010. English Language Development (ELD) training is scheduled for all staff in August 2010. 2. 8/08- The district continues to provide the standards aligned SBE-adopted core curriculum and utilizes differentiated approaches to instruction to meet the needs of all students with disabilities in R/LA and mathematics. The district ensures that all teachers of students with disabilities participate in the development of IEP goals/objectives for each student with disabilities they instruct. 1/09- District wide intervention master plan has been developed and implemented at all school sites utilizing the SBE-adopted intervention materials for all students with disabilities. 8/09- The Director of Special Education meets with the special education teachers for collaboration purposes on a monthly basis to address initial placement and for continuous monitoring of student performance. Special education teachers participate in grade level collaboration on a monthly basis and are also part of the UCLA Classroom walkthrough protocol and debrief. March 15, 2010 update: Special education teachers participate in all scheduled collaboration district wide July 15, 2010 update: Special education teachers will continue to attend district professional development training sessions in 2010-11 and will collaborate with regular education teachers during school site teacher collaboration meetings every month. 3. All school sites in the district schedule R/LA instructional support through the use of reading specialists at each school site as needed. Lead teachers in mathematics currently provide grade level instructional assistance to teachers of mathematics and provide ongoing instructional assistance and support. March 15, 2010 update: The district is currently developing job descriptions and working with the bargaining unit to identify the requirements and process for hiring lead teachers in mathematics who will provide instructional assistance and ongoing support to teachers of mathematics and to deepen their knowledge about the content and the delivery of instruction beginning in the fall of 2010. July 15, 2010 update: The district provides ongoing, targeted support and instructional assistance to all teachers of Reading/Language Arts through the use of district reading specialists assigned to each school site who are knowledgeable about the content and delivery of instruction for the current SBE-adopted Reading/Language Arts program. The district is planning in the 2010-11 school year to identify one lead teacher in mathematics at each school site who will provide grade level specific instructional assistance and support through the data analysis process and through ongoing assistance in identifying targeted instructional strategies to support improved student achievement in mathematics. | Sp Ed Director, Principals Principals | 8/08 8/08 | X X | X X | X X |  | 2. Special education monthly collaborative meetings address the following: core curriculum and intervention implementation, multiple measure assessment, IEP goals and objectives, and special education identification 3. The district is scheduled to identify mathematics specialists within the district in fall 2010 to provide ongoing instructional assistance and to support all teachers of mathematics |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part I (B): Template for Documentation of District Assistance and Intervention Team Recommendations

County: Kern		Local Educational Agency: Fairfax Elementary

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| - Provide regularly scheduled time for grade level/department collaborative meetings to guide and plan instruction. Develop a district wide protocol for the systematic analysis and interpretation of student data to inform classroom instruction, school site decision-making, and district policies and practices. | 4. 5/09- Classroom Walk Through (CWT) Protocol Training of Lead Teachers 8/09- Classroom Walk Through (CWT) Protocol Training of all teachers 10/09-Classroom Walk Through (CWT) Protocol Training Implementation occurs quarterly in 2009-10 8/09- Grade level/department collaboration is scheduled twice monthly at each school site for the systematic analysis and interpretation of student data to inform classroom instruction. Quarterly curriculum embedded assessment data is used to inform teachers and principals on student placement, diagnosis, progress, and effectiveness of instruction. 10/09- District has developed data monitoring form for grade levels K-5 and uses the Data Teams Protocol for grade level 6-8 for use in grade level data analysis in 2009-10 March 15, 2010 update: 1/10- Classroom Walk Though (CWT) Cohort 1 Training Follow-up for Teacher Leads and Administrators- CWT Debrief meeting are scheduled quarterly July 15, 2010 update: The district has fully implemented the Classroom Walk Through (CWT) Protocol and the CWT Lead Teachers participated in follow-up training from the CWT UCLA School Management Program trainers in 2009-10. The district met with the District Leadership Team in May 2010 for CWT evaluation and input. The CWT process will be fully implemented in 2010-11; including quarterly classroom walk throughs and collaborative school site CWT debrief meetings to promote teacher collaboration and to increase instructional effectiveness. | District CWT Team, Principals | 8/09 | X | X | X |  | 4. District wide Classroom Walk Through and debrief schedules are in place for 2009-10. 12/3/09- CWT follow-up training for CWT Leads |
| Fiscal Operations - Develop fiscal policies and a resource allocation plan to fully implement the EPCs in regard to Reading/Language Arts and mathematics. Review budgets to ensure that all available funds are allocated to high leverage actions to accelerate student achievement. Communicate regularly between the school site and district levels to discuss budget/expenditure issues and to ensure fiscal alignment throughout the district. | The LEA is implementing fiscal policies that appropriately allocate general and categorical funds of the district to support the R/LA and mathematics program goals in the school plans and that support the implementation of the nine Essential Program Components. Administrators meet two times per month to review budgets and to ensure that all available funds are allocated to high leverage actions as outlined in the 9 EPC's. March 15, 2010 update: Administrators meet two times per month and may review budgets as needed to ensure that all available funds are allocated to high leverage actions as outlined in the 9 EPC's. July 15, 2010 update: The district continues to implement fiscal policies that appropriately allocate general and categorical funds of the district to support the R/LA and mathematics program goals in the LEA Plan and all school sites' Single Plan for Student Achievement. Administrators review budgets regularly to ensure that all available funds are allocated to high leverage actions. | Superintendent, Assistant Superintendent, Principals | 8/08 | X | X | X |  | District administrators currently schedule meetings with all site principals regularly for the purpose of budget development and EPC alignment. |
| Parent and Community Involvement None |  |  |  |  |  |  |  | Family Friendly Schools Inservice in 11/09 |

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Human Resources One finding, but no recommendations. |  |  |  |  |  |  |  | 100% Highly Qualified |
| Data Systems and Achievement Monitoring None |  |  |  |  |  |  |  | District utilizes Edusoft |
| Professional Development None |  |  |  |  |  |  |  | Ongoing: Materials based professional development training in ELA/mathematics/ ELPD is provided to all teachers. Title III Inservice/ District wide EL strategies inservice |
| Other None |  |  |  |  |  |  |  |  |

California Department of Education

Template for Documentation of Local Educational Agency in Program Improvement Corrective Action

with Intensive Technical Assistance

Part II: Template for Documentation of Local Educational Agency Student Achievement Data and a Local Educational Agency Report on Local Collection and Use of Formative Student Assessment Data

County: Kern			Local Educational Agency: Fairfax Elementary

|  | 2007 AYP |  | 2009 AYP |  | Difference in % Proficient |  | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/language arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide | 20.9 | 28.7 | 28.4 | 33.7 | 7.5 | 5.0 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD | Quarterly | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| Hispanic or Latino | 20.3 | 28.6 | 28.0 | 33.3 | 7.7 | 4.7 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD | Quarterly | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| White | 25.7 | 33.0 | 31.1 | 34.4 | 5.4 | 1.4 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD | Quarterly | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| Socioeconomically Disadvantaged | 19.5 | 27.8 | 27.0 | 33.1 | 7.5 | 5.3 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD | Quarterly | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| English Learners | 16.3 | 28.4 | 21.8 | 29.4 | 5.5 | 1.0 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD | Quarterly | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| Students with Disabilities | 3.1 | 4.5 | 6.5 | 8.1 | 3.4 | 3.6 | District benchmark curriculum embedded assessments for ELA, mathematics, ELD Cognitive: WISC-IV, CAS, UNIT, KBIT-2 Psychological: TAPS-3, CTOPP, VMI-5, TVPS-3 Developmental: DP-3, Vineland-II -Social-Emotional: BASC-2, BES-3, ADDES-3, BBRS-2 Autistic: CARS, ADI-R | Quarterly Initial/ Annual/ Progress Monitoring | Data analysis and comparison of prior individual and group assessment performance | 11/09 | District utilizes data analysis system form to analyze assessment data |
| Statewide Targets | 24.4 | 26.5 | 46.0 | 47.5 | 21.6 | 21.0 |  |  |  |  |  |

Fairfax School District

Local Benchmark Analysis March 2010

Fairfax School District utilizes curriculum based quarterly assessments.  Each grade level’s performance bands are set as follows:

0 – 69%		= Below Grade Level

70% - 84.9% 	= At Grade Level

85% - 100% 		= Above Grade Level

Kindergarten

68% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark.  This is an increase of 1% from the 2008-2009 quarter two data.

55% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark, maintaining prior year second quarter performance.

First Grade

71% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark.  This is an increase of 8% from the 2008-2009 quarter two data.

61% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark.  This is an increase of 14% increase from the 2008-2009 quarter two data.

Second Grade

56% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark.  This is an increase of 2% from the 2008-2009 quarter two data.

30% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark.  This was a decrease of 4% from prior year second quarter performance.  The grade level has identified most commonly missed items on this assessment and has created a grade level wide goal to address this decrease in proficiency.

Third Grade

50% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark, maintaining prior year second quarter performance.

37% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark.  This is an increase of 2% from the 2008-2009 quarter two data.

Fourth Grade

41% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark.  This is an increase of 16% from the 2008-2009 quarter two data.

22% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark.  This is an increase of 6% increase from the 2008-2009 quarter two data.

Fifth Grade

19% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark. This was a decrease of 11% from prior year second quarter performance.  The grade level has identified most commonly missed items on this assessment and has created a grade level wide goal to address this decrease in proficiency

21% of students scored at or above grade level on the Houghton Mifflin Reading Quarter two Benchmark.  This is an increase of 1% from the 2008-2009 quarter two data.

Sixth Grade

8% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter two Benchmark, maintaining prior year second quarter performance.

26% of students scored at or above grade level on the Prentice Hall Reading Quarter two Benchmark.  This is an increase of 12% from the 2008-2009 quarter two data.

Seventh Grade

14% of students scored at or above grade level on the Prentice Hall Mathematics Quarter two Benchmark.  This is an increase of 4% from the 2008-2009 quarter two data.

14% of students scored at or above grade level on the Prentice Hall Reading Quarter two Benchmark.  This is an increase of 1% from the 2008-2009 quarter two data.

Eighth Grade

22% of students scored at or above grade level on the Prentice Hall Algebra Quarter two Benchmark, maintaining prior year second quarter performance.

19% of students scored at or above grade level on the Prentice Hall Reading Quarter two Benchmark, maintaining prior year second quarter performance.

Following quarterly assessments, each principal provides collaboration time for quarterly data analysis.  A district data analysis tool was created and implemented during the 2009-2010 school year.  With this tool, each grade level identifies most commonly missed standards on the assessment and sets goals to achieve proficiency.  A post test is administered to continuously assess progress.

Fairfax School District

Local Benchmark Analysis June 2010

Fairfax School District utilizes curriculum based quarterly assessments.  Each grade level’s performance bands are set as follows:

0 – 69%		= Below Grade Level

70% - 84.9% 	= At Grade Level

85% - 100% 		= Above Grade Level

Kindergarten

92% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark.  This is an increase of 24% from the 2009-2010 quarter two data.

92% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 37% from the 2009-2010 quarter two data.

First Grade

68% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark.  This is a decrease of 3% from the 2009-2010 quarter two data.

65% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 4% from the 2009-2010 quarter two data.

Second Grade

56% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark, maintaining quarter two performance.

48% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 18% from the 2009-2010 quarter two data.

Third Grade

47% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark.  This is a decrease of 3% from 2009-2010 quarter two data.

45% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 8% from the 2009-2010 quarter two data.

Fourth Grade

44% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark.  This is an increase of 3% from the 2009-2010 quarter two data.

36% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 14% from the 2009-2010 quarter two data.

Fifth Grade

15% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark. This is a decrease of 4% from the 2009-2010 second quarter performance.

32% of students scored at or above grade level on the Houghton Mifflin Reading Quarter four Benchmark.  This is an increase of 11% from the 2009-2010 quarter two data.

Sixth Grade

13% of students scored at or above grade level on the Houghton Mifflin Mathematics Quarter four Benchmark.  This is an increase of 5% from the 2009-2010 quarter two data.

26% of students scored at or above grade level on the Prentice Hall Reading Quarter four Benchmark, maintaining 2009-2010 quarter two performance.

Seventh Grade

14% of students scored at or above grade level on the Prentice Hall Mathematics Quarter four Benchmark, maintaining 2009-2010 quarter two performance.

36% of students scored at or above grade level on the Prentice Hall Reading Quarter four Benchmark.  This is an increase of 22% from the 2009-2010 quarter two data.

Eighth Grade

16% of students scored at or above grade level on the Prentice Hall Algebra Quarter four Benchmark.  This is a decrease of 6% from the 2009-2010 quarter two data.

17% of students scored at or above grade level on the Prentice Hall Reading Quarter four Benchmark.  This is a decrease of 2% from the 2009-2010 quarter two data.

Following quarterly assessments, each principal provides collaboration time for quarterly data analysis.  A district data analysis tool was created and implemented during the 2009-2010 school year.  With this tool, each grade level identifies most commonly missed standards on the assessment and sets goals to achieve proficiency.  A post test is administered to continuously assess progress.