| California Department of Education Executive Office SBE-002 (REV. 06/2008) |  |
| --- | --- |
| State of California | Department of Education |
| memorandum |  |

| Date: | November 16, 2010 |
| --- | --- |

| TO: | Members, STATE BOARD of EDucation |
| --- | --- |

| FROM: | Dr. William Ellerbee, Jr., Deputy Superintendent Special Services and Support Branch |
| --- | --- |

| SUBJECT: | Los Angeles Unified School District’s Specific School Building Plan to Eliminate the Concept 6 Program and Provide Adequate Pupil Capacity. |
| --- | --- |

Concept 6 is a multitrack year-round calendar that divides a school’s student population into three tracks of which two tracks attend the school at one time. The Concept 6 calendar provides districts the maximum number of students that can attend any school, but limits the number of instructional days to 163 instead of the required 180 (California Education Code [EC] Section 37670). The lost days of instruction are made up by adding additional minutes to each school day.

EC Section 37687, which was added pursuant to the Eliezer Williams, et al. vs. State of California, et al. settlement, prohibits the use of Concept 6 calendars after July 1, 2012. Any district that is operating a school on a Concept 6 multitrack year-round calendar after July 1, 2009, is required to submit evidence in writing each July 1 to the State Superintendent of Public Instruction (SSPI), who shall report to the State Board of Education (SBE), on the specific school building plan to provide adequate pupil capacity to eliminate the Concept 6 program by the earliest practicable date and no later than July 1, 2012.

The SBE approved the Los Angeles Unified School District (LAUSD) comprehensive action plan on July 6, 2005. On June 15, 2010, the District reported to the SSPI on the specific school building plan as required by EC Section 37687. LAUSD is the only district with remaining Concept 6 schools.

As of July 1, 2010, the District has developed a specific school building plan to eliminate the Concept 6 program and provide adequate pupil capacity. The District has made tremendous progress in the elimination of the Concept 6 program. During the 2010–11 school year, there will be eight existing schools scheduled on a Concept 6 calendar (Attachment 1). The District has identified preferred sites to build new schools and has approved buildings needed to satisfy the pupil capacity projected on the comprehensive action plan (Attachment 2). Additionally, the District has identified and obtained the funding necessary to complete the particular projects identified.

Attachment 1: List of 2010–11 Concept 6 Schools in the Los Angeles Unified School District

(1 page)

Attachment 2: Los Angeles Unified School District Specific School Building Plan (1 page)

List of 2010–11 Concept 6 Schools in the Los Angeles Unified School District

|  Concept 6 Location Code | School Name | 2010–11 Calendar | 2011–12 Calendar | 2012–13 Calendar |
| --- | --- | --- | --- | --- |
| 8536 | Bell Senior High | X | X |  |
| 8094 | Carver Middle | X |  |  |
| 8650 | Fremont Senior High | X | X |  |
| 8151 | Gage Middle | X | X |  |
| 8700 | Huntington Park Senior High | X | X |  |
| 8200 | Los Angeles Academy Middle | X |  |  |
| 8743 | Manual Arts Senior High | X | X |  |
| 8750 | Marshall Senior High | X | X |  |
| Total Number of Schools on Concept 6 |  | 8 | 6 | 0 |

	Not Concept 6

Los Angeles Unified School District Specific School Building Plan

| Project Name | Board Approval Date of Preferred Site | California Environmental Quality Act/Project Approval | School Occupancy | Schools Relieved | 2010–11 Calendar | 2011–12 Calendar | 2012–13 Calendar |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Frida Kahlo HS (Jefferson New Continuation HS) | 04/11/00 | 04/09/02 | 07/05/05 | Manual Arts Senior High |  |  |  |
| Santee Education Complex (South Los Angeles HS #1) | 04/11/00 | 04/09/02 | 07/05/05 | Manual Arts Senior High |  |  |  |
| Southeast HS (Southeast Area New HS #2) | 10/25/00 | 02/26/02 | 09/06/05 | Huntington Park Senior High, Bell Senior High |  |  |  |
| Clinton MS (Central LA MS #4) | 04/23/01 | 04/23/02 | 09/05/06 | Carver Middle, Los Angeles Academy Middle |  |  |  |
| Maywood Academy HS (Southeast Area New Learning Center) | 05/06/01 | 03/31/02 | 09/05/06 | Huntington Park Senior High, Bell Senior High |  |  |  |
| West Adams Prep HS (Central LA HS #2) | 05/28/02 | 05/28/02 | 09/04/07 | Manual Arts Senior High |  |  |  |
| Helen Bernstein HS (Central LA HS #1) | 09/25/01 | 09/25/01 | 09/03/08 | Marshall Senior High |  |  |  |
| Central Region HS #13 | 12/14/04 | 01/24/06 | 09/06/11 | Marshall Senior High |  |  |  |
| Central Region MS #7 | 09/21/04 | 01/24/06 | 09/06/11 | Carver Middle, Los Angeles Academy Middle |  |  |  |
| South Region HS #2 | 07/22/04 | 05/23/06 | 09/06/11 | Fremont Senior High |  |  |  |
| Augustus F. Hawkins HS (South LA New HS #3) | 11/28/06 | 02/26/08 | 09/04/12 | Manual Arts Senior High |  |  |  |
| South Region HS #9 | 06/21/05 | 06/30/09 | 09/04/12 | Huntington Park Senior High, Bell Senior High |  |  |  |
| South Region HS #12 | 02/14/06 | 02/26/08 | 09/04/12 | Fremont Senior High |  |  |  |
| South Region MS #3 | 04/22/08 | 12/09/08 | 09/04/12 | Gage Middle |  |  |  |
| South Region HS #8 | 05/28/09 | 12/31/09 | 09/02/14 | Bell Senior |  |  |  |

   Concept 6

   Not Concept 6

    Un-shaded schools are not yet opened

Note: School names in parentheses were the original names submitted on the Comprehensive Action Plan.