Common Core State Standards: Development of an Implementation Plan

The State Superintendent of Public Instruction (SSPI) and the California Department of Education (CDE) are providing the following information to the State Board of Education (SBE) for information at their joint meeting with the Commission on Teacher Credentialing

on November 8, 2010 (See agenda at http://www.cde.ca.gov/be/pn/pn/ctcsbeagenda08nov2010.asp). Because Education Code (EC) Section 60200.7 prohibits the SBE from acting on instructional materials adoptions or procedures related to them, there will be no specific action at this time.

On August 2, 2010, the SBE adopted the Common Core State Standards (CCSS) in English Language Arts & Literacy in History/Social Studies, Science and Technical Subjects, and Mathematics in response to the recommendation of the Academic Content Standards Commission (ACSC). The action included the CCSS and specific additional standards that the Commission had deemed necessary to maintain the integrity and rigor of California’s previous state academic standards. The CCSS were developed by the Council of Chief State School Officers (CCSSO) and the National Governors Association Center for Best Practices (NGA Center).

In the fall of 2009, governors and state commissioners of education from 48 states (including California), two territories, and the District of Columbia, committed to developing a set of standards that would help prepare students with the knowledge and skills needed to succeed in education and careers after high school. The development of the CCSS was a voluntary state-led effort coordinated by the CCSSO and NGA Center, with stakeholders from nearly every state in the country contributing to their development. The feedback and the review process was integral to the shaping of these new standards, and included educators from kindergarten through grade twelve, postsecondary faculty, curriculum and assessment experts, researchers, national organizations, and community groups. In January 2010, the passage of Senate Bill X5 1

EC included the ACSC. The ACSC was composed of members appointed by the Governor and the Legislature, the majority of whom were current public school elementary or secondary classroom teachers. The ACSC was authorized to make recommendations to the SBE to approve or disapprove the CCSS, and to supplement those standards with up to 15 percent additional standards. The ACSC met four times in June and July 2010, and provided its recommendations to the SBE on August 2, 2010.

CDE staff is working on implementation scenarios for the CCSS that were adopted by the SBE on August 2, 2010. The actual timelines for that implementation will be dependent on actions by the Legislature to authorize and fund implementation-related activities. Noteworthy is that current statute (EC Section 60200.7) restricts the SBE from taking actions related to the development of curriculum frameworks and the adoption of instructional materials through July 1, 2013. To illustrate the effect of the law on implementation plans, there are two timelines, one that assumes legislative action repealing EC Section 60200.7 (Attachment 1) and another that is based upon no change in the law (Attachment 2). The timelines take into account curriculum framework development and instructional materials adoptions, as both activities would be crucial components of any implementation plan. If no legislative action is taken to lift the suspension, the soonest that a framework could be presented to the SBE for action would be 2015 with an instructional materials adoption in 2017.

The California application for the Race to the Top competition included detailed proposals and requests for funding to cover the costs of curriculum framework development, professional development, and other activities in support of the implementation of the Common Core. Since California did not receive federal funding through Race to the Top, those activities will have to be supported by the Legislature through additional appropriations if the implementation is to take place.

In addition to new curriculum and instructional materials, teachers, administrators,

and educators will need professional development focusing on the CCSS. Previous initiatives have focused on adopted instructional materials with an emphasis on kindergarten through grade eight. The new initiative will have to be broader and deeper, as the focus must be on teachers and educators at the elementary, middle, and high school levels to meet the needs of their diverse learner population. Lastly, teacher education programs will need to shift their attention to the CCSS.

Another critical component of the implementation of the CCSS is the development

of new assessments based on the new standards. California is a participant in the Partnership for Assessment of Readiness for College and Careers (PARCC), a consortium that is developing assessments based upon the CCSS. PARCC has established a timeline of developing pilot tests by 2011–12 with field testing in 
2012–13 and 2013–14 and full implementation by 2014–15.

EC Section 60605.8 (h) requires the SSPI and SBE to present a schedule and an implementation plan to the Governor and the appropriate policy and fiscal committees of the Legislature for integrating the CCSS into the state educational system. Important legislative actions will include allowing the development of curriculum frameworks and adoption of instructional materials, creating and directing professional development programs, and reauthorizing statewide assessment systems.

More immediate action has been taken, as the CDE has created a dedicated Web page that includes Power Point presentations giving an overview of the standards and the new assessment system. The CDE has presented on the CCSS and the PARCC to educators in northern and southern California. The Power Point presentations are available at http://www.cde.ca.gov/ta/tg/sa/infomeeting10.asp [Note: the preceding Web address is no longer valid.] Additional activities that will be taken include the editing, publication, and posting of the final version of the standards; translating them into Spanish; developing a Web page for responding to Frequently Asked Questions and presentations and other information for teachers, administrators, and parents regarding the potential impacts of the statewide adoption of CCSS; and working with other agencies to prepare for the implementation activities described above.

According to internal CDE estimates, the average cost of developing and publishing a curriculum framework is approximately $1.2 million. The average cost of a major instructional materials adoption in mathematics or reading/language arts–English language development is approximately $2.1 million. Furthermore, in order to conduct the activities associated with those projects, the cut of $705,000 that defunded the

Curriculum Development and Supplemental Materials Commission in 2009 would have to be restored to the CDE budget and continued in future budget years. The Legislature would have to restore the funding removed from the CDE’s regular budget and return the Instructional Materials Funding Realignment Program to levels that guarantee materials for every student.

Funding would be needed to provide professional development support for teachers and principals. The costs of developing new assessments aligned to the CCSS may be reduced through the state’s participation in the PARCC, but there will be some costs associated with the state’s development of assessments for the 15 percent of state-specific content standards.

The implementation of the Common Core State Standards provides opportunities and challenges for California. We look forward to beginning this next phase of updating and improving California’s standards-based educational system.

Attachments

Attachment 1: Common Core State Standards: Implementation Timeline 1

Attachment 2: Common Core State Standards: Implementation Timeline 2

Common Core State Standards: Implementation Timeline 1

Assumes Legislative Action to Lift Suspension Under Education Code Section 60200.7

Part 1: Curriculum Frameworks

| Milestones | Mathematics Implementation Timeline | Reading/Language Arts Implementation Timeline |
| --- | --- | --- |
| Curriculum Development and Supplemental Materials Commission (Curriculum Commission) Approves Plan, Timeline, Curriculum Framework and Evaluation Criteria Committee (CFCC) Application | Completed 2009 | January 2012 |
| State Board of Education (SBE) Approves Plan, Timeline, CFCC Application | May 2011 | March 2012 |
| Minimum 90-day Recruitment of CFCC (from date application posted through SBE appointment of CFCC) §9513 | May 2011 - August 2011 | April - June 2012 |
| 4 Focus Groups §9511(c) | 2011 June Central Valley June Bay Area June Los Angeles Area June San Diego Area | 2012 May Central Valley May Bay Area May Los Angeles area May San Diego area |
| Curriculum Commission Recommends CFCC, receives Focus Group input, recommends guidance | September 2011 | September 2012 |
| SBE Appoints CFCC, receives Focus Group input, approves guidance | November 2011 | November 2012 |
| CFCC Work: 5-6 months (6 meetings) | March 2012 April 2012 May 2012 June 2012 July 2012 August 2012 | March 2013 April 2013 May 2013 June 2013 July 2013 August 2013 |
| Curriculum Commission Sends out Framework for Initial Field Review | September 2012 | September 2013 |
| Required 60-day Public Review of Document Prior to Curriculum Commission Recommendation §9515(a)(3) | October - November 2012 | October - November 2013 |
| Curriculum Commission analyzes field review results and revises draft framework | December 2012 | December 2013 |
| Curriculum Commission Action on Draft Framework | January 2013 | January 2014 |
| Required 60-day Public Review of Document After Curriculum Commission Recommendation §9515(c) | February - March 2013 | February - March 2014 |
| SBE Action on Framework | May 2013 | May 2014 |

Part 2: Adoption of Instructional Materials (Accelerated Schedule)

| Milestones | Mathematics Implementation Timeline | Reading/Language Arts Implementation Timeline |
| --- | --- | --- |
| Adoption of Framework/ Evaluation Criteria | May 2013 | May 2014 |
| Curriculum Commission approves timeline, reviewer application | January 2013 | January 2015 |
| SBE approves timeline, reviewer application | March 2013 | March 2015 |
| Recruitment of reviewers (at least 90 days per §9513) | April - August 2013 | April - August 2015 |
| Curriculum Commission recommends reviewers to SBE | September 2013 | September 2015 |
| SBE appoints reviewers | November 2013 | November 2015 |
| Invitation to Submit Meeting | January 2014 | January 2016 |
| Submission Date | March 2014 | March 2016 |
| Reviewer Training | April 2014 | April 2016 |
| Independent Review | April - July 2014 | April - July 2016 |
| Reviewer Deliberations | July 2014 | July 2016 |
| Curriculum Commission holds public meeting to receive comment (§9524) | August 2014 | August 2016 |
| Implementation of Common Core Assessment | 2014-15 | 2014-15 |
| Curriculum Commission makes recommendation | September 2014 | September 2016 |
| SBE takes action on Commission recommendation | November 2014 | November 2016 |

Common Core Standards: Implementation Timeline 2

Assumes No Legislative Action to Lift Suspension Under Education Code Section 60200.7

Part 1: Curriculum Frameworks

| Milestones | Mathematics Implementation Timeline | Reading/Language Arts Implementation Timeline |
| --- | --- | --- |
| Curriculum Development and Supplemental Materials Commission (Curriculum Commission) Approves Plan, Timeline, Curriculum Framework and Evaluation Criteria Committee (CFCC) Application | Completed 2009 | January 2015 |
| State Board of Education (SBE) Approves Plan, Timeline, CFCC Application | July 2013 | March 2015 |
| Minimum 90-day Recruitment of CFCC (from date application posted through SBE appointment of CFCC) §9513 | July - October 2013 | April - August 2015 |
| 4 Focus Groups §9511(c) | 2013 April Central Valley April Bay Area May Los Angeles Area May San Diego Area | 2015 April Central Valley April Bay Area May Los Angeles area May San Diego area |
| Curriculum Commission Recommends CFCC, receives Focus Group input, recommends guidance | November 2013 | September 2015 |
| SBE Appoints CFCC, receives Focus Group input, approves guidance | January 2014 | November 2015 |
| CFCC Work: 5-6 months (6 meetings) | February 2014 March 2014 April 2014 May 2014 June 2014 July 2014 | February 2016 March 2016 April 2016 May 2016 June 2016 July 2016 |
| Implementation of Common Core Assessments | 2014-15 | 2014-15 |
| Curriculum Commission Sends out Framework for Initial Field Review | September 2014 | September 2016 |
| Required 60-day Public Review of Document Prior to Curriculum Commission Recommendation §9515(a)(3) | October - November 2014 | October - November 2016 |
| Curriculum Commission analyzes field review results and revises draft framework | December 2014 | December 2016 |
| Curriculum Commission Action on Draft Framework | January 2015 | January 2017 |
| Required 60-day Public Review of Document After Curriculum Commission Recommendation §9515(c) | February - March 2015 | February - March 2017 |
| SBE Action on Framework | May 2015 | May 2017 |

Part 2: Adoption of Instructional Materials

| Milestones | Mathematics Implementation Timeline | Reading/Language Arts Implementation Timeline |
| --- | --- | --- |
| Adoption of Framework/ Evaluation Criteria | May 2015 | May 2017 |
| Curriculum Commission approves timeline, reviewer application | January 2016 | January 2018 |
| SBE approves timeline, reviewer application | March 2016 | March 2018 |
| Recruitment of reviewers (at least 90 days per §9513) | April - August 2016 | April - August 2018 |
| Curriculum Commission recommends reviewers to SBE | September 2016 | September 2018 |
| SBE appoints reviewers | November 2016 | November 2018 |
| Invitation to Submit Meeting | January 2017 | January 2019 |
| Submission Date | March 2017 | March 2019 |
| Reviewer Training | April 2017 | April 2019 |
| Independent Review | April - July 2017 | April - July 2019 |
| Reviewer Deliberations | July 2017 | July 2019 |
| Curriculum Commission holds public meeting to receive comment (§9524) | August 2017 | August 2019 |
| Curriculum Commission makes recommendation | September 2017 | September 2019 |
| SBE takes action on Commission recommendation | November 2017 | November 2019 |
| Elapsed time since previous adoption | 10 years | 11 years |

# Footnotes

This timeline assumes that the activities of the Curriculum Commission are funded for 2011 and subsequent years. The CDE is proposing legislation that would empower the Superintendent of Public Instruction to conduct these activities in the absence of such funding.

These items were originally approved in 2009, but with the adoption of the Common Core California State Standards, the SBE should approve an updated timeline and restart the CFCC recruitment. Under the suspension established by Assembly Bill X4 2 in Education Code Section 60200.7, the SBE can take no actions on curriculum frameworks or instructional materials adoptions until July 1, 2013. Specific legislation must be passed with an urgency clause, within the first few months of the 2011 legislative session, to allow the SBE to meet the dates in this timeline. If such legislation is not passed, the milestone dates will slip to the following year for the mathematics framework (and subsequent instructional materials). If no legislative action is taken to remove the suspension, the soonest a mathematics framework could be completed within current statutory and regulatory requirements would be May 2015 (with a subsequent adoption in 2016 or 2017).

Sections on this timeline refer to the California Code of Regulations, Title 5, Education (5 CCR).

CFCC members were recruited and recommended by the Curriculum Commission in 2009, but due to the delay caused by the legislative suspension, an additional recruitment is necessary to meet the requirements of 5 CCR §9513.

Four focus groups were held on the mathematics framework in 2009. Due to the adoption of the Common Core California Standards, new focus groups are proposed for 2011.

Senate Bill X5 1 (2009) added Section 60605.9 to the Education Code, waiving the requirement of Education Code Section 60200(c)(6), which requires that the SBE take action on an adoption at least 30 months after the adoption of an evaluation criteria for that adoption. As a result, this timeline outlines an accelerated schedule that would complete the mathematics adoption just 18 months after the completion of the framework and evaluation criteria. This would assume that publishers of instructional materials would be willing and able to complete their materials within the accelerated timeline.

Per Education Code Section 60200(a), the adoptions of instructional materials in language arts and mathematics must be separated by at least one year.

The adoption of the curriculum framework and evaluation criteria generally mark the start of the adoption process. However, in order to complete the mathematics adoption in an accelerated schedule of just 18 months, some activities, such as approval of the timeline and reviewer application and the recruitment of reviewers, will have to take place before the SBE adopts the framework and criteria in this case.

Under the suspension established by Assembly Bill X4 2 in Education Code Section 60200.7, the SBE can take no actions on curriculum frameworks or instructional materials adoptions until July 1, 2013. This timeline assumes that no legislative action is taken to lift that suspension.

Sections on this timeline refer to the California Code of Regulations, Title 5, Education (5 CCR).

CFCC members were recruited and recommended by the Curriculum Commission in 2009, but due to the delay caused by the legislative suspension, an additional recruitment will be necessary to meet the requirements of 5 CCR §9513.

Four focus groups were held on the mathematics framework in 2009. Due to the adoption of the Common Core California Standards and the long delay since the original focus groups were held, new focus groups are proposed once work on the framework resumes. The focus groups are conducted administratively by CDE and do not require SBE approval; thus they can be scheduled before the end of the legislative suspension.

This timeline assumes that the activities of the Curriculum Commission are funded.

Senate Bill X5 1 (2009) added Section 60605.9 to the Education Code, waiving the requirement of Education Code Section 60200(c)(6), which requires that the SBE take action on an adoption at least 30 months after the adoption of an evaluation criteria for that adoption. As a result, this timeline could be accelerated, depending on whether publishers of instructional materials would be willing and able to complete their materials within the accelerated timeline. This timeline reflects the more typical unaccelerated pace of events associated with an adoption.

Per Education Code Section 60200(a), the adoptions of instructional materials in language arts and mathematics must be separated by at least one year. This section was not waived by Senate Bill X5 1.

California Department of Education – November 2010