Last Reviewed December 14, 2017

State of California

Annual Performance Report

for

Federal Fiscal Year 2008

(2008-2009)

Individuals with Disabilities Education Act of 2004

Due:  February 1, 2010

| Table of Content |  |
| --- | --- |
| ##### Overview of Annual Performance Report Development | 1 |
| ##### Improvement Activities across Multiple Indicators | 9 |
| ##### Indicator 1 - Graduation | 10 |
| Indicator 2 - Dropout | 14 |
| Indicator 3 - Statewide Assessment | 18 |
| Indicator 4 - Suspension and Expulsion | 27 |
| Indicator 5 - Least Restrictive Environment | 33 |
| Indicator 8 - Parent Involvement | 37 |
| Indicator 9 - Disproportionality Overall | 43 |
| Indicator 10 - Disproportionality Disability | 56 |
| Indicator 11 - Eligibility Evaluation | 63 |
| Indicator 12 - Part C to Part B Transition | 67 |
| Indicator 13 - Secondary Transition Goals and Services | 72 |
| Indicator 15 - General Supervision | 75 |
| Indicator 16 - Complaints | 82 |
| Indicator 17 - Due Process | 84 |
| Indicator 18 - Hearing Requests | 86 |
| Indicator 19- Mediation | 88 |
| Indicator 20 - State-reported Data | 90 |
| Appendix 1 - Table 7, Report of Dispute Resolution under Part B of the Individuals with Disabilities Education Act | 108 |
| Appendix 2 - Acronyms | 110 |

Overview of the Annual Performance Report Development

The State Board of Education (SBE) is the lead State Education Agency (SEA). Hereafter, the term California Department of Education (CDE) refers to the CDE operating under the policy direction of the SBE.

The Annual Performance Report is prepared using instructions forwarded to the California Department of Education (CDE), Special Education Division (SED) by the U.S. Department of Education (DE), Office of Special Education Programs (OSEP). For 2008-09, instructions were drawn from several documents:

•	California’s 2007-08 Compliance Determination letter and table (June 2009)

•	General Instructions for the State Performance Plan (SPP) and Annual Performance Report (APR)

•	State Performance Plan (SPP) and Annual Performance Report (APR) Part B Indicator Measurement Table (Expiration Date 2/29/2012)

•	OSEP Letter:  Reporting on Correction of Noncompliance in the Annual Performance Report Required under Sections 616 and 642 of the Individual with Disabilities Education Act (October 17, 2008) (OSEP 0902)

CDE staff and contractors collected data and made calculations for each of the 20 indicators. However, CDE is not required to report on Indicators 6 (Preschool Least Restrictive Environment), Indicator 7 (Preschool Assessment), and Indicator 14 (Secondary Transition/Post Secondary Outcomes). Technical assistance was provided by several federal contractors – most notably the Western Regional Resource Center (WRRC). SED management discussed each of the requirements, reviewed calculations and discussed improvement activities. Updated indicator language and measurement changes (baselines and targets) were established for the following indicators:  1, 2, 3, 5, 7, 11, 12, 16, and 17.

During 2008-09, CDE disseminated information and solicited input from a wide variety of groups:

•	The CDE SED continued utilizing Improving Special Education Services (ISES), a broad stakeholder group established to combine various existing stakeholder groups into one larger stakeholder constituency. Members include parents, [Parent Training and Information Centers (PTI), Family Empowerment Centers (FEC), and Family Resource Centers(FRC)], teachers, administrators, professors in higher education, Special Education Local Plan Area (SELPA) Directors, Special Education Administrators of County Offices (SEACO), staff of various CDE divisions, and outside experts. Two meetings were held to discuss SPP and APR calculations and improvement activities – in June 2009 and December 2009. In late November 2009, drafts of the APR and SPP were disseminated to solicit field input.

•	The SPP and APR requirements and results were presented at two separate California Special Education Management Information System (CASEMIS) training sessions with the SELPA and local education agency (LEA) administrators during the spring and fall of 2009.

•	The SPP and APR requirements were presented at regular meetings of the California Advisory Commission on Special Education (ACSE) during 2009. In February 2009 the SED presented the ABC's of Disproportionality Determination to the ACSE, in May 2009, an overview of the compliance determination process, and in December 2009, the Director’s Report.

•	SPP requirements and APR data related to Preschool Assessment, Preschool Least Restrictive Environment (LRE), and Transition from Part B to Part C were presented and discussed at the Special Education Early Childhood Administrators Project (SEECAP) Symposium in February 2009 and at the North and South Infant Preschool Field Meetings Webinar in May 2009. These meetings were open to staff and parents of all districts in California.

•	Selected SPP revisions and APR data have been reviewed at the regular monthly meetings of the Directors of the SELPAs and at the quarterly meetings of the Special Education Administrators of County Offices (SEACO). Drafts of SPP and APR were disseminated in late November 2009 for comments.

•	The SPP and APR were approved by the California State Board of Education (SBE) in January 2010.

•	The revised SPP and APR will be posted on the CDE Web site once they have been approved by the OSEP. The most recently approved SPP and APR may be found at http://www.cde.ca.gov/sp/se/qa/ .

•	A consolidated SPP reflecting changes made to date may be found at http://www.cde.ca.gov/sp/se/qa/documents/consolspp.doc .

General Notes

Data Sources:  Data for the APR indicators are collected from the following sources:

- Indicators 1 (Graduation Rates) and 2 (Dropout Rates) are gathered from Adequate Yearly Progress (APY) data, 2007-08.

- Indicator 3 (Statewide Assessment) is collected from AYP Database and the California Special Education Management Information System (CASEMIS) 2008-09.

- Indicator 4 (Rates of Suspension and Expulsion) is gathered from CASEMIS 2007-08 and a LEA self-review of policies, procedures, and practices.

- Indicator 5 (LRE) is derived from CASEMIS December 2008.

- Indicators 6 (Preschool LRE), 7 (Preschool Assessment) and 14 (Secondary Transition/Post School Outcomes) are not reported this year.

- Indicator 8 (Parent Involvement) is collected through monitoring data.

- Indicators 9 (Disproportionality by Race and Ethnicity) and 10 (Disproportionality by Disability) are collected through the CASEMIS December 2008, CASEMIS June 2009, and CBEDS.

- Indicator 11 (60 Day Timeline), 12 (Transition, Part C to Part B)  and 13 (Secondary Transition) are also gathered through CASEMIS December 2008 and June 2009, with an additional Department of Developmental Services (DDS) Part C data set for Indicator 12.

- Indicator 15 (General Supervision) is derived from monitoring and procedural safeguard activities conducted by CDE from July 1, 2008 to June 30, 2009.

- Indicator 16 (Complaints) is gathered from the complaints data base, July 1, 2008 to June 30, 2009.

- Indicators 17 (Hearings), 18 (Resolutions) and 19 (Mediations) are derived from Office of Administrative Hearings (OAH) data, July 1, 2008 to June 30, 2009.

- Indictor 20 (State Reported Data) is gathered from office archives.

Determination and Correction of Noncompliance: As noted in Indicator 15 (General Supervision) in the Apr, the CDE has used multiple methods to carry out its monitoring responsibilities. These monitoring activities are part of an overall Quality Assurance Process (QAP) designed to ensure that procedural guarantees of the law are followed and that programs and services result in educational benefits. The CDE uses all of its QAP activities to monitor for procedural compliance and educational benefit. Formal noncompliance may be identified and corrective action plans developed through a wide variety of means, including data collection and analysis, investigation of compliance complaints and due process hearings, and reviewing policies and procedures in local plans. For example, the CDE uses data collected through the CASEMIS to identify districts that are not completing annual reviews of individualized educational programs (IEPs) in a timely way. These result in formal findings of noncompliance citing specific state and federal laws and regulations and require that a corrective action plan be completed.

In addition to these components of the QAP, there are four types of traditional monitoring review processes: Facilitated Reviews, Verification Reviews (VR), Special Education Self-reviews (SESRs), and Nonpublic School Reviews (both onsite and self-reviews). Each of the formal review processes may result in findings of noncompliance at the student and district level. All findings require correction. At the student level the district must provide specified evidence of correction within a 45-day time period. At the district level, the district must provide updated policies and procedures, evidence that the new policies and procedures have been disseminated and, in a six-month follow-up review, the district must demonstrate that no new instances of noncompliance in that area have occurred. CDE has a variety of sanctions available to use in situations in which noncompliance goes uncorrected (e.g., special grant conditions, withholding of funds, and court action).

Compliance and Non-Compliance: CDE has adjusted all of its monitoring data from an initiation year basis. For the purpose of this and other indicators, compliance findings are reported in the year in which the district was notified of noncompliance. “On time” calculations are based on a span of one year from the date that the noncompliance finding was reported (e.g., VR initiated in 2006-07) to a notification year basis (e.g., the ABC School District review findings were notified of noncompliance in 2005-06). As a result, noncompliance findings made in 2006-07 should be corrected within one year in 2007-08. For this reason, some of the finding totals cited in prior APRs may not match with this APR because they were reported by initiation date (date of the review) rather than notification date.

### Improvement Activities across Multiple Indicators

Many statewide improvement activities in the APR address multiple indicators. Instead of listing a multitude of repetitive activities to each indicator, we have chosen to highlight those large-scale activities that cut across indicators provide, a brief description of state improvement activities, and include Web links as appropriate. These improvement activities reflect various CDE initiatives and programs that include the work of several divisions in collaboration with the Special Education Division.

Improvement Planning

Analysis and thoughtful planning of improvement activities for each of the indicators takes place in a variety of ways:

- A broad-based stakeholder group – ISES, provides CDE with feedback and recommendations for improvement activities based on data in the SPP and APR. For more information about ISES, please visit the California Services for Technical Assistance and Training (CalSTAT) Web site. In addition to collaboration with ISES, SED staff has worked to identify improvement activities for each indicator and to analyze data to identify effective improvement activities.

- The California Advisory Commission on Special Education (ACSE) – is an advisory body required by Federal (20 USC 1412(a)(21) and State Statute (EC 33590-6). The Commission provides recommendations and advice to the State Board of Education, the Superintendent of Public Instruction, the Legislature, and the Governor in new or continuing areas of research, program development and evaluation in California special education. The Advisory Commission consists of appointed members from the Speaker of the Assembly, Senate Committee on Rules, and the Governor. One member of the State Board of Education serves as liaison to the ACSE. The membership includes parents, persons with disabilities, persons knowledgeable about the administration of special education, teachers, and legislative representation from the Assembly and Senate. The SED provides the ACSE with information on the SPP/APR through monthly information sharing updates, staff presentations, and through ACSE participation in the ISES stakeholder meetings.

The SED will more actively involve the ACSE, the SBE liaison, and the SBE staff in the development of the SSP, 2009 and APR, 2009-2010. Additionally, ACSE members and the SBE liaison will be included in the membership of the ISES stakeholders group and will be invited to all ISES meetings during which the SED seeks advice regarding the effectiveness of improvement activities and suggestions for new alternative activities. ACSE representatives will be supported by the SED to prepare for and report to the ACSE the outcomes of ISES meetings. SED will also provide the ACSE, the SBE liaison, and the SBE staff a calendar of important dates, report to the ACSE any instructions from OSEP to CDE, provide dates of OSEP technical assistance calls, data collection deadlines, and deadlines for submitting information and preparation of the SPP/APR. The SED will provide drafts to the ACSE, the SBE liaison, and the SBE staff and other information regarding the development of the SPP and ARP in order to receive their input. SED will also provide support for the ACSE to prepare recommendations to the SBE regarding the SPP/APR.

- Monitoring – In 2007-08, CDE began the development of improvement planning modules that will be integrated into the Verification and SESR software. Currently, CDE software customizes a district’s self-review based on a monitoring plan that, when entered into the software, generates student record review forms, policy and procedure review forms, and parent and staff interview protocols. All the items in the software assist districts in conducting self-reviews including parent input, student IEP record reviews, and analysis of data. In the current software, all of the items are related to compliance requirements in state and federal law. Existing software draws on the compliance elements of all SPP indicators, whether they are compliance indicators or not. Over the next year, CDE will incorporate programmatic self-review items related to the performance based indicators. These items will generate required, self study instruments for those districts that fall below the benchmark on performance based indicators such as Indicator 3 (Statewide Assessment) and Indicator 5 (LRE). Items for these self study instruments will be drawn from a variety of sources, starting with those instruments being prepared by the CDE and OSEP technical assistance contractors. Results of the self study will be entered into the software and, based on the results; the district will develop and enter an improvement plan that can be tracked as a part of the follow-up to the monitoring review.

- SPP Technical Assistance (TA) System – The CDE is in the process of designing a statewide SPP Technical Assistance System to assist local educational agencies (LEAs) to correct noncompliance findings in any of the SPP indicators. CDE will initially focus on the disproportionate representation by ethnicity and race of students receiving special education services. This design process will include convening a Design Team of key professionals, meetings with the SBE liaison and SBE staff, holding a facilitated focus group to gain input on the draft design, identifying and training a key content specialist and master trainer, and launching the new SPP TA System by July 1, 2010.

Communication/Information and Dissemination

CDE communication and information is disseminated in a variety of formats and forums. A quarterly newsletter, The Special EDge, is published and sent out free of charge to personnel, parents, and the public. The Special EDge covers current topics in special education in California and nationally. The Division also takes advantage of technology by providing information and training through the CDE Web site and through CDE Web casts. The SED provided Web-based training on the California Modified Assessment and IEP Team Decisions, Early Childhood Inclusion, the Self-review Process, and CASEMIS which have been archived for later access. CDE consultants are available to the field by phone or e-mail to offer technical assistance and provide information.

Assessment

Assessment activities cross over several indicators in the SPP. The SEA has developed the Standardized Testing and Reporting (STAR) program, a statewide assessments for all students. The STAR includes the following assessments:

- California Standards Test (CST), for all students including students with IEPS and 504 Plans

- California Modified Assessment (CMA), for students who have an IEP and meet the State Board of Education-adopted eligibility criteria

- California Alternate Performance Assessment (CAPA), for students with IEPs with significant cognitive disabilities

- Standards Test in Spanish (STS), required for Spanish-speaking English learners (ELs) who either received instruction in Spanish or were enrolled in a school in the United States for less than 12 months

- California High School Exit Exam (CAHSEE), for all students to graduate from high school. The CAHSEE is designed to ensure that all high school graduates have achieved a solid foundation of knowledge and skills in English-language arts (ELA) and mathematics. The CAHSEE test questions are based on the state content standards. Students have eight opportunities to take the CAHSEE. As of July 1, 2009, students with disabilities with IEPs or 504 Plans are exempt from passing the CAHSEE in order to receive a high school diploma.

Data are gathered from these assessments to inform Indicator 3 (Statewide Assessment). Through the development of a series of training sessions and materials/resources, IEP teams have been offered extensive training on how students participate in statewide assessments to maximize student success.

In addition, CDE has developed a statewide assessment for preschoolers called the Desired Results Developmental Profile (DRDP). To provide an instrument to capture developmental progress on children with disabilities, the SED has developed the DRDP access. The results from these preschool assessments inform Indicator 7 (Preschool Assessment).

Closing the Achievement Gap

In December 2004, State Superintendent of Public Instruction, Jack O’Connell, established the California P-16 Council. The role of the Council was to examine ways to improve student achievement at all levels and link preschool, elementary, middle, high school, and higher education to create a comprehensive, integrated system of student learning.

The goals of the Superintendent's California P-16 Council are to:

- Improve student achievement at all levels and eliminate the achievement gap.

- Link all education levels including preschool, elementary, middle, high school, and higher education, to create a comprehensive, seamless system of student learning.

- Ensure that all students have access to caring and qualified teachers.

- Increase public awareness of the link between an educated citizenry and a healthy economy.

The P-16 Council was charged to develop, implement, and sustain a specific, ambitious plan that holds the State of California accountable for creating the conditions necessary for closing the achievement gap. The Council’s four subcommittees are:

- Access Subcommittee

- Culture/Climate Subcommittee

- Expectations Subcommittee

- Strategies Subcommittee

We know all children can learn to the same high levels, so we must identify and change those things that are not allowing groups of students to learn to their fullest potential. To address this, the SED has collaborated with the Culture/Climate Subcommittee of the P-16 Council and the Equity Alliance Center regarding the instructional needs of student with disabilities. In addition, the SED, in collaboration with the California Comprehensive Center at WestEd, is developing a series of Web-based interactive training modules on standards-based IEPs to address the achievement gap by improving instruction for students with disabilities.

The CDE continues to use the California’s State Personnel Development Grant (SPDG) to fund training and technical assistance in research-based instruction in the areas of literacy and behavior. These funds are also used to implement activities designed to foster special education/general education collaboration and the use of effective practices to improve the academic achievement of students with disabilities. The CDE provides technical assistance and support to districts designed to implement evidence-based practices and to increase the recruitment and retention of highly qualified special education teachers. Particular emphasis is placed on the sharing of data and training to improve the ability to collect, manage, and analyze data to improve teaching, decision-making, school improvement efforts, and accountability.

Response to Instruction and Intervention (RtI2)

RtI is emerging nationally as an effective strategy to support every student. The CDE is using the term Response to Instruction and Intervention (Rtl2) to define a general education approach to high quality instruction, early intervention, prevention, and behavioral strategies. The CDE’s definitions, philosophy, and core components of Rtl2 are available at: http://www.cde.ca.gov/ci/cr/ri/rtiphilosphydefine.asp .

Rtl2 offers a way to eliminate achievement gaps through a school-wide process that provides assistance to every student, both high achieving and struggling learners. It is a process that utilizes all resources within a school and district in a collaborative manner to create a single, well-integrated system of instruction and interventions informed by student outcome data. Rtl2 is fully aligned with the research on the effectiveness of early prevention and intervention and the recommendations of the California P-16 Council.

A cohesive RtI2 process integrates resources from general education, categorical programs, and special education into a comprehensive system of core instruction and interventions to benefit every student. The following components are critical to the full implementation of a strong RtI2 process:

- Research-based instruction

- Universal screening and continuous student progress monitoring

- Research-based interventions supported by ongoing progress monitoring to evaluate the effectiveness of instruction

- Fidelity of program implementation

- Ongoing staff development and collaboration

- Parental involvement

- Specific Learning Disability Determination

The Individuals with Disabilities Education Act of 2004 and related federal regulations state that the RtI2 approach may be one component of Specific Learning Disability determination. As part of determining eligibility, the data from the RtI2 process may be used to ensure that a student has received research-based instruction and appropriate interventions prior to referral to special education.

On November 4, 2008, Jack O’Connell, Superintendent of Public Instruction of CDE issued a letter on RtI² stating “Thus, the data gained during the implementation of an effective RtI² system can be part of the process to identify students with learning disabilities. Research shows that implementation of RtI² in general education reduces the disproportionate representation of certain groups of students identified as needing special education services. Together, we can close the achievement gap and open the door to a better future for every student, without exception. I look forward to continuing our work together.” The SED staff continues collaboration with other CDE divisions regarding the implementation of RtI² in districts.

A major revision of the 2001 edition of the Student Success Team (SST) Manual was completed during 2009 through a collaborative effort of the Learning Supports and Partnerships Division and SED. The revisions included updating the publication with new information about RtI2, resiliency research, culturally responsive instructional practices, and closing the achievement gap.

NIMAS/NIMAC

The reauthorization of IDEA in 2004 included new mandates establishing the National Instructional Materials Accessibility Standard (NIMAS) and the National Instructional Materials Accessibility Center (NIMAC). The new mandates require states to adopt a standard electronic file format for instructional materials. The creation of a standard electronic file format will help to ensure that students with print disabilities will have timely access to print materials. The timely availability of print materials in a variety of accessible formats will provide expanded learning opportunities for all students in the LRE and will better prepare students with disabilities to participate in the state assessments and to succeed in coursework required to earn a regular high school diploma.

The NIMAC serves as a national repository for NIMAS files. It is also the conduit through which the NIMAS files are made available to authorized users so that the files can be converted into accessible textbooks. Since California has joined the NIMAC, publishers of K-8 State adopted textbooks will be required to send NIMAS files to the NIMAC. The SED collaborates with the Clearinghouse for Specialized Media and Translations (CSMT) to ensure that all LEAs become familiar with NIMAS and NIMAC requirements.

NIMAS and NIMAC contribute to improvement activities across several indicators including graduation, dropout rate, assessments, LRE, and post secondary outcomes. Providing students with disabilities with access to the core curriculum with supports greatly increases their opportunities for success in school.

The Clearinghouse for Specialized Media and Translations (CSMT)

The Clearinghouse for Specialized Media & Translations (CSMT) provides instructional resources in accessible formats to students with disabilities in California. It is a part of the Curriculum Frameworks and Instructional Resources Division of the California Department of Education (CDE). The CSMT produces accessible versions of textbooks, workbooks, and literature books adopted by the SBE. Products and services are provided pursuant to California law, No Child Left Behind (NCLB), the Individuals with Disabilities Education Act (IDEA), the Americans with Disabilities Act (ADA), and Sections 504 and 508 of the Rehabilitation Act of 1973.

Production and dissemination of materials, including braille, large print, recordings, and American Sign Language Video-books, are funded by California's Instructional Materials Fund (IMF). CSMT also assists in providing devices such as monoculars to view the curricula. Funds to purchase specialized books, materials, and equipment are provided by the IMF for qualified students with hearing or vision impairments, severe orthopedic impairments, or other print disabilities. The Clearinghouse products and services to students with disabilities contribute to state improvement efforts and support several SPP indicators including assessments, LRE, graduation rates, access to the core curriculum, and post secondary outcomes.

Highly Qualified Teacher (HQT) and Personnel Development

The IDEA does not require states to address highly qualified teachers or administrator requirements in their SPP. However, many of the underlying improvement strategies in the California SPP focus on personnel preparation and training.

SED staff has collaborated with staff in other CDE divisions (Title I and IV Offices, the P-16 Council Cultural/Climate Subcommittee) to develop and disseminate technical assistance and training to increase the number of highly qualified special education teachers and improve instruction and learning for students with disabilities.

Collaboration actives include:

- Developing and disseminating guidance regarding the NCLB and IDEA requirements for highly qualified teachers, and providing information to districts on teacher qualification requirements and employment practices

- Providing research based training programs to LEAs focused on current research, youth resiliency, school connectedness, and positive behavior supports

- Developing and disseminating the expanded California School Climate Survey (CSCS) and the Culturally Responsive Instructional Practices in California on-line training

California’s teacher workforce is the largest in the country with more that 320,000 teachers serving a student population of over six million. The CDE serves more than 9,920 schools under the local control of more than 1,073 school districts. Ensuring that there is an adequate supply of highly qualified and effective teachers and administrators, in general education and special education, who are prepared to meet the challenges of teaching California’s growing and diverse student population continues to be a priority. The state is also working to ensure the equitable distribution of the most well prepared teachers and administrators throughout the state, particularly in low-performing schools that serve a disproportionate number of poor and minority students, English learners, and special education students. Recruiting, preparing and retaining Highly Qualified Teachers (HQT) and administrators is the most important investment of resources that local, state, business, and community leaders can make in education.

California developed a statewide action plan: The Strategic Plan for Recruiting, Preparing, and Retaining Special Education Personnel in 1997 in response to special education teacher shortages. Many activities outlined in the plan were successful in increasing the number of teachers entering special education programs at the time, but had limited impact on teacher retention. The plan focused on professional development and technical assistance related to teacher recruitment and retention in areas such as: a) school climate, b) administrative support and c) working conditions.

The California Commission on Teacher (CTC) Credentialing convened a task force (June 2006), to recommend revisions to special education credentials, eliminate credentialing redundancy, identify alternatives to increase access to teacher preparation programs, expand the existing entry points for teacher candidates, and streamline the credential process. The improvements to the special education credentialing program are intended to increase the number of special education teachers in the state that meet the NCLB teacher requirements. The final regulations implementing the task force recommendations were approved by CTC in December 2008. Universities may begin offering the new special education credential program as soon as their plan is approved by CTC, and not later than January 2011.

The State Plan of Action for No Child Left Behind (NCLB): HQT was approved by the SBE in November 2006 and by the United States Department of Education in December 2006. The plan includes the new California Subject Matter Verification Process for Middle and High Teachers in Special Settings (VPSS), an advanced certification option, and a commitment by the CDE to develop a new subject matter verification process for secondary alternative education and secondary special education teachers as a means to provide an opportunity for them to meet NCLB HQT requirements. In addition, the Web-based CSCS was revised in November 2009 to include questions in four areas that address reasons why special education personnel prematurely leave the profession. Many stakeholders, including state and national technical assistance centers, are assisting in the effort to implement a new statewide action plan. WestEd California Comprehensive Center is collaboration with CDE in the development of tools that use the California School Climate Survey data to create an integrated process to assist school site councils with the development of their improvement plan and strategies.

The chart below provides a “crosswalk” of some of the major CDE initiatives and projects described in this report that contribute to APR improvement activities and address multiple indicators in the APR. An “X” under each indicator number signifies that the activity to the left are the activities designed to improve the designated indicator.

| INDICATORS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improvement Planning | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Communication | X | X | X |  | X |  |  |  | X | X |  |  | X | X | X |  |  |  |  |  |
| Assessment | X | X | X |  | X | X | X |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Achievement Gap | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| RtI² | X | X | X | X | X |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| NIMAS/NIMAC | X | X | X |  | X |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Clearinghouse | X | X | X |  | X |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |
| HQT/Prof. Development | X | X | X | X | X |  |  | X | X | X | X |  | X | X | X |  |  |  |  | X |

Monitoring Priority: FAPE in the LRE

Indicator 1:  Percent of youth with IEPs graduating from high school with a regular diploma.

(20 U.S.C. 1416 (a)(3)(A))

Measurement: Measurement for youth with IEPs should be the same measurement as for all youth. Explain calculation. The methods for calculating the graduation rate for students receiving special education are the same methods used by general education in California. The SED collects information about individual students receiving special education from the Data Management Division. Graduation Rate Formula is based on the NCES definition. See graduation rate formula below. CAHSEE Exemption: The requirements to graduate with a regular diploma in California are the same for all students. In addition to meeting the district's requirements for graduation, all students are required to pass the CAHSEE in order to earn a public high school diploma. Beginning July 1, 2009, California state law provides an exemption from the requirement to pass the CAHSEE as a condition of receiving a diploma of graduation for eligible students with disabilities who have otherwise met the district requirements for graduation and the awarding of a regular diploma to such students. CAHSEE Waivers: In addition, at the request of the student’s parent or guardian, a school principal must submit to the local school governing board a request for a waiver of the requirement to pass the part(s) of the CAHSEE on which a modification was used and the equivalent of a passing score was earned. Algebra Waivers: Students with disabilities may obtain a waiver of the requirement to pass a course in Algebra from the SBE if their transcript demonstrates that the student has been on track to receive a regular diploma, has taken Algebra and the appropriate pre-courses or math courses, and because of the nature of their disability cannot pass the course.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2007 (2007-08) | Minimum graduation rate of 83.0% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school wide or LEA-wide) |

Actual Target Data for 2007 (2007-08):

For FFY 2008 (2008-09), Indicator 1:  Graduation Rates, is to be reported using data from 2007-08.There is a new calculation based on data from California’s ESEA reporting. The calculation is made as follows:

Graduation Rate = Number of graduates divided by number of graduates + grade 9 dropouts from year 1 + grade 10 dropouts from year 2 + grade 11 dropouts from year 3 + grade 12 dropouts from year 4.

In 2007-08, 60.2% (16,366 / 27,177) of students with disabilities graduated with a high school diploma.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

This is the first time ESEA data and benchmarks have been used in the State Performance Plan and Annual Performance Report. There is no progress or slippage to report.

Improvement Activities for 2008 (2008-09): The following improvement activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 1: Graduations Rates |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Continue to provide technical assistance regarding: - graduation standards - students with disabilities participation in graduation activities - promotion/retention guidelines - preparation for the CAHSEE . | 2005-2011 | Curriculum and Instruction, Special Education, and Statewide Assessments Divisions, STAR and CAHSEE Offices |
| Development of English Learners with Disabilities Handbook to provide guidance about ways to support the twelfth graders who are English learners and how to assist them in meeting their goals for graduation. | Began Spring 2009 – Ongoing | Special Education and English Learners Divisions with assistance from the California Comprehensive Center |
| Development of a Web-based training module for understanding and writing standards-based IEPs, impacting graduation rate, achievement, and passing the CAHSEE. | Began Spring 2009 – Ongoing | Special Education Division with assistance from the California Comprehensive Center NASSED: http://www.nasdse.org/ IDEA at Work: https://www.osepideasthatwork.org/ |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are the benchmarks used by the California Department of Education for ESEA:

| FFY | Measurable and Rigorous Benchmarks and Targets |
| --- | --- |
| 2005 (2005-06) | Minimum graduation rate of 82.9% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school-wide or LEA-wide) |
| 2006 (2006-07) | Minimum graduation rate of 82.9% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school-wide or LEA-wide) |
| 2007 (2007-08) | Minimum graduation rate of 83.0% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school-wide or LEA-wide) |
| 2008 (2008-09) | Minimum graduation rate of 83.1% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school-wide or LEA-wide) |
| 2009 (2009-10) | Minimum graduation rate of 83.2% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school-wide or LEA-wide) |
| 2010 (2010-11) | Minimum graduation rate of 83.4% OR improvement of at least 0.1 from the previous year’s rate OR improvement in the rate of 0.2 in the average two year rate (school wide or LEA-wide) |

The following activities are being added to facilitate improvement in graduation rates of student with disabilities:

| ADDED ACTIVITIES – Indicator 1: Graduations Rates |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Facilitate and provide training and technical assistance in a wide range of research-based practices to provide technical assistance and training to LEAs and the ISES stakeholder group in areas such as Core messages on: - Positive Behavior Supports - Reading - Standards-based IEPs - Family-School Partnerships Additional areas of focus: - Quality and number of teachers and other personnel who work with students with disabilities - Coordination of services for students with disabilities, including the behavioral supports that are available. - Academic outcomes with emphasis on literacy/English-language arts - Participation of parents and family members - Collection and dissemination of data These trainings provide support to district leadership and teachers in preparing students with disabilities for graduation. | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) A focus of the State Personnel Development Grant (SPDG), a federally funded grant, is to communicate common messages to the field about selected topics. These common, or core messages, articulate critical research findings and essential components of effective application. All core messages have been identified by experts in the field and have been approved by the California Department of Education, Special Education Division. |
| CDE contracts with the California Juvenile Court Schools to facilitate electronic transmissions of records across public agencies, implement Response to Instruction and intervention (RTI²), and improve student academic achievement). | 2009-2011 | CDE staff and contractors (San Diego, San Bernardino and Sacramento County Offices of Education) provide resources and training to county offices of education personnel regarding the provision of services to students with disabilities enrolled court schools. |
| Implementation of the CALPADS and CALTIDES data collection systems designed to integrate statewide data collection and meet ESEA and IDEA requirements. | 2009-2011 | Special Education and the Accountability and Data Management Divisions http://www.cde.ca.gov/ta/ http://www.cde.ca.gov/ds/ |
| Collaborate with other CDE divisions regarding shared data collection for graduation rates and benchmarks. | Ongoing | Special Education, Accountability, and Data Management Divisions http://www.cde.ca.gov/ta/ http://www.cde.ca.gov/ds/ |
| Disseminate and provide training based the Transition to Adult Living: A guide for Secondary Education, a comprehensive handbook written for students’ parents, and teachers, offering practical guidance and resources to support the transition efforts for students with disabilities as they move into the world of adulthood and/or independent living. Emphasis is placed on effective transition practices and improved guidance to students in transition to result increase graduation rates. Additional activities include the reprint and distribution of 5,000 copies of the handbook free of charge to LEAs and parent organizations. The Handbook, PowerPoint training modules, and other training materials are available online. | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) Transition to Adult Living: A Guide for Secondary Education |

Monitoring Priority: FAPE in the LRE

Indicator 2:  Percent of youth with IEPs dropping out of high school.

(20 U.S.C. 1416 [a][3][A])

Measurement: States must report using the dropout data used in the ESEA graduation rate calculation and follow the timeline established by the Department under the ESEA. The ESEA dropout rates are calculated from student level data using grades 9 through 12 and ungraded. The CDE calculates two different rates, a one-year rate and a four-year derived rate. The Calculations are made as follows: 1-year Rate Formula: (Adjusted Grade 9-12 Dropouts/Grade 9-12 Enrollment)*100 4-year Derived Rate Formula: {1-([1-(Reported or Adjusted Grade 9 Dropouts/Grade 9 Enrollment])*(1-[Reported or Adjusted Grade 10 Dropouts/Grade 10 Enrollment])*(1-[Reported or Adjusted Grade 11 Dropouts/Grade 11 Enrollment])*(1-[Reported or Adjusted Grade 12 Dropouts/Grade 12 Enrollment])}*100 The 4-year derived dropout rate is an estimate of the percent of students who would drop out in a four year period based on data collected for a single year.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2007 (2007-08) | The California Department of Education has a proposed a benchmark of 23.6%for 2008-09. This benchmark is proposed for students with disabilities, until such time as the California Department of Education establishes benchmarks under the ESEA. |

Actual Target Data for 2007 (2007-08):

For 2007-08, the 4-year Derived Rate Formula rate was 23.6%. The calculation is summarized in the following table.

Table 2a - 4-year Derived Rate Formula for Students with Disabilities Calculation

Indicator 2: Drop Outs

| Grade | Enrollment | Drop Outs | Drop Out % | 1-Drop Out % |
| --- | --- | --- | --- | --- |
| 9 | 46,425 | 1,187 | 0.0256 | 0.9744 |
| 10 | 43,294 | 1,498 | 0.0346 | 0.9654 |
| 11 | 40,867 | 1,962 | 0.0480 | 0.9520 |
| 12 | 44,645 | 6,557 | 0.1469 | 0.8531 |
|  |  | 4 year product |  | 0.7640 |
|  |  | 4 -Year Derived Drop Out Rate |  | 23.60 |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

# Explanation of Progress or Slippage

California does not currently have benchmarks for dropout rates. Annual benchmarks are not required by the ESEA. Calculations used to determine benchmarks and targets for the purposes of this report are proposed for students with disabilities, until such time as the California Department of Education establishes benchmarks under the ESEA for all students. This is the first time CDE has used the proposed benchmarks for students with disabilities. Therefore, there is no progress or slippage to report.

Improvement Activities for 2008 (2008-09): The following improvement activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 2: Dropout Rates |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Provide Building Effective Schools Together (BEST) providing training and technical assistance on positive behavioral supports focused on decreasing dropout rates. The research based principles of Positive Behavior Supports (PBS) center on school site-based teams and are a required element to implement the BEST program | 2005-June 30, 2011 Fall and Spring | CDE staff and California Services for Technical Assistance and Training (CalSTAT) The CalSTAT contract funded one district, Los Angeles USD PBS research based principles: |
| Promote awareness of the GE dropout prevention initiative on behalf of students with disabilities. | 2005-June 30, 2011 | CDE and LEA staff . http://www.cde.ca.gov/ls/ai/dp/ |
| Participate in Superintendent’s initiative to close the achievement gap for students with disabilities. | Through 2010 | CDE and LEA staff. ¦ |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

California does not currently have benchmarks for drop out rates. The following benchmarks and targets are proposed for students with disabilities, until such time as the California Department of Education establishes benchmarks under the ESEA.

| FFY | Measurable and Rigorous Benchmarks and Targets |
| --- | --- |
| 2008 (2008-09) | Less than 23.1% of students with disabilities will drop out. |
| 2009 (2009-10) | Less than 22.6% of students with disabilities will drop out. |
| 2010 (2010-11) | Less than 22.1% of students with disabilities will drop out. |

The following activities are being added to facilitate improvement in dropout rates for students with disabilities:

| ADDED ACTIVITIES– Indicator 2: Dropout Rates |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Facilitate and provide training and technical assistance in a wide range of research-based practices to assist and train LEAs and the ISES stakeholder group in areas such as Core messages on: - Positive Behavior Supports - Reading - Standards-based IEPs - Family-School Partnerships Additional areas of focus: - Quality and number of teachers and other personnel who work with students with disabilities - Coordination of services for students with disabilities and behavioral supports available for students with disabilities - Academic outcomes, with emphasis on increasing proficiency in literacy/English-language arts - Participation of parents and family members - Collection and dissemination of data These trainings focus on support to district leadership and teachers to improve their understanding the issues related to student dropout. | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) Dropout information and resources: http://www.cde.ca.gov/ls/ai/dp/ A focus of the State Personnel Development Grant (SPDG), a federally funded grant, is to communicate common messages to the field about selected topics. These common, or core messages, articulate critical research findings and essential components of effective application. All core messages have been identified by experts in the field and have been approved by the California Department of Education, Special Education Division. |
| CDE contract with the California Juvenile Court Schools to facilitate electronic transmissions of records across public agencies, implement Response to Instruction and intervention (RTI²), and improve academic achievement. | 2009-2011 | CDE staff and contractors ( San Diego, San Bernardino, and Sacramento County Offices of Education) provide resources and training to county offices of education personnel related to their provision services to students with disabilities enrolled court schools |
| Disseminate and provide training based on the Transition to Adult Living: A Guide for Secondary Education, a comprehensive handbook written for students’ parents and teachers, offering practical guidance and resources to support the transition of students with disabilities as they move into the world of adulthood and/or independent living. Emphasis is placed on effective transition practices that lead to better guidance to students to decrease the dropout rate among students with disabilities. CDE reprinted and distributed 5,000 copies free of charge to LEAs and parent organizations. The handbook, PowerPoint training modules, and other training materials are available online. | 2009-2011 | CDE staff and California Services for Technical Assistance and Training (CalSTAT) Transition to Adult Living: A Guide for Secondary Education |
| CALPADS and CALTIDES is a state-level integrated data collection system designed to collect information required by ESEA and IDEA and the state. | 2009-2011 | CDE staff: Special Education and Data Management Divisions http://www.cde.ca.gov/ds/ |
| CDE will increase the number of school sites implementing the Building Effective Schools Together (BEST) positive behavioral supports program training and technical assistance focused on decreasing dropout rates. | 20010-2011 | CDE staff, CalSTAT The California SPDG received additional (restored) federal funding allowing the CDE to increase funding to 70 previously identified school sites in 7 districts to support the implementing of the BEST program, a program based on the tenets of Positive Behavioral Supports (PBS). |

Monitoring Priority: FAPE in the LRE

Indicator 3:  Participation and performance of children with IEPs on statewide assessments:

- Percent of the districts with a disability subgroup that meets the State’s minimum “n” size that meet the State’s AYP targets for the disability subgroup.

- Participation rate for children with IEPs.

C.	Proficiency rate for children with IEPs against grade level, modified, and alternate academic achievement standards.

(20 U.S.C. 1416 (a)(3)(A))

Measurement: A. AYP percent = [(# of districts with a disability subgroup that meets the State’s minimum “n” size that meet the State’s AYP targets for the disability subgroup) divided by the (total # of districts that have a disability subgroup that meets the State’s minimum “n” size)] times 100. B. Participation rate percent = [(# of children with IEPs participating in the assessment) divided by the (total # of children with IEPs enrolled during the testing window, calculated separately for reading and math)]. The participation rate is based on all children with IEPs, including both children with IEPs enrolled for a full academic year and those not enrolled for a full academic year. C. Proficiency rate percent = ([(# of children with IEPs enrolled for a full academic year scoring at or above proficient) divided by the (total # of children with IEPs enrolled for a full academic year, calculated separately for reading and math)].

| ### FFY | ### Measurable and Rigorous Target |  |  |
| --- | --- | --- | --- |
| 2008 (2008-09) | 3A. Annual benchmarks and six-year target for the percent of districts meeting the State’s AYP objectives for progress for the disability subgroup Percent of Districts – 58% |  |  |
|  | 3B. The annual benchmark and target for participation on statewide assessments in ELA and Math, 95 percent (rounded to nearest whole number), is established under ESEA. |  |  |
|  | 3C. Consistent with ESEA accountability framework, the 2005-11 AMOs (benchmarks) for the percent proficient on statewide assessments are broken down by school subgroup and are provided in the cells below. |  |  |
|  | School Subgroup | ELA Percent | Math Percent |
|  | Elementary Schools, Middle Schools, Elementary School Districts | 46.0 | 47.5 |
|  | High Schools, High School Districts | 44.5 | 43.5 |
|  | Unified School Districts, High School Districts, County Office of Education | 45.0 | 45.5 |
| Note: Targets and Benchmarks apply to charter schools and charters acting as LEAs for the purposes of special education. For more information see http://www.cde.ca.gov/sp/cs/re/qandasec4mar04.asp#q12 |  |  |  |

Actual Target Data for 2008 (2008-09):

Table 3a

Number and Percent of Districts meeting AYP Objectives: Indicator 3 – Statewide Assessment

|  |  | 2007-08 |  |  |  | 2008-09 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Measured |  |  |  | Met |  |
|  |  | N |  | Percent |  | N | Percent |
| Participation | ELA |  | 491 |  | 88.36 | 462 | 94.09 |
|  | Math |  | 491 |  | 93.10 | 472 | 96.13 |
|  | Both |  | 487 |  | 85.01 | 453 | 93.02 |
| Proficiency | ELA |  | 264 |  | 66.67 | 251 | 95.08 |
|  | Math |  | 279 |  | 58.66 | 223 | 79.93 |
|  | Both |  | 274 |  | 30.35 | 201 | 73.36 |
| Overall | All AYP |  | 491 |  | 24.85 | 190 | 38.70 |
| Includes students in grades 2 through 8 and 10. |  |  |  |  |  |  |  |
| Students in grades 2 through 8 take the STAR tests. |  |  |  |  |  |  |  |
| Students in grade 10 take the California High School Exit Exam. |  |  |  |  |  |  |  |
| Data source for 2007-08 is AYP database: apr08adb.dbf updated 11/17/2008 |  |  |  |  |  |  |  |
| Data source for 2008-09 is AYP database: apr09adb.dbf updated 9/15/2009 |  |  |  |  |  |  |  |
| California generally uses an N size of 100 for calculating AYP results. |  |  |  |  |  |  |  |

There was an increase in the percent of districts meeting overall AYP objectives in 2008-09 (38.70 percent) from 2007-08 (24.85 percent). This appears to be due to the increase in the percent of districts proficient in ELA and Math in 2008-09 (ELA 95.08, Math 79.93 percent) from 2007-08 (ELA 66.67, Math 58.66 percent). Despite the increased percentages, the state did not meet its overall AYP target.

3B Participation Table 3b depicts the number and percent of students participating in statewide assessment programs under various test conditions.

Actual Target Data for 2008 (2008-09):

Table 3b

Participation of Students Receiving Special Education Services in California, 2007-08 through 2008-09:

Indicator 3 – Statewide Assessment

| Assessment Description | English Language Arts |  |  |  | Mathematics |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2007-08 |  | 2008-09 |  | 2007-08 |  | 2008-09 |  |
|  | Number | Percent | Number | Percent | Number | Percent | Number | Percent |
| - children with IEPs in assessed grades | 372,472 | 100.00 | 353,791 | 100.0 | 372,337 | 100.0 | 353,767 | 100.0 |
| - Regular assessment with no accommodations | 267,040 | 71.7 | 164,330 | 7.1 | 266,482 | 71.6 | 175,233 | 49.5 |
| - Regular assessments with accommodations | 27,154 | 7.3 | 25,219 | 46.4 | 35,438 | 9.5 | 28,848 | 8.2 |
| - Alternate assessment based on grade-level standards | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 |
| - (1) Alternate assessment based on alternate achievement standards | 28,260 | 7.7 | 31,350 | 8.9 | 31,219 | 8.4 | 31,266 | 8.8 |
| - (2) Alternate assessment based on modified achievement standards | 38,217 | 10.3 | 94,668 | 26.8 | 32,320 | 8.7 | 74,046 | 20.9 |
| Other - Absent, Exempt, or Invalid | 17,195* |  | 14,359 | 4.1 | 8,345* | * | 16,894 | 4.8 |
| Overall Percent (b+c+d+e)/a |  | 96.9 |  | 93.3 |  | 98.2 |  | 92.2 |
| Sources: 618 Report, Table 6, 2007-08 and 2008-09 |  |  |  |  |  |  |  |  |
| * Unresolved anomalies in data set, see attached Table 6, pages 9 and 18 explanations. |  |  |  |  |  |  |  |  |

Overall participation in ELA dropped to 93.3 percent in 2008-09 from 96.9 percent in 2007-08. This decrease was also found in Mathematics, where participation dropped from 98.2 percent to 92.2%.The increased participation in modified assessment and decreased participation in the regular assessment with accommodations found between 2006-07 and 2007-08 continued in 2008-09. Overall participation in ELA decreased from 96.9 percent in 2007-08 to 93.3 percent in 2008-09.The implementation of the CMA (2007-08) was accompanied by a substantial decline in the number and percent of students in the Other category. There was a decrease in the number and percent of students taking the regular assessment both with and without accommodations. Participation in Mathematics decreased also from 98.2 percent in 2007-08 to 92.2 percent in 2008-09. Decreases were noted in the number and percent of students taking regular assessments both with and without accommodations.

The reason for the decrease in the number and percent of students taking regular state assessments, without accommodations is not known. The number of students not included in participation statistics has remained relatively stable across 2007-08 and 2008-09 (an increase of 5,623 nonparticipating students). CDE is proposing to study changing participation rates as an improvement activity in 2009-10.

Table 3c

Proficiency Rate of Students Receiving Special Education Services in California, 2007-08 Through 2008-09:

Indicator 3 – Statewide Assessment

| Assessment Description | English Language Arts |  |  |  |  |  | Mathematics |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2007-08 |  |  | 2008-09 |  |  | 2007-08 |  |  | 2008-09 |  |
|  | Number | Percent | Number |  | Percent | Number |  | Percent | Number |  | Percent |
| - children with IEPs in assessed grades | 372,472 | 100.0 | 353,791 |  | 100.0 | 372,337 |  | 100.0 | 353,767 |  | 100.0 |
| - Regular assessment with and without accommodations & c. Regular assessment with and without accommodations | 55,2875 | 14.8 | 44,450 |  | 12.6 | 67,5676 |  | 18.2 | 54,244 |  | 15.3 |
| - Alternate assessment against grade-level standards regular assessment no accommodations | 053,005 | 0.014.2 | 0 |  | 0.0 | 064,641 |  | 0.017.4 | 0 |  | 0.0 |
| - (1) Alternate assessment against alternate achievement standards | 21,064 | 5.70.6 | 24,539 |  | 6.9 | 17,577 |  | 4.70.8 | 19,466 |  | 5.5 |
| - (2) Alternate assessment against modified achievement standards | 10,6160 | 2.90.0 | 27,654 |  | 7.8 | 10,2190 |  | 2.70.0 | 23,591 |  | 6.7 |
| Overall |  | 23.3 |  |  | 27.3 |  |  | 25.6 |  |  | 27.5 |
| Sources: 618 Report, Table 6, 2007-08 and 2008-09 |  |  |  |  |  |  |  |  |  |  |  |

Proficiency rates for students with disabilities on the ELA test have increased to 27.3 percent in 2008-09 from 23.3 percent in 2007-08. A smaller increase was observed on the Mathematics test, rising to 27.5 percent in 2008-09 from 25.6 percent in 2007-09. In 2007-08, the CMA was given for the first time. Students with disabilities continue to demonstrate slightly higher proficiency rates on Mathematics than on ELA. Table 3c represents students who scored proficient and advanced on the CST, the CAPA, the CMA, and the CAHSEE (grade 10). Table 3c does not include students who scored below the proficient level; it does not include students who did not test due to parental exemption or absence; and it does not include students who had invalid scores. The increases in proficiency are consistent with continuing efforts to close the achievement gap for students with disabilities. However, the large increase in the Annual Measureable Objectives (AMOs) targets for California make meeting the targets increasingly challenging. Efforts on behalf of students with disabilities must be increased and focused on instruction in the standards-based general curriculum, teacher professional development, differentiation of instruction to meet the needs of all learners, consistent use of student progress monitoring to improve instruction, and increased support for students served in the least restrictive environment.

Table 3.c.1

Percent of Students Scoring Proficient by District Type 2007-08 and 2008-09:

Indicator 3 - Statewide Assessment

| District Type | 2007-08 |  |  |  | 2008-09 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | English Language Arts |  | Math |  | English Language Arts |  | Math |  |
|  | Target Percent | Actual Percent | Target Percent | Actual Percent | Target Percent | Actual Percent | Target Percent | Actual Percent |
| Unified, COE, HS 7-12 | 34.00 | 24.19 | 34.60 | 27.66 | 45.0 | 29.8 | 45.5 | 31.6 |
| Elementary * | 35.20 | 26.28 | 37.00 | 30.28 | 46.0 | 33.1 | 47.5 | 35.3 |
| HS 9-12 ** | 33.40 | 18.55 | 32.20 | 17.43 | 44.5 | 20.1 | 43.5 | 19.3 |
| * Includes direct funded charter elementary and middle schools* Includes direct funded charter elementary and middle schools |  |  |  |  |  |  |  |  |
| ** Includes direct funded charter high schools** Includes direct funded charter high schools |  |  |  |  |  |  |  |  |
| Data source for 2008-09is AYP database: apr09adb.dbf Revised 4-Dec-2009Data source for 2008-09is AYP database: apr08adb.dbf updated 11/17/2009 |  |  |  |  |  |  |  |  |

Overall, the percent of students scoring proficient or advanced increased between 2007-08 and 2008-09 in both ELA and Mathematics across all district types. The relatively modest increases were, however, not sufficient for any district type to meet the large increases in the annual benchmarks in 2008-09 over 2007-08. Table 3.C.2 displays the raw data used to calculate the percent of students scoring proficient by district type in 2007-08 and 2009-09. Although students are making gains in ELA and mathematics, they are not achieving at a level commensurate with the increased target expectations. Continued statewide efforts to improve instruction for students with disabilities in all educational settings are needed to reach the targets.

Table 3.c.2

Data Used to Calculate Percent of Students Scoring Proficient in 2008-09:

Indicator 3 - Statewide Assessment

| Special Education |  | ELA |  |  | Math |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TYPE | Number of LEAs | Number of Valid Tests | Number Scoring Proficient or Advanced | Percent Scoring Proficient or Advanced | Number of Valid Tests | Number Scoring Proficient or Advanced | Number Scoring Proficient or Advanced |
| Unified, COE, HS 7-12 | 401 | 286,746 | 85,398 | 29.8 | 288,619 | 91.261 | 31.6 |
| Elementary * | 549 | 93,047 | 30,754 | 33.1 | 93,401 | 32,931 | 35.3 |
| HS 9-12 ** | 74 | 8,632 | 1,787 | 20.1 | 8,760 | 1,695 | 19.3 |
| * Includes direct funded charter elementary and middle schools* Includes direct funded charter elementary and middle schools |  |  |  |  |  |  |  |
| ** Includes direct funded charter high schools** Includes direct funded charter high schools |  |  |  |  |  |  |  |
| Data source for 2008-09 is AYP database: apr09adb.dbf Revised 4-Dec-2009Data source for 2008-09 is AYP database: apr08adb.dbf updated 11/17/2009 |  |  |  |  |  |  |  |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

Explanations of progress and slippage follow each of the tables, above.

Improvement Activities for 2008 (2008-09): The following improvement activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 3: Statewide Assessment |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Cross Branch Coordination with the Program Improvement Division to utilize data on statewide assessments for analysis and development of improvement plans. | 2006 - 2010 | Special Education, High Priority/Interventions, Learning and Support Divisions http://www.cde.ca.gov/ta/tg/sr/ |
| Develop CMA (grades 3-11) in coordination with Standards and Assessment Division. Collaborate with the Standards and Assessment Division on statewide assessments for students with disabilities. | May 2005-2011 | Special Education, Standards and Assessments Divisions, and the STAR Office http://www.cde.ca.gov/ta/tg/sr/ |
| Provide technical assistance to schools focused on the implementation of programs to reform to high poverty and ESEA school wide schools. Provide focused monitoring technical assistance at facilitated school sites. | Ongoing | CDE staff and the California Comprehensive Assistance Center |
| Develop and maintain IDEA 2004 information Web page with links to important references and resources on the Reauthorization of IDEA, including statewide assessments. | Ongoing | CDE/SED staff; Web capability of CDE |
| Collaborate with the CDE Program Improvement and Interventions Office to infuse special education indicators into the Academic Performance Survey (APS) and District Assistance Survey (DAS). | Ongoing | Special Education, High Priority/Interventions, and Learning and Support Divisions http://www.cde.ca.gov/ta/tg/sr/ |
| Continue to update and provide state guidance on student participation in statewide assessments in alignment with the April 2007 Federal regulations. Provide Guidelines for the IEP Team Decision-Making Tool Kit. Train the Trainers workshops to build local capacity to ensure special education student participation in statewide assessments. | 2007-2011 | Special Education, Standards and Assessments Divisions, and the STAR Office http://www.cde.ca.gov/ta/tg/sr/ |
| Collaborate with the field on the development of guidelines for students with significant cognitive disabilities regarding participation on alternate assessments. | Ongoing | Special Education Division |
| Conduct Webinars on statewide on Assessments: Guidelines for IEP Team Decision-Making to reach a wider audience. | 2009-2011 | Special Education, Standards and Assessments Divisions, and the STAR Office http://www.cde.ca.gov/ta/tg/sr/ Training archive |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 3: Statewide Assessment |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Facilitate and provide training and technical assistance in a wide range of research-based practices to assist and train LEAs and the ISES stakeholder group in areas such as Core messages on: - Positive Behavior Supports - Reading - Standards-based IEPs - Family-School Partnerships Additional areas of focus: - Quality and number of teachers and other personnel who work with students with disabilities - Coordination of services for students with disabilities and the behavioral supports available for students with disabilities Academic outcomes with emphasis on literacy/English-language arts - Participation of parents and family members - Collection and dissemination of data These trainings provide on support to district leadership and teachers in improving the performance of students with disabilities on state assessments. Special Education and Statewide Assessments Divisions exchange data on participation and proficiency rates for students with disabilities. | Ongoing | CDE and California Services for Technical Assistance and Training (CalSTAT) Statewide Assessment information and resources: http://www.cde.ca.gov/ta/tg/sr/ |
| SED collaboration with the Statewide Assessments Division on the exchange of data between the divisions, including data on student participation rates and the dissemination of data to the field. | 2009-2011 | Special Education and Standards and Assessments Divisions, and the STAR Office http://www.cde.ca.gov/ta/tg/sr/ |
| In collaboration with the California Comprehensive Center, develop and disseminate training modules on Standards-based IEPs promote and sustain activities that foster special education/general education collaboration. (Chapter topics: Access, Standards-based IEPs, Grade-level and Standards-based Goals, Service Delivery Models, and Curriculum and Instruction Strategies) This training is for general education as well as special education teachers and administrators. The Service Delivery Models and Curriculum and Instruction modules address how teams of teachers work together to support students with disabilities in LRE and how to differentiate instruction to meet the needs of all learners. | Began Spring 2009 – Ongoing | Special Education Division with assistance from the California Comprehensive Center National Association of State Special Education Directors (NASDSE): http://www.nasdse.org/ IDEA at Work: https://www.osepideasthatwork.org/ |
| The formation of the Instructional Support Workgroup to address the instructional needs of students with significant cognitive disabilities and their participation in statewide assessments. |  | Special Education, Statewide Assessments and Accountability Divisions in collaboration with the California Comprehensive Center and CalSTAT |
| Conduct a study to analyze statewide assessment data, (participation and proficiency rates) for students with disabilities to assess how students have participated and performed over time; including identifying which conditions (e.g. accommodations and modification, differentiated instruction, and access to general education standards and content) affect performance. The study will also identify districts that have increased participation and proficiency rates to identify effective practices that may contribute to increased student participation rates and improved academic achievement. |  | Special Education and Standards and Assessments Divisions , and the STAR Office http://www.cde.ca.gov/ta/tg/sr/ |

Monitoring Priority: FAPE in the LRE

Indicator 4:  Rates of suspension and expulsion:

A. Percent of districts that have a significant discrepancy in the rate of suspensions and expulsions of greater than 10 days in a school year for children with IEPs; and

B. Percent of districts that have:  (a) a significant discrepancy, by race or ethnicity, in the rate of suspensions and expulsions of greater than 10 days in a school year for children with IEPs; and (b) policies, procedures or practices that contribute to the significant discrepancy and do not comply with requirements relating to the development and implementation of IEPs, the use of positive behavioral interventions and supports, and procedural safeguards.

(20 U.S.C. 1416(a)(3)(A); 1412(a)(22))

Measurement: - Percent = [# of districts that have a significant discrepancy in the rates of suspensions and expulsions for greater than 10 days in a school year of children with IEPs) divided by the # of districts in the State)] times 100. - Percent = [# of districts that have: (a) a significant discrepancy, by race or ethnicity, in the rates of suspensions and expulsions of greater than 10 days in a school year of children with IEPs; and (b) policies, procedures or practices that contribute to the significant discrepancy and do not comply with requirements relating to the development and implementation of IEPs, the use of positive behavioral interventions and supports, and procedural safeguards) divided by the (# of districts in the State)] times 100. Per OSEP’s Instructions: Discrepancy can be computed by either comparing the rates of suspensions and expulsions for children with IEPs to rates for non-disabled children within the LEA or by comparing the rates of suspensions and expulsions for children with IEPs among LEAs within the State. California compares the rates for individual districts to the statewide average, approximately 1%. This average is to be recomputed each year (see actual target data section below).

| # FFY | Measurable and Rigorous Target |
| --- | --- |
| 2007 (2007-2008) | No more than 10.3 percent of districts will have rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year that exceed one percent (indicator 4A). 0.0 percent of districts will have a significant discrepancy in the rates of suspensions and expulsions for greater than 10 days in a school year of children with disabilities by race (indicator 4B). |

Actual Target Data for 2007 (2007-08):

In its FFY 2007 SPP/APR Response Table OSEP indicated that:

For this indicator, the State calculated the percent of districts with rates of suspensions and expulsions of children with disabilities for greater than ten days in a school year that exceed one percent. The State’s SPP, as approved by OSEP, set out the threshold as the State’s average percentage…In its FFY 2008 APR, due February 1, 2010, the State must report consistent with the approved SPP and, based on FFY 2008 data, recalculate its threshold and determine the percent of districts identified as having a significant discrepancy in the rates of suspension and expulsion of children with disabilities for greater than ten days in a school year using the revised threshold. The State must also do this for subsequent years.

In 2007-08, there were 5,776 students with disabilities reported in CASEMIS Table C (Discipline) that were suspended or expelled for greater than 10 days in a school year. Using the June 30, 2008 CASEMIS total of 862,838 total students with IEPs, birth to 22 years of age, the statewide percentage of the number of students suspended or expelled for greater than 10 days is 0.67%. This is less than the percentage used to identify districts in 2007-08. Thus, there are no new districts identified for 2007-08 based on the recalculated statewide average.

The 2007 SPP/APR Response Table also indicated that:

As noted in the revised Part B Indicator Measurement Table, in reporting on this indicator in the FFY 2008 APR, due February 1, 2010, the State must again describe the results of the State’s examination of data from FFY 2007 (2007-2008). In addition, the State must again describe the review, and if appropriate, revision of policies, procedures and practices relating to the development and implementation of IEPs, the use of positive behavioral interventions and supports, and procedural safeguards to ensure compliance with the IDEA for LEAs identified with significant discrepancies in FFY 2007, as required by 34 CFR §300.170(b).

Please Note:  California is reporting data that were previously reported in the FFY 2007 (2007-08) Annual Performance Report. Per instructions included in the Part B Indicator Measurement Table, CDE is describing the results that were obtained for the “year before the reporting year.” (2007-08). Since these data were previously reported, we are re-reporting it here with updated information about correction of noncompliance reported by districts in 2007-08.

.

Indicator 4A:  Percent of districts having an overall suspension or expulsion rate greater than one percent for 2007-08.

Calculation:  95 / 895 * 100 = 10.6 percent

Indicator 4B:  The measure is not reported this year as per instructions for the FFY 2008 SPP/APR

Percents are not calculated for districts of residence reporting fewer than 20 students receiving special education services. Districts of residence reporting 20 or more students receiving special education services were considered large enough to be calculated.

Of the 895 districts with a population of students receiving special education large enough to calculate (N>19), 95 districts did not meet the target (of not more than one percent of students ages 3 through 22 suspended or expelled for more than 10 days during the 2006-2007 school year). Statewide, 5,776 students with IEPs were suspended or expelled for more than ten days, 0.67 percent of the total population of 862,838 students served during 2006-2007.

All districts having more than 1 percent of their special education population suspended or expelled for 10 days or more are required to complete a special self-review of policies, procedures and practices related to positive behavioral interventions and supports and procedural safeguards to ensure compliance. Data are submitted through a Web survey. Table 4a depicts the number of noncompliance findings identified through the special self-review of policies, procedures, and practices relating to the development of and implementation of IEPs, the use of positive behavioral interventions and supports and procedural safeguards.

Of those districts that were required to complete a special self-review of policies, procedures, and practices all 95 made changes to their policies, procedures, and practices. These comply with the requirements regarding the development and implementation of IEPs, the use of positive behavioral interventions and supports, and procedural safeguards, to ensure compliance with IDEA, pursuant to 34 CFR §300.170(b).

The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §§300.111, 300.201, and 300.301 through 300.311; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memorandum 09-02, dated October 17, 2008 (OSEP Memo 09-02).

The corrective action process requires that districts remedy noncompliant findings when individual student level or policy, procedure and practice noncompliance is found. All district policy and procedure documents, including suspension and expulsion policies, procedures and practices are reviewed every four years or more frequently if data calculations warrant a review.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Table 4a

Analysis of Noncompliance Findings Identified Through the Special Self-review of Policies, Procedures, and Practices Relating to the Development of and Implementation of IEPS, the Use of Positive Behavioral Interventions and Supports and Procedural Safeguards

| Number of Non-compliance Findings | Compliance Test |
| --- | --- |
| 65 | Does the IEP team specify the development of a functional analysis behavior assessment, when it has been determined that other behavioral/instructional approaches specified in the student’s IEP have been ineffective? |
| 63 | Does the general education teacher help decide supplementary aids and services for the student? |
| 58 | When a disciplinary action involving suspension or expulsion of more than 10 days in a school year occurs, is the student provided all IEP services on the 11th day? |
| 57 | Does the functional analysis assessment include an ecological analysis of the setting in which the behavior occurs most frequently? |
| 57 | Does the functional analysis assessment result in a written report that includes a description of the targeted behaviors including baseline data, antecedents and consequences? |
| 57 | If disciplinary action is considered to change a student’s placement for 10 days or more, are the parents notified on the same day this decision is made and given a copy of their rights or Notice of Procedural Safeguards? |
| 56 | Does the functional analysis assessment result in a written report that includes a description of the rate of the alternative behaviors, their antecedents and consequences? |
| 55 | Does the functional analysis assessment include all of the required elements, including a systematic observation of the antecedent events? |
| 54 | Does the functional analysis assessment include a systematic observation of the targeted behavior? |
| 54 | Does the functional analysis assessment include a systematic observation and analysis of the consequences? |
| 54 | Does the functional analysis assessment result in a written report that includes a description of the nature and severity of the targeted behaviors? |
| 52 | Does the functional analysis assessment include a review of records for health and medical factors? |
| 50 | Does the functional analysis assessment result in a written report that includes recommendations for consideration by the IEP team, which may include a proposed behavior plan? |
| 43 | Is there evidence that the current assessment includes information about social, emotional, and behavioral status? |
| 42 | If disciplinary action is considered to change a student's placement for 10 days or more, are functional analysis assessments and behavioral plans developed to address the behavior that resulted in the suspension if such a plan is not already in place? |
| 39 | If disciplinary action is considered to change a student's placement for 10 school days or more, is the IEP meeting held before the 10th day of suspension to consider if the behavior was a manifestation of the student's disability? |
| 35 | In making the manifestation determination, did the IEP team consider all required elements? |
| 31 | Is an interim alternative educational setting determined by the IEP team when there is a change in placement? |
| 29 | Does the IEP team include the case manager, for the behavior intervention plan whenever the team reviews the functional analysis assessment and develops the behavior intervention plan (Hughes Act), which becomes part of the IEP? |
| 27 | If disciplinary action changes a student’s placement for 10 days or more, does the student return to the pre disciplinary action placement unless a court order or parent permission has been obtained? |
| 27 | Are relevant disciplinary procedures applicable to all children carried out only when it has been determined that the placement was appropriate and that the behavior was not a manifestation of the disability? |
| 26 | Are parents informed that they have the right to pursue a due process hearing if they disagree with the decisions of the IEP team regarding expulsion? |
| 25 | Is the expulsion hearing conducted only after the pre-expulsion assessment is completed and the IEP team convenes and makes the required findings? |
| 23 | If a parent is unable to attend the IEP meeting, is a telephone conference used for the IEP meeting to consider expulsion? |
| 21 | If a parent received proper notice of the meeting, chooses not to participate in the IEP meeting or to consent to an extension beyond 20 consecutive school days, is the meeting conducted without the parent? |
| 20 | If disciplinary action is considered to change a student’s placement for 10 days or more because the student has violated a rule or code of conduct applying to all students does the LEA follow all of the required procedures? |
| 15 | Does the LEA use technically sound instruments that may assess the relative contribution of cognitive and behavioral factors, in addition to physical or developmental factors? |

Noncompliance related to Indicator 4 (Suspension and Expulsion) was identified in several ways:  1) Special Self-reviews that are the result of calculations for Indicator 4A; 2) Verification and Self-Reviews; 3) Complaints and Due Process Findings. As a result, the numbers reported in the calculations for Indicator 4 (Suspension and Expulsion) are smaller than the numbers reported in Indicator 15, General Supervision because the other monitoring processes may make findings of noncompliance in districts that are not identified as disproportionate. Correction of all noncompliance reported to LEAs related to indicators 9, Disproportionality by race and ethnicity and 10, Disproportionality by disability is discussed below:

Correction of Monitoring Findings in 2007-08 Monitoring conducted in 2007-08 included 131 districts identified using 2006-07 data (June 2007) and included the 70 districts that were not reviewed in 2006-07 as indicated in the section on monitoring findings in 2006-07, below. Of the 131 districts, 43 had findings of noncompliance related to suspension and expulsion. Forty-one of the districts corrected the noncompliance within one year of identification to the district. The other two districts corrected the noncompliance prior to submission of this APR. All findings of noncompliance were corrected have been corrected.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

California did not meet the annual suspension and expulsion benchmark of 10.3 percent of districts for 2007-08. There was an increase from 88 in 2006-07 to 95 in 2007-08 of districts that exceeded the one percent standard for students with disabilities suspended/expelled for more than 10 days. There was also an increase in the number of students with disabilities suspended/expelled for more than 10 days from 4,528 in 2006-07 to 5, 776 in 2007-08. Stakeholders speculated that this may be due to the increased number and percent of “zero tolerance” offenses (e.g., weapons, drugs). However, the data show no significant differences in “zero tolerance” offenses as the reason for suspension/expulsion between 2006-07 and 2007-08.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 4: Suspension and Expulsion |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| In collaboration with other divisions of CDE and the P-16 Council, provide technical assistance to LEAs and schools on reinventing high schools. | Ongoing | Special Education and Curriculum and Instruction Divisions http://www.cde.ca.gov/ci/ |
| Provide technical assistance to schools focused on the implementation of reform programs that have been successful in high poverty. | Ongoing | CDE staff |
| Work with SELPAs, LEAs and County Offices of Education (COE) to clarify responsibilities and improve behavior emergency and other behavioral incident reporting. | Ongoing | Special Education, Program Improvement, Learning and Supports Divisions, SELPAs and LEAs http://www.cde.ca.gov/ds/ |
| Work with SELPAs, LEAs and COE to update and improve monitoring items and instruments for reviewing policies, practices and procedures related to this indicator. | Ongoing | Special Education, Program Improvement, and Learning and Supports Divisions, SELPAs and LEAs http://www.cde.ca.gov/sp/se/qa/ |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09):

The following are being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 4. Suspension and Expulsion |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Provide Building Effective Schools Together (BEST) training and technical assistance positive behavioral supports focused on decreasing dropout rates. This program integrates the research based principles of Positive Behavior Supports (PBS) and includes school site-based teams that are a required element for all implementing BEST sites. | 2005-June 30, 2011 Fall and Spring | CDE staff and California Services for Technical Assistance and Training (CalSTAT) The CalSTAT contract funded one district, Los Angeles USD, which is the largest district in the State for the most recent year. |
| Positive Behavior Supports (PBS) research based core messages promoting customized training and technical assistance at the school site level, increasing time in academic instruction and decreasing suspension and expulsion incidents. | 2011 | CDE and LEA Staff and CalSTAT |
| Promote the IRIS modules in behavior, diversity, and other content. This is a special project training and technical assistance work. | 2009-2011 | CDE and LEA staff, IRIS Center |
| Promote the Culturally Responsive Teaching in California online training modules for the school site general and special educators dealing with utilizing positive behavior supports. | 2009-2011 | CDE staff, Contractor (Equity Alliance Center at Arizona State University), and LEA staff |
| Increase the number of school sites implementing the Building Effective Schools Together (BEST) positive behavioral supports program training and technical assistance designed to decrease dropout rates. | 20010-2011 | CDE staff, contractor The California received additional (restored) funding under its SPDG that will be used to increase funding to 70 previously identified schools in seven districts to support implementation the BEST program which is based on the tenets of PBS. |

Monitoring Priority: FAPE in the LRE

Indicator 5:  Percent of children with IEPs aged 6 through 21 served:

A.	Inside the regular class 80% or more of the day;

B.	Inside the regular class less than 40% of the day; and

C.	In separate schools, residential facilities, or homebound/hospital placements.

(20 U.S.C. 1416(a)(3)(A))

Measurement: - Percent = [(# of children with IEPs served inside the regular class 80% or more of the day) divided by the (total # of students aged 6 through 21 with IEPs)] times 100. - Percent = [(# of children with IEPs served inside the regular class less than 40% of the day) divided by the (total # of students aged 6 through 21 with IEPs)] times 100. Percent = [(# of children with IEPs served in separate schools, residential facilities, or homebound/hospital placements) divided by the (total # of students aged 6 through 21 with IEPs)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 5A. 62 percent or more of students will be removed from regular class less than 21 percent of the day; 5B. No more than 18 percent will be removed from regular class more than 60 percent of the day; and 5C. No more than 4.0 percent are served in public or private separate schools, residential placements, or homebound or hospital placements. |

Actual Target Data for 2008 (2008-09):

Table 5a depicts the number and percent of students, aged 6 through 21 with IEPs, who receive special education and related services in various settings.

Table 5a

Number and Percent of Students Served in Various Settings: Indicator 5 – LRE

| Setting | Number of Students | Percent of Students | 2008 Target Percent |
| --- | --- | --- | --- |
| 5 A. Removed from regular class less than 21 percent of the day | 310,030 | 51.6% | 62% or more |
| 5 B. Removed from regular class greater than 60 percent of the day | 134,991 | 22.5% | No more than 18% |
| 5 C. Served in public or private separate schools, residential placements, or homebound or hospital placements | 27,285 | 4.5% | No more than 4.0% |

- 51.6 percent were removed from regular class less than 21 percent of the day;

Calculation:  310,030 / 600,598 * 100 = 51.6 percent

- 22.5 percent were removed from regular class more than 60 percent of the day; and

Calculation:  134,911 / 600,598 * 100 = 22.5 percent

- 4.5 percent were served in public or private separate schools, residential placements, or homebound or hospital placements

Calculation:  27,285 / 600,598 *100 = 4.5% percent

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

California did not meet the benchmarks for 5A, 62 percent (removal less than 21 percent of the day) for 5B, 18 percent (removal greater than 60 percent), or for 5C, 4.0 percent (served in separate schools and facilities). The percent of students removed less than 21 percent decreased from 52.3 percent in 2007-08 to 51.6 percent in 2008-09. The percent of students removed greater than 60 percent decreased from 22.6 percent in 2007-08 to 22.5 percent in 2008-09. The percent of students served in separate schools and facilities remained the same at 4.5 percent in both 2007-08 and 2008-09. Over the last years the CDE has continued to emphasize policies and practices related to providing services in the Least Restrictive Environment and have revised its IEP training modules to more strongly emphasize access to the general curriculum. However, LRE issues continue among the most frequent compliance violations:

- IEPs not containing a direct relationship between assessments, goals and services;

- IEPs not containing descriptions of the modifications and supports for regular classroom personnel;

- General education teachers not being included in IEP team meetings or placement decision making;

- IEPs not containing a statement related to how the student’s disability will affect their ability to be involved in and progress in the general curriculum.

Future IEP training will emphasize IEP team placement decision making and quality IEP development. CDE monitoring and corrective actions will be strengthened to ensure that LEAs implement all required  procedures before noncompliance is considered corrected.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 5: LRE |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Continue implementation of the Facilitated Focused Monitoring Project including the “scaling up” focused monitoring activities that contain targeted technical assistance to LEAs related to LRE and improved academic outcomes for all students, including students with disabilities. | Through June 30, 2011 | CDE and LEA staff and CalSTAT |
| Using requirements of IDEA 2004, evidence-based research, State Board of Education adopted policy on LRE, and state content and performance standards, conduct Regional and Statewide Personnel Development Grant (SPDG) Leadership Institutes and provide technical assistance to schools staff to support improved practices related to placement of students with disabilities in conformity with their IEPs. | Through June 30, 2011 Fall and spring regional Annually for statewide | CDE staff and CalSTAT |
| Implement the State Personnel Development Grant (SPDG) that provides training and technical assistance in scientifically-based research and instruction in the areas of literacy and behavior and that promote and sustain practices that foster special education/general education collaboration. | January-March 2007 and implementation of the new federal grant January 2008-2012. | CDE staff, State Personnel Development Grant (SPDG), and United State Department of Education (USDOE),Office of Special Education Programs (OSEP) |
| Conduct activities related to parent involvement, LRE, RtI2, and secondary transition. CDE promotes parental involvement by inviting their membership and participation in ISES and in CDE trainings. CDE supported trainings are posted on the Internet to increase parent access to training materials. In addition through CDE partnerships with PTI, FRC, and FEC parents are provided training and technical assistance statewide. CDE also maintains a parent ‘hot line’ to provide parent information and assistance. | January-March 2007 and implementation of the new federal grant January 2008-2012. | CDE staff and State Personnel Development Grant (SPDG), United State Department of Education (USDOE), Office of Special Education Programs (OSEP) federal grant competition |
| Based on CDE data review of monitoring findings, including CASEMIS information, determine state technical assistance needs regarding noncompliant findings and provide focused technical assistance to sites and LEAs regarding LRE. | 2005-June 30, 2011 | CDE staff |
| Provide a Web-based IEP training module that emphasizes how IEP teams can address standards-based IEPs; Educational Benefit Processes for develop IEPs, IEP team decisions making related to student participation in state assessments, and information for IEP teams about LRE. | 2008-2011 Ongoing | CDE and California Comprehensive Center |
| Begin preliminary development and implementation of training and technical assistance on identified topics, including LRE to LEAs participating in a CDE pilot project that includes the participation of a Charter LEA. | 2007-2010 Pilot timeline | CDE staff, SELPA Directors, and CalSTAT |
| Participate in the development, implementation, and evaluation of the LRE survey that will be utilized in state Program Improvement activities, including use of the survey by the Site Assistance Intervention Teams (SAIT) and District Assistance Intervention Teams (DAIT). Provide training and technical assistance on the LRE survey to LEAs and schools in Program Improvement under ESEA. | 2005-June 30, 2011 | CDE staff, contractor, California Comprehensive Center |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 5: LRE |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Develop and maintain training modules on standards-based IEPs in collaboration with the California Comprehensive Center to promote and sustain activities that foster special education/general education collaboration. (Chapter topics include: Access, Standards-based IEPs, Service Delivery Models, and Curriculum and Instruction Strategies) | 2009-2010 Ongoing | CDE staff, contractor, California Comprehensive Center |
| In collaboration with the California Comprehensive Center and Program Improvement Office, SED will assist in the development of the Inventory of Services and Supports (ISS) for Students with Disabilities and training for District Assistance and Intervention Teams (DAIT) on the ISS. | 2009 Ongoing | CDE staff and the California Comprehensive Center |

Monitoring Priority: FAPE in the LRE

Indicator 8:  Percent of parents with a child receiving special education services who report that schools facilitated parent involvement as a means of improving services and results for children with disabilities.

(20 U.S.C. 1416(a)(3)(A))

Measurement: Percent = [(number of respondent parents who report schools facilitated parent involvement as a means of improving services and results for children with disabilities) divided by the (total number of respondent parents of children with disabilities)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 82 percent of parents will report that schools facilitated parent involvement as a means of improving services and results for children with disabilities |

Actual Target Data for 2008 (2008-09):

Overall, 84.4 percent of respondents (26,996 out of 31,987 parents) reported that schools facilitated parent involvement as a means of improving services and results for children with disabilities. Table 8a depicts information about Parent Survey responses statewide. This data are collected through monitoring processes (VRs and SESRs). As part of the monitoring process parents complete a survey in which they report whether the schools facilitated parent involvement as a means of improving services and results for children with disabilities. A copy of the Parent Survey may be found as Attachment 8a.

Table 8a

2008-09 Parent Survey Responses: Indicator 8 – Parent Involvement

| Survey Distribution | Responses |
| --- | --- |
| Surveys Mailed | 120,652 |
| Surveys Returned | 32,431 |
| Percent of Mailed Returned | 26.9 |
| Surveys with answers to Q5 | 31,987 |
| Surveys with "YES" to Q5 | 26,996 |
| Percent Responding "YES" | 84.4 |

While the 84.4 percent response in FFY 2008 exceeds the target of 82 percent, it is a very slight increase from the 83.6 percent reported in FFY 2007.

As indicated in the FFY 2006 APR, CDE collected additional data regarding the ethnicity and disability of the respondents’ children. In this way, CDE is able to assess the extent to which the statewide and LEA samples are representative of the statewide and LEA populations. Table 8b summarizes information about the characteristics of students whose parents responded to the parent survey statewide. CDE used a variation of the Response Calculator provided by the National Post Secondary Outcomes Center (NPSO). According to the Response Calculator, differences between the respondent group and the statewide population of ±3 percent are important. Negative differences indicate an over-representativeness of the group and positive differences indicate under-representativeness. In the Response Calculator, a bolded percentage is used to indicate a difference that exceeds the ±3 percent interval.

# Table 8b

# Characteristics of Students Whose Parents Responded to the Parent Survey

# 2008-09: Indicator 8 – Parent Involvement

| Disability | Sample N | State N | Sample Percent | State Percent | Difference: State Percent - Sample Percent | Sample as Percent of State |
| --- | --- | --- | --- | --- | --- | --- |
| Mental Retardation | 1,943 | 42,646 | 5.99 | 6.29 | 0.30 | 4.56 |
| Hard of Hearing | 271 | 9,016 | 0.84 | 1.33 | 0.49 | 3.00 |
| Deaf | 167 | 4,162 | 0.51 | 0.61 | 0.10 | 4.01 |
| Speech or Language Impairment | 7,057 | 172,669 | 21.76 | 25.46 | 3.70 | 4.09 |
| Visual Impairment | 229 | 4,588 | 0.70 | 0.68 | -0.03 | 4.98 |
| Emotional Disturbance | 886 | 27,124 | 2.73 | 4.00 | 1.27 | 3.27 |
| Orthopedic Impairment | 509 | 15,404 | 1.57 | 2.27 | 0.70 | 3.31 |
| Other Health Impairment | 2,263 | 50,614 | 6.98 | 7.46 | 0.49 | 4.47 |
| Specific Learning Disability | 16,343 | 291,456 | 50.39 | 42.98 | -7.41 | 5.61 |
| Deaf-Blindness | 29 | 182 | 0.09 | 0.03 | -0.06 | 15.93 |
| Multiple Disabilities | 260 | 5,210 | 0.80 | 0.77 | -0.03 | 4.99 |
| Autism | 2,358 | 53,183 | 7.27 | 7.84 | 0.57 | 4.43 |
| Traumatic Brain Injury | 116 | 1,851 | 0.36 | 0.27 | -0.09 | 6.28 |
| Total | 32,431 | 678,105 | 100.00 | 100.00 | 0.00 | 4.78 |

| Ethnicity | Sample N | State N | Sample Percent | State Percent | Difference: State Percent - Sample Percent | Sample as Percent of State |
| --- | --- | --- | --- | --- | --- | --- |
| Native American | 497 | 5,896 | 1.53 | 0.87 | -0.66 | 8.42 |
| Hispanic | 14628 | 333,346 | 45.10 | 49.16 | 4.05 | 4.39 |
| African-American | 2988 | 74,064 | 9.21 | 10.92 | 1.71 | 4.03 |
| White | 11920 | 218,448 | 36.76 | 32.21 | -4.54 | 5.46 |
| Asian | 2398 | 46,351 | 7.40 | 6.84 | -0.56 | 5.17 |
| Total | 32431 | 678,105 | 100.00 | 100.00 | 0.00 | 4.78 |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Discussion of Progress

California met the benchmark that 82 percent of parents will report that schools facilitated parent involvement as a means of improving services and results for children with disabilities. Though there was only a slight increase in the overall percent from 83.6 percent in 2007-08 to 84.4 percent in 2008-09, stakeholders, including the California Parent Training and Information Centers, felt that this was a typical year-to-year variation.

Sampling Plan

In its California Part B FFY 2006 SPP/APR Response Table, OSEP indicated that: In the FFY 2008 APR, due February 1, 2010, the State must continue to indicate whether its response group is representative of the State’s population and, if not, the actions the State is taking to address this issue”.

As noted above, representative data have been collected and calculated for 2008-09. Instructions to LEAs emphasized the importance of securing a representative sample. It should be noted that the CDE is working with the ISES stakeholder group which includes the PTI and the SELPA Director organization to design a universal sample to be collected in 2009-10. CDE has pilot tested an online version of the NCSEAM parent involvement survey with both LEAs and Parent Training and Information Centers.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 8: Parent Involvement |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Conduct analysis and prepare plans for APR on all indicators, including parent involvement. | July 1, 2005 to June 30, 2011 | Special Education Division and SEEDS |
| Explore Web-based applications for all components of the monitoring system including parent involvement. | 2009-2011 | CDE staff and Supporting Early Education Delivery Systems (SEEDS) Project |
| During 2008-09, CDE will work with PTIs and FECs to develop a three year sampling plan to collect family involvement information using the NCSEAM parent involvement survey. | 2009-2011 | CDE staff, parent organizations, and SEEDS project |
| Data collection will be conducted independent of the monitoring processes by parent centers and CDE staff (PSRS Parent Helpline). | June 30, 2011 | CDE staff, parent organizations, and SEEDS Project |
| Develop a detailed revised universal sampling plan to survey parental involvement. | 2009-2010 | CDE staff, parent organizations. and SEEDS Project |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09):

The following is being added at the recommendation of the improving Special Education Services (ISES) Stakeholder group:

| ADDED ACTIVITIES– Indicator 8: Parent Involvement |  |  |
| --- | --- | --- |
| Activities | Activities | Activities |
| Develop a Web-based survey process and a statewide data collection through CASEMIS to capture a universal sample of families to address the Parent Involvement Indicator. | June 2010 Ongoing | CDE staff, SEEDS Project, ISES stakeholders workgroup, and SELPA Directors |
| Develop and implement a universal sampling plan for the collection of parent involvement data for indicator 8 (Parent Involvement). | Ongoing | CDE staff, SEEDS Project, ISES stakeholders workgroup, and SELPA Directors |
| Conduct activities related to parent involvement, LRE, RtI2, and Secondary Transition. CDE promotes parental involvement by inviting their membership and participation in ISES and in CDE trainings. CDE supported trainings are posted on the Internet to increase parent access to training materials. In addition through CDE partnerships with PTI, FRC, and FEC parents are provided training and technical assistance statewide. CDE also maintains a parent ‘hot line’ to provide parent information and assistance. | Ongoing | CDE staff and State Personnel Development Grant (SPDG), United State Department of Education (USDOE), Office of Special Education Programs (OSEP) |

Attachment 8a – Parent Survey

SPECIAL EDUCATION SELF-REVIEW PARENT SURVEY

District:  ______________________________     School Site:  _________________________________

The CDE, SED requires all school districts to complete a Special Education Self-Review (SESR) once every four years. One essential component of the SESR is gathering parent input regarding district services and programs provided to students with disabilities. As part of the district’s effort to gather parent input, please complete this survey and return the form as your school district directs.

Please circle your answers with one of the following responses:

Y = Yes     N = No     DK = Don’t Know

| Questions 1 – 5 apply to all parents |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Does the district make a good faith effort to assist your child with achieving the goals and objectives or benchmarks listed in his/her Individualized Education Program (IEP)? | Y | N | DK |
| 2 | Do you receive progress reports on how your child is meeting his/her IEP/ Individualized Family Service Plan (IFSP) goals/outcomes at least as often as the regular report card schedule? | Y | N | DK |
| 3 | Are the services your child is receiving in accordance with his/her IEP? | Y | N | DK |
| 4 | Do you receive a copy of your parental rights (procedural safeguards) at least one time per year? | Y | N | DK |
| 5 | Did the school district facilitate parent involvement as a means of improving services and results for your child? | Y | N | DK |
| Questions 6 – 7 are for parents of Infants/Toddlers only |  |  |  |  |
| 6 | If your child is under three (3)-years of age, is his/her Individualized Family Service Plan (IFSP) reviewed with you at least every six (6) months? | Y | N | DK |
| 7 | Were the transition services for your child from infant to preschool programs planned and implemented as written? | Y | N | DK |
| Questions 8 – 21 are for parents of School Age children (Preschool through 12th grade) |  |  |  |  |
| 8 | Do you understand the reasons why your child was referred for Special Education services? | Y | N | DK |
| 9 | Were your child’s strengths considered during the IEP Meeting? | Y | N | DK |
| 10 | Were the results of your child’s assessment used to plan IEP goals? | Y | N | DK |
| 11 | Is your child re-evaluated for Special Education every three (3) years? | Y | N | DK |
| 12 | Does the district have an IEP meeting for your child at least once a year? | Y | N | DK |
| 13 | Does a regular education teacher attend your child’s IEP meeting, unless you and the district agree, under specified circumstances, to excuse him/her? | Y | N | DK |
| 14 | Were information and any concerns you had about your child considered when planning and writing his/her IEP? | Y | N | DK |
| 15 | At your child’s IEP meeting, did the team discuss your child’s program in terms of the least restrictive environment (e.g., general education classroom, resource, special day class, etc.) for him/her? | Y | N | DK |
| 16 | Are teachers and service providers informed of specific responsibilities related to implementing your child’s IEP, and the specific accommodations, program modifications and support for school personnel? | Y | N | DK |
| 17 | Did you discuss a variety of program options for your child at the IEP meeting? | Y | N | DK |
| 18 | Are IEP goals and objectives reviewed and revised at the IEP meeting, based on both progress and lack of progress? | Y | N | DK |
| 19 | Does your child have the opportunity to participate in school and extra curricular activities (such as, assemblies, field trips and after school activities)? | Y | N | DK |
| 20 | Did the IEP team discuss how your child would participate in State and district testing? | Y | N | DK |
| 21 | If your child will turn 16 years of age before his/her next IEP meeting, did the IEP team discuss transition services (e.g., career interests, employment, high school classes) at the most recent meeting? | Y | N | DK |
| Questions 22 – 26 are for parents who don’t speak English at home or for parents of students who are learning English at school |  |  |  |  |
| 22 | Does your child’s IEP indicate that he/she is an English Learner? | Y | N | DK |
| 23 | As an English Learner, does your child receive services to assist with progress in English language development? | Y | N | DK |
| 24 | As an English learner, does your child receive the language support in Special Education classes necessary to learn subjects other than English, such as math or science? | Y | N | DK |
| 25 | If you speak a language other than English, upon request, do you receive information from the school in your native language? | Y | N | DK |
| 26 | Upon request, does the district provide a language interpreter for your child’s IEP meeting? | Y | N | DK |
| Question 27 applies to all parents |  |  |  |  |
| 27 | Do you have any other concerns or information about you or your child’s special education experience that you would like to tell us? Please attach your comments to this form. |  |  |  |

Child’s Age:  _____     Child’s Ethnicity:  _________________     Child’s Disability:  _________________

The information below is optional; however, it would be helpful in case we need to follow-up on any of the issues or questions that you may have.

Parent or Guardian Name: ______________________________________________________________

Child’s Name: ________________________________________________________________________

Home Address: ____________________________________     Phone Number: (_____) ____________

THANK YOU FOR TAKING YOUR TIME TO HELP US

Monitoring Priority: Disproportionality

Indicator 9:  Percent of districts with disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification.

(20 U.S.C. 1416(a)(3)(C))

Measurement: Percent = [(# of districts with disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification) divided by the (# of districts in the State)] times 100. Include State’s definition of “disproportionate representation.” Based on its review of the 618 data for FFY 2008, describe how the State made its annual determination that the disproportionate representation it identified (consider both over and under representation) of racial and ethnic groups in special education and related services was the result of inappropriate identification as required by sections 300.600(d)(3) and 300.602(a), e.g., using monitoring data; reviewing policies, practices and procedures, etc. In determining disproportionate representation, analyze data, for each district, for all racial and ethnic groups in the district, or all racial and ethnic groups in the district that meet a minimum 'n' size set by the State. Report on the percent of districts in which disproportionate representation of racial and ethnic groups in special education and related services is the result of inappropriate identification, even if the determination of inappropriate identification was made after the end of the FFY 2009 reporting period, i.e., after June 30, 2010. If inappropriate identification is identified, report on corrective actions taken.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | Zero percent of districts will have disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification. |

Actual Target Data for 2008 (2008-09):

Overall, there were 61 of 838 districts with denominators greater than 20 who were identified as having disproportionate representation. Of the 61 districts found potentially disproportionate, 42 were found to have noncompliant policies, procedures, or practices as a result of inappropriate identification.

Calculation:  42 / 838 *100 = 5 percent

Table 9a provides a description of the methods used and a calculation example for identifying districts that have disproportionate representation.

For each district, California calculates a race-neutral measure labeled the Disparity Index as part of the Quality Assurance Process (QAP). Specifically, the number of students ages six through twenty-two receiving special education within each ethnic category is divided by the total number of all students ages six through twenty-two in that ethnic category (e.g., the percentage of African Americans receiving special education relative to the total number of African Americans in the district). The index is simply the range between the lowest and the highest group percentages. For example, if the percentage for African Americans is the highest at 15 percent and the percentage for Hispanics is the lowest at 8 percent, then the Disparity Index is 7 points. The underlying concept is that if the identification process is race neutral, the disparity index will be relatively low. The state has set a system of decreasing annual benchmarks leading to a maximum disparity of 5 points by 2011-12.

California combined the disparity measure with the e-formula in a race neutral approach to identifying which districts are disproportionate. The first test is to identify those districts that have a disparity that is higher than the annual benchmark.

The second test, based on the e-formula, looks at the over and under representation of each ethnic group compared to the distribution of those ethnic groups in the general education population. The percent of a particular ethnic group is compared to the maximum and minimum percentage values calculated using the e-formula. A district fails the e-formula test if the percent of an ethnicity in special education either exceeds the maximum value or falls below the minimum value for that ethnicity.

If the district exceeds the benchmark using the disparity test AND the district is determined to have disproportionate representation using the e-formula (either over or under represented), the district is identified as having disproportionate representation.

The tables below provide statewide disproportionality data for 2008-09. the data indicate that African American students are proportionately overrepresented; Asian students are underrepresented. These disproportions are observed using both statewide percentage calculations (see Table 9a) and also when compared to the overall representation of students with disabilities.

Table 9a

Over- and Under-Representation of Students by Ethnicity using the Disparity Index in California

Indicator 9 – Disproportionate Representation

| Ethnic Disparity |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Native American | Asian | Hispanic | African American | White | Total |
| General Ed | 46,446 | 734,025 | 3,064,614 | 454,781 | 1,741,664 | 6,041,530 |
| Special Ed | 5,896 | 46,351 | 333,346 | 74,064 | 218,448 | 678,105 |
|  | 12.7% | 6.3% | 10.9% | 16.3% | 12.5% | 11.2% |
| Disparity Index | High Percent |  | Low Percent |  | Difference |  |
|  | 16.3% |  | 6.3% |  | 10.0% |  |

The e-formula (see Table 9b) indicates on a statewide basis that White African American and Native American students are all over identified, while Asian and Hispanic students are under identified.

Table 9b

Over- and Under-Representation of Students by Ethnicity using the E- formula in California

Indicator 9 – Disproportionate Representation

| Overall |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Native American | Asian | Hispanic | African American | White | Total |
| State GE% | 0.8% | 12.2% | 50.7% | 7.5% | 28.8% | 100.0% |
| State SE% | 0.9% | 6.8% | 49.2% | 10.9% | 32.2% | 100.0% |
| Max E-form | 0.9% | 12.5% | 51.2% | 7.8% | 29.3% |  |
| Min E-form | 0.7% | 11.8% | 50.2% | 7.3% | 28.4% |  |
| Over/Under? | Over | Under | Under | Over | Over |  |

Disproportionate representation is determined using the disparity and e-formula calculations, described above. The calculations for Indicator 9 (Overall Disproportionality) are based on data collected during the LEA self-reviews of policies, procedures and practices who were found to have disproportionate representation. If an LEA reports noncompliance findings in the review policies, procedures, and practices related to identification, then that LEA’s disproportionate representation; is considered to be the result of inappropriate identification. Beginning in 2007-08, the LEA self-review of policies, procedures and practices was conducted through a Web survey rather than a paper review. Findings of noncompliance identified through the special self-review result in a corrective action plan, monitored by the Focused Monitoring and Technical Assistance (FMTA) consultant assigned to the district. Attachment 9b contains 58 items of Federal and State requirements related to ensuring proportionate representation and appropriate identification.

Noncompliance related to indicators 9 (Disproportionality by Race and Ethnicity) and 10 (Disproportionality by Disability) are identified in several ways:  1) LEA Self-Reviews that are the result of calculations of disproportionate representation; 2) Verification and Self-Reviews; 3) Complaints and Due Process Findings. As a result, the numbers reported in the calculations for indicators 9 and 10 are smaller than the numbers reported in Indicator 15, because the other monitoring processes may make findings of noncompliance in districts that are not identified as disproportionate. Correction of all noncompliance reported to LEAs related to indicators 9 and 10 is discussed below.

Noncompliance Identified in FFY 2008 (2008-09). As noted above, there were 61 of 838 districts with denominators greater than 20 who were identified as disproportionately represented. These districts participated in a special self-review related to Indicator 9.

Correction of Noncompliance Identified in FFY 2007 (2007-08). In 2007-08, there were 257 of 974 districts with denominators greater than 20 who were identified as disproportionately represented. These districts participated in a special self-review related to Indicator 9. Of the 257 districts found potentially disproportionate, 52 (5 percent) were found to have noncompliant policies, procedures, or practices that result in inappropriate identification.

Of the 52 districts, all 52 districts corrected their identified noncompliance within one year of identification to the district. The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §§300.111, 300.201, and 300.301 through 300.311; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memorandum 09-02, dated October 17, 2008 (OSEP Memo 09-02).

The corrective action process requires that districts remedy noncompliant findings when individual student level or policy, procedure and practice noncompliance is found. All district policies, procedures, and practices documents are reviewed every four years or more frequently if data calculations warrant a review.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

The percent of districts having disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification in 2008-09 is the same as in 2007-08. (5%) However, it is difficult to compare 2008-09 to prior year results, because the method of disproportionality identification was different in 2008-09 and resulted in large difference in the number of districts identified. The continuing low percentage of districts with noncompliance in this indicator may be related to the increased number of districts that completed self-reviews in prior years and resolved non-compliance and then repeated self-reviews in 2008-09.

Improvement Activities for 2008 (2008-09): The following improvement activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 9: Disproportionality by Race and Ethnicity |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Work with the Western Regional Resource Center (WRRC) and other federal contractors to identify and disseminate research-based practices related to preventing disproportionate representation and to address the relationship between eligibility and disproportionality of racial and ethnic groups. | 2005-2010 Ongoing | CDE staff with the Western Regional Resource Center (WRRC) |
| Refine policies, procedures, and practices instruments to assist the LEAs in reviewing their policies, procedures and practices in relation to disproportionality of racial and ethnic groups. | Annually | CDE staff and the Western Regional Resource Center (WRRC), Office of Special Education Programs (OSEP), and SELPA directors http://www.cde.ca.gov/sp/se/as/caselpas.asp http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Convene special meetings of ISES and SELPA stakeholder groups to develop two types of practice reviews: - Compliance based to address IDEA monitoring requirements - Research based to address improvement needed outside of a compliance context | January 2008 to June 2010 | CDE Staff and the Western Regional Resource Center (WRRC), Office of Special Education Programs (OSEP), SELPA directors http://www.cde.ca.gov/sp/se/as/caselpas.asp http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Incorporate preliminary self-review and improvement planning modules, based on National Center for Culturally Responsive Educational Systems (NCCRESt), into monitoring software. | June 2008-2011 | CDE staff and the National Center on Culturally Responsive Educational Systems (NCCRESt), Office of Special Education Programs (OSEP), SELPA directors http://www.cde.ca.gov/sp/se/as/caselpas.asp http://www.ed.gov/about/offices/list/osers/osep/index.html |
| The SED, in collaboration with other divisions, participates in the Superintendents Closing the Achievement Gap initiative to address closing the achievement gap for students with disabilities: - Assign staff to participate - Provide information contained in SPP and APR - Assist in the development of products and materials, such as: - Culturally Responsive Teaching in California - Expand the web-based California School Climate Survey (CSCS) to include a Special Education Supports Module (SESM). - Obtain general education input and participation in the development of district level practices review. | June 2007 to June 2010 Completed Fall 2009 | CDE staff, Special Education Division and Equity Alliance Center at Arizona State University (Contractor) and the State Superintendent’s P-16 Council. (To be Completed Spring 2010) CDE staff and California Comprehensive Center at WestED |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are being added to decrease the rate of disproportionate representation:

| ADDED ACTIVITIES– Indicator 9: Disproportionality by Race and Ethnicity |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Annually identify districts that are significantly disproportionate, using existing instruments and procedures. | Ongoing | CDE staff, OSEP, and SELPA http://www.cde.ca.gov/sp/se/sr/selinks.asp |
| In collaboration with the WRRC, conduct a study of promising practices among districts that are not disproportionate to identify causes of disproportionate identification of students by race and ethnicity and practices that achieve successful identification and improved outcomes for students with disabilities. | January 2007 to January 2010 | CDE staff and the Western Regional Resource Center (WRRC) |
| SED, with the assistance of the WRRC, will reconvene a Larry P. Task Force to identify appropriate pre-referral assessment practices and procedures and practices related to effective instruction and determination of eligibility for special education. In addition, CDE will develop a criteria for selection of evaluation instruments consistent with Larry P. case and publish revised matrix. | 2010-2011 | CDE staff, field experts, Larry P. Task Force, and the Western Regional Resource Center (WRRC) |
| Develop and maintain a series of Web pages providing information on disproportionate representation of students receiving special education services by race and ethnicity. | October 2009 | CDE staff, WRRC, and Equity Alliance Center http://www.cde.ca.gov/sp/se/qa/disproportionality.asp |
| Design and develop a SPP technical assistance system to assist LEAs to correct non-compliance findings in anyone of the indicators. - Hire two nationally recognized experts in systems change and disproportionality - Convene a design team to gain input on the proposed SPP TA system. - Draft a proposed SPP TA system design. - Convene focus group of key stakeholders to solicit input on the proposed SPP TA system. - Present a briefing of the proposed TA system to ACSE and meet with the SBE liaison and staff to solicit input - Develop a briefing paper on the final SPP TA system. - Identify technical assistance and training consultants in SPP content areas. Train identified consultants in the CDE monitoring systems, data, SPP TA system, SPP content resources and tools. | 2009-2010 | CDE staff, Contractor NAPA COE, WestEd California Comprehensive Center, WRRC, Equity Alliance Center (Arizona State University), two national experts on technical assistance systems, and technical assistance on disproportionality by Perry Williams (OSEP) |
| Execute a contract to implement a SPP technical assistance system. | July I, 2010-2011 | CDE staff, Contractor NAPA COE CalSTAT |
| Collaborate with other CDE divisions and advisory groups to gain meaningful input regarding the over-representation of certain ethnic groups receiving special education services: - Advisory Commission on Special Education (ACSE) - African-American Advisory Committee (AAAC) to the SBE - Cultural/Climate Subcommittee of the P-16 Council - SBE liaison and staff | July I, 2010-2011 | CDE staff English Learner Support Division http://intranet.cde.ca.gov/ac/bd/el/ Improvement and Accountability Division http://intranet.cde.ca.gov/ac/bd/sd/index.aspx |

Attachment 9a

Calculation Methodologies

Disproportionate Representation will be determined using two calculations:  Ethnic Disparity and the E-Formula.

Ethnic Disparity

Ethnic disparity is determined by comparing the likelihood that a student from one ethnicity will be in special education to the likelihood that a student from another ethnicity will be in special education. For each race/ethnicity category, the number of students receiving special education is divided by the number of students in that race/ethnicity category in general education yielding the likelihood (or risk) that a student from that category will be found eligible for special education. This calculation is repeated for each of the race/ethnicity categories. The smallest risk percentage is subtracted from the largest, producing an index of the size of the disparity in identification among race/ethnicity categories. The annual benchmark for this index decreases each year.

Table 1 depicts the enrollments in general education and special education as well as the likelihood that a student of a given ethnicity will be in special education (percent of special education students in the general education population). Table 1 also calculates the difference between the highest and the lowest risks (the disparity index) and compares the sample value to the benchmark for the district.

Table 1 - Sample Calculation to Determine Ethnic Disparity Using the Ethnic Disparity Index: Indicator 9 – Disproportionate Representation

|  | Native American | Asian | African American | Hispanic | White | Total |
| --- | --- | --- | --- | --- | --- | --- |
| General Education (GE) | 9 | 696 | 58 | 235 | 4,231 | 5,229 |
| Special Education (SPED) | 0 | 37 | 19 | 33 | 378 | 467 |
| Disparity Percent (Percent of SPED in GE) | 0.0% | 5.3% | 32.8% | 14.0% | 8.9% | 8.9% |
|  |  | Low Percent | High Percent |  |  |  |
| Disparity Index High – Lows Percents |  |  |  |  |  |  |
| Index | 27.4 |  |  |  |  |  |
| Benchmark | 19.5 |  |  |  |  |  |
| Met (Y/N) | N |  |  |  |  |  |

Disparity Percent:  The number of students in an ethnic category receiving special education divided by the number of students in general education in that category.

Disparity Index:  The difference between the largest and smallest disparity percents

Met Disparity Benchmark:  “Y” if the district was at or below the benchmark and “N” if the district is above the benchmark. Disparity Benchmarks were established between 2000 and 2004 by the Key Performance Indicator (KPI) Workgroup. Benchmarks were established separately for Elementary, High School and Unified School Districts. District disparity indexes were arrayed within each district type. The 75th percentile was selected as the beginning level and decreasing values were selected down to the target at the 25th percentile. These values were adjusted through based on the recommendations of the KPI stakeholders.

Cut Points for Determining Disproportionate Representation. For the purposes of disproportionate representation (the calculations required for the State Performance Plan Indicators and the Compliance Determinations), CDE is using the most recent single year. Districts that exceed the annual benchmark are then measured using the E-formula.

E-Formula

The E-formula was developed as required in the court rulings in the Larry P. vs. Riles lawsuit which was filed in California in the mid-1970. The lawsuit alleged that the number of young African-American students identified as educable mentally retarded (EMR) and placed in a special day class (SDC) setting for special education services was disproportionately higher than in the general education program in the district. As part of the settlement of the lawsuit, the presiding judge ordered the CDE to monitor disproportionate placement of African-American students identified as EMR in SDC placement setting, using the E-formula.

Neither the EMR disability category, nor the SDC placement setting, exists today in California; however, the E-formula has been found to be an effective measure to determine ethnic disproportionality in special education. This is because the underlying statistical principles in the development of the E-formula make the measure robust, and it allows the necessary flexibility to districts of different sizes. The intent of the original E-formula was to determine overrepresentation only.

The E-formula is defined as:

E = A + SQRT [A*(100-A)/N]

Where:  E = 	Maximum percentage of the total special education enrollment (or special education enrollment in a disability category or service delivery environment) in a district allowed for a specific ethnic group

A =	Percentage of the same ethnic group in general education in the district

N =	The total special education enrollment (or special education enrollment in a disability category or service delivery environment) in a district, as defined in E

In E-formula, special education enrollment is viewed as a sample drawn from a population of the general education enrollment (GE). In statistical terms, the second component in the E-formula “SQRT [A*(100-A)/N]” is comparable to standard error of the sampling distribution of the proportion of a racial/ethnic group in question. To determine overrepresentation, the standard error is added to the percentage of the ethnic group in general education (A) to determine the acceptable level for the district. To determine whether a district is over represented, the percent the ethnic group represents in special education is compared to the acceptable E-formula value for that group. If the special education (SE) percentage is greater than the E-formula value, then the district is over represented.

Table 2 shows the results of the E-formula calculations for various racial/ethnic groups in mental retardation.

Table 2:  E-formula Results for Overrepresentation of Various Racial/Ethnic Groups in Mental Retardation: Indicator 9 – Disproportionate Representation

|  | Native American | Asian | African American | Hispanic | White | Total |
| --- | --- | --- | --- | --- | --- | --- |
| District GE (%) | 0.20 | 40.88 | 10.04 | 40.53 | 8.35 | 100.00 |
| District SE (%) | 0.00 | 33.75 | 17.50 | 40.00 | 8.75 | 100.00 |
| Maximum E-formula value | 0.69 | 46.38 | 13.40 | 46.02 | 11.44 | NA |
| Over Represented | No | No | Yes | No | No | NA |

NA = Not applicable.

In the above example, African-American students constitute 10.04 percent of general education enrollment in the district, and the maximum E-formula value allowed in order for African Americans not to be overrepresented is13.40 percent of the total number of SE students. The actual percentage of African-American students in SE is 17.50 percent, which is 4.10 percentage points above the allowed maximum, and therefore, they are overrepresented.

It is important to note that while exceeding the maximum E-formula value indicates overrepresentation, a value below the E-formula maximum does not mean under-representation – it simply means lack of or short of overrepresentation.

The calculation for under-representation in the E-formula is similar to the original formula for overrepresentation, except that the connector between the first and the second component is a minus sign (-), instead of a plus (+) sign. This creates a lower bound around the percentage of a racial/ethnic group in general education beyond which the group is considered underrepresented.

The E-formula for under-representation can be shown as:

E = A - SQRT [A*(100-A)/N]

Where:  E = Minimum percentage of the total special education enrollment (or special education enrollment in a disability category or service delivery environment) in a district needed for a specific ethnic group

A =	Percentage of the same ethnic group in general education in the district

N =	The total special education enrollment (or special education enrollment in a disability category or service delivery environment) in a district, as defined in E

Table 3 shows the results of under-representation calculations using the E-formula.

Table 3:  E-formula Results for Under-representation of

Various Racial/Ethnic Groups in Mental Retardation:

Indicator 9 – Disproportionate Representation

|  | Native American | Asian | African American | Hispanic | White | Total |
| --- | --- | --- | --- | --- | --- | --- |
| District GE (%) | 0.20 | 40.88 | 10.04 | 40.53 | 8.35 | 100.00 |
| District SE (%) | 0.00 | 33.75 | 17.50 | 40.00 | 8.75 | 100.00 |
| Minimum E-formula value | -0.30 | 35.39 | 6.68 | 35.04 | 5.26 | NA |
| Underrepresented | No | Yes | No | No | No | NA |

NA = Not applicable.

In the above example, Asian students constitute 40.88 percent of general education enrollment in the district and the minimum E-formula value allowed for them not to be underrepresented is 35.39 percent of the total number of SE students. The actual percentage of Asian students in SE is 33.75 percent, which is below the allowed minimum, and therefore, they are underrepresented.

Cut Points for Determining Disproportionate Representation. For the purposes of disproportionate representation (the calculations required for the State Performance Plan Indicators and the Compliance Determinations), CDE will be using “8” standard errors for over and under-representation. This changes the formula to:

E = A + {8*SQRT [A*(100-A)/N]} (overrepresentation)

E = A - {8*SQRT [A*(100-A)/N]} (underrepresentation)

Attachment 9b

Policy, Procedure and Practice Protocol Findings Related to State Performance Plan

Item Nine and Ten

| Number of Non Compliant Findings | Compliance Standard |
| --- | --- |
| 1 | Is there documentation that all students, three to five years of age, enrolled in preschool special education programs meet eligibility criteria and are identified by the IEP team as needing specially designed instruction or services? |
| 3 | Does a student who transfers from outside the State to a District within California receive a free appropriate public education, including services comparable to those described in the previously approved individualized education program until the local educational agency conducts an assessment, if determined to be necessary, and develops a new individualized education program? |
| 5 | Does the IEP team include, for a student suspected of having a specific learning disability, at least one member who is qualified to conduct individual diagnostic examinations of students, such as a school psychologist, speech-language pathologist, or remedial reading teacher? |
| 5 | Is there documentation that the preschooler meets eligibility criteria and is identified by the IEP team as having needs that cannot be met with modification of a regular environment in the home or (pre-) school, or both without ongoing monitoring or support? |
| 5 | Do assessment procedures ensure that IQ tests are not administered to African-American students? |
| 6 | Are assessments conducted by trained personnel in conformance with the instructions provided by the producer? |
| 8 | Is there evidence that early education services for preschool age students takes place in the appropriate settings such as a special site where preschool programs for both disabled and typically developing students are located close to each other and have an opportunity to share resources and programming? |
| 11 | Is there evidence that, when standardized tests are considered invalid for students between three and five years, alternative means of assessment (i.e., scales, instruments, observations, and interviews) are specified in the Assessment Plan and used for evaluation and assessment? |
| 12 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? |
| 14 | Is there evidence that the current assessment includes information about academic performance, as appropriate? |
| 15 | Does the LEA use technically sound instruments that may assess the relative contribution of cognitive and behavioral factors, in addition to physical or developmental factors? |
| 16 | Is there evidence that the current assessment includes information about motor abilities, as appropriate? |
| 16 | Is an appropriate reassessment of the student conducted to determine continued eligibility prior to transitioning from a preschool program to kindergarten, or to first grade? |
| 17 | Does the LEA take whatever action is necessary to ensure that the parent understands the proceedings at the IEP meeting, including arranging for an interpreter for parents with deafness or whose native language is other than English? |
| 19 | Are a variety of tools and strategies used to gather functional, developmental and academic information to determine eligibility and the content of the IEP? Do the tools and strategies directly assist in determining the educational needs of the student? |
| 19 | Is there evidence that the current assessment includes information about communication status and language function, as appropriate? |
| 20 | Does the LEA conduct a full and individual initial evaluation prior to the provision of special education and related services? |
| 20 | Is there evidence that the current assessment includes information about general intelligence and ability? |
| 21 | Is there evidence that the current assessment includes information about self-help, as appropriate? |
| 21 | Are testing and assessment materials and procedures selected and administered so as not to be racially or culturally discriminatory? |
| 24 | Is a student transferring into the District, from another District within California, immediately placed in a District or agency program in conformity with the student's IEP for a period not to exceed 30 days before a new IEP is developed in consultation with the parent? |
| 26 | Is there evidence that the current assessment is comprehensive and that individually administered tests of intellect or emotional functioning are administered by a credentialed school psychologist? |
| 31 | Is there evidence that the current assessment is comprehensive and that assessments were administered in all areas related to the suspected disability by trained and knowledgeable personnel using sound instruments? |
| 32 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student's English proficiency? |
| 33 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals, objectives, programs and services? |
| 34 | Is there evidence that the LEA uses non-discriminatory evaluation procedures to ensure that any assessment and evaluation procedures are selected and administered so as not to be racially or culturally discriminatory? |
| 35 | Is there evidence that the current assessment includes information about social and emotional status? |
| 36 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency? |
| 37 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? |
| 38 | Did the LEA utilize the required members of the IEP team and other qualified professionals as appropriate, to review existing evaluation data, and on the basis of that review, and input from the student's parents, identify what additional data, if any, are needed to determine whether the student continues to have a disability, and the student's educational needs? |
| 42 | Is there evidence that the current assessment includes information about career and vocational abilities and interests, as appropriate? |
| 50 | Does the assessment include information related to enabling the child to be involved in and progress in the general curriculum? |
| 51 | Do assessments result in a written report or reports, that include the findings of each assessment? |
| 64 | Does the written assessment report include the results of tests administered in the student's primary language by qualified personnel? |
| 65 | Does the written Assessment Report include determination of the effects of environmental, cultural, or economic disadvantage, where appropriate? |
| 68 | Is there evidence that the current assessments include, as appropriate, health and developmental information? |
| 74 | Does the written Assessment Report include information related to enabling the student to be involved in and progress in the general education curriculum or, for preschool students, to participate in appropriate activities? |
| 75 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? |
| 80 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation? Is the Assessment Plan provided in the primary language of the parent or other mode of communication used by the parent, unless it is clearly not feasible to do so? Is the Assessment Plan written in language easily understood by the general public? |
| 82 | Does the IEP of students identified as English learners include a determination of whether the CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? |
| 94 | Is there evidence that the current assessments include, as appropriate, information about vision, including low vision? |
| 98 | Is there evidence that the current assessments include, as appropriate, information about hearing status? |
| 144 | Do students evaluated for initial and three-year reviews have a hearing and vision screening unless parental permission is denied? |

Monitoring Priority: Disproportionality

Indicator 10:  Percent of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification.

(20 U.S.C. 1416(a)(3)(C))

Measurement: Percent = [(# of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification) divided by the (# of districts in the State)] times 100. Include State’s definition of “disproportionate representation.” Based on its review of the 618 data for FFY 2008, describe how the State made its annual determination that the disproportionate representation it identified (consider both over and under representation) of racial and ethnic groups in specific disability categories was the result of inappropriate identification as required by sections 300.600(d)(3) and 300.602(a), e.g., using monitoring data; reviewing policies, practices and procedures, etc. In determining disproportionate representation, analyze data, for each district, for all racial and ethnic groups in the district, or all racial and ethnic groups in the district that meet a minimum 'n' size set by the State. Report on the percent of districts in which disproportionate representation of racial and ethnic groups in specific disability categories is the result of inappropriate identification, even if the determination of inappropriate identification was made after the end of the FFY 2009, i.e., after June 30, 2010. If inappropriate identification is identified, report on corrective actions taken.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 0 percent of districts will have disproportionate representation of racial and ethnic groups in specific disability categories that are the result of inappropriate identification. |

Actual Target Data for 2008 (2008-09):

Overall, there were 61 of 838 districts with denominators greater than 20 who were identified as having disproportionate representation. Of the 61 districts found potentially disproportionate, 42 were found to have noncompliant policies, procedures, or practices as a result of inappropriate identification.

Calculation: 42 / 838 *100 = 5 percent

Attachment 10a provides a description of the methods used and a calculation example for identifying districts that have disproportionate representation.

For each district, California calculates a race-neutral measure labeled the Disparity Index as part of the Quality Assurance Process (QAP). Specifically, the number of students ages six through twenty-two receiving special education within each ethnic category is divided by the total number of all students ages six through twenty-two in that ethnic category (e.g., the percentage of African Americans receiving special education relative to the total number of African Americans in the district). The index is simply the range between the lowest and the highest group percentages. For example, if the percentage for African Americans is the highest at 15 percent and the percentage for Hispanics is the lowest at 8 percent, then the Disparity Index is 7 points. The underlying concept is that if the identification process is race neutral, the disparity index will be relatively low. The state has set a system of decreasing annual benchmarks leading to a maximum disparity of 5 points by 2011-12.

California combined the disparity measure with the e-formula in a race neutral approach to identifying which districts are disproportionate. The first test is to identify those districts that have a disparity that is higher than the annual benchmark.

The second test is based on the e-formula and calculates maximum and minimum e-formula values for each ethnic group in each of the six most frequent disabilities (mental retardation, specific learning disabilities, emotional disturbance, speech or language impairments, other health impairments, and autism). The e-formula establishes an “acceptable” range of values using the distribution of those ethnic groups in the overall special education population. The percent of a particular ethnic group with a specific disability is compared to the maximum and minimum percentage values calculated using the e-formula. A district fails the e-formula test if the percent of the ethnicity-disability pair in special education either exceeds the maximum value or falls below the minimum value for that ethnicity-disability pair.

If the district exceeds the benchmark using the disparity test AND the district is determined to have disproportionate representation using the e-formula (either over or under represented in any one ethnicity-disability pair), the district is identified as having disproportionate representation.

The tables below provide statewide disproportionality data for 2008-09. The data indicate that African American students are proportionately overrepresented; Asian students are underrepresented. These disproportions are observed using both statewide percentage calculations (see Table 9a) and also when compared to the overall representation of students with disabilities.

d using both statewide percentage calculations (see Table 10a) and also when compared to the overall representation of students with disabilities.

Table 10a

Over- and Under-Representation of Students by Ethnicity Using the Disparity Index in California

Indicator 10 – Disproportionate Representation

| Ethnic Disparity |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Native American | Asian | Hispanic | African American | White | Total |
| General Ed | 46,446 | 734,025 | 3,064,614 | 454,781 | 1,741,664 | 6,041,530 |
| Special Ed | 5,896 | 46,351 | 333,346 | 74,064 | 218,448 | 678,105 |
|  | 12.7% | 6.3% | 10.9% | 16.3% | 12.5% | 11.2% |
| Disparity Index | High Percent |  | Low Percent |  | Difference |  |
|  | 16.3% |  | 6.3% |  | 10.0% |  |

The E-formula indicates that there is disproportionate representation within the most frequent disability groups. Native Americans are the most appropriately represented – they are over represented in two of the six disability categories. African American students are the most frequently over represented group, though they appear to be appropriately represented among students with autism and under represented in speech and language impairments. Asian students are consistently under represented in all categories while Hispanic and White students are over represented in some categories and under represented in others.

Table 10b

Over- and Under-Representation of Students by Ethnicity using the E- formula in California

Indicator 10 – Disproportionate Representation

|  |  | Native American | Asian | Hispanic | African American | White | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Children with Autism |  |  |  |  |  |  |  |
| State SE% | 0.6% |  | 15.5% | 32.3% | 8.1% | 43.6% | 100.0% |
| Max E-form | 1.1% |  | 13.3% | 52.5% | 8.4% | 30.4% |  |
| Min E-form | 0.5% |  | 11.0% | 49.0% | 6.6% | 27.3% |  |
| Over/Under |  |  | Over | Under |  | Over |  |
| Children with Emotional Disturbances |  |  |  |  |  |  |  |
| State SE% | 1.4% |  | 3.3% | 27.2% | 21.3% | 46.9% | 100.0% |
| Max E-form | 1.2% |  | 13.7% | 53.2% | 8.8% | 31.0% |  |
| Min E-form | 0.3% |  | 10.6% | 48.3% | 6.3% | 26.6% |  |
| Over/Under | Over |  | Under | Under | Over | Over |  |
| Children with Mental Retardation |  |  |  |  |  |  |  |
| State SE% | 0.8% |  | 8.9% | 53.6% | 11.4% | 25.3% | 100.0% |
| Max E-form | 1.1% |  | 13.4% | 52.7% | 8.6% | 30.6% |  |
| Min E-form | 0.4% |  | 10.9% | 48.8% | 6.5% | 27.1% |  |
| Over/Under |  |  | Under | Over | Over | Under |  |
| Children with Other Health Impairments |  |  |  |  |  |  |  |
| State SE% | 1.0% |  | 4.5% | 33.6% | 12.7% | 48.3% | 100.0% |
| Max E-form | 1.1% |  | 13.3% | 52.5% | 8.5% | 30.4% |  |
| Min E-form | 0.5% |  | 11.0% | 49.0% | 6.6% | 27.2% |  |
| Over/Under |  |  | Under | Under | Over | Over |  |
| Children with Speech or Language Impairments |  |  |  |  |  |  |  |
| State SE% | 0.8% |  | 9.5% | 48.4% | 6.7% | 34.6% | 100.0% |
| Max E-form | 0.9% |  | 12.8% | 51.7% | 8.0% | 29.7% |  |
| Min E-form | 0.6% |  | 11.5% | 49.8% | 7.0% | 28.0% |  |
| Over/Under |  |  | Under | Under | Under | Over |  |
| Children with Specific Learning Disabilities |  |  |  |  |  |  |  |
| State SE% | 0.9% |  | 3.7% | 57.0% | 13.0% | 25.4% | 100.0% |
| Max E-form | 0.9% |  | 12.6% | 51.5% | 7.9% | 29.5% |  |
| Min E-form | 0.6% |  | 11.7% | 50.0% | 7.1% | 28.2% |  |
| Over/Under | Over |  | Under | Over | Over | Under |  |

If the district exceeds the benchmark using the disparity test AND the district is determined to have disproportionate representation using the e-formula (either over or under represented in any one ethnicity-disability pair), the district is identified as disproportionate representation.

A district is found to be non-compliant if disproportionate representation is determined to be the result of inappropriate identification that are identified during a review of policies, procedures and practices. Districts identified as having disproportionate representation are required to complete a special self-review of policies, procedures and practices. Data are submitted through a Web survey in response to the questions in Attachment 9b. This was new in 2007-08. A district is considered to have disproportionate representation that is the result of inappropriate identification if they find any noncompliance in any portion of the special self-reviewFindings of noncompliance identified through the special self-review result in a corrective action plan, monitored by the FMTA Consultant assigned to the district.

Noncompliance related to indicators 9 (Disproportionality by Race and Ethnicity) and 10 (Disproportionality by Disability) are identified in several ways:  1) Special Self-Reviews that are the result of calculations of disproportionate representation; 2) Verification and Self-Reviews; 3) Complaints and Due Process Findings. As a result, the numbers reported in the calculations for indicators 9 and 10 are smaller than the numbers reported in Indicator 15, General Supervision, because the other monitoring processes may make findings of noncompliance in districts that are not identified as disproportionate. Correction of all noncompliance reported to LEAs related to indicators 9 and 10 is discussed below:

Noncompliance Identified in FFY 2008 (2008-09).

As noted above, there were 61 of 838 districts with denominators greater than 20 who were identified as disproportionately represented. These districts participated in a special self-review related to Indicator 9. Of the 61 districts found potentially disproportionate, 42 were found to have noncompliant policies, procedures, or practices as a result of inappropriate identification.

Noncompliance Identified in FFY 2007 (2007-08). In 2007-08, there were 686 of 974 districts with denominators greater than 20 who were identified as disproportionately represented. These districts participated in a special self-review related to Indicator 10 (Disproportionality by Disability). Of the 686 districts found potentially disproportionate, 142 were found to have noncompliant policies, procedures, or practices as a result of inappropriate identification.

Of the 142 districts, 140 corrected the identified noncompliance within one year. The other two districts have subsequently corrected the noncompliance. Both of the districts were provided technical assistance and received site visits. The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §§300.111, 300.201, and 300.301 through 300.311; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memorandum 09-02, dated October 17, 2008 (OSEP Memo 09-02).

The corrective action process requires that districts remedy noncompliant findings when individual student level or policy, procedure and practice noncompliance is found. All district policies, procedures, and practices documents are reviewed every four years or more frequently if data calculations warrant a review.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage

The percent of districts having disproportionate representation of racial and ethnic groups in special education and related services is the result of inappropriate identification is the same as in 2007-08 (5%) However, it is difficult to compare 2008-09 to results from prior years, as the method of identification and the number of districts is very different in 2008-09. It has been suggested that the continuing low percentage of districts with noncompliance may be the result of many districts having completed self-reviews in prior years, repeating in 2008-09 and having corrected their previous problems. Nonetheless, the CDE is continuing to develop technical assistance materials and resources (see improvement activities

Improvement Activities for 2008 (2008-09): The following improvement activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITES – Indicator 10: Disproportionality by Disability |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Refine policies, procedures, and practices guidance to assist the LEAs in reviewing their policies, procedures and practices in relation to disproportionality by disability groups.. | Annually | CDE staff and the Western Regional Resource Center (WRRC), Office of Special Education Programs (OSEP), SELPA directors http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Use refined procedures to identify districts with significant disproportionality and establish plans for supervision and technical assistance. | 2011 | CDE staff and the Western Regional Resource Center (WRRC), Office of Special Education Programs (OSEP), SELPA directors http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Convene special meetings of ISES and SELPA stakeholder groups to develop two types of practices reviews: - Compliance-based to address IDEA monitoring requirements - Research-based to address improvement needed outside of a compliance context. | January 2008 to June 2010 | CDE staff and the Western Regional Resource Center (WRRC), Office of Special Education Programs (OSEP), SELPA directors http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Incorporate preliminary self-review and improvement planning modules, based on National Center for Culturally Responsive Educational Systems (NCCRESt), into monitoring software. | June 2008-2011 | CDE staff and the National Center on Culturally Responsive Educational Systems (NCCRESt), Office of Special Education Programs (OSEP), SELPA directors http://www.ed.gov/about/offices/list/osers/osep/index.html |
| Prepare information about the E-Formula for statewide presentations and technical assistance. Identify the effect of different cut points on the number of district identified. | Fall 2009-2010 | CDE staff |
| The SED, in collaboration with other CDE divisions, participates in Superintendent’s Closing the Achievement Gap initiative, to address issues related to closing the achievement gap for students with disabilities: 1) Assign SED staff to participate 2) Provide information contained SPP and APR - Assist in the development of products and materials such as: - Culturally Responsive Teaching in California. - Expand the web-based California School Climate Survey (CSCS) to include a Special Education Supports Module (SESM). - Obtain general education input and participation in the development of district level practices review. | June 2007 to June 2010 Completed Fall 2009 | CDE staff and Contractors, Equity Alliance Center at Arizona State University (Contractor), and the State Superintendent’s P-16 Council. (To be Completed Spring 2010) CDE staff and WestED, |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are being added to decrease the rate of disproportionate representation:

| ADDED ACTIVITIES– Indicator 10: Disproportionality by Disability |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Annually identify districts that are significantly disproportionate, using existing instruments and procedures related to disability. | Ongoing | CDE staff and OSEP |
| In collaboration with the WRRC conduct a study of promising practices among districts that are not disproportionate to identify practices that may result in disproportionate identification of students by race and ethnicity and practices that achieve successful identification and improved outcomes for students with disabilities. | January 2007 to January 2010 | CDE staff with the Western Regional Resource Center (WRRC) |
| SED, with the assistance of the WRRC, will reconvene a Larry P. Task Force to identify appropriate pre-referral assessment practices and procedures and practices related to effective instruction and determination of eligibility for special education eligibility. In addition, CDE will develop criteria for selection of evaluation instruments consistent with Larry P. case and publish revised matrix. | 2010-2011 | CDE staff, field experts, Larry P. Task Force, with the Western Regional Resource Center (WRRC) |
| Develop and maintain a series of Web pages providing information on disproportionate representation of students receiving special education services by race and ethnicity. | October 2009 | CDE staff, WRRC, and Equity Alliance Center |
| Design and develop a SPP technical assistance system to assist LEAs to correct non-compliance findings in any one of the indicators. - Hire two nationally recognized experts in systems change and disproportionality. - Convene a design team to gain input on the proposed SPP TA system. - Draft a proposed SPP TA system design. - Convene a focus group of key stakeholders to solicit input on the proposed SPP TA system. - Present a briefing of the proposed TA system to ACSE and meet with the SBE liaison and staff to solicit input. - Develop a briefing paper on the final SPP TA system. - Identify technical assistance and training consultants in SPP content areas. Train identified consultants in the CDE monitoring systems, data, SPP TA system, SPP content resources and tools. | 2009-2010 | CDE staff, Contractor NAPA COE, WestEd California Comprehensive Center, WRRC, Equity Alliance Center (Arizona State University), two national experts on technical assistance systems, and technical assistance on disproportionality by Perry Williams (OSEP). |

Monitoring Priority: Effective General Supervision Part B / Child Find

Indicator 11:  Percent of children who were evaluated within 60 days of receiving parental consent for initial evaluation or, if the State establishes a timeframe within which the evaluation must be conducted, within that timeframe.

(20 U.S.C. 1416(a)(3)(B))

Measurement: - # of children for whom parental consent to evaluate was received. b. # of children whose evaluations were completed within 60 days (or State-established timeline). Account for children included in a but not included in b. Indicate the range of days beyond the timeline when the evaluation was completed and any reasons for the delays. Percent = [(b) divided by (a)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | Eligibility determinations will be completed within 60 days 100 percent of children for whom parental consent to evaluate was received. |

Actual Target Data for 2008 (2008-09):

Table 11a summarizes the target data for FFY 2007 (2007-08)

## Table 11a

Actual Target Data for Initial Evaluation: Indicator 11 – 60 Day Timeline

| Measurement Item | Target Data |
| --- | --- |
| A. Number of children for whom parental consent to evaluate was received. | 124,522 |
| B. Number of children whose evaluations were completed within 60 days (or State-established timeline). | 109,059 |
| Percent of children with parental consent to evaluate, who were evaluated within 60 days. Percent = [(b + c) divided by (a)] times 100. | 87.58 |

These data were calculated using CASEMIS data fields related to Parent Consent Date, and Initial Evaluation Date. Determination of eligibility was made using the Plan Type field which includes the type of plan a student has (IEP, IFSP, ISP) if the student is eligible or no plan if the student is determined ineligible. If the parent of a child repeatedly failed or refused to produce the child for the evaluation; or a child enrolled in a school of another public agency after the timeframe for initial evaluations has begun, and prior to a determination by the child’s previous public agency as to whether the child is a child with a disability, then the child was eliminated from both the numerator and the denominator. California Education Code (30 EC 56043(f)(1)) specifies allowable delays in the 60 day timeline:

(f) (1) An IEP required as a result of an assessment of a pupil shall be developed within a total time not to exceed 60 calendar days, not counting days between the pupil's regular school sessions, terms, or days of school vacation in excess of five schooldays, from the date of receipt of the parent's or guardian's written consent for assessment, unless the parent or guardian agrees, in writing, to an extension, pursuant to Section (§) 56344.

Students whose assessments were late except for the state’s timelines (per 34 CFR 300.301(c)(1)(ii)) were included in the number of children whose evaluations were completed within 60 days.

Table 11b depicts the range of days beyond 60 days that evaluations were completed for students whose assessments went beyond 60 days. The bulk of the late evaluations were completed within 30 days of the deadline. Reasons cited for delays included: lack of staff, ineffective tracking systems, student illness, and failure to keep appointments.

Table 11b

Total of all Student Initial Evaluations that exceeded Time lines and the Number and Percent in Each Data Range: Indicator 11 – 60 Day Timeline

| Date Range | Number | Percent of All Consents |
| --- | --- | --- |
| 1 to 30 days | 3,492 | 64.24 |
| 31 to 60 days | 1,117 | 20.54 |
| 61 to 90 days | 525 | 9.65 |
| 91 to 120 days | 169 | 3.11 |
| 121 to 150 days | 69 | 1.27 |
| Over 150 days | 64 | 1.17 |

### Monitoring Data

All Verification and SESRs include the following item:

| Item No. | Compliance Test |
| --- | --- |
| 3-1-1.1 | Is there an IEP developed and implemented for each student (including students placed by the LEA in a private school or facility), within 60 days of obtaining written parental consent to the assessment plan? |

Noncompliance findings reported through monitoring in 2008-09: In 2008-09 there were 1,071 findings of noncompliance reported to 153 districts and agencies related to the initial evaluation item above. A total of 9,096 students were tested using the initial evaluation item. These results are an on time percentage of 88.2 (100-(1587/9096*100).

Correction of Noncompliance reported in 2007-08: In 2007-08, there were 1,337 findings of noncompliance related to initial identification of students with disabilities. These findings were identified through monitoring and dispute resolution processes in 2007-08. Of the total noncompliance findings, 1,243 had timely correction within one year of identifying the noncompliance to the district while 167 have been subsequently corrected, but prior to the submission of this APR.

The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §300.301(c)(1); and (2) has completed the required action, although late, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memo 09-02. Therefore, the State has not demonstrated that it corrected the noncompliance.

The corrective action process requires that districts remedy noncompliant findings when individual student level or policy, procedure and practice noncompliance is found. All district policies, procedures, and practices documents are reviewed every four years or more frequently if data calculations warrant a review.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09):

Explanation of Progress and Slippage

There was an increase from 75 percent in 2007-08 to 87.58 percent in 2008-09. This was due, in part to the addition of a field in the CASEMIS data collection that records information about the reasons students’ assessment appears to be late, but is actually on time. OSEP exceptions to the timeline include: parent refusal to make the child available and any additional state timeline rules.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 11: 60 Day Timeline |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Explore Web-based applications for all components of the monitoring system including 60-day evaluation timeline. | 2005-2010 | CDE staff |
| Analyze data from compliance complaints and all monitoring activities to determine areas of need for technical assistance, in addition to correction of noncompliance. | 2005-2010 | CDE staff |
| Prepare and install initial evaluation compliance reports into the CASEMIS software to enable districts and SELPAs to self-monitor. | 2009 -2010 | CDE staff |
| Prepare and send noncompliance-finding letters based on CASEMIS data to LEAs to reinforce the importance of correcting all non-compliant findings resulting from Verification and Self-review monitoring. | Annually | CDE staff |
| Prepare analysis of existing patterns of recording “date” information in self-reviews and emphasize the importance of accurate completion of “date” fields during SELPA Director meetings and biannual CASEMIS training. | Biannually | CDE staff and SELPA http://www.cde.ca.gov/sp/se/as/caselpas.asp |
| Prepare and send statewide letter regarding the requirements related to initial evaluation. Post initial evaluation policy and technical assistance information on CDE Web site. | Annually | CDE staff |
| Meet with the California Speech and Hearing Association, California School Psychologist Association, SELPA Directors, and other related service organizations to explore issues related to personnel shortages and develop a coordinated action plan to increase the availability of personnel. | Ongoing | CDE staff, California Speech and Hearing Association (CSHA), California Association School Psychologists (CASP), and SELPA Directors |
| Collect data about students whose assessment timeline is affected by a break in excess of 5 days through a survey in the spring 2009 and add to CASEMIS. | Spring 2009 | CDE staff |
| In FFY 2008 -09, CDE completed the collection of census information related to students who exceed the 60 day timeline due to a break of 5 days or more through CASEMIS. | Spring 2009 | CDE staff |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following are being added to address identified slippage:

| ADDED ACTIVITIES– Indicator 11: 60 Day Timeline |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| In collaboration with the California Comprehensive Center, develop and maintain training modules on Standards-based IEPs designed to promote and sustain practices that foster special education/general education collaboration. (Chapter topics: Access, Standards-based IEPs, Grade-level, Standards-based Goals, Service Delivery Models, and Curriculum and Instruction Strategies). | 2009-2010 Ongoing | CDE staff, contractor, California Comprehensive Center |
| Facilitate and provide training, technical assistance in a wide range of research-based practices to assist and train LEAs and the ISES stakeholder group in areas such as Core messages on: - Positive Behavior Supports - Standards-based IEPs - Family-School Partnerships Additional areas of focus: - Quality and number of teachers and other personnel who work with students with disabilities - Coordination of services for students with disabilities, including the behavioral supports that are available. - Participation of parents and family members - Collection and dissemination of data | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) Core messages |

Monitoring Priority: Effective General Supervision Part B / Effective Transition

Indicator 12:  Percent of children referred by Part C prior to age 3, who are found eligible for Part B, and who have an IEP developed and implemented by their third birthdays.

(20 U.S.C. 1416(a)(3)(B))

Measurement: - # of children who have been served in Part C and referred to Part B (LEA notified pursuant to IDEA section 637(a)(9)(A) for Part B eligibility determination.) - # of those referred determined to be NOT eligible and whose eligibilities were determined prior to their third birthdays. - # of those found eligible who have an IEP developed and implemented by their third birthdays. - # of children for whom parent refusal to provide consent caused delays in evaluation or initial services. - # of children who were referred to Part C less than 90 days before their third birthdays. Account for children included in a but not included in b, c, d, or e. Indicate the range of days beyond the third birthday when eligibility was determined and the IEP developed and the reasons for the delays. Percent = [(c) divided by (a – b – d – e)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 100 percent of children referred by IDEA Part C prior to age three and who are found eligible for IDEA Part B will have an IEP developed and implemented by their third birthdays |

Actual Target Data for 2008 (2008-09):

Overall 92.57 percent of children referred by Part C prior to age 3, were found eligible for Part B, and had an IEP developed and implemented by their third birthdays. These data were collected through CASEMIS and data from the Department of Developmental Services. The total number of children served in Part C and referred to Part B for eligibility determination prior to their third birthday was 17,095.

Table 12a summarizes the target data for FFY 2008 (2008-09)

Table 12a

Target Data for FFY 2008 (2008-09): Indicator 12 – C to B Transition)

| Measurement Item | Target Data |
| --- | --- |
| - # of children who have been served in Part C and referred to Part B (LEA notified pursuant to IDEA section 637(a)(9)(A) for Part B eligibility determination.) | 17,095 |
| - # of those referred determined to be NOT eligible and whose eligibilities were determined prior to their third birthdays. | 878 |
| - # of those found eligible who have an IEP developed and implemented by their third birthdays. | 12,286 |
| - # of children for whom parent refusal to provide consent caused delays in evaluation or initial services. | 2,945 |
| Percent of Children referred by Part C prior to age 3, found eligible for Part B, and who had an IEP developed and implemented by their third birthday. (Calculation: Percent = [(c) divided by (a – b – d ] times 100) | 92.57 |

While this does not meet the target, it represents an increase n the percent of children from 80.2 percent in 2007-08 to 92.57 percent in 2008-09.

Range of days beyond third birthday. Table 12b depicts the range of days beyond the third birthday when children were found eligible and had their IEP developed and implemented. Reasons cited for delays included:  late referrals (before third birthday, but with insufficient time to complete the assessment), lack of staff, ineffective tracking systems, student illness, and failure to keep appointments.

Table 12b

Percentage and Number of Days and the Number of Children that were made Eligible for Part B after their Third Birthday and After Transitioning from Part C: Indicator 12 – C to B Transition

| Days from Third Birthday | No. of Children | Percent of All Referrals |
| --- | --- | --- |
| 1 to 14 After | 261 | 1.5 |
| 15 to 30 After | 202 | 1.2 |
| 31 to 60 After | 217 | 1.3 |
| 61 to 90 After | 107 | 0.6 |
| 91 to 180 After | 79 | 0.5 |
| Greater Than 180 After | 120 | 0.7 |

All Verification Reviews and Special Education Self-Reviews included the following item:

| 7-4-1 | Did all students transitioning from early intervention services under Part C have an IEP developed and implemented by the student’s third birthday? |
| --- | --- |

Monitoring findings for FFY 2008 (2008-09)

In 2008-09 there were a total of 854 preschool age children with disabilities (who transitioned from Part C) whose files were reviewed. Of those files, there were 28 found noncompliant related to having an IEP developed and implemented by the third birthday. Using these data, it would appear 96.5 percent of the files reviewed were compliant on this item.

Correction of Noncompliance reported in 2007-08.

There were 167 findings of noncompliance related to transition from Part C to Part B of students with disabilities. These findings were identified through monitoring and dispute resolution processes in 2007-08.

Of the total noncompliance findings, 167 had timely correction within one year of identifying the noncompliance to the district. The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §300.124(b); and (2) has completed the required action, although late, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memo 09-02. Therefore, the State has not demonstrated that it corrected the noncompliance.

The corrective action process requires that districts remedy noncompliant findings when individual student level or policy, procedure and practice noncompliance is found. All district policies, procedures, and practices documents are reviewed every four years or more frequently if data calculations warrant a review.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Discussion of Progress or Slippage

As noted above, there was an increase in the percent of children having an IEP in place by their third birthday from 80.2 percent in 2007-08 to 92.57 percent in 2008-09. This increase is due to changes in the indicator language, increased information about the reasons student evaluations were late, and the elimination of children referred after their third birthday.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 12: Transition Part C to Part B |  |  |
| --- | --- | --- |
| Improvement Activity | Timeline | Resources and Type |
| Meet annually with SELPA, LEA, and Regional Centers to review data and plan for corrective action plans and technical assistance activities related to transition from Part C to Part B, based on APR data. | 2006-2010 | CDE staff; Department of Developmental Services, Early Start, WestEd, and SEEDS http://www.seedsofpartnership.org// |
| Convene ISES stakeholder group to obtain input on aspects of Part C to Part B transition (e.g. moving from family focus to child focus). | 2005-2010 Ongoing | CDE staff; Department of Developmental Services, Early Start, WestEd, and SEEDS http://www.seedsofpartnership.org// |
| Revise CASEMIS to include separate referral and evaluation dates for Part B and Part C. | Continue to update | CDE staff; Department of Developmental Services, and Early Start |
| Participate in OSEP National Early Childhood Conference. | Annually | CDE staff; Department of Developmental Services, Early Start, NECTAC, and OSEP |
| Participate in a joint Transition Project with the Department of Developmental Services, Part C Lead Agency, with the assistance of the WRRC. | 2008-2011 | CDE and DDS staff and Western Regional Resource Center |
| Target symposiums, field meetings, and training on Transition from C to B. | 2008-2011 | CDE and DDS staff and Western Regional Resource Center, SEEDS, and Special Education Early Childhood Administrators Project (SEECAP) http://www.seedsofpartnership.org// |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09

The following are being added to address identified slippage:

| ADDED ACTIVITIES– Indicator 12: Transition Part C to Part B |  |  |
| --- | --- | --- |
| Improvement Activity | Timeline | Resources and Type |
| Add data collection for new measurement element (e) for of children who were referred to Part C less than 90 Days before their third birthdays. | 2010-2011 | CDE staff and SELPA |
| Revise existing C to B Transition Handbook to update and align language in collaboration with Part C lead agency and Part B lead agency. | 2010-2011 | CDE and DDS staff, SEEDS and WestEd http://www.seedsofpartnership.org// |
| Train special education personnel on the Transition Handbook and provide updates at symposiums, workshops and Webinars, and through the use of other Internet technologies. | Ongoing | CDE and DDS staff, SEEDS, and WestEd http://www.seedsofpartnership.org// |
| Update and train personnel on the Special Education Early Childhood Handbooks (birth to 5) which address the following topics: IFSP/IEP, Service Delivery, Interagency Agreements, Transition, Administration, Assessment, and Families. | Ongoing | CDE and DDS staff, SEEDS and WestEd http://www.seedsofpartnership.org// . |
| Continue participating with DDS, Part C lead agency, on the Interagency Coordinating Council (ICC), monitoring activities, symposiums, and planning meetings to build a strong state level community of practice (CoP) | Ongoing | CDE and DDS staff, SEEDS, and WestEd http://www.seedsofpartnership.org// |

Monitoring Priority: Effective General Supervision Part B / Effective Transition

Indicator 13:  Percent of youth with IEPs aged 16 and above with an IEP that includes appropriate measurable postsecondary goals that are annually updated and based upon an age appropriate transition assessment, transition services, including courses of study, that will reasonably enable the student to meet those postsecondary goals, and annual IEP goals related to the student’s transition services needs. There also must be evidence that the student was invited to the IEP Team meeting where transition services are to be discussed and evidence that, if appropriate, a representative of any participating agency was invited to the IEP Team meeting with the prior consent of the parent or student who has reached the age of majority.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(# of youth with IEPs aged 16 and above with an IEP that includes appropriate measurable postsecondary goals that are annually updated and based upon an age appropriate transition assessment, transition services, including courses of study, that will reasonably enable the student to meet those postsecondary goals, and annual IEP goals related to the student’s transition services needs. There also must be evidence that the student was invited to the IEP Team meeting where transition services are to be discussed and evidence that, if appropriate, a representative of any participating agency was invited to the IEP Team meeting with the prior consent of the parent or student who has reached the age of majority) divided by the (# of youth with an IEP age 16 and above)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | One hundred percent of youth aged 16 and above with an IEP will have annual IEP goals and transition services that will reasonably enable the student to meet the postsecondary goals. |

Actual Target Data for 2008 (2008-09):

CDE is not required to report on this indicator in 2008-09, except to report the correction of noncompliance reported to LEAs in 2007-08.

Report on Correction of noncompliance in 2007-08

Monitoring Results in 2007-08. In 2007-08, there were 552 students (16+ years of age) found noncompliant in one or more of the items listed above. There were a total of 1,857 findings of noncompliance. Of the findings related to the 552 students, 1,832 were corrected within one year of identification. All other findings were subsequently corrected in 2008-09.

The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §300.320(b), consistent with OSEP Memo 09-02.

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 13: Secondary Transition |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Use transition data collected through state-funded Workability I grant procedures to ensure programs include the provision of transition services.. | Annually | CDE staff, SELPA, and LEAs |
| Provide CASEMIS training for SELPAS and ongoing technical assistance to ensure reliable and accurate submission of data. | 2005-2010 Ongoing and twice a year trainings | CDE staff, SELPA, and LEAs |
| Develop and implement selected activities related to secondary transition including training to build local capacity, technical assistance, CoP, materials dissemination with emphasis on compliance, guidance based upon exemplary researched based practices, and stakeholder input. | Ongoing | CDE staff, Workability I staff, and field trainers |
| Provide regionalized training and technical assistance regarding elements of transition services, goals and objectives IEP. This is a collaboration, monitoring, training and technical assistance activity to support secondary transition. | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) |
| Use statewide CoP for collaborative efforts related to transition services across multiple agencies (DRS, EDD, SILC, parents, and consumers). | 2005-2011 | CDE staff, Workability I Staff, and NASDSE facilitation for CoP |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09

The following is being added at the recommendation of the improving Special Education Services (ISES) Stakeholder group:

| ADDED ACTIVITIES– Indicator 13: Secondary Transition |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Disseminate and provide training on the Transition Handbook written for students’ parents, and teachers which offers practical guidance and resources to support the transition of students with disabilities as they move into the world of adulthood and/or independent living. In addition the CDE reprinted and distributed 5,000 copies to LEAs and parent organizations free of charge, and posted the Handbook on the Internet along with; PowerPoint training modules, and other training materials. | Ongoing | CDE staff and California Services for Technical Assistance and Training (CalSTAT) Transition to Adult Living: A Guide for Secondary Education |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 15:  General supervision system (including monitoring, complaints, hearings, etc.) identifies and corrects noncompliance as soon as possible, but in no case later than one year from identification.

(20 U.S.C. 1416 [a][3][B])

Measurement: Percent of noncompliance corrected within one year of identification: - number of findings of noncompliance. - number of corrections completed as soon as possible but in no case later than one year from identification. Percent = [(b) divided by (a)] times 100. States are required to use the “Indicator 15 Worksheet” to report data for this indicator (see Attachment A).

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 100 percent of noncompliance will be corrected within one year of identification |

Actual Target Data for 2008 (2008-09):

Table 15a summarizes the data and calculation for the percent of noncompliance corrected within one year of identification (Corrected in 2008-09, data collected in 2007-08).

Table 15a

Percent of Noncompliance Corrected within One Year of Identification:

Indicator 15 – General Supervision

| Item | Number |
| --- | --- |
| a. Number of findings of noncompliance | 32,902 |
| b. Number of corrections completed as soon as possible but in no case later than one year from identification | 33,241 |
| Percent = [(b) divided by (a)] times 100. 32,902/ 33,241 * 100 = 97.99% | 97. 99% |

In 2007-08, 97.99 percent of noncompliance was corrected within one year of identification. For all indicators, findings are reported in the year in which the district was notified of noncompliance. “On time” calculations are based on a span of one year (365 days) from the date that the district was notified of noncompliance findings. For this reason, some of the finding totals cited in prior APRs may not match with this APR because they were reported by initiation date (date of review) rather than the notification date.

Findings for this indicator are based on findings reported by CDE to districts in 2007-08 and include noncompliance identified through onsite monitoring (Verification and Nonpublic School Reviews), Special Education Self-reviews (SESRs), Complaints and Due Process Hearings as well as ongoing data collection, local plan reviews, annual maintenance of effort reviews, and audits related to state and federal special education funds.

The State also verified that each LEA with noncompliance identified in FFY 2007:  (1) is correctly implementing the specific regulatory requirements in 34 CFR §§300.111, 300.201, and 300.301 through 300.311; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the LEA, consistent with OSEP Memorandum 09-02, dated October 17, 2008 (OSEP Memo 09-02).

Verification of both student and district level noncompliance includes the review of:

- Evidence of student level correction;

- Review of policies, procedures, and practices including dissemination and staff training; and

- Review of a new sample of student records

A more stringent level of follow-up review and reporting is required of districts that have previously corrected non-compliance related to this indicator. This is to ensure that LEAs are correctly implementing the specific regulatory requirements.

General procedures for monitoring and correction: As noted in Indicator 15 (General Supervision) in the SPP, CDE has used multiple methods to carry out monitoring responsibilities. These monitoring activities are part of an overall Quality Assurance Process (QAP) designed to ensure that procedural guarantees of the law are followed and that programs and services result in educational benefits to students with disabilities. The CDE uses all of its QAP activities to monitor for procedural compliance and educational benefit. Formal noncompliance may be identified and corrective action plans developed through a wide variety of means, including data collection and analysis, investigation of compliance complaints and due process hearings, and reviewing policies and procedures in local plans. For example, the CDE uses data collected through the CASEMIS to identify districts that are not completing annual reviews of individualized educational programs (IEPs) in a timely way. All of these methods result in formal findings of noncompliance citing specific state and federal regulations and require that a corrective action plan be completed.

In addition to these components of the QAP, there are four types of traditional monitoring review processes:  Facilitated Reviews, Verification Reviews, Special Education Self-Reviews, and Nonpublic School Reviews (both onsite and self-reviews). Each of the formal review processes results in findings of noncompliance at the student and district level. District level findings are made based on a combination of factors including student record reviews, staff and parent interviews, reviews of policies and procedures. All findings require correction. At the student level the district must provide specified evidence of correction within a 45-day time period. It should be noted that some findings are not correctible at the student level (e.g., missed timelines) though student level findings of this type must be corrected and verified at the district level. At the district level, the district must still correct any student findings by providing updated policies, procedures and practices evidence that the new policies, procedures and practices have been disseminated and, in a six-month follow-up review, the district must demonstrate that no new instances of noncompliance in that area have occurred. CDE has a variety of sanctions available to use in situations in which noncompliance goes uncorrected (e.g., special grant conditions, withholding of funds, and court action).

Agencies Monitored. Findings from monitoring sources were reported to 181 school districts, COE and nonpublic schools and agencies. Noncompliant findings related to dispute resolutions were reported to 181 districts and agencies.

Table 15b (Timely Correction of Noncompliance Findings Disaggregated by APR Indicator) depicts the number of noncompliance findings identified for each cluster of APR indicators. Indicators are generally based on the clustering contained in the Part B SPP/APR Related Requirements document. This document identifies those federal regulations that are associated with each of the SPP/APR indicators. The CDE used the Part B SPP/APR Related Requirements document to categorize noncompliance findings from monitoring reviews and from dispute resolutions processes into the appropriate APR indicators. Not all of the noncompliance findings fit into the APR indicators. As a result, Table 15b has an “other” category related to Local General Supervision and another related to qualified personnel.

Table 15b includes information about the general supervision component used to identify the noncompliance (monitoring or dispute resolution). For each indicator the table summarizes the number of LEAs found noncompliant for each indicator, the total number of noncompliance findings, and the number of those findings corrected within one year of the date they were reported to the public.

Table 15b

Timely Correction of Noncompliance Findings Disaggregated by APR Indicator:

Indicator 15 – General Supervision

| Indicator/Indicator Clusters | General Supervision System Components | Number of LEAs Issued Findings in FFY 2007 (7/1/07 to 6/30/08) | (a) Number of Findings of noncompliance identified in FFY 2007 (7/1/07 to 6/30/08) | (b) Number of Findings of noncompliance from (a) for which correction was verified no later than one year from identification |
| --- | --- | --- | --- | --- |
| 1. Percent of youth with IEPs graduating from high school with a regular diploma. 2. Percent of youth with IEPs dropping out of high school. 14. Percent of youth who had IEPs, are no longer in secondary school and who have been competitively employed, enrolled in some type of postsecondary school, or both, within one year of leaving high school. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 52 | 3186 | 3182 |
|  | Dispute Resolution: Complaints, Hearings | 126 | 665 | 574 |
| 3. Participation and performance of children with disabilities on statewide assessments. 7. Percent of preschool children with IEPs who demonstrated improved outcomes. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 59 | 494 | 489 |
|  | Dispute Resolution: Complaints, Hearings | 0 | 0 | 0 |
| 4A. Percent of districts identified as having a significant discrepancy in the rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 44 | 1099 | 1090 |
|  | Dispute Resolution: Complaints, Hearings | 12 | 29 | 25 |
| 5. Percent of children with IEPs aged 6 through 21 -educational placements. 6. Percent of preschool children aged 3 through 5 – early childhood placement. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 173 | 8061 | 7840 |
|  | Dispute Resolution: Complaints, Hearings | 10 | 32 | 29 |
| 7. Percent of parents with a child receiving special education services who report that schools facilitated parent involvement as a means of improving services and results for children with disabilities. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 181 | 2459 | 2429 |
|  | Dispute Resolution: Complaints, Hearings | 36 | 80 | 74 |
| 9. Percent of districts with disproportionate representation of racial and ethnic groups in special education that is the result of inappropriate identification. 10. Percent of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 143 | 3836 | 3776 |
|  | Dispute Resolution: Complaints, Hearings | 0 | 0 | 0 |
| 11. Percent of children who were evaluated within 60 days of receiving parental consent for initial evaluation or, if the State establishes a timeframe within which the evaluation must be conducted, within that timeframe. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 194 | 1114 | 1076 |
|  | Dispute Resolution: Complaints, Hearings | 50 | 223 | 167 |
| 12. Percent of children referred by Part C prior to age 3, who are found eligible for Part B, and who have an IEP developed and implemented by their third birthdays. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 32 | 167 | 167 |
|  | Dispute Resolution: Complaints, Hearings | 0 | 0 | 0 |
| 13. Percent of youth aged 16 and above with IEP that includes coordinated, measurable, annual IEP goals and transition services that will reasonably enable student to meet the post-secondary goals. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 92 | 1843 | 1824 |
|  | Dispute Resolution: Complaints, Hearings | 5 | 14 | 6 |
| Other areas of noncompliance: Indicator 15 Local Monitoring of Procedural Guarantees, Timelines, FAPE and Educational Benefit. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 35 | 8757 | 8752 |
|  | Dispute Resolution: Complaints, Hearings | 99 | 442 | 357 |
| Other areas of noncompliance: Qualified Personnel. | Monitoring Activities: Self-Assessment/ Local APR, Data Review, Desk Audit, On-Site Visits, or Other | 29 | 362 | 370 |
|  | Dispute Resolution: Complaints, Hearings | 10 | 31 | 30 |
| Sum the numbers down Column a and Column b |  |  | 32, 902 | 32,241 |
| Percent of noncompliance corrected within one year of identification = (column (b) sum divided by column (a) sum) times 100.(b) / (a) X 100 |  |  |  | 97.99% |

The overall percentage of noncompliance findings had timely correction within one year of identification decreased only slightly from 98.3 percent in 2007-08 to 97.99 percent in 2008-09. There was a significant decrease in the number of findings from 2007-08 (46,707) to 2008-09 (32,902). This is due, in part, to catching up on the of VR’s and SESR’s schedule. In 2005-06 and 2006-07 the CDE initiated major overhauls of the item tables used in the monitoring software. This was done to align the items to updated IDEA regulations and applicable state laws. As a result, monitoring results, initiated in 2005-06 were reported to districts in 2006-07, along with findings made in 2006-07. In addition, 2007-08 reviews were started later in the program year, and, as a result, some 2007-08 findings were not reported to districts until 2008-09.

Of the 680 findings corrected more than one year after being reported to the district, 533 have been subsequently corrected. Two districts are responsible for the remaining 147 findings. They have been issued sanction letters.

In the FFY 2007 APR, Developmental Centers (state hospitals) operated by the Department of Developmental Services were identified as agencies whose noncompliance was not corrected within one year or by the submission of the APR on February 1, 2009. One of the three findings has been corrected. The remaining two findings related to statewide assessment noncompliance have raised significant issues of jurisdiction and authority under California law. These issues have been resolved and are being addressed through the state interagency agreement process. The preliminary settlement vests responsibility for statewide assessment with County Offices of Education where the state hospitals are located rather than with the Developmental Centers. These issues will not be considered corrected until all students in the Developmental Centers are included in one round of statewide assessments.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2007 (2007-08):

Explanation of Progress or Slippage:

See discussion above.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 15: General Supervision |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| IDEA Final Regulation Training Web cast presented during fall 2006. Web cast archived for continued accessibility and DVD widely distributed. | Ongoing through 2011 | CDE staff and a presentation by Art Cernosia, Esq., a nationally known expert in the IDEA. Free to the public and funded through IDEA funds. |
| Conduct analysis and prepare plans for APR on all general supervision indicator requirements. | July 1, 2007-June 30, 2011 | CDE Staff |
| Develop and maintain IDEA 2004 information Web page with links to important references and resources on the Reauthorization of the IDEA. This activity constitutes Public Reporting/Data Awareness/Data Utilized to Reflect Upon Practice efforts as part of general supervision obligations under of IDEA 2004 | Ongoing update | CDE/SED staff; Web capability of CDE Web page http://www.cde.ca.gov/sp/se/sr/#srinf |
| Provide staff training for corrective actions, timelines, and sanctions. Incorporate notice of potential sanctions in monitoring correspondence. | 2005-2011 Ongoing through 2011 | http://www.cde.ca.gov/sp/se/as/ |
| Recruit candidates and hold civil service examinations to fill unfilled vacancies with new staff, retired annuitants, or visiting educators. This activity is intended to ensure that CDE maintains an adequate number of qualified staff to support the work and activities (monitoring and enforcement as part of general supervision) of the Special Education Division. | Ongoing to 2011 | CDE staff http://www.cde.ca.gov/sp/se/sr/#srinf http://www.cde.ca.gov/re/di/jb/index.asp |
| Continue to update and keep current the interagency agreement with the Department of Developmental Services (DDS). | 2010 | CDE staff and Department of Developmental Services |
| Prepare and maintain a compliance tracking application for use by managers and individual staff, which includes a “tickler” notification system. | 2010 Ongoing | CDE staff http://www.cde.ca.gov/sp/se/sr/#srinf http://www.cde.ca.gov/sp/se/ds/ |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following is being added to address identified slippage:

| ADDED ACTIVITIES– Indicator 15: General Supervision |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Provide targeted training on implementing the IDEA 2004 including court cases and legal interpretations for CDE staff. | November 2009 | CDE staff with a presentation by Perry Zirkel, Esq., nationally known expert in IDEA. |
| Conduct analysis of improvement activities by indicator to: - relate them more closely with the indicators - identify more targeted activities - show the impact of change in data | Begin Spring 2010 and Ongoing | CDE staff, ISES, outside contractors and other divisions within the CDE (Accountability, Data Management, Standards and Assessments, Program Improvement, English Learners, Department of Developmental Services, Office of Administrative Hearings, Mental Health, WestEd, California Comprehensive Center, Western Regional Resource Center, SEEDS, and Desired Results Project). http://www.cde.ca.gov/sp/se/sr/ |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 16:  Percent of signed written complaints with reports issued that were resolved within 60-day timeline or a timeline extended for exceptional circumstances with respect to a particular complaint, or because the parent (or individual or organization) and the public agency agree to extend the time to engage in mediation or other alternative means of dispute resolution, if available in the State.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(1.1(b) + 1.1(c)) divided by 1.1] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 100 percent of written complaints resolved within 60-day timeline, including a timeline extended for exceptional circumstances with respect to a particular complaint. |

Actual Target Data for 2008 (2008-09):

| Report of Dispute Resolution Under Part B of the Individuals with Disabilities Education Act Complaints, Mediations, Resolution Sessions, and Due Process Hearings |  |
| --- | --- |
| SECTION A: Signed, written complaints |  |
| (1) Signed, written complaints total | 838 |
| (1.1) Complaints with reports issued | 679 |
| (a) Reports with findings | 679 |
| (b) Reports within timeline | 665 |
| (c) Reports within extended timelines | 14 |
| (1.2) Complaints withdrawn or dismissed | 159 |
| (1.3) Complaints pending | 0 |
| (a) Complaint pending a due process hearing | 0 |

The table indicates that the CDE resolved 100 percent of written complaints within the 60-day timeline and extended timelines for exceptional circumstances with respect to a particular complaint.

Calculation:  [(665+ 14) / 679]*100 = 100 percent

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09):

The CDE achieved the target percentage of written complaints resolved within the 60-day timeline and extended timelines. This demonstrates maintenance of the 100 percent timely completion rate from last reporting year (2007-08), and demonstrates continuous improvement from the two previous reporting periods (i.e., 93 percent in 2006-2007, and 84 percent in 2005-2006).

Each the five regional Focused Monitoring and Technical Assistance (FMTA) units continue to complete the complaints investigation and corrective action monitoring processes, including:  investigating of allegations of noncompliance; issuing investigatory reports with corrective actions; monitoring of school district completion of corrective actions; and closing the complaint file. The CDE continually monitors the completion of each step to ensure timely completion of each step in the process.

Improvement Activities for 2008 (2008-09):

The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITES – Indicator 16: Complaints |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Develop an integrated database to proactively identify upcoming corrective actions across all components of the monitoring system. This activity supports the continued effort to calculate and provide valid and reliable data for monitoring and enforcement as part of general supervision. | Ongoing | CDE staff http://www.cde.ca.gov/sp/se/ds/ |
| Continue to cross-unit train for complaint investigations and other monitoring activities to focus on inter-rater reliability and consistency. This activity continues to improve the expertise of CDE staff in monitoring and enforcement as part of general supervision. | Ongoing | CDE staff http://www.cde.ca.gov/sp/se/as/ |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

The following is being added at the recommendation of the improving Special Education Services (ISES) Stakeholder group:

| ADDED ACTIVITES – Indicator 16: Complaints |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Provide targeted training on implementing the IDEA 2004 including clarifying court cases and legal interpretations for CDE staff. | November 2009 | CDE staff with a presentation by Perry Zirkel, Esq., nationally known expert in IDEA. |
| Provide ‘legal rounds’ with the Legal Audits and Compliance Branch for Special Education Division staff on legal issues related to special education legal issues, complaints and noncompliance. |  | Special Education Division and Legal Audits and Compliance Branch http://www.cde.ca.gov/re/di/or/lacbranch.asp |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 17:  Percent of adjudicated due process hearing requests that were adjudicated within the 45-day timeline or a timeline that is properly extended by the hearing officer at the request of either party or in the case of an expedited hearing, within the required timelines.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(3.2(a) + 3.2(b)) divided by 3.2] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | One hundred percent of due process hearing requests will be fully adjudicated within the 45-day timeline or a timeline that is properly extended by the hearing officer at the request of either party. |

Actual Target Data for 2008 (2008-09):

Table 7 reflects the Required 618 Data Collection Section C regarding hearing requests

Table 7

| Section C: Due Process Complaints |  |
| --- | --- |
| (3) Due process complaints total | 2,709 |
| (3.1) Resolution meetings | 530 |
| (a) Written settlement agreements | 140 |
| (3.2) Hearings (fully adjudicated) | 104 |
| (a) Decisions with timeline (including expedited) | 12 |
| (b) Decisions within extended timeline | 84 |
| (3.3) Resolved without a hearing | 2,605 |

Calculation:  [(12+84) / 104] *100 = 92 percent

Ninety-two percent of due process hearing requests were fully adjudicated within the 45-day timeline or within a time line that was properly extended by the hearing officer at the request of either party.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09):

The target of 100 percent was met in 2006-07 and 2007-08. California did not meet the target of 100 percent in 2008-09. The decrease to ninety-two percent was due to eight hearing requests not adjudicated within the 45-day time line or within a time line that was properly extended by the hearing officer at the request of either party.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 17: Hearings |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Obtain data on resolution sessions and settlement agreements deriving solely from those sessions directly from school districts with due process fillings during 2008-09. | Ongoing | CDE staff and OAH staff and its advisory group |
| The OAH will consult with its advisory group in areas such as: revisions to the OAH Web site, forms, documents, scheduling procedures, staff training, training materials, parent procedure manual, consumer brochure, outreach to families and students, and proposed revisions to laws and rules. | 2008-2011 Ongoing | CDE staff and contractors OAH staff and its advisory group |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

[If applicable]

The following is being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 17: Hearings |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Conduct a records review at OAH as part of CDE's efforts to implement recommendations of the Bureau of State Audits (BSA) report 2008-09 on CDE and to determine how it is handling oversight of the special education hearings and mediation process. This review is part of an on-going monitoring activity as a result of the BSA report and constitutes the final review. | 2009-2011 | CDE staff and OAH staff and its advisory group |
| Utilization of a monitoring system as well as the letters to districts, are part of the on going and required training agenda for staff involved in due process efforts at OAH. Training sessions are planned through mid March or April, 2010. | 2009-2011 | CDE staff and OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 18:  Percent of hearing requests that went to resolution sessions that were resolved through resolution session settlement agreements.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = (3.1(a) divided by 3.1) times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 67 percent of hearing requests that went to resolution sessions were resolved through resolution session settlement agreements. |

Actual Target Data for 2008 (2008-09):

Table 7 of the Required 618 Data Collection Section C Regarding Hearing Requests

| Section C: Due Process Complaints |  |
| --- | --- |
| (3) Due process complaints total | 2,709 |
| (3.1) Resolution meetings | 530 |
| (a) Written settlement agreements | 140 |
| (3.2) Hearings (fully adjudicated) | 104 |
| (a) Decisions with timeline (including expedited) | 12 |
| (b) Decisions within extended timeline | 84 |
| (3.3) Resolved without a hearing | 2,605 |

Calculation:  (140/530) *100 = 26 percent

Twenty six percent of hearing requests that went to resolution sessions were resolved through resolution session settlement agreements.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09):

In 2008-09, the target was that 67 percent of hearing requests that went to resolution sessions would be resolved through settlement agreements. California did not meet this target. The actual percentage of hearing requests that were resolved through resolution session agreements was 26 percent. This was lower than 2007-08, when 40 percent of the hearing requests were resolved through resolution session agreements. This slippage was due to a decrease in the number of resolution meetings and written settlement agreements.

Office of Administrative Hearing (OAH) recently implemented a process wherein letters were sent to school districts to prompt them to report if a resolution session was held. OAH anticipates that this number will increase in 2009-2010, as the letter notification process was implemented in the later half of 2008-2009.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITES – Indicator 18: Resolutions |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Obtain data on resolution sessions and settlement agreements deriving solely from those sessions directly from school districts with due process filings during 2008-09. | Ongoing | CDE staff and OAH staff and its advisory group |
| The OAH will consult with its advisory group in areas such as: revisions to the OAH Web site, forms, documents, scheduling procedures, staff training, training materials, parent procedure manual, consumer brochure, outreach to families and students, and proposed revisions to laws and rules. | 2008-2011 | CDE staff and contractors OAH staff and its advisory group |
| CDE and OAH will collaborate to investigate circumstances influencing the decline in resolution sessions resolved through settlement agreements. | 2008-2011 | CDE staff and contractors OAH staff and its advisory group |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

[If applicable]

The following is being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 18: Resolutions |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Conduct records review at OAH as part of CDE's efforts to implement recommendations of the Bureau of State Audits (BSA) report 2008-09 on CDE and how it is handling oversight of the special education hearings and mediation process. This review is part of an on-going monitoring activity as a result of the BSA report and constitutes the final review. | 2009-2011 | CDE staff and contractors OAH staff and its advisory group |
| Utilization of a monitoring system as well as the letters to districts, are part of the on going and required training agenda for staff involved in due process efforts at OAH. Training sessions are planned through mid March or April, 2010. | 2009-2011 | CDE staff and contractors OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 19:  Percent of mediations held that resulted in mediation agreements.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(2.1(a)(i) + 2.1(b)(i)) divided by 2.1] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | At least seventy-five percent of mediation conferences will result in mediation agreements. |

Actual Target Data for 2008 (2008-09):

Table 7 below, includes the IDEA – required data for mediation requests. A full copy of the OSEP’s Table 7 is attached to this APR.

Table 7

| Section B: Mediation Requests |  |
| --- | --- |
| (2) Mediation requests total | 2,706 |
| (2.1) Mediations held | 1,585 |
| (a) Mediations held related to due process | 1,406 |
| (i) Mediation agreements | 852 |
| (b) Mediations held not related to due process | 179 |
| (i) Mediation agreements | 100 |
| (2.2) Mediations not held (including pending) | 1,121 |

Calculation:  [(852+100) /1585] *100 = 60 percent

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09):

The target for 2008-09 was at least 75 percent of mediation conferences will result in mediation agreements. California did not meet its target. The percent of mediation conferences resulting in mediation agreements was 60 percent. The measurement was lower than 2007-08, when 74 percent of mediation conferences resulted in mediation agreements. This is due to the increased of number of mediations held from the previous year (2007-08 1,034, 2008-09 1,585).

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 19: Mediations |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Implement standards for the training of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH staff and its advisory group |
| Implement standards for the qualifications of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH staff and its advisory group |
| Implement standards for the supervision of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH staff and its advisory group |
| The OAH will consult with its advisory group in areas such as: revisions to the OAH Web site, forms, documents, scheduling procedures, staff training, training materials, parent procedure manual, consumer brochure, outreach to families and students, and proposed revisions to laws and rules. | Ongoing | CDE staff and contractors OAH staff and its advisory group |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)

[If applicable]

The following is being added to address identified slippage:

| ADDED ACTIVITIES – Indicator 19: Mediations |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Conduct training sessions for staff and LEAs on dispute resolution and mediations on an ongoing basis. | 2009-2011 | CDE staff and OAH staff and its advisory group |
| Utilization of a monitoring system as well as the letters to districts, are part of the on going and required training agenda for staff involved in due process efforts at OAH. | 2009-2011 | CDE staff and OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 20:  State reported data (618 and State Performance Plan and Annual Performance Report) are timely and accurate.

(20 U.S.C. 1416(a)(3)(B))

Measurement: State reported data, including 618 data, State Performance Plan, and Annual Performance Reports, are: - Submitted on or before due dates (February 1 for child count, including race and ethnicity; placement; November 1 for exiting, discipline, personnel and dispute resolution; and February 1 for Annual Performance Reports and assessment); and - Accurate, including covering the correct year and following the correct measurement. States are required to use the “Indicator 20 Scoring Rubric” for reporting data for this indicator (see Attachment B).

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2008 (2008-09) | 20A. One hundred percent of state-reported data, including 618 data and APRs are submitted on time and are accurate. 20B. One hundred percent of the SELPAs will submit accurate data to CDE in a timely manner. |

Actual Target Data for 2008 (2008-09):

The overall percentage for Indicator 20 is 97.62 percent (see attachment 20a – Part B Indicator 20 Rubric).

Timeliness – CDE submitted all required IDEA related data through two systems: the Education Data Exchange Network (EDEN) and through the OSEP’s Data Analysis System (DANS). One report was late. Table 20a depicts due dates and submission dates for each of the federal data tables.

# Table 20a

Submission Dates for 2008-09 618 Data Reports): Indicator 20a – State Reported Data and Reports

|  | Due Date | Submission Date | On Time |
| --- | --- | --- | --- |
| Table 1 | February 1, 2009 | February 1, 2009 | Yes |
| Table 2 | November 1, 2009 | October 30, 2009 | Yes |
| Table 3 | February 1, 2008 | January 30, 2008 | Yes |
| Table 4 | November 1, 2008 | October 30, 2008 | Yes |
| Table 5 | November 1, 2008 | October 30, 2008 | Yes |
| Table 6 | February 1, 2008 | January 30, 2008 | Yes |
| Table 7 | November 1, 2008 | November 19, 2008 | No |

Data Accuracy: The data collection software for the State, CASEMIS, includes data edits and logical checks in the verification process to ensure data accuracy. In addition the CASEMIS program provides reports during the verification process that identifies further potential discrepancies that cannot be detected using logical data edits and checks.

CDE staff collected and reviewed potential anomaly data from SELPAs. CDE staff also reviewed and evaluated data submitted in any modified CASEMIS data fields. No data needed to be resubmitted to OSEP or EDEN due to inaccurate data.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2008 (2008-09:

The CDE conducted a number of improvement activities in 2008-09. Training regarding the CASEMIS data collection, the State Performance Plan, compliance determinations and disproportionality were conducted onsite at SELPA Director meetings and via Webinar. The CDE modified the data collection parameters to conform to changes in the 618 data collection and guidance provided by the OSEP. The CDE modified it technical assistance guide and CASEMIS software to update the data collection, improve error trapping, and enhance the accountability tools.

Explanation of Slippage:

The percent of state-reported data, including 618 data and APRs submitted on time and are accurate, fell from 100 percent in 2007-08 to 97.62 percent in 2008-09. One reports was submitted late due to CDE staff error.

Improvement Activities for 2008 (2008-09): The following activities were implemented and will continue in 2009-10:

| CONTINUING ACTIVITIES – Indicator 20: State Reported Data |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Modify validation codes and develop prototype reports. This activity supports general IDEA 2004 requirements. | 2005-2011 Ongoing as needed | CDE staff in collaboration with Accountability and Data Management http://www.cde.ca.gov/sp/se/ds/ |
| Provide statewide CASEMIS training for SELPAs. This activity supports data collection through CASEMIS and provides training and technical assistance. | 2005-2011 Annually Fall and Spring as necessary | CDE staff, SELPA, LEAs http://www.cde.ca.gov/sp/se/ds/ |
| Provide ongoing technical assistance to ensure reliable and accurate submission of data. This activity supports data collection through CASEMIS and provides training and technical assistance. | 2005-2011 Ongoing throughout the year | CDE staff http://www.cde.ca.gov/sp/se/ds/ |
| Improve and expand anomaly analysis and reporting. This activity supports general IDEA 2004 requirements. | Began 2004 and continuing 2014 | CDE staff http://www.cde.ca.gov/sp/se/ds/ |
| Participation, development, implementation and monitoring of Highly Qualified Teachers (HQTs) under ESEA and IDEA 2004. This activity supports: stakeholder, public reporting/data awareness/data used to reflect upon practice and compliance. | Began 2004 and continuing 2014 | CDE Professional Development and Special Education Divisions |
| Provide increased technical assistance regarding data entry particularly for data fields concerning referral, assessment, IEP, and entry dates. | Ongoing throughout the year and continuing 2014 | CDE staff |
| Work with SELPAs/LEAs to ensure comprehensive use of valid school codes and unique student identifiers (Statewide Student Identifiers (SSID)). This activity supports: stakeholders, public reporting/data awareness/data used to reflect upon practice and compliance. | Ongoing and provided throughout the year | CDE staff and contractors |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2008 (2008-09)
[If applicable]

Attachment 20a - Part B Indicator 20 Data Rubric

| Part B Indicator 20 - SPP/APR Data |  |  |  |
| --- | --- | --- | --- |
| APR Indicator | Valid and reliable | Correct calculation | Total |
| 1 | 1 |  | 1 |
| 2 | 1 |  | 1 |
| 3A | 1 | 1 | 2 |
| 3B | 1 | 1 | 2 |
| 3C | 1 | 1 | 2 |
| 4A | 1 | 1 | 2 |
| 5 | 1 | 1 | 2 |
| 7 | 1 | 1 | 2 |
| 8 | 1 | 1 | 2 |
| 9 | 1 | 1 | 2 |
| 10 | 1 | 1 | 2 |
| 11 | 1 | 1 | 2 |
| 12 | 1 | 1 | 2 |
| 13 | NA | NA | 0 |
| 14 | NA | NA | 0 |
| 15 | 1 | 1 | 2 |
| 16 | 1 | 1 | 2 |
| 17 | 1 | 1 | 2 |
| 18 | 1 | 1 | 2 |
| 19 | 1 | 1 | 2 |
|  |  | Subtotal | 34 |
| APR Score Calculation | Timely Submission Points (5 pts for submission of APR/SPP by February 2, 2009) |  | 5 |
|  | Grand Total |  | 39.00 |

| Part B Indicator 20 - 618 Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Table | Timely | Complete Data | Passed Edit Check | Responded to Date Note Requests | Total |
| Table 1 – Child Count Due Date: 2/1/08 | 1 | 1 | 1 | 1 | 4 |
| Table 2 – Personnel Due Date: 11/1/08 | 1 | 1 | 1 | N/A | 3 |
| Table 3 – Ed. Environments Due Date: 2/1/08 | 1 | 1 | 1 | 1 | 4 |
| Table 4 – Exiting Due Date: 11/1/08 | 1 | 1 | 1 | N/A | 3 |
| Table 5 – Discipline Due Date: 11/1/08 | 1 | 1 | 1 | N/A | 3 |
| Table 6 – State Assessment Due Date: 2/1/09 | 1 | NA | NA | N/A | 1 |
| Table 7 – Dispute Resolution Due Date: 11/1/08 | 0 | 1 | 1 | N/A | 2 |
|  |  |  |  | Subtotal | 21 |
|  |  |  |  |  | 37.14 |

| ## Indicator # 20 Calculation |  |
| --- | --- |
| ## A. APR Grand Total | ## 39.00 |
| ## B. 618 Grand Total | ## 37.14 |
| ## C. APR Grand Total (A) + 618 Grand Total (B) = | ## 76.14 |
| ## Total N/A in APR | ## 0 |
| ## Total NA in 618 | ## 0 |
| ## Base | ## 78.00 |
| ## D. Subtotal (C divided by Base*) | ## 0.976 |
| ## E. Indicator Score (Subtotal Dx100) = | ## 97.62 |

## Attachment 20b

CASEMIS Data Accuracy

## System Features

The major features of the CASEMIS software are: (1) to extract student level data for various reporting cycles; (2) to verify data files and generate error, warning, and unextracted records reports; (3) to generate summary reports from various data tables; and (4) to generate the data Certification Report.

The file extraction component of the CASEMIS creates new files by copying records from source data files maintained by the LEA or SOP. This process requires that the LEA source data files have the same data fields and codes as in the 2008-09 CASEMIS database structure. New files are generated to meet the appropriate criteria for various reporting requirements (see Chapter IV).

The Verification routine checks the data fields in the data files for any logical inconsistency and produces a report of errors, warnings, and unextracted records (if any). The errors must be corrected and the warnings must be verified prior to submitting data to the Department.

The report generation component prepares various reports by SELPA, by district, or by site within the SELPA, according to the format specified by the CDE. Additionally, the system generates summary reports by SELPA, and by districts,

When the data files are verified and determined to be error-free, the user may upload the data files to the CDE via the CASEMIS secured Web site available in the “Upload Data File” option. The user can generate a Certification Report using the existing data files on the computer and fax a signed copy to CDE.

In addition, the CASEMIS software offers a set of Tools that are helpful for editing the data files. The utilities contain the latest information on the SELPA and district configuration, file and manipulation options.

## Errors and Warnings

CASEMIS software generates three types of errors and warnings while verifying student level data tables. These are: (1) file verification errors, (2) file verification warnings, and (3) warnings for possible duplicate records.

These errors and warnings are listed in numerical order with explanations of the message and how to correct them. All errors must be corrected and the warning messages must be verified to make sure they are not errors.

### File Verification Errors

| Error | Error Message and Explanation |
| --- | --- |
| D911 | DUPLICATE STUDENT NAME, BIRTHDATE, GENDER The student has the same LAST_NAME, FIRST_NAME, BIRTHDATE, and GENDER as another student in the data table. Please verify all other information in the record for these students and make sure they are not the same student. If the records are about the same student, remove all but one record on the student from the table. |
| E100 | SELPA_CODE IS IN ERROR The entry in the field SELPA_CODE is not one of the codes listed, or the field is blank. Enter the correct four-digit code for your SELPA or SOP. |
| E101 | SELPA_FROM CODE IS IN ERROR The entry in the field SELPA_FROM is not one of the codes listed. Enter the correct code from the SELPA code list. |
| E102 | DIST_SERV CODE IS IN ERROR The entry in the field DIST_SERV is not a valid district/site code, or the field is blank. Please verify the entry against the list of districts under this SELPA/SOP and enter the correct seven-digit DIST_SERV code (2-digit county code plus 5-digit district code). You may obtain the correct county-district code from the California Public School Directory. |
| E103 | DIST_RESI CODE IS IN ERROR The entry in the field DIST_RESI is not a valid district code or the field is blank. Please verify the code against the CDS (county-district-school) codes published in the California Public School Directory and enter the correct code. |
| E104 | STUDENT_ID IS BLANK There is no entry in the field STUDENT_ID. This field must contain a student identifier, assigned by the SELPA or SOP. |
| E105 | DUPLICATE STUDENT, SEE RECORD NNNNNN The entry in the field STUDENT_ID is the same as in another record in the file. The entry in the field STUDENT_ID must be unique -- no two students in the same SELPA/SOP can have the same code in the field STUDENT_ID. |
| E106 | SSN CODE IS IN ERROR The entry in the field SSN (social security number) is not a valid number. The entry must have only numeric data. Please enter correct social security number. |
| E107 | DUPLICATE SSN, SEE RECORD NNNNNN The entry in the field SSN (social security number) is the same as in another record in the file. The SSN must be unique -- no two students may have the same social security number. |
| E108 | REPT_DATE IS NOT MM/DD/CCYY The entry in the field REPT_DATE is not one of the dates for the state reporting requirements, or the field is blank. See Field Detail in Chapter II for correct reporting dates under this field. Enter appropriate date to correct the error. |
| E109 | SCH_CODE IS BLANK The entry in the field SCH_CODE is blank. This field must have a seven-digit school code from the California Public School Directory or California Private School Directory. If a numeric code for a school of attendance is not available from the above two documents, enter the first seven letters of the name of the school. |
| E110 | SCH_TYPE CODE IS IN ERROR The entry in the field SCH_TYPE is not one of the codes listed for the field. Please enter correct code. |
| E111 | LAST_NAME IS BLANK OR IN ERROR The entry in the field LAST_NAME is blank or the name starts with a blank or includes a special character. Enter the correct last name. |
| E112 | FIRST_NAME IS BLANK OR IN ERROR The entry in the field FIRST_NAME is blank or the name starts with a blank or includes a special character. Enter the correct first name. |
| E113 | BIRTHDATE IS BLANK OR IN ERROR There are no data in the field BIRTHDATE or the entry in the field is not a valid date. Enter the correct date in this field. |
| E114 | BIRTHDATE IS AFTER REPORTING DATE The entry in the field BIRTHDATE is after REPT_DATE. BIRTHDATE can never be after the reporting date. Enter correct date(s) in either or both fields. |
| E115 | AGE IS 23 OR OVER FOR ACTIVE STUDENT The age of an active student (who is still in the program) computed as of the REPT_DATE cannot be 23 years or more. If the BIRTHDATE is in error, enter the correct date in the BIRTHDATE field. If, however, the student is over age 22, the student can no longer be an active student; in that case, exit the student with an appropriate date in the field EXIT_DATE. |
| E116 | AGE IS OVER 23 UPON EXIT The age of the student is over 23 as of the EXIT_DATE. A student can, at most, be 23 years old upon exit from special education. If the BIRTHDATE is incorrect, causing this error, enter correct BIRTHDATE. If the EXIT_DATE is incorrect, enter the correct EXIT_DATE. |
| E117 | BIRTHDATE IS AFTER EXIT_DATE The entry in the field BIRTHDATE is after EXIT_DATE. BIRTHDATE cannot be after exit date. Enter correct date(s) in one or both fields. |
| E118 | GENDER IS NOT M OR F The entry in the field GENDER is not "M" or "F". Enter correct entry in the field. |
| E119 | ETHNICITY CODE IS IN ERROR The ETHNICITY (1-4) code is not one of those listed under this field. Enter the correct code in this field. ETHNICITY1 is a mandatory field. ETHNICITY (2-4) code is not a valid code. Use a code from the list or if there are not other ethnicities to report, use a blank. |
| E120 | EL CODE IS IN ERROR The entry in the field English Learner is not "Y" or "N". Enter the correct code in this field. |
| E121 | EL TRUE FOR NATIV_lANG ENGLISH The entry in the field English Learner is "Y", while the entry in the field NATIV_LANG is "00" or blank (English). A student cannot be limited English proficient, if NATIV_LANG is English. Enter the correct code in EL and/or NATIV_LANG field(s). |
| E122 | NATIV_LANG CODE IS IN ERROR The NATIV_LANG code is not one of those listed under this field. Enter the correct code in this field. |
| E123 | MIGRANT CODE IS IN ERROR The entry in the field MIGRANT is not "Y" or "N". Enter the correct code in this field. |
| E124 | RESID_STAT CODE IS IN ERROR The RESID_STAT code is not one of those listed under this field. Enter the correct code in this field. |
| E125 | ENTRY_DATE IS BLANK OR IN ERROR There are no data in the field ENTRY_DATE or the entry in the field is not a valid date. Enter the actual of first entry into special education in this field. |
| E126 | ENTRY_DATE IS BEFORE BIRTHDATE The date in the field ENTRY_DATE is before BIRTHDATE. Entry date cannot be before BIRTHDATE. Enter correct date(s) in ENTRY_DATE and/or BIRTHDATE field(s). |
| E127 | ENTRY_DATE IS AFTER REPORTING DATE The date in the field ENTRY_DATE is after REPT_DATE. Entry date cannot be after the reporting date. Enter correct date(s) in ENTRY_DATE and/or REPT_DATE field(s). |
| E128 | LAST_IEP IS BLANK OR IN ERROR There are no data in the field LAST_IEP or the entry in the field is not a valid date. Enter the correct date of the last IEP meeting in this field. |
| E129 | LAST_IEP IS BEFORE BIRTHDATE The date in the field LAST_IEP is before BIRTHDATE. LAST_IEP cannot be before BIRTHDATE. Enter correct date(s) in LAST_IEP and/or BIRTHDATE field(s). |
| E130 | LAST_IEP MUST BE AN ACTUAL DATE The date in the field LAST_IEP is a future date or projected date, based on the calendar and clock in your computer. The date of last IEP meeting must be an actual date that took place in the past -- not a meeting date in the future. Enter the latest IEP meeting date in this field. |
| E131 | LAST_EVAL IS BEFORE BIRTHDATE The date in the field LAST_EVAL is before BIRTHDATE. The date of last evaluation cannot be before BIRTHDATE. Enter correct date(s) in LAST_EVAL and/or BIRTHDATE field(s). |
| E132 | LAST_EVAL MUST BE AN ACTUAL DATE The date in the field LAST_EVAL is a future date or projected date, based on the calendar and clock in your computer. The date of last evaluation must be an actual date that took place in the past -- not a projected date in the future. Enter the latest evaluation date in this field. |
| E133 | LAST_EVAL IS BLANK OR IN ERROR There are no data in the field LAST_EVAL or the entry in the field is not a valid date. Enter the correct date of the last evaluation in the field. |
| E134 | DISABILIT1 CODE IS IN ERROR The DISABILIT1 code is not of the listed under this entry. Enter a correct code in the field. |
| E135 | GRADE IS IN ERROR The GRADE code is not one of those listed under this field. The entry in this field must be 01-18. Enter the correct code in this field. |
| E136 | GRADE IS GG FOR AGE AA The entry in the field GRADE is "13" (12+/transition) for age under 16. It is highly unlikely for a special education student under 16 to be in a community college or in a postsecondary program. Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E137 | GRADE IS GG FOR AGE AA The student is at least three years younger than the normal age for the reported GRADE. It is highly unlikely for a special education student of age "AA" to be in GRADE "GG". Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E138 | GRADE IS GG FOR AGE AA The student is at least five years older than the normal age for the reported GRADE. It is highly unlikely for a student of age "AA" to be in GRADE "GG". Enter the correct code(s) in GRADE and/or BIRTHDATE. You may also use code "15" (ungraded) to correct the error. |
| E139 | AGE IS AA FOR GRADE INFANT The student is more than four years old for infant GRADE. Infant GRADE is limited to age group 0-2 years only. Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E140 | GRADE IS PRESCHOOL FOR AGE AA The student is less than two or more than seven years old for preschool GRADE. Preschool GRADE is limited to age group 3-5 years only. Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E141 | GRADE IS KINDERGARTEN FOR AGE AA The student is less than three years old for kindergarten. Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E142 | GRADE IS KINDERGARTEN FOR AGE AA The student is more than ten years old for kindergarten. Enter the correct code(s) in GRADE and/or BIRTHDATE. |
| E149 | DUPLICATE ETHNICITY CODES Two or more of the entries in the fields ETHNICITY1-4 have the same code. An ethnicity code may only be used once per student. Please remove one or more of the duplicate codes. Or, if one or more codes are in error please enter correct code(s). |
| E150 | EXIT_DATE IS BEFORE ENTRY_DATE The date in the field EXIT_DATE is before ENTRY_DATE. A student can not exit from the program before entering the program. Enter correct date(s) in EXIT_DATE and/or ENTRY_DATE field(s). |
| E151 | EXIT_DATE IS BEFORE REPORTING DATE The date in the field EXIT_DATE is before REPT_DATE. For the December enrollment reports, an active student can not exit before the reporting date. Enter correct date(s) in EXIT_DATE and/or REPT_DATE field(s). |
| E152 | EXIT_DATE MUST BE AN ACTUAL DATE The date in the field EXIT_DATE is a future date according to the calendar and clock in the computer. By definition, an exit date is an actual date of exit from the program -- not a projected date of exit. Enter the actual exit date in the field EXIT_DATE. |
| E153 | NO EXIT_DATE FOR EXIT_RESON NN There is no entry in the field EXIT_DATE but there is an entry "NN" in the field EXIT_RESON. A student can have an exit reason only after the student has exited the program. Enter the exit date in the field EXIT_DATE or if the student has not exited the program, leave EXIT_RESON field blank. |
| E154 | EXIT_DATE IS BEFORE MM/DD/CCYY The date in the field EXIT_DATE is before the starting date "MM/DD/CCYY" of the school year in the End-of-Year data file. A student may not have exited before the school year to be in the End-of-Year data file. Enter the correct EXIT_DATE or remove the record from the End-of-Year data file. |
| E155 | EXIT_RESON CODE IS IN ERROR The entry in the field EXIT_RESON is not one of those listed under this field. Enter the correct code in EXIT_RESON field. |
| E156 | STUDENT GRADUATING AT AGE NN The entry in the field EXIT_RESON is "71" (graduated from high school with diploma) or "72" (graduated from high school certificate of completion or other than diploma.) or “81” (GED) for a student under age 16. It is highly unlikely for a student to graduate under age 16. If the BIRTHDATE is incorrect, causing this error, enter the correct BIRTHDATE. Otherwise, enter the correct code in the field EXIT_RESON. |
| E157 | STUDENT AGE:NN MAX AGE TO EXIT >=21 The entry in the field EXIT_RESON is "73" (maximum age) for age less than 21. A student exiting special education as a result of reaching maximum age must be of age 21 or more. Enter the correct code in the field EXIT_RESON. If the BIRTHDATE is in error, enter the correct BIRTHDATE. |
| E158 | LAST_IEP IS AFTER EXIT_DATE The entry in the field LAST_IEP is after EXIT_DATE. The LAST_IEP date must be before EXIT_DATE for a student. Please verify the date(s) and/or correct the error(s). |
| E159 | LAST_EVAL IS AFTER EXIT_DATE The entry in the field LAST_EVAL is after EXIT_DATE. The LAST_EVAL date must be before EXIT_DATE for a student. Please verify the date(s) and/or correct the error(s). |
| E160 | REFR_DATE IS BEFORE BIRTHDATE The entry in the field REFR_DATE is before the date in the field BIRTHDATE. A student cannot be referred for determining eligibility for special education before birthdates. Please verify the entries in these two fields and correct the error. |
| E161 | REFR_DATE IS AFTER REPT_DATE The entry in the field REFR_DATE is after the date in the field REPT_DATE. If a student is referred after the reporting date, the student may not be part of the data file for the reporting cycle. Please enter correct date(s) or remove the record from the data table. |
| E162 | REFR_DATE IS BLANK FOR INFANT There is no entry in the field REFR_DATE for an infant (age 0-2). Please enter the referral date for the infant or if the BIRTHDATE of the student is incorrect, enter the correct birth date. |
| E163 | SOLE_LOW CODE IS IN ERROR The entry in the field SOLE_LOW is not one of the codes on the list under this data field for an infant (age 0-2) who has a low-incidence disability (Hearing Impairment, Deafness, Visual Impairment, Orthopedic Impairment or Deaf-blindness) in the field DISABILIT1. If the entry in the field DISABILIT2 is not “220”, “230”, “250”, “270” or “300”, please leave this field (SOLE_LOW) blank. |
| E164 | FEDSET_PRS CODE IS IN ERROR The entry in the field FEDSET_PRS is not one of the codes on the list under this data field. Please enter correct code. There MUST be an entry in this field for students ages 3-5. |
| E165 | FEDSET_PRS CODE IS FOR UNDER AGE 3 There is an entry in the field FEDSET_PRS for a student under age 3. A student must be at least 3 years old to be in a preschool setting. If the student's birth date is in error, correct the birth date or leave the field blank. |
| E166 | IN_REGCLS CODE IS IN ERROR The entry in the field IN_REGCLS is not valid. Please verify the entry and correct the error. |
| E172 | NO SERVICES TABLE There is no service data table for a CASEMIS student on file. Please remove the record or correct the error. |
| E174 | Plan_type is either blank or invalid The entry in the field PLAN_TYPE is not 10, 20, 80, 90 or is not one of the codes listed under the field. Please verify the entry and correct the error. |
| E181 | INFANT_SET CODE IS IN ERROR The entry in INFANT_SET is an invalid setting code. Please verify the entry and correct the error |
| E182 | MHS_ELIGIB CODE IN ERROR The entry in MHS_ELIGIB is an invalid code. Please verify the entry and correct the error. |
| E183 | MHS_LANG CODE IN ERROR The entry in MHS_LANG is an invalid code. Please verify the entry and correct the error. |
| E185 | EARLY_INT CODE IS IN ERROR The entry in the field EARLY_INT is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E186 | REFR_BY IS EMPTY WITH REFR_DATE There is no entry in the field REFR_BY for a valid REFR_DATE. Please enter REFR_BY for a valid REFR_DATE. |
| E187 | REFR_BY CODE IS IN ERROR The entry in the field REFR_BY is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E188 | PRNT_CSNT BEFORE REFR_DATE OR BIRTHDATE The entry in the field PRNT_CSNT is before the date in the field REFR_DATE or BIRTHDATE. Please enter a correct date. |
| E189 | INIT_EVAL BEFORE PRNT_CSNT OR BIRTHDATE The entry in the field INIT_EVAL is before the date in the field PRNT_CSNT or BIRTHDATE. Please enter a correct date. |
| E190 | INIT_EVAL IS AFTER LAST_IEP The entry in the field INIT_EVAL is after the date in the field LAST_IEP. Please enter a correct date. |
| E191 | DISABILIT2 CODE IS IN ERROR The entry in the field DISABILIT2 is not one of the codes on the list under the field. Please verify the entry, and correct the error. |
| E192 | DUPLICATE DISABILIT CODE ERROR Entries in the fields DISABILIT1 and DISABILIT2 have the same code. A disability code may only be used once per student. Please remove one or more of the duplicate codes. Or, if one or more codes is in error please enter correct code(s). |
| E193 | FEDSET_INF CODE IS IN ERROR The entry in the field FEDSET_INF is not one of the codes on the list under the field for an infant (ages 0-2). There must be an entry for an infant. Please verify the entry, and correct the error. |
| E194 | FEDSET_SCH CODE IS IN ERROR The entry in the field FEDSET_SCH is not one of the codes on the list under the field for an infant (ages 6-22). There must be an entry for students ages 6-22. Please verify the entry, and correct the error. |
| E195 | DUPLICATE ENTRIES IN FIELDS TRAN_GOAL1-4 Entries in the fields TRAN_GOAL1 to TRAN_GOAL4 have one or more of the same codes. A TRAN_GOAL X code may only be used once per student. Please remove one or more of the duplicate codes. Or, if one or more codes is in error please enter correct code(s). |
| E196 | TRAN_GOAL X CODE IS IN ERROR The entry in the field TRAN_GOAL X is not one of the codes on the list under the field. Please verify the entry, and correct the error. |
| E197 | SPEC_TRANS CODE IS IN ERROR The entry in the field SPEC_TRANS is not one of the codes on the list under the field. Please verify the entry, and correct the error. |
| E198 | GRAD_PLAN CODE IS IN ERROR The entry in the field GRAD_PLAN is not one of the codes on the list under the field. Please verify the entry, and correct the error. |
| E200 | NO SERVICES RECORD FOR STUDENT There is no services record I the SERVICE data table for student. |
| E201 | NO STUDENT RECORD FOR SERVICES A record exists in the Services Data Table (Table B) that has no corresponding student record in the CASEMIS Student Data Table (Table A). For a valid entry in the Services Data Table, there must be a record with the same SELPA_CODE and STUDENT_ID for that student in the CASEMIS Student Data Table. Please verify the data and correct the error. |
| E-202 | SERVICE CODE IS IN ERROR The entry in the field SERVICE is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E204 | LOCATION CODE IS IN ERROR The entry in the field LOCATION is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E205 | FREQUENCY CODE IS IN ERROR The entry in the field FREQUENCY is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E206 | DURATION CODE IS IN ERROR The entry in the field DURATION is not a valid format. See the field for definition. Please verify the entry and correct the error. This number cannot be less than 10. |
| E208 | REPT_DATE IS NOT MM/DD/CCYY The entry in the field REPT_DATE is not one of the dates for the state reporting requirements, or the field is blank. See Field Detail in Chapter II for correct reporting dates under this field. Enter appropriate date to correct the error. |
| E209 | FREQUENCY CODE FOR AGES 0-2 AND MH The entry in the field FREQUENCY is not one of the codes on the list under the field for an infant (ages 0-2) and Mental Health. There must be an entry for an infant and Mental Health. Please verify the entry, and correct the error. |
| E210 | DURATION ERROR FOR AGES 0-2 and MH The entry in the field DURATION is not one of the valid entries for the field for an infant (ages 0-2) and Mental Health. There must be an entry for an infant and Mental Health. Please verify the entry, and correct the error. |
| E211 | SERVICE DUPLICATE FOUND SEE: NN Entries in the SERVICE field records for the same student have one or more of the same codes. A SERVICE code may only be used once per student. Please remove one or more of the duplicate codes. Or, if one or more codes is in error please enter correct code(s). |
| E213 | PROVIDER CODE IS IN ERROR The entry in the field PROVIDER is not one of the codes on the list under the field. Please verify the entry, and correct the error. |
| E214 | PROVIDER ERROR FOR AGES 0-2 AND MH The entry in the field PROVIDER is not one of the codes on the list under the field for an infant (ages 0-2) and Mental Health. There must be an entry for an infant and Mental Health. Please verify the entry, and correct the error. |
| E300 | NO STUDENT RECORD FOR DISCIPLINE DATA A record was found in the Discipline Data Table (Table C) that has no corresponding student record in the CASEMIS Student Data Table (Table A). For an entry in the Discipline Data Table, there MUST be a record with the same SELPA_CODE and STUDENT_ID for that student in the CASEMIS Student Data Table. Please verify the data and correct the error. |
| E301 | DSPL_DATE IS BEFORE /AFTER SCHOOL YEAR The date in the field DSPL_DATE is either before or after the duration of the school year. If the data of the disciplinary action was before the school year or after the school year, the incident shall not be reported in the current year's data table. Please correct the error. |
| E302 | DSPL_TYPE CODE IS IN ERROR The entry in the field DSPL_TYPE is not one of the codes on the list under the field. Please verify the list and enter the correct code. |
| E303 | DSPL_DAYS CODE IS IN ERROR The entry in the field DSPL_DAYS is not a valid code. Please check the entry and correct the error. Note that the number of days cannot be more than 365. |
| E304 | DSPL_BY CODE IS IN ERROR The entry in the field DSPL_BY is not a valid code. Please check the entry and correct the error. |
| E305 | REASON1 CODE IS IN ERROR The entry in the field REASON1 is not one of the codes on the list under the field. Please verify the list and enter the correct code. Note that this field cannot be left blank. |
| E306 | REASON2 CODE IS IN ERROR The entry in the field REASON2 is not one of the codes on the list under the field. Please verify the list and enter the correct code. |
| E307 | REASON3 CODE IS IN ERROR The entry in the field REASON3 is not one of the codes on the list under the field. Please verify the list and enter the correct code. |
| E308 | DSPL_STAT CODE IS IN ERROR The entry in the field DSPL_STAT is not one of the codes on the list under the field. Please verify the list and enter the correct code. |
| E400 | REPT_DATE IS IN ERROR The entry in the field REPT_DATE is not one of the dates for the state reporting requirements, or the field is blank. See Field Detail in Chapter II for correct reporting dates under this field. Enter appropriate date to correct the error. |
| E401 | SELPA_CODE IS IN ERROR The entry in the field SELPA_CODE is not one of the codes listed, or the field is blank. Enter the correct four-digit code for your SELPA or SOP. |
| E402 | DIST_SERV CODE IS IN ERROR The entry in the field DIST_SERV is not a valid district/site code, or the field is blank. Please verify the entry against the list of districts under this SELPA/SOP and enter the correct seven-digit DIST_SERV code (2-digit county code plus 5-digit district code). You may obtain the correct county-district code from the California Public School Directory. |
| E403 | DIST_RESI CODE IS IN ERROR The entry in the field DIST_RESI is not a valid district/site code, or the field is blank. Please verify the entry against the list of districts under this SELPA/SOP and enter the correct seven-digit DIST_RESI code (2-digit county code plus 5-digit district code). You may obtain the correct county-district code from the California Public School Directory. |
| E404 | SCH_CODE CODE IS IN ERROR |
| E405 | LAST_NAME IS BLANK OR IN ERROR The entry in the field LAST_NAME is blank or the name starts with a blank or includes a special character. Enter the correct last name. |
| E406 | FIRST_NAME IS BLANK OR IN ERROR The entry in the field FIRST_NAME is blank or the name starts with a blank or includes a special character. Enter the correct first name. |
| E407 | STUDENT_ID IS BLANK There is no entry in the field STUDENT_ID. This field must contain a student identifier, assigned by the SELPA or SOP. |
| E408 | SSN CODE IS IN ERROR The entry in the field SSN (social security number) is not a valid number. The entry must have only numeric data. Please enter correct social security number. |
| E409 | BIRTHDATE IS BLANK OR IN ERROR There are no data in the field BIRTHDATE or the entry in the field is not a valid date. Enter the correct date in this field. |
| E410 | GENDER IS NOT M OR F The entry in the field GENDER is not "M" or "F". Enter correct entry in the field. |
| E411 | ETHNICITY CODE IS IN ERROR The ETHNICITY (1-4) code is not one of those listed under this field. Enter the correct code in this field. ETHNICITY1 is a mandatory field. ETHNICITY (2-4) code is not a valid code. Use a code from the list or if there are not other ethnicities to report, it may be left blank. |
| E412 | PST_SECPRG CODE IS IN ERROR The entry in the field PST_SECPRG is not one the codes listed for that field. Please verify the code and correct the error. |
| E413 | PST_SECEMP CODE IS IN ERROR The entry in the field PST_SECEMP is not one the codes listed for that field. Please verify the code and correct the error |
| E414 | SCH_TYPE CODE IS IN ERROR The entry in the field SCH_TYPE is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E416 | DUPLICATE ETHNICITY CODES Two or more of the entries in the fields ETHNICITY1-4 have the same code. An ethnicity code may only be used once per student. Please remove one or more of the duplicate codes. Or, if one or more codes are in error, please enter correct code(s). |
| E501 | PRNT_CSNT IS EMPTY W/ CURRENT ENTRY_DATE The field PRNT_CSNT must have an entry. Please verify the entry and correct the error. |
| E502 | INIT_EVAL IS EMPTY W/ CURRENT ENTRY_DATE The field INIT_EVAL must have an entry. Please verify the entry and correct the error. |
| E503 | REFR_DATE EMPTY W/ CURRENT ENTRY_DATE The field REFR_DATE must have an entry. Please verify the entry and correct the error. |
| E504 | EMPTY IN_RFRBY WITH IN_RFRDATE ENTRY There is no entry in the field IN_RFRBY for an infant (age 0-2). For valid IN_RFRDATE. Please enter the IN_RFRBY for a valid IN_RFRDATE. |
| E505 | EMPTY IN_PRNTCST WITH IN_RFRDATE ENTRY The field IN_PRNTCST must have an entry with valid IN_RFRDATE entry. Please verify the entry and correct the error. |
| E506 | EMPTY IN_INTEVAL WITH IN_RFRDATE ENTRY The field IN_INEVAL must have an entry with valid IN_RFRDATE entry. Please verify the entry and correct the error. |
| E507 | IN_PRNTCST BEFORE IN_RFRDATE OR BIRTHDATE The date in the field IN_PRNTCST is before IN_RFRDATE or BIRTHDATE. IN_PRNTCST date cannot be before IN_RFRDATE or BIRTHDATE. Enter correct date(s) in IN_PRNTCST and/or BIRTHDATE field(s). |
| E508 | IN_RFRBY CODE IS IN ERROR The entry in the field IN_RFRBY is not one of the codes on the list under the field. Please verify the entry and correct the error. |
| E509 | IN_RFRDATE IS BEFORE BIRTHDATE The entry in the field IN_RFR_DATE is before the date in the field BIRTHDATE. A student cannot be referred for determining eligibility for special education before BIRTHDATE. Please verify the entries in these two fields and correct the error. |
| E510 | IN_RFRDATE IS AFTER REPT_DATE The entry in the field IN_RFRDATE is after the date in the field REPT_DATE. If an infant is referred after the reporting date, the student may not be part of the data file for the reporting cycle. Please enter correct date(s) or remove the record from the data table. |
| E511 | PARTI_CAH CODE IS IN ERROR The entry for the field PARTI_CAH is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E512 | PARTI_MATH CODE IS IN ERROR The entry for the field PARTI_MATH is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E513 | PARTI_SCI CODE IS IN ERROR The entry for the field PARTI_SCI is not one of the codes listed for the field. Please verify the entry and correct the error |
| E514 | PARTI_ELA CODE IS IN ERROR The entry for the field PARTI_ELA is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E515 | PARTI_HIS CODE IS IN ERROR The entry for the field PARTI_ELA is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E516 | PARTI_WRTG CODE IS IN ERROR The entry for the field PARTI_ELA is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E517 | EVLDLAY CODE IS IN ERROR The entry for the field EVLDLY is not one of the codes listed for the field. Please verify the entry and correct the error. |
| E518 | TBDDLAY CODE IS IN ERROR The entry for the field TBDDLY is not one of the codes listed for the field. Please verify the entry and correct the error. |

### File Verification Warnings

| Warning | Warning Message and Explanation |
| --- | --- |
| W900 | RESID_STAT CODE IS 71 OR 72 The entry in the field RESID_STAT is "71" (State Hospital) or "72" (Developmental Center) for an LEA. These codes are generally used by the state operated programs and they are not meant for the LEAs, unless there are special circumstances. Make sure it is not an error. Also make sure that the student is not reported by both agencies. |
| W901 | RESID_STAT CODE IS NOT 71 OR 72 The entry in the field RESID_STAT is not "71" (State Hospital) or "72" (Developmental Center) for corresponding RESID_STAT codes in programs operated by the Department of Developmental Services (DDS). Please verify the entries in these two fields to make sure the codes are correct. |
| W902 | RESID_STAT CODE IS NOT 60 The entry in the field RESID_STAT is not "60" for programs operated by the California Department of Corrections and Rehabilitation, Division of Juvenile Justice. It is unlikely that the individuals under these institutions have different residential status. Make sure that it is not an error. |
| W903 | GRADE IS GG FOR AGE AA The entry in the field GRADE is "13" (12+/transition) for age under 17. It is highly unlikely, if not impossible, to be in community college or in a postsecondary program for a student under age 17. Check the GRADE code and the BIRTHDATE to make sure there is no error. |
| W904 | GRADE IS GG FOR AGE AA The student is at least two years younger than the normal age for the reported GRADE. Please check the field(s) BIRTHDATE and/or GRADE to make sure this is not an error. |
| W905 | AGE IS AA FOR GRADE INFANT The age of the student is more than three years while GRADE is "16" (Infant). Generally, a student in an infant program is under three years of age. Make sure this is not an error. |
| W906 | GRADE IS PRESCHOOL FOR AGE NN The entry in the field GRADE is "17" (Preschool) for age higher than six years. Normally, the preschool program is for students who are of age group 3-5, although there may be exceptions. Make sure that the BIRTHDATE and GRADE fields have the correct codes. |
| W907 | GRADE IS KINDERGARTEN FOR AGE AA The entry in the field GRADE is "18" (Kindergarten) for age less than four years. Normally the age of a kindergarten student is five years. Make sure this is not an error. |
| W909 | LAST_IEP IS OVER ONE YEAR The entry in the field LAST_IEP is more than one year before the REPT_DATE or more than one year before the EXIT_DATE if there is an entry in the field EXIT_DATE. Please make sure this is not an error. |
| W910 | LAST_EVAL IS OVER THREE YEARS The entry in the field LAST_EVAL is more than three years before the REPT_DATE or more than three years before the EXIT_DATE if there is an entry in the field EXIT_DATE. Please make sure this is not an error. |
| W914 | INVALID AGE\GRADE\PLAN_TYPE FOR PARTICIP The entry in the field PARTICIP is not appropriate for the student’s age and plan type. Please verify the student’s age, plan type, and participation in statewide testing. |
| W916 | PRNT_CSNT IS EMPTY W/ CURRENT ENTRY_DATE There is no entry in the field PRNT_CSNT with a valid current year entry date. There should be an entry for PRNT_CSNT for students who just have entered special education. |
| W917 | INIT_EVAL IS EMPTY W/ CURRENT ENTRY_DATE There is no entry in the field INIT_EVAL with a valid current year entry date. There should be an entry for INIT_EVAL for students who just have entered special education. |
| W918 | REFR_DATE EMPTY W/ CURRENT ENTRY_DATE There is no entry in the field REFR_DATE with a valid current year entry date. There should be an entry for REFR_DATE for students who just have entered special education. |
| W919 | TRAN_GOAL1 EMPTY FOR AGE 15 AND OLDER There is no entry in the field TRAN_GOAL1 for age 15 and older. There should be an entry for TRAN_GOAL1 for age 15 and older. |
| W920 | NO GRAD_PLAN FOR GRADE 8 AND UP There is no entry in the field GRAD_PLAN for grade 8 and up. Should be an entry for GRAD_PLAN for grade 8 and higher. |
| W925 | STUDENT EXISTS IN TABLE A OR ID DUPLICATE Student with same SELPA_CODE and STUDENT_ID exists in both Table A and Table D. Please verify and correct the error. |
| W926 | DISABILIT1 or DISABILIT2 is EMD (281) FOR AGE LESS THAN 3 OR AGE IS GREATER THAN 4 The disability code 281 is only for ages 3 and 4. Please verify the entry and correct the error. |
| W927 | EXIT RESON PASSED SUNSET DATE The EXIT_RESON code 82 is valid through December 31, 2007. Please verify the entry and correct the error. |
| W928 | PARTI_CAH CODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W929 | PARTI_MATH CODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W930 | PARTI_SCI CODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W931 | PARTI_ELA CODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W932 | PARTI_HISCODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W934 | PARTI_WRTG CODE IS IN ERROR FOR TESTING RANGE Student is in testing range. Please verify entry and correct the error. |
| W935 | EVLDLAY CODE IS MISSING Student evaluation is beyond the 60-day time line and reason code for delay is missing. Please verify data entries and correct the error. |
| W933 | TBDLAY CODE IS MISSING Initial IEP is after third birthday and reason code is missing. Please verify data entries and correct the error. |

# Anomaly Reports

The U.S. Department of Education, Office of Special Education Programs (OSEP) and the Office of the Inspector General (OIG) require that states provide explanations of data anomalies by category, if changes are significant. In the CDE effort to provide accurate and quality data and timely response to the OSEP and OIG, CASEMIS software automatically generates reports showing year-to-year comparison of data for districts and SELPAs as a part of the verification process. These reports are designed to assist SELPA directors and staff in identifying potential data anomalies from last year to the current year before sending the data to the CDE. Potential data discrepancies or anomalies are encircled on these reports. The SELPAs shall review these reports prior to sending SELPA data files to the CDE and provide an explanation regarding any encircled data element. In order for SELPAs to be compliant, these explanations must be received by the Department along with the data files and signed certification page.

Calculated by comparison with prior year. Must have at least 20 in at least one of the years for comparison

Test 1: (2007-2006)/2006*100>=100%

Test 2: (2007-2006)/2007*100>=100%

Test 3: (2007-2006)>=50

Anomaly reports are a required part of the CASEMIS data submission

Duplicate Students

## Removing Duplicate Students from File – December Report

In order to eliminate reporting the same student by more than one SELPA, the Department will verify the statewide student data file after the submission deadline (December Reporting Cycle only). The verification will be conducted by comparing selected demographic data fields (LAST_NAME, FIRST_NAME, BIRTHDATE, and GENDER) for all students. Reports listing matching students will be sent to the SELPAs involved to examine their file for possible duplication and correction.

It is extremely important that all SELPAs submit their file containing all students by the initial deadline so the department can verify the file for possible duplicate students. An unduplicated count is a mandate under the Individuals with Disabilities Education Act (IDEA). If a single SELPA fails to submit its complete file by the deadline, the department's effort to eliminate duplicate students from the statewide file would be incomplete. In addition, it delays the other SELPAs, who met the time line, from declaring their files as final.

In order to streamline the process of unduplication, the Department will follow the steps listed below:

Step 1:	Following the file submission reporting deadlines, the Department will verify the statewide student data file for possible duplicate report of students. This will be done even if the statewide file does not have data from all SELPAs (see Step 5 below).

Step 2:	A cover letter and report access instructions will be sent by CDE to each SELPA director involved.

Step 3:	SELPAs shall verify the reports showing possible duplicates against their data file and remove students as appropriate. SELPAs will submit a new unduplicated data file to the department within one week or as otherwise directed. SELPAS submitting potential duplicate students during this step must provide documentation describing the methods used for determining the student should be included in their data file.

NOTE: NO new student records may be added during this process.

Step 4:	After the one-week window period the Department will again verify the statewide student data file for duplicates student records from all revised files from Step 3. The Department will determine the disposition of any remaining potential duplicate student records as described in Step 5.

Step 5:	If the verification in Step 4 shows a duplicate student between a SELPA that had failed to submit a revision or meet the initial timeline and another SELPA that did meet all timelines, the Department may exercise its authority to unduplicate the file by removing that student from the SELPA that failed to submit a revision or failed to meet the initial timeline. If two or more SELPAs resubmit duplicate student records without documentation that they are different students, the Department will remove the students from all SELPAs.

The statewide student data file will then be finalized and a report showing the status and count for all SELPAs will be released. The reporting cycle will then be closed.

Each year, Special Education Local Plan Areas are sent a letter to initiate the unduplication process:

To:	Email address:

From:	Special Education Division

Subject:  Password Information for Duplicate Report for December 2007 Data

The California Department of Education (CDE), Special Education Division (SED) previously sent an email with instructions for downloading and installing the Unduplicated December 2007 Student Data listing program.

The following information is necessary for you to access your particular SELPAs un-duplication report:

User Name is:     Undup

User Password is:  0708

SELPA Name:  South Bay Service SELPA

SELPA Password:

Please secure this access information. The data contained in these files should be regarded as confidential in nature. As the SELPA Director you should designate who will coordinate the report and which PC the software will be installed. The duplication report software should be installed on a single Windows computer.

The deadline for submitting the corrected data files is Friday, January 25, 2008 (receiving date - not sending date).

Appendix 1 - Table 7, Report of Dispute Resolution under Part B of the Individuals with Disabilities Education Act

| U.S. DEPARTMENT OF EDUCATION | TABLE 7 |  |  |  |
| --- | --- | --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION |  |  |  |  |
| AND REHABILITATIVE SERVICES | REPORT OF DISPUTE RESOLUTION UNDER PART B, OF THE |  | OMB NO.: | 1820-0677 |
| OFFICE OF SPECIAL EDUCATION | INDIVIDUALS WITH DISABILITIES EDUCATION ACT |  |  |  |
| PROGRAMS | 2008-09 |  | FORM EXPIRES: | 08/31/2009 |
|  |  |  | STATE: | CA |
|  | SECTION A: WRITTEN, SIGNED COMPLAINTS |  |  |  |
|  | (1) Total number of written, signed complaints filed | 838 |  |  |
|  | (1.1) Complaints with reports issued | 679 |  |  |
|  | (a) Reports with findings of noncompliance | 679 |  |  |
|  | (b) Reports within timeline | 665 |  |  |
|  | (c) Reports within extended timelines | 14 |  |  |
|  | (1.2) Complaints pending | 0 |  |  |
|  | (a) Complaints pending a due process hearing | 0 |  |  |
|  | (1.3) Complaints withdrawn or dismissed | 159 |  |  |
|  | SECTION B: MEDIATION REQUESTS |  |  |  |
|  | (2) Total number of mediation requests received | 2706 |  |  |
|  | (2.1) Mediations held | 1585 |  |  |
|  | (a) Mediations held related to due process complaints | 1406 |  |  |
|  | (i) Mediation agreements related to due process complaints | 852 |  |  |
|  | (b) Mediations held not related to due process complaints | 179 |  |  |
|  | (i) Mediation agreements not related to due process | 100 |  |  |
|  | (2.2) Mediations not held (including pending) | 1121 |  |  |
|  | SECTION C: DUE PROCESS COMPLAINTS |  |  |  |
|  | (3) Total number of due process complaints filed | 2709 |  |  |
|  | (3.1) Resolution meetings | 530 |  |  |
|  | (a) Written Settlement agreements | 140 |  |  |
|  | (3.2) Hearings fully adjudicated | 104 |  |  |
|  | (a) Decisions within timeline (include expedited) | 12 |  |  |
|  | (b) Decisions within extended timeline | 84 |  |  |
|  | (3.3) Resolved without a hearing | 2332 |  |  |
|  | SECTION D: EXPEDITED DUE PROCESS COMPLAINTS (RELATED TO DISCIPLINARY DECISION) |  |  |  |
|  | (4) Total number of expedited due process complaints filed | 42 |  |  |
|  | (4.1) Resolution meetings | 3 |  |  |
|  | (a) Written settlement agreements | 0 |  |  |
|  | (4.2) Expedited hearings fully adjudicated | 3 |  |  |
|  | (a) Change of placement ordered | 0 |  |  |

Appendix 2:  Acronyms

| Acronym | Full Name |
| --- | --- |
| § | Section |
| ACSE | California Advisory Commission on Special Education |
| ADA | Americans with Disabilities Act |
| API | Academic Performance Index |
| APR | Annual Performance Report |
| AYP | Adequate Yearly Progress |
| BEST | Building Effective Schools Together |
| CAHSEE | California High School Exit Examination |
| CAPA | California Alternate Performance Assessment |
| CASEMIS | California Special Education Management Information System |
| CBEDS | California Basic Educational Data System |
| CDE | California Department of Education |
| CELDT | California English Language Development Test |
| CMA | California Modified Assessment |
| CMM | Complaints Management and Mediation Unit |
| COE | County Offices of Education |
| CoP | Community of Practice |
| CSCS | California School Climate Survey |
| CST | California Standards Test |
| DANS | Data analysis System |
| DDS | Department of Developmental Services |
| DE | U.S. Department of Education |
| DR | Desired Results |
| DRDP | Desired Results Developmental Profile |
| DRDP-R | Desired Results Developmental Profile Revised |
| EDD | Employment Development Department |
| EDEN | Education Data Exchange Network |
| ELA | English Language Arts |
| ELL | English Language Learners |
| ESEA | Elementary and Secondary Education Act |
| FAPE | Free Appropriate Public Education |
| FEC | Family Empowerment Centers |
| FFY | Federal Fiscal Year |
| FMTA | Focused Monitoring and Technical Assistance |
| FRC | Family Resource Centers |
| GE | General Education |
| HQT | Highly Qualified Teacher |
| ICC | Interagency Coordinating Council |
| IDEA | Individuals with Disabilities Education Act |
| IEP | Individualized Education Program |
| IFSP | Individualized Family Service Plan |
| ISES | Improving Special Education Services |
| KPI | Key Performance Indicators |
| LEA | Local Educational Agency |
| LRE | Least Restrictive Environment |
| NASDSE | National Association of State Directors of Special Education |
| NCCRESt | National Center for Culturally Responsive Educational Systems |
| NIMAC | National Instructional Materials Accessibility Center |
| NIMAS | National Instructional Materials Accessibility Standard |
| OAH | Office of Administrative Hearing |
| OSEP | Office of Special Education Programs |
| PI | Program Improvement |
| PTI | Parent Training and Information Centers |
| QAP | Quality Assurance Process |
| RtI | Response to Intervention |
| SBE | State Board of Education |
| SEACO | Special Education Administrators of County Offices |
| SED | Special Education Division |
| SEDRS | Special Education Desired Results System |
| SELPA | Special Education Local Plan Area |
| SESR | Special Education Self-review |
| SIG | State Improvement Grant |
| SILC | California State Independent Living Council |
| SPP | State Performance Plan |
| SSPI | State Superintendent of Public Instruction |
| STAR | Standardized Testing and Reporting |
| VR | Verification Reviews |
| WRRC | Western Regional Resource Center |

California Department of Education, Special Education Division

Last Reviewed on February 21, 2014