California Comprehensive Center Overview of Proposed Activities

The Project Plan for WestEd’s California Comprehensive Center proposal is organized around the following areas:

- Quality Schooling Framework to Guide, Motivate, and Support Effective Instruction and Student Outcomes

- Planning and Successful Implementation of Common Core State Standards

- Educator Excellence

- Increased Capacity to Support Productivity, Effectiveness, and Efficiency

Following is a description of key activities and the approach proposed to address each of the above listed areas.

Project Area: Quality Schooling Framework to Guide, Motivate, and Support Effective Instruction and Student Outcomes

YEAR 1 - Finalize development of Quality Schooling Framework (QSF) - Develop tools and resources to facilitate use of Quality Schooling Framework - Create a process to collect and share emerging and promising practices aligned to Quality Schooling Framework domains - Support creation of policies, guidance, and procedures within CDE that facilitate local implementation and use of Quality Schooling Framework - Build local awareness of the QSF through outreach and convening

YEAR 2 - Finalize organizing emerging and promising practices aligned to Quality Schooling Framework domains - Continue to update tools - Launch emerging, promising practice interactive web site - Organize Quality Schooling Framework Symposium to highlight effective practice and promote resource sharing - Review impact of policies, guidance, and procedures within CDE that facilitate local implementation and use of Quality Schooling Framework and work to improve as necessary

YEARS 3-5 - Refine and improve QSF - Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience - Convene and disseminate information about QSF to promote use and participation in expanding resources associated with the QSF - Assess impact of QSF on local implementation and outcomes for students

Project Area: Planning and Effective Implementation of Common Core State Standards

YEAR 1 - Provide assistance and support to CDE’s CCSS Implementation Team (project managers and integrated action team) - Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) - Support development and use of professional development modules supportive of CCSS implementation - Support development and integration of English Language Development (ELD) standards into revised English/Language Arts framework - Promote understanding of purpose and usefulness of revised ELD standards - Develop resources for schools and districts to provide access and learning opportunities related to CCSS for students with disabilities - Develop resources for schools and districts to build awareness and prompt attention to equity concerns (e.g., teacher distribution, outcomes for students) related to CCSS - Collaborate with the California Preschool Instructional Network to articulate CCSS to preschool and support objectives of Race to the Top Early Learning Imitative - Incubate and support development and identification of promising and emerging practices - Create a process to collect and share promising and emerging practices for CCSS implementation - Contribute to CDE’s knowledge regarding local practice and pathways to career and college readiness

YEAR 2 - Continue to assist and support CDE’s CCSS Implementation Team (project managers and integrated action team) - Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) - Promote professional development modules supportive of CCSS implementation - Launch emerging, promising practice interactive web site - Collaborate with the California Preschool Instructional Network to articulate CCSS to preschool and support objectives of Race to the Top Early Learning Imitative - Incubate and support development and identification of promising and emerging practices - Share effective examples of pathways to career and college readiness aligned to CCSS

YEAR 3-5 - Continue to assist and support CDE’s CCSS Implementation Team (project managers and integrated action team) - Provide assistance and support to convene a cross-agency CCSS network (CDE, SBE, CTC, IHEs, LEAs) - Assess impact of CCSS on local implementation and outcomes for students - Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience

Project Area: Educator Excellence

YEAR 1 - Support development of plan to implement recommendations from the Educator Excellence Task Force - Support development of Professional Learning Standards and related quality indicators - Identify models of effective evaluation practice for development and support of classroom and site leadership with tools and resources to support application - Convene and support teacher and principal evaluation design team - Create a process to collect and share promising and emerging practices related to teacher and administrator recruitment, induction retention, professional learning, and evaluation - Provide support related to teacher and principal evaluation to School Improvement Grant districts and schools - Provide support related to teacher evaluation to Teacher Incentive Fund grantees

YEAR 2 - Continue to provide support to implement recommendations from the Educator Excellence Task Force - Facilitate development of tools that support application of Professional Learning - Launch emerging, promising practice interactive web site - Continue providing support related to teacher and principal evaluation to School Improvement Grant districts and schools - Provide support related to teacher evaluation to Teacher Incentive Fund grantees

YEAR 3-5 - Continue to assist and support implementation of Educator Excellence recommendations - Assess impact of Educator Excellence initiatives on local implementation and outcomes for students - Support sharing and management of promising and emerging practices to ensure high-quality, relevant, and useful experience

Project Area: Increased Capacity and Support Productivity, Effectiveness, and Efficiency

YEARS 1-5 - Develop and coordinate professional growth series for CDE and CDE-affiliated networks of support - Support ongoing use of the California Accountability and Improvement System (CAIS) to streamline reporting and monitoring and increase efficiency - Develop tools and resources to facilitate efficient and effective program and fiscal monitoring and offerings of technical assistance - Develop creative approaches to using available data from CDE, IHEs, and others to inform local decisions impacting student outcomes.

Prepared by WestEd California Comprehensive Center | October 2012