| California Department of Education Executive Office SBE-003 (REV. 09/2011) dsib-adad-nov13item02 |  | ITEM #18 |  |  |
| --- | --- | --- | --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION NOVEMBER 2013 AGENDA |  |  |  |
| ### SUBJECT Standardized Testing and Reporting Program: Release of 10 Percent Withheld for 2012–13 Educational Testing Service Contract. |  |  |  | Action |
|  |  |  |  | Information |
|  |  |  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

Per state law, the California Department of Education (CDE) withholds 10 percent from progress payments invoiced for each component task in the Standardized Testing and Reporting (STAR) Program contract with Educational Testing Service (ETS).

The STAR contract establishes the process and criteria by which the CDE recommends, and the State Board of Education (SBE) approves the annual release of the 10 percent withheld from progress payments.

The STAR contract component tasks are listed in Attachment 1, and the approved contract provisions regarding the annual determination of successful completion of component tasks are outlined in Attachment 2.

RECOMMENDATION

The CDE recommends that the SBE release progress payment withholdings (10 percent) for all contract component tasks for all tests as part of the 2012–13 STAR Program contract with ETS, pending completion of all contract component tasks for the 2013 STAR Program test administration through December 2013.

BRIEF HISTORY OF KEY ISSUES

The CDE has performed an evaluation and determined that ETS has satisfactorily performed all the contract component tasks during the 2013 test administration to date, pending completion of all contract requirements through December 2013 and, as such, is recommending approval of the 10 percent release. If ETS fails to satisfactorily perform any component tasks, the CDE will recommend further action to the SBE at its next regular meeting regarding releasing the 10 percent of funds.

SUMMAR OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

In 2012, the SBE approved the release of the 10 percent of funds withheld from the progress payments to ETS for all contract component tasks for all STAR Program tests.

At the November 2011 meeting, the SBE did not approve the release of a total of $7,233.70 from the 10 percent of funds withheld from the progress payments to ETS.

In 2010 and 2008, the SBE approved the release of the 10 percent of funds withheld from the progress payments to ETS for all contract component tasks for all STAR Program tests.

At the November 2009 meeting, the SBE did not approve the release of a total of $107,992.91 from the 10 percent of funds withheld from the progress payments to ETS.

At the November 2007 meeting, the SBE did not approve the release of a total of $1,101,814.60 from the 10 percent of funds withheld from the progress payments to ETS.

FISCAL ANALYSIS (AS APPROPRIATE)

The funds to be released were withheld during 2012–13 from invoices paid with existing STAR Program contract funding, shown in Attachment 3. The CDE recommends the release of $5,343,711.10. Any portion of the funds withheld during 2012–13 that are not released will revert back to the state General Fund.

ATTACHMENT(S)

Attachment 1: Completion Criteria (4 Pages)

Attachment 2: Standardized Testing and Reporting Program, Process for Determination of Successful Completion of Component Tasks (1 Page)

Attachment 3: Standardized Testing and Reporting Contract, 2013 Test Administration Component Task Budget (1 Page)

Attachment 3 to Exhibit C

Contract 5417, Educational

Testing Service (ETS)

Completion Criteria

The criteria by which the California Department of Education (CDE) recommends and the State Board of Education (SBE) will determine successful completion of each component task for payment of the final 10 percent is set forth in the following table.

Standardized Testing and Reporting (STAR) Program

CRITERIA FOR SUCCESSFUL COMPLETION OF COMPONENT TASKS

2007 through 2013 Test Administrations

| COMPONENT TASK | CRITERIA | COMPLETION DATE SPECIFIED IN AGREEMENT |
| --- | --- | --- |
| 3.1 Component Task 1 Comprehensive Plan and Schedule for Project Deliverables and Activities | - CDE received written results of the quality control audit. Delivered all electronic data files, documentation, and materials developed for the STAR Program to the bidder designated by the SBE in 2013. | - December 31, 2007 and each subsequent year - December 31, 2013 |
| 3.2 Component Task 2 Program Support Services | - All materials specified were developed and distributed to local educational agencies (LEAs) within the specified timelines. - The California Technical Assistance Center processed all district orders as specified and responded to district requests for assistance. - CDE received electronic files and other reports as specified. | - July 30, 2007 and each subsequent year - December 31 of each year - December 31 of each year |
| 3.3 Component Task 3 Test Security Measures 3.3 Component Task 3 Test Security Measures (cont.) | - Completed on-site visits of schools before, during, and after testing (for the 2007 through 2009 administrations only). - All test items, test materials, electronic files, and data were developed, used, transferred, delivered, and maintained in a secure manner. - Provided the CDE with summary reports of the results of each security breach investigation. - Provided the CDE with a complete report of each investigation. | - October 15, 2007 and each subsequent (for the 2007 through 2009 administrations only). - October 15, 2007 and each subsequent year - Within 10 working days of a security breach being reported - September 1 of each year |
| 3.4 Component Task 4 Norm-referenced Test | - Norm-referenced test was administered to students in grades 3 and 7 only (for 2007 and 2008 administrations only). | Within the California Standards Tests (CST) testing window each year for 2007 and 2008 administrations only |
| 3.5 Component Task 5 Electronic Item Bank, Data Management, and Documentation | - Delivered to the CDE all test items in the item bank, including existing items as well those newly developed. | - December 31 of each year |
| 3.6 Component Task 6 Item and Task Development | - Developed for all grades and subjects the number of test items agreed upon under the contract. - The minimum number of items developed were field-tested and have adequate technical characteristics, as defined in the contract, to be used on operational tests. - A review of the scaling and equating processes showed them to meet or exceed industry standards. - The performance level settings generated results for all content areas and performance levels were reported to schools, districts, counties, and the state. | - December 31 of each year - December 31 of each year |
| 3.7 Component Task 7 Test Form, Test Booklet, and Answer Document Construction | - Test forms conformed to industry standards and Universal Design principles. - Answer documents allowed for demographic and identification data required by statute and regulations. | - March 31 of each year - March 31 of each year |
| 3.8 Component Task 8 Pre-Identification and Ordering | - Pre-identification data were processed in a timely manner to LEAs. - All orders were processed and were processed in a timely manner. | - December 31 of each year - December 31 of each year |
| 3.9 Component Task 9 Test Materials Production and Packaging | - All test materials required for the program were produced on time in quantities sufficient for conducting the annual STAR testing in all districts, with no more than 0.5 percent printing or collating errors reported. - The CDE received copies of all tests materials. | - September 30, 2007 and each subsequent year - February 15 of each year |
| 3.10 Component Task 10 Delivery and Collection of Test Materials | - Test materials were delivered to and retrieved from districts within the regulatory time and by the statutory limit. | - September 30, 2007 and each subsequent year |
| 3.11 Component Task 11 Test Processing, Scoring, and Analysis | - All tests were correctly processed and scored within timelines specified in this scope of work. - Data analysis was completed as specified. - Mark Discrimination Report delivered to CDE (for 2007 and 2008 administrations only). - Returned materials reports were delivered to the CDE. - Demographic edit reports were delivered to the CDE. | - August 31, 2007 and each subsequent year - August 31, 2007 and each subsequent year - August 31, 2007 and each subsequent year (for 2007 and 2008 administrations only). - September 30, 2007 and each subsequent year - Biweekly June through September of each year |
| 3.12 Component Task 12 Reporting Test Results to LEAs | - Accurate and complete reports of test results as required in statute were provided to all LEAs. | - No later than August 8 of each year or within five weeks of receipt of processable answer documents or completion of requirements in annual scoring specifications |
| 3.13 Component Task 13 Reporting Test Results to CDE | - Accurate state-level reports of test results were provided to the CDE. - Complete and accurate Internet files were posted within statutory timelines, including results for all students and all subgroups. | - Preliminary complete files by August 8 of each year - Final files by November 8 of each year |
| 3.14 Component Task 14 | - Annual Technical Report was received by the CDE. - Data files to use for apportionment purposes were received by the CDE. | - December 31 of each year - September 1 of each year |

Standardized Testing and Reporting Program

Process for Determination of Successful Completion

of Component Tasks

California Education Code Section 60643 requires:

- The California Department of Education (CDE) to withhold no less than 10 percent of the amount budgeted for each separate and distinct component task provided for in the Standardized Testing and Reporting (STAR) Program contract pending final completion of all component tasks.

- The STAR contract to establish the process and criteria by which the successful completion of each component task will be recommended by the CDE and approved by the State Board of Education (SBE).

The approved STAR contract is the result of a collaborative process involving SBE staff, the SBE testing liaisons, the CDE, and Educational Testing Service (ETS). It includes the following contract provisions regarding the annual determination of successful completion of component tasks:

- On or before the annual November SBE meeting, the CDE shall present to the SBE for its consideration a recommendation regarding the performance of ETS for the SBE’s initial determination as to whether ETS has substantially complied with the terms and conditions of the agreement with the CDE.

- The criteria by which the CDE will recommend SBE adoption to determine successful completion of each component task for payment of the final 10 percent are set forth in Attachment 1.

- Once the SBE has determined that ETS has successfully completed a component task, the 10 percent withheld from invoices for the component task for the prior fiscal year may be released by the CDE.

- In the event that the SBE determines that ETS has not substantially complied with the terms and conditions of the agreement with the CDE, the SBE shall, within ten days of its determination, notify ETS and the CDE, in writing, of which component tasks the SBE has determined that ETS allegedly has failed to substantially perform; and a description of the failure shall be included. ETS shall submit an invoice for all tasks that are not set forth in the notice, and the invoice shall be paid within 30 days of receipt. ETS shall have ten days from receipt of the notice to respond in writing, and the response shall be promptly circulated to the CDE and each member of the SBE.

- At its next scheduled meeting, the SBE shall offer the CDE and ETS an opportunity to make any final oral presentation to the SBE regarding the alleged failures. At the same meeting, the SBE shall decide which component tasks, if any, ETS has failed to complete. ETS shall invoice the CDE for the remaining amount due to ETS, and the invoice shall be paid within 30 days of receipt.

Standardized Testing and Reporting Contract

2013 Test Administration Component Task Budget

The California Department of Education (CDE) recommends releasing a total of $5,343,711.10 from funds withheld during the 2013 test administration.

| Component Task | Total 2013 Administration Budget | Amount Paid/ To Be Paid from Progress Payments* | 10 Percent Withhold Pending Release | Recommend Release |
| --- | --- | --- | --- | --- |
| 1 Comprehensive Plan | $929,629 | $836,666.10 | $92,962.90 | $92,962.90 |
| 2 Program Support | $3,919,908 | $3,527,917.20 | $391,990.80 | $391,990.80 |
| 3 Test Security Measures | $55,000 | $49,500.00 | $5,500.00 | $5,500.00 |
| 4 Norm-referenced Test (eliminated in 2009) | $0 | $0 | $0 | $0 |
| 5 Item Bank/Data Management/Documentation | $440,910 | $396,819.00 | $44,091.00 | $44,091.00 |
| 6 Item and Task Development | $3,116,878 | $2,805,190.20 | $311,687.80 | $311,687.80 |
| 7 Test Form/Test Booklet/Answer Document | $4,401,925 | $3,961,732.50 | $440,192.50 | $440,192.50 |
| 8 Pre-Identification and Ordering | $1,602,108 | $1,441,897.20 | $160,210.80 | $160,210.80 |
| 9 Test Materials Production/Packaging/ Shipping | $8,476,198 | $7,628,578.20 | $847,619.80 | $847,619.80 |
| - Delivery and Collection of Test Materials | $3,616,849 | $3,255,164.10 | $361,684.90 | $361,684.90 |
| 11 Test Processing, Scoring, and Analysis | $18,721,328 | $16,849,195.20 | $1,872,132.80 | $1,872,132.80 |
| 12 Reporting Results to Local Educational Agencies (LEAs) | $7,819,754 | $7,037,778.60 | $781,975.40 | $781,975.40 |
| 13 Reporting Results to CDE | $79,469 | $71,522.10 | $7,946.90 | $7,946.90 |
| 14 Technical Report/Other Reports/Analyses | $257,155 | $231,439.50 | $25,715.50 | $25,715.50 |
| Totals | $53,437,111 | $48,093,399.90 | $5,343,711.10 | $5,343,711.10 |

*Pending completion of all contract component tasks for the 2013 test administration through December 2013.