| California Department of Education Executive Office SBE-003 (REV. 09/2011) ilsb-cfird-janitem03 |  | ITEM #16 |  |  |
| --- | --- | --- | --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION JANUARY 2014 AGENDA |  |  |  |
| ### SUBJECT Science Framework for California Public Schools, Kindergarten Through Grade Twelve, 2016 Revision: Approval of the Timeline of Significant Events and the Curriculum Framework and Evaluation Criteria Committee Application Form. |  |  |  | Action |
|  |  |  |  | Information |
|  |  |  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

California Education Code (EC) Section 60200.9 requires the State Board of Education (SBE) to adopt a revised Science Framework for California Public Schools, Kindergarten Through Grade Twelve (Science Framework) on or before January 31, 2016. California Code of Regulations, Title 5 (5 CCR) Section 9511 allows the SBE to establish a Curriculum Framework and Evaluation Criteria Committee (CFCC) to assist in the development of curriculum frameworks and evaluation criteria, and lists the requirements regarding the recruitment process and qualifications for members of the CFCC. This item is the first in what will be a series of items regarding the 2016 revision of the Science Framework.

RECOMMENDATION

The California Department of Education (CDE) recommends that the SBE approve the Timeline of Significant Events and the CFCC application form for the 2016 revision of the Science Framework.

BRIEF HISTORY OF KEY ISSUES

When the SBE adopted the Next Generation Science Standards for California Public Schools, Kindergarten through Grade Twelve (CA NGSS) in September 2013, these standards became the current subject-matter standards in science. The full implementation of these standards will occur over several years. Revising the Science Framework to align with the CA NGSS is an important component in that implementation.

The Science Framework revision will also provide guidance in implementing the Common Core State Standards, English Language Arts & Literacy in History/Social Studies, Science, and Technical Subjects and give direction for applying the new Engineering domain of the CA NGSS.

The revision of the Science Framework is a multi-step process. It involves educators, content experts, and other stakeholders participating in the focus group meetings and as members of the CFCC. Throughout the revision process, there are opportunities for public input at focus group, CFCC, Instructional Quality Commission (IQC), and SBE meetings and during two 60-day public review periods. Attachment 1 outlines the major steps in the framework revision process.

The framework revision process requires action by the SBE at key points, including the approval of a Timeline of Significant Events (Attachment 2) and the CFCC application form (Attachment 3) as first steps in the process. In January 2016, the SBE will take action on the IQC recommendation regarding adoption of the revised Science Framework.

The Curriculum Frameworks and Instructional Resources Division and a professional writing team will be supporting the framework revision.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

September 2013: Pursuant to SB 300 (2011), the SBE adopted the Next Generation Science Standards for California Public Schools, Kindergarten through Grade Twelve

November 2013: The SBE took action on the middle grades learning progressions.

FISCAL ANALYSIS (AS APPROPRIATE)

The cost to revise the Science Framework is anticipated to be $1.3 million. This includes the expenses of the focus groups, the CFCC, and the meetings of the IQC and Science Subject Matter Committee, the costs of a contracted Science Framework writing team, ($289,700) and CDE staff costs ($1,014,577).

ATTACHMENT(S)

Attachment 1: California Department of Education Science Framework Development Process (1 Page)

Attachment 2: Draft Timeline of Significant Events for the 2016 Revision of the Science Framework for California Public Schools, Kindergarten Through Grade Twelve (2 Pages)

Attachment 3: Draft Application for Appointment to the Science Curriculum Framework and Evaluation Criteria Committee (8 Pages)

Schedule of Significant Events for the 2016 Revision of the

Science Framework for California Public Schools,

Kindergarten Through Grade Twelve

| Event | Schedule |
| --- | --- |
| State Board of Education (SBE) Approved CA NGSS, K–12 | September 4, 2013 |
| Governor Brown signed Senate Bill 300 into law | October 2, 2013 |
| Focus Group recruitment letter and application distributed to Local Educational Agencies (LEAs), scientists and stakeholder organizations, and institutes of higher education | October 2013 |
| Recruitment of Focus Group members, pursuant 5 CCR, §9511(c) and Education Code Section 44013(a) | October–December 2013 |
| SBE action on middle grades learning progressions | November 6–7, 2013 |
| Instructional Quality Commission (IQC) Approves Schedule of Significant Events, Curriculum Framework and Evaluation Criteria Committee (CFCC) Application | November 21–22, 2013 |
| Superintendent appoints Focus Group members | December 2013 |
| SBE action on a timeline and CFCC application form | January 15–16, 2014 |
| CFCC recruitment letter and application published/released online for LEAs, Science stakeholder organizations, and institutes of higher education | January 2014 |
| Focus Group Meeting Locations, pursuant to 5 CCR, §9511(c): *Exploratorium, San Francisco Saturday, January 25, 2014, 10 a.m.–noon *San Diego County Office of Education Thursday, January 30, 2014, 5–7 p.m. *Orange County Department of Education, Friday, January 31, 2014, 4:30–6:30 p.m. *CDE, Sacramento Tuesday, February 4, 2014, 4–6 p.m. Video Conference Included (Siskiyou, Shasta, Humboldt) *Fresno County Office of Education Tuesday, February 11, 2014, 4–6 p.m. | January–February 2014 |
| Recruitment of CFCC members (at least 90 days pursuant to 5 CCR, §9513) | January–April 2014 |
| IQC meets, establishes Science Subject Matter Committee (Science SMC), reviews Focus Group Report, and recommends CFCC members and guidance for revision of the framework to the SBE | May 15–16, 2014 |
| SBE appoints CFCC members, receives Focus Group Report, and approves guidance for revision of the framework | July 9–10, 2014 |
| CFCC Meetings, 6 Meetings The CFCC meetings are schedule for the following dates: * September 9–10, 2014 (Tuesday and Wednesday) * October 9–10, 2014 (Thursday and Friday) * November 5–6, 2014 (Wednesday and Thursday) @ 900 N Street * December 11–12, 2014 (Thursday and Friday) * January 22–23, 2015 (Thursday and Friday) * February 26–27, 2015 (Thursday and Friday) | September 2014– February 2015 |
| Science SMC reviews draft Science Framework in preparation for full IQC review | Early April 2015 |
| IQC approves draft Science Framework for initial 60-day public review period | May 2015 |
| 60-day public review period prior to IQC recommendation to SBE, pursuant to 5 CCR, §9515(a)(3) | June–July 2015 |
| Science SMC reviews public review results and staff recommendations for edits to draft Science Framework | August 2015 |
| IQC analyzes public review results and revises draft Science Framework, approves draft Science Framework for second 60-day public review period | September 2015 |
| Required 60-day public review and comment on IQC’s recommended Science Framework Section §95159(c) | October–November 2015 |
| SBE action on IQC’s recommended Science Framework includes public hearing | January 31, 2016 Statutory Deadline Per SB 300 |

Application for Appointment to the Science Curriculum Framework and Evaluation Criteria Committee

Applications must be received by 3 p.m., April 16, 2014

The State Board of Education (SBE) is recruiting members for the Science Curriculum Framework and Evaluation Criteria Committee (CFCC). The CFCC will play a significant role in the revision of the Science Framework for California Public Schools, Kindergarten Through Grade Twelve (Science Framework). The Science Framework will be revised to incorporate and support the Next Generation Science Standards for California Public Schools, Kindergarten through Grade Twelve (CA NGSS), adopted by the SBE in September 2013, and to reflect current research in science instruction. The CFCC provides input into the initial draft of the revised framework in accordance with guidelines approved by the SBE.

CFCC members include single-subject and multi-subject credentialed teachers; college and university personnel representing academic departments and schools of education; and representatives of citizen groups, educational organizations, industry, or other agencies. The Instructional Quality Commission (IQC), which serves as an advisory body to the SBE, recommends applicants for the CFCC to the SBE.

Serving on the CFCC represents a significant commitment of time and personal energy. Between September 2014 and February 2015, CFCC members will participate in up to six meetings (two days each) in Sacramento and spend a considerable amount of time between meetings reviewing or researching portions of framework drafts. Travel and per diem costs are reimbursed at standard state rates; however, no stipend or substitute pay is provided.

Instructions:

- Answer all of the questions. An asterisk (*) denotes a required field.

- After answering all of the questions on a page, select the “Next” button

- You must submit a résumé with your application.

- On the last page of the Application, select the “Preview” button.

- On the next screen, review all of the responses, and then select the “Submit” button on the bottom of the screen.

- After you have submitted the Application, save your Confirmation ID given on the next page. Select the “Print” button to obtain a hard copy. Select the “Download Application in pdf” button to download a pdf version of your application.

Personal Information

First Name:

Last Name:

MI:

Home Street Address:

Home City:

Home State:

Home Zip Code:

Home Phone:

Business Phone:

E-mail:

Employer’s Business Name:

Position Title:

Business Street Address:

Business City:

Business State:

Business Zip Code:

Areas of Expertise:

Check all that apply.

- Administrator

- Teacher providing instruction to students in kindergarten or grades one to twelve. Note that teachers must meet the requirements for a highly qualified teacher under the No Child Left Behind Act of 2001.

- Teacher not providing instruction to students in kindergarten or grades one to twelve (e.g., mentor teacher or certificated teacher employed by school districts or county offices of education who is not in a position that requires a service credential with a specialization in administrative services)

- Parent

- Higher Education/ Researcher

- Community Member

- School Board Member

- Other Areas of Expertise (drop down menu: “Explain”)

Grade Levels of Expertise:

Check all that apply.

- K–2

- 3–5

- 6–8

- 9–12

- Other Grade Levels (e.g. university, college):

Subjects Taught:

Check all that apply.

- Integrated Science

- Earth Science

- Life Science

- Physical Science

- Engineering

- Chemistry

- Physics

- Biology

- Other subject not mentioned above:

Years Teaching:

Experience Teaching English Learners:

Have you provided instruction to English learners?		 No     Yes

If yes, at what grade levels and for how many years? List any specialized credential, certificate, or training in this area.

Experience Teaching Students with Disabilities:

Have you provided instruction to students with disabilities?	 No     Yes

If yes, at what grade levels and for how many years? List any specialized credential, certificate, or training in this area.

Highest Degrees/Certifications:

List your four highest academic degrees and/or certifications earned and the awarding institution. List your highest achievement first.

Degree/Certification #1:

Institution #1:

Degree/Certification #2:

Institution #2:

Degree/Certification #3:

Institution #3:

Degree/Certification #4:

Institution #4:

Knowledge of the Next Generation Science Standards:

Describe how the CA NGSS, adopted in September 2013, will impact instruction and student learning. Use 2,000 characters or less.

Standards-Based Instruction Experience:

Describe a standards-based activity, lesson, or instructional unit that you have used, or one that could be used with a diverse student population, including students with special

needs, students who read below grade level, students who are English Learners, and students who are advanced learners. Explain how you would assess the effectiveness of the instruction. Use 2,000 characters or less.

Areas of Expertise and Leadership:

Describe how your education and experience prepare you to participate in the CFCC to revise the Science Framework. As part of your response, please describe your knowledge and use of the NGSS and your experience providing effective instruction to a diverse student population, which helps them explore and understand the scientific practices included in the NGSS, developing curriculum or assessments, and serving as an instructional leader. Use 2,000 characters or less.

Previous Committee Experience: Have you ever served on a committee that was engaged in standards or curriculum development, or the review of instructional materials? If yes, briefly detail your experience. Use 1,000 characters or less.

Relationship with Publishers: Conflict of Interest Disclosure Statement

Your answers below will serve as the disclosure of certain information as required by the “Statement of Activities that are Inconsistent, Incompatible, or in Conflict with Duties of a Member of an Educational Policy Advisory Commission or a Committee or Panel Thereof,” as amended January 1978, and California Code of Regulations, Title 5, Education, Section 18600. Your answers will be the basis for an eligibility ruling in the event some activity appears to be inconsistent, incompatible, or in conflict with the duties assigned to the advisory framework committee.

For the questions below, “immediate family” is defined as your spouse and dependent children (California Government Code Section 82029).

Question 1:

Do you or a member of your immediate family have, or have you had, a business relationship at any time over the last twelve months with a publisher that produces instructional materials for California? If YES, list the company(-ies) that you have dealt with, and the amount (if any) of remuneration received. Use 1,000 characters or less.

Question 2:

Are you currently employed by or under contract to any person, firm, or organization which will do business with or submit instructional material to the California Department of Education (CDE)? If YES or UNCERTAIN, please explain and provide as much detail as possible, including name of firm, nature of contract, dates of contract, and compensation. Use 1,000 characters or less.

Question 3:

Have you ever been employed by or had any other kind of contractual relationship with any person, firm, or organization doing business with, or submitting instructional materials to, the CDE? If YES or UNCERTAIN, please explain and provide as much detail as possible, including name of firm, nature of contract, dates of contract, and compensation. Use 1,000 characters or less.

Question 4:

Do you expect to receive any royalty payments during your period of service on the Science CFCC? If YES or UNCERTAIN, please explain and provide as much detail as possible, including name of firm, nature of contract, dates of contract, and compensation. Use 1,000 characters or less.

Question 5:

Were you or any member of your immediate family an author, contributor, or editor of (or consultant on) any textbook, other curriculum material, or project proposal that is likely to be submitted to the CDE? If YES or UNCERTAIN, please explain and provide as much detail as possible, including name of firm, nature of contract, dates of contract, and compensation. Use 1,000 characters or less.

Question 6:

Have you received compensation, do you expect to receive compensation, or do you have any other kind of contractual relationship with any organization that is either a subsidiary, parent organization, or “sister organization” of any entity which will do business with your advisory body or will submit materials to your advisory body? If YES or UNCERTAIN, please explain and provide as much detail as possible, including name of firm, nature of contract, dates of contract, and compensation. Use 1,000 characters or less.

Language 1:

Skill for Language 1:

- Speak

- Read

- Write

Language 2:

Skill for Language 2:

- Speak

- Read

- Write

Gender:

- Male

- Female

Ethnicity (optional):

Please select all that apply from below:

- Hispanic/Latino

- American Indian or Alaska Native

- Asian

- Black or African American

- Native Hawaiian or Other Pacific Islander

- White

- Decline to state

- Other

Applicant Acknowledgement/Certification

- I understand that this application becomes public information when submitted. The answers to the questions under Relationship to Publisher: Conflict of Interest Disclosure Statement are true and correct to the best of my knowledge and belief. My supervisor and I are aware that while travel and per diem costs will be reimbursed at standard state rates, no stipend is provided to IMRs. I have discussed this application with my supervisor and have received approval for release time to participate in all related activities.

- Supervisor/Employer Information

First Name:

Last Name:

Position Title:

Phone:

E-mail: (generates e-mail message to employer)

When you submit your application form, a message will be automatically sent to the employer’s email address you enter above.

[sent from scienceframework@cde.ca.gov]

Dear <First Name> <Last Name>,

This message is being sent to notify you that <First Name> <Last Name>

(<e-mail address>), a member of your staff, has submitted an application to participate as a Science Curriculum Framework and Evaluation Criteria Committee Member for the revision of the 2016 Science Framework. If appointed by the State Board of Education (SBE), the candidate is committing to attend a sequence of meetings and to support the revision of the Science Framework. Panel members will attend six meetings at the

California Department of Education in Sacramento from September 2014 to February 2015 (One meeting per month and each meeting will last two days). Travel and per diem costs are reimbursed at standard state rates; however, no stipend or substitute pay is provided.

Professional References

Please provide the names and contact information for at least one and up to three professional references.

First Name:

Last Name:

Position Title:

Institution:

Street Address:

City:

State:

Zip Code:

Phone:

E-mail:

First Name:

Last Name:

Position Title:

Institution:

Street Address:

City:

State:

Zip Code:

Phone:

E-mail:

First Name:

Last Name:

Position Title:

Institution:

Street Address:

City:

State:

Zip Code:

Phone:

E-mail:

Upload a Résumé

Note: Please attach a current résumé as it relates to your educational background and experience in science education in kindergarten through grade twelve and/or higher education. If you are a classroom teacher, list the classes you are currently teaching and the grade level(s). Also, please indicate any specialized training you have had in science instruction in the past five years. Please limit your résumé to two or three pages and include your name on each page.

Please limit the size of the file to under 5 MB. This document will replace any previously uploaded résumé.