| California Department of Education Executive Office SBE-003 (REV. 09/2011) ilsb-cfird-sep14item01 |  | ITEM #06 |  |  |
| --- | --- | --- | --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION SEPTEMBER 2014 AGENDA |  |  |  |
| ### SUBJECT Update of the History–Social Science Framework for California Public Schools: Revised Timeline and Guidelines. |  |  |  | Action |
|  |  |  |  | Information |
|  |  |  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

Pursuant to Senate Bill 1540 (Chapter 288, Statutes of 2012), the State Board of Education (SBE) is authorized to complete work on the updated History–Social Science Framework for California Public Schools (History–Social Science Framework) that was suspended in 2009. The revised timeline presented for action in this item establishes a schedule of events for the project that is consistent with that statute and other curriculum frameworks currently under development. The revised guidelines update those originally adopted by the SBE in November 2008.

RECOMMENDATION

The California Department of Education (CDE) recommends that the SBE approve the revised timeline and guidelines for the completion of the History–Social Science Framework for California Public Schools.

BRIEF HISTORY OF KEY ISSUES

The History–Social Science Framework was in the middle of a major update in July 2009 when the Legislature passed, and the Governor signed, Assembly Bill X4 2. The law suspended all work on instructional materials adoptions and curriculum framework development until July 1, 2013. The suspension was subsequently extended by SB 70 until July 1, 2015.

When the suspension took effect, the draft-updated framework had just been approved by the Curriculum Development and Supplemental Materials Commission (later renamed the Instructional Quality Commission [IQC]) for the first of two public field reviews required by the California Code of Regulations, Title 5 (5 CCR), Section 9515.

In 2012, SB 1540 authorized the SBE to complete work on the framework, with the stipulation that the project could only resume once the new frameworks in mathematics and English language arts were completed. The new Mathematics Framework for California Public Schools was adopted by the SBE at its November 2013 meeting, while the new English Language Arts/English Language Development Framework for California Public Schools was adopted by the SBE at its July 2014 meeting.

The recommended changes to the timeline for the update of the History–Social Science Framework outline the events that have to happen consistent with SB 1540 and provisions of the Education Code and 5 CCR that govern the framework development process. The timeline anticipates final SBE action on the History–Social Science Framework in May 2015.

The revised guidelines incorporate statutory changes that have taken effect since the update was suspended in July 2009. Because the Curriculum Framework and Evaluation Criteria Committee (CFCC) has already completed its work and produced a draft, the revised guidelines will primarily serve to direct the work of the IQC as it conducts the first field review of the History–Social Science Framework and prepares the updated draft for recommendation to the SBE.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

March 12, 2008: The SBE took action to approve the update plan, timeline, and CFCC application for the update of the History–Social Science Framework.

November 5, 2008: The SBE appointed 20 members to the CFCC and approved guidelines for the framework update.

FISCAL ANALYSIS (AS APPROPRIATE)

SB 1540 provided no additional funding for the completion of the History–Social Science Framework. If outside funding is provided, the CDE may work with an outside writer to help develop proposed revisions to the framework draft that incorporate civic education, the Common Core State Standards, and changes in statute that have been implemented since work on the draft was suspended in July 2009. Any such proposed revisions would be reviewed and approved in the public meetings of the IQC as noted in the schedule of events originally approved by the SBE and proposed modifications in Attachment 1. The remaining work, including the two field reviews required by 5 CCR and the meetings of the IQC related to the framework, will be funded out of the existing operating budget of the CDE and IQC.

ATTACHMENT(S)

Attachment 1: Revised Schedule of Significant Events for the Update of the

History–Social Science Framework (4 Pages)

Attachment 2: Revised Guidelines for the Update of the History–Social Science Framework (7 Pages)

Timeline for Update of the History–Social Science Framework for California Public Schools

Approved by the State Board of Education on March 12, 2008; Updated on November 5, 2008

Recommended Changes for 2014–15, Pursuant to Senate Bill 1540

(Chapter 288, Statutes of 2012)

Proposed additions are italicized; proposed deletions are struck through. The bracketed comments have been added to conform to CDE Web posting accessibility requirements.

| Event | Schedule |
| --- | --- |
| Curriculum Commission takes action on update plan, timeline, and Curriculum Framework and Evaluation Criteria Committee (CFCC) application | January 24–25, 2008 |
| State Board of Education (SBE) takes action on update plan, timeline, and CFCC application | March 12–13, 2008 |
| Recruitment of CFCC members (at least 90 days per 5 CCR 9513) | March 20, 2008–September 3, 2008 |
| Focus Groups held to solicit public input on the framework update - Bay Area - Sacramento - Los Angeles Area - San Diego Area | May–June, 2008 |
| Curriculum Commission reviews applications and makes recommendations on CFCC members | September 24–26, 2008 |
| SBE action on CFCC recommendations | November 5–6, 2008 |
| CFCC meets approximately every four weeks, for a total of five meetings to draft framework | February 5–6, 2009 March 4–5, 2009 April 2–3, 2009 April 30–May 1, 2009 June 4–5, 2009 |
| Work on draft suspended pursuant to Assembly Bill X4 2 [The preceding event has been italicized and it is proposed as an addition.] | July 2009 [The preceding date has been italicized and it is a proposed addition.] |
| Work on draft resumes pursuant to Senate Bill 1540 [The preceding event has been italicized and it is proposed as an addition.] | July 2014 [The preceding date has been italicized and it is a proposed addition.] |
| Curriculum Instructional Quality Commission approves draft Framework for field review [Note that the word “Curriculum” in the preceding event has strikethrough and is proposed for deletion. The words “Instructional Quality” have been italicized and are proposed as an addition.] | July 2009 (additional meeting) September 18–19, 2014 [The preceding date, July 2009 has been proposed for deletion. The new proposed date is September 18–19, 2014.] |
| 60-day field review of draft Framework (required by CCR 9515) | August– September–November 2009 2014 [The preceding date, August–September 2009 has been proposed for deletion. The new proposed date is September–November 2014.] |
| Curriculum Instructional Quality Commission analyzes field review results and revises draft framework [Note that the word “Curriculum” in the preceding event has strikethrough and is proposed for deletion. The words “Instructional Quality” have been italicized and are proposed as an addition.] | September 2009 December 2014–January 2015 [The preceding date, September 2009 has been proposed for deletion. The new proposed date is December 2014–January 2015.] |
| Curriculum Instructional Quality Commission holds hearings and takes action on draft framework/sends recommendation to SBE [Note that the word “Curriculum” in the preceding event has strikethrough and is proposed for deletion. The words “Instructional Quality” have been italicized and are proposed as an addition.] | November 2009 February 5–6, 2015 [The preceding date, November 2009 has been proposed for deletion. The new proposed date is February 5–6, 2015.] |
| Required 60-day period for public review and comment on Curriculum Instructional Quality Commission’s recommended framework (CCR 9515) [Note that the word “Curriculum” in the preceding event has strikethrough and is proposed for deletion. The words “Instructional Quality” have been italicized and are proposed as an addition.] | December 2009–January 2010 February–March 2015 [The preceding dates, December 2009–January 2010 have been proposed for deletion. The new proposed date is February–March 2015.] |
| SBE receives Curriculum Instructional Quality Commission recommendation, holds public hearing and acts on draft framework [Note that the word “Curriculum” in the preceding event has strikethrough and is proposed for deletion. The words “Instructional Quality” have been italicized and are proposed as an addition.] | March 2010 (final action in May 2010, if necessary) May 2015 [The preceding date, March 2010, has been proposed for deletion. The new proposed date is May 2015.] |
| Document Preparation | Fall 2010 Summer 2015 [The preceding date, Fall 2010 has been proposed for deletion. The new proposed date is Summer 2015.] |
| Final Publication | Winter 2010 2015 [The preceding date, Winter 2010 has been proposed for deletion. The new proposed date is Winter 2015.] |

Curriculum Framework and Evaluation Criteria Committee Guidelines for

History–Social Science Framework for California Public Schools Update

Recommended Changes for 2014–15, Pursuant to Senate Bill 1540

(Chapter 288, Statutes of 2012)

Proposed additions are italicized; proposed deletions are struck through. The bracketed comments have been added to conform to CDE Web posting accessibility requirements.

The following guidelines are based on statutory requirements, information provided to the Curriculum Development and Supplemental Materials Commission (now renamed the Instructional Quality Commission) and the State Board of Education (SBE) at their January and March 2008 meetings respectively, feedback from the four focus group meetings held in May and June 2008, and public comment. They were adopted by the SBE at its meeting on November 5, 2008. [The phrase “(now renamed the Instructional Quality Commission)” is italicized and is proposed as an addition.]

The guidelines recommended by the Curriculum Commission and approved by the SBE will directed the work of the Curriculum Framework and Evaluation Criteria Committee (CFCC) when it completed its work in February–June 2009. [Note that the word “will” has strikethrough and it is proposed for deletion. The suffix “ed” has been added to the word “direct” and is proposed as an addition. The words “when it completed its work in February–June 2009” is italicized and is proposed as an addition.]

- General principles. The updated History–Social Science Framework for California Public Schools (History–Social Science Framework) shall:

- Retain its narrative format.

- Keep the basic overarching goals and objectives of the current History–Social Science Framework.

- Be aligned to the state-adopted history–social science standards adopted by the SBE in October 1998.

- Include accurate information based on current and confirmed research.

- When appropriate, follow the organization and design of other standards-based frameworks.

- Be easy to use both for teachers with educational backgrounds in history–social science, and those without such experience.

- Include information that supports the development of academic vocabulary.

- Be accessible and inclusive to all students.

- Promote the values of civic engagement and civic responsibility.

- The History–Social Science Framework should address the “big picture” by taking a look at global perspectives at particular eras in time (using broad, synthetic statements).

- Align to the Literacy Standards for History/Social Studies within the California Common Core State Standards for English Language Arts and Literacy in History/Social Studies, Science, and Technical Subjects, as appropriate. [The preceding bullet is italicized and proposed for addition.]

- Develop a new chapter on assessments, including information on 
entry-level/diagnostic, progress monitoring, and summative assessments, that inform teachers on how to use assessments to shape instruction.

The CFCC should use as a model Chapter 6 in the Reading/Language Arts Framework for California Public Schools, Kindergarten through Grade Twelve (Reading/Language Arts Framework), with adaptations for those elements that are unique to history–social science instruction. [The preceding sentence contains strikethrough and it is proposed for deletion] The chapter should include the following information:

- Assessments should be based on multiple measures of student ability, and include a variety of techniques for various learning styles and levels of readiness.

- Guidance for teachers on how to use assessment data.

- The latest scholarly research on effective assessment strategies.

- Suggestions for performance assessments and other creative ways of assessing student mastery of the material.

- Information about the current statewide assessment system in history–social science. [The preceding sentence contains strikethrough and it is proposed for deletion.]

- Examples of effective assessments and rubrics.

- Assessments should test student mastery of higher-order thinking skills, not just recitation of specific facts. The Historical and Social Sciences Analysis Skills should be an integral part of any assessment system.

- Develop a new chapter on universal access, which includes strategies for differentiating instruction to meet the needs of all students, including English language learners, students with disabilities, and advanced students. This chapter should support teachers in providing standards-aligned instruction to all learners to close the achievement gap.

- The CFCC should use as a model Chapter 7 in the Reading/Language Arts Framework, with adaptations for those elements that are unique to history–social science instruction. [The preceding sentence contains strikethrough and it is proposed for deletion.] This chapter should include the following information:

- Suggestions for making academic vocabulary accessible to all students.

- Provide specific models of differentiating instruction.

- Provide specific support strategies for:

  - English language learners.

  - Advanced learners.

  - Students with disabilities.

  - Students with reading skills below grade level.

- Provide support for teachers in meeting the needs of students with diverse cultural and educational backgrounds.

- Develop a new chapter on instructional strategies and professional development, to provide guidance to both new and experienced teachers of history–social science.

This new chapter should include the following information:

- Promote instructional strategies based on current and confirmed research that support student engagement in the history–social science curriculum.

- Provide support for the use of technology in the history–social science classroom.

- Provide examples of different methods of instruction.

- Provide support for a collaborative teaching model that encourages teachers to work with colleagues across subjects and grade levels.

- Provide resources on professional development opportunities.

- Provide information for district administrators to support the history–social science curriculum and instruction.

- Provide strategies for instruction that incorporate the history–social science analysis skills.

- Update the narrative to reflect current and confirmed scholarly research in history–social science, and changes in California, and the United States, and the world since the last edition of the History–Social Science Framework was published. [The commas after “California” and “States,” and the words “and the world” are italicized and proposed for addition. The word “and” after “California is strikethrough and proposed for deletion.]

- Update the narrative to improve the inclusivity of the History–Social Science Framework, and to reflect the contributions of all groups to the history of California and United States.

Examples:

- Include information about the Mendez v. Westminster court case, and its significance in the history of school desegregation.

- Insert a reference to Sikhism in the course description for the ninth-grade elective “World Religions.”

- Update the current appendices to reflect new scholarship and new emphases in history–social science education.

- Either remove Appendix A (“Nationalism, Free Markets, and Democracy in the Contemporary World”), and integrate this material into the tenth grade narrative, or update with more relevant contemporary examples.

- Update and integrate the content of Appendix D (“The World History Sequence at Grades Six, Seven, and Ten: Content, Breadth/Depth, and Coverage Issues with Some Local Options”) into the narrative of the History–Social Science Framework.

- Remove Appendix E (“Examples of Careers in History–Social Science”) and incorporate information about the relevance of history–social science education to career paths into the narrative of the History–Social Science Framework.

- Update Appendix F (“Using Primary Sources in the Study of History”) and include information about the use of primary sources in all grades, including elementary.

- Remove Appendix G (“Bowling Alone: America’s Declining Social Capital”).

- Revise Appendix H (“History–Social Science and Service Learning”) or replace it with a broader emphasis on civic education throughout the History–Social Science Framework.

- If possible, include the revised list of recommended literature in history–social science that is currently being updated by the California Department of Education on a CD-ROM attached to the History–Social Science Framework. This CD-ROM could also contain the primary source documents required to be included by statute (see guideline #8 below). [The preceding sentences contain strikethrough and they are proposed for deletion.]

- Consider adding new appendices based on the following:

  - The Environmental Principles and Concepts developed as part of the Education and the Environment Initiative

  - The Partnership for 21st Century Skills, and issues of technology in history education in general (This issue was addressed in the body of the framework.) [The preceding parenthetical is in italics and is proposed for addition.]

- Statutory Requirements

The History–Social Science Framework update must reflect changes in statute affecting the history–social science curriculum that have been enacted since the last revision of the History–Social Science Framework, in addition to continuing statutes. These statutes specifically require that certain topics be referenced in the

History–Social Science Framework. These include, but are not necessarily limited to, the following topics:

- Financial preparedness literacy, including, but not limited to, budgeting and managing credit, student loans, consumer debt, and identity theft security (Education Code [EC] Section 51284) [Note that the word “preparedness” has strikethrough and it is proposed for deletion. The words, “literacy, including, but not limited to, budgeting and managing credit, student loans, consumer debt, and identity theft security” are italicized and are proposed for addition.]

- The Great Irish Famine of 1845-1850 (EC Section 51226.3)

- Cesar Chavez and the history of the farm labor movement, and the role of immigrants, including Filipino Americans, in that movement (EC Section 51008) [The words, “and the role of immigrants, including Filipino Americans, in that movement” are italicized and are proposed for addition.]

- Inclusion of the Declaration of Independence, the United States Constitution, the Federalist Papers, the Emancipation Proclamation, the Gettysburg Address, and George Washington's Farewell Address, the Magna Carta, the Articles of Confederation, and the California Constitution (EC Section 33540) [The words, “the Magna Carta, the Articles of Confederation, and the California Constitution” are italicized and are proposed for addition.]

- Encourage instruction that promotes an understanding of the governments of California and the United States of America, including, but not limited to, the development of democracy and the history of the development of the United States Constitution (EC Section 33540) [The sentence above is italicized and proposed for addition.]

- Description of how content can be delivered to intentionally build all of the following skills:

  - Creativity and innovation, including, but not limited to, thinking creatively, working creatively with others, and implementing innovations

  - Critical thinking and problem solving, including, but not limited to, reasoning effectively, using systems thinking, making judgments and decisions, and solving problems

  - Collaboration, including, but not limited to, working effectively in diverse teams, adapting to change and being flexible, demonstrating initiative and self-direction, working independently, demonstrating productivity and accountability, and demonstrating leadership and responsibility

  - Communication, including, but not limited to, communicating clearly and effectively through reading, writing, and speaking

  - Construction and exploration of new understandings of knowledge through the integration of content from one subject area to another to provide pupils with multiple modes for demonstrating innovative learning. (EC 60207) [The five numbered items and the preceding sentence above are italicized and are proposed for addition.]

- The Environmental Principles and Concepts developed by the California Environmental Protection Agency and adopted by the SBE (Public Resources Code Section 71301)

The Curriculum Commission and the SBE directs the CFCC to incorporate into the evaluation criteria for kindergarten through grade eight the following topics that are referenced in code that are required to be included in instructional materials. These topics include: [Note that the word “Curriculum” has strikethrough and is proposed for deletion.]

- Information to guide the selection of textbooks that contain sections that highlight the life and contributions of Cesar Chavez, the history of the farm labor movement in the United States, and the role of immigrants, including Filipino Americans, in that movement (EC Section 51008). [The sentence above is italicized and proposed for addition.]

- Portrayal of the contributions of both genders, diverse ethnic and cultural groups, lesbian, gay, bisexual, and transgender Americans, persons with disabilities, and the role of entrepreneur and labor in the development of California and the United States (EC Section 60040). [The words “and cultural” and “lesbian, gay, bisexual, and transgender Americans, persons with disabilities” are italicized and proposed for addition.]

- Humanity’s place in ecological systems and the necessity for protection of our environment (EC Section 60041, and Public Resources Code Section 71301)

- Civics education, including material that impresses upon students the importance of American values and civic responsibilities (EC Section 60200.5)

- The life of Martin Luther King, Jr. (EC Section 60200.6)

The Curriculum Commission and the SBE recommend that the CFCC incorporate the following areas of study that are encouraged within code. [Note that the word “Curriculum” has strikethrough and is proposed for deletion.] These include:

- The Mexican Repatriation Program (Senate Concurrent Resolution 58, 
Chapter 128, Statutes of 2007)

- Labor History Week (EC Section 51009)

- Understanding the wise use of natural resources (EC Section 51221)

- Instruction on World War II, the Korean War, and the Vietnam War that incorporates oral or video history of American soldiers, and instruction on the Bracero program that incorporates oral or video histories of individuals who were involved in that program (EC Section 51221.3) [Note that the words “and instruction on the Bracero program that incorporates oral or video histories of individuals who were involved in that program” are italicized and are proposed for addition.]

- Instruction on the “Secret War” in Laos and the role of Southeast Asians in that war that includes personal testimony and oral/video histories. (EC Section 51221.4)

- Materials and content resources for teaching about civil rights, human rights violations, slavery, and the Holocaust (EC Section 51226.3)

- The federal Constitution Day requirement (118 Stat. 2809, 3344-45)