| California Department of Education Executive Office SBE-003 (REV. 09/2011) ilsb-plsd-sep14item01 |  | ITEM #09 |  |  |
| --- | --- | --- | --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION SEPTEMBER 2014 AGENDA |  |  |  |
| ### SUBJECT Update on the State Implementation Plan for California Next Generation Science Standards for Public Schools, Kindergarten through Grade Twelve. |  |  |  | Action |
|  |  |  |  | Information |
|  |  |  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

As required by California Education Code (EC) Section 60605.85 (b), the State Superintendent of Public Instruction (SSPI), in consultation with the State Board of Education (SBE), must submit a schedule and implementation plan for integrating the adopted science content standards into the state educational system. It is anticipated the implementation plan will be presented to the SBE for action in November 2014.

The process for developing the California State Implementation Plan for the Next Generation Science Standards (NGSS) has encompassed several steps, including the convening of a Strategic Leadership Team (SLT). The SLT comprised of representatives from key education organizations, business representatives, and representatives from each level of education, pre-kindergarten through postsecondary. The SLT met in March, April, and May 2014, to develop implementation strategies for the California Department of Education (CDE), local educational agencies, and support providers. The K–12 Alliance of WestEd facilitated this process. The CDE then requested input from the CDE Division Directors and integrated that feedback into the draft document. The CDE posted the draft implementation plan for public comment from July 25–August 25, 2014. The comments and CDE response to them will be provided in Attachment 2 and the complete set of comments will be included in Attachment 3.

The State Implementation Plan for the NGSS is based on the following strategies presented in the SBE-adopted Common Core State Standards Systems Implementation Plan for California and for the English Language Development Standards Implementation Plan, with the addition of an eighth standard specific to CA NGSS.

- Facilitate high quality professional learning opportunities for educators to ensure that every student has access to teachers who are prepared to teach to the levels of rigor and depth required by the NGSS.

- Provide NGSS-aligned instructional resources designed to meet the diverse needs of all students.

- Develop and transition to NGSS-aligned assessment systems to inform instruction, establish priorities for professional learning, and provide tools for accountability.

- Collaborate with parents, guardians, and the early childhood and extended learning communities to integrate the NGSS into programs and activities beyond the kindergarten through grade twelve school setting.

- Collaborate with the postsecondary and business communities and additional stakeholders to ensure that all students are prepared for success in career and college.

- Seek, create, and disseminate resources to support stakeholders as NGSS systems implementation moves forward.

- Design and establish systems of effective communication among stakeholders to continuously identify areas of need and disseminate information.

- Build coalitions to ensure a common message and to sustain momentum during implementation.

The timeline for completion is:

CA NGSS Implementation Plan

| Date | Entity | Action |
| --- | --- | --- |
| July 25, 2014 | Professional Learning Services Division (PLSD) | Posting of initial draft plan on the CDE Web site and announcement of 30-day public comment |
| July 25-August 25, 2014 | Public Review | Comments received by CDE at nggs@cde.ca.gov |
| September 3-4, 2014 | State Board of Education | Receive information on draft plan and public comment |
| September-October, 2014 | PLSD | Revise plan based on public comment and SBE input |
| October 15, 2014 | PLSD | Post revised plan on the CDE Web site |
| November 13-14, 2014 | SBE | Action on final plan |

RECOMMENDATION

The CDE recommends that the SBE authorize SBE liaisons and staff to work with CDE to review public comments and develop a revised implementation plan for approval in November 2014.

BRIEF HISTORY OF KEY ISSUES

EC Section 60605.85 (a) required the SSPI to submit a set of revised Science Content Standards for California Public Schools, Kindergarten through Grade Twelve to the SBE by July 31, 2013, and the adoption, rejection, or modification of those standards by November 30, 2013. The revised science standards for California must be based upon the nationally developed NGSS. These standards were submitted and adopted by the SBE on September 4, 2013. The standards as well as additional information are available on the NGSS Web site at http://www.nextgenscience.org/ and on the CDE Web site at http://www.cde.ca.gov/pd/ca/sc/ngssintrod.asp.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

N/A

FISCAL ANALYSIS (AS APPROPRIATE)

N/A

ATTACHMENT(S)

Attachment 1: Draft State Implementation Plan for California Next Generation Science Standards for Public Schools, Kindergarten through Grade Twelve (79 Pages).

http://www.cde.ca.gov/pd/ca/sc/documents/scienceimplementationplan072414draft.pdf

Attachment 2: Summary of Public Comment with the CDE Response

Attachment 3: Public Comment on Draft State Implementation Plan for California Next Generation Science Standards for Public Schools, Kindergarten through Grade Twelve

Expected Availability of Attachments 2 and 3: These documents will not be ready until August 28, 2014, due to the fact that they are dependent on the window for receiving public input, which does not conclude until August 25, 2014. The 30-day public review extends from July 25–August 25, 2014.