- Educational Testing Service

CDE Agreement # CN150012

EXHIBIT A

SCOPE OF WORK

I.  	GENERAL SCOPE:

The contractor will conduct the development, administration, scoring, reporting and analysis of assessments and technology support for the California Assessment of Student Performance and Progress (CAASPP) system as defined in California Education Code (EC) sections 60601 through 60649 as described herein.

This agreement also incorporates all requirements established in Chapter 5 (commencing with Section 60600 of Part 33), of the Education Code, and the regulations promulgated by the State Board of Education to implement the California Assessment of Student Performance and Progress (CAASPP) System as set forth in subchapter 3.75 (commencing with Section 850) of Title 5 of the California Code of Regulations and their amendments, which are incorporated herein by this reference. The Agreement shall be interpreted to include all these items as though fully set out herein.

II.  	 PROJECT MONITORS:

The CDE assigns Lily Roberts, LRoberts@cde.ca.gov, 916-319-0803 as state project monitor to oversee this project. Said monitor is not authorized by the state to make any commitments or make any changes which will affect the price, terms or conditions of this agreement without a formal contract amendment.

The contractor assigns Tom Foster, TFoster@ets.org, 916-403-2409 as contractor project monitor to oversee this project. Said monitor is not authorized by the state to make any commitments or make any changes which will affect the price, terms or conditions of this agreement without a formal contract amendment.

This page was intentionally left blank.

- Educational Testing Service

CDE Agreement # CN150012

2016–2018 California Assessment of Student Performance and Progress (CAASPP) Administration

***DRAFT*** Scope of Work
Contract CN150012

April 21, 2015

This page was intentionally left blank.

# Table of Contents

TASK 1: Comprehensive Plan & Schedule of Deliverables	1

1.1. Work Plan, Narrative Schedule, and Timeline	2

1.2. Orientation Meeting	2

1.3. Management Meetings	3

1.3.A. Weekly Meetings	3

1.3.B. Annual Meetings	4

1.3.C. State Board of Education (SBE) Meetings	4

1.3.D. Technical Advisory Group (TAG) Meetings	4

1.4. Coordination, Continuous Improvement, and Independent Evaluation	4

1.4.A. Coordination with the Consortium (UCLA) and CDE/SBE Entities and Staff	5

1.4.B. Development of Plan for Continuous Improvement	5

1.4.C. Coordination with the Independent Evaluator	5

1.4.D. Responding to Concerns	6

1.5. Transition of Contracts	7

1.6. Records and Minutes	7

1.7. Accomplishments and Monthly Progress Reports	7

1.8. Document Format and Style	9

1.9. CDE Notification and Approval Schedule	9

Issue Escalation Procedure	9

TASK 2: Program Support Services	12

2.1. Coordinators	12

2.2. Administration Management System LEA Support	13

2.3. Data Driven Improvement	13

2.4. Technical Assistance Center	14

Tier 1: California Technical Assistance Center (CalTAC)	14

Tiers 2 and 3: Technology Support (xBT and AIR)	15

Training of CalTAC Staff, Training Materials, and Informational Updates	15

Annual and Periodic Customer Support Services Reports	17

2.5. Student Accessibility Tool	17

2.6. Internet Resource Site	17

2.7. Workshops and Webcasts	18

Webcasts	18

In-person Training	18

Videos and Narrated PowerPoint Presentations	18

2.8.	Local Assessments: Smarter Balanced Interim Assessments and Digital Library	18

2.8.A. Smarter Balanced Interim Assessments	19

2.8.B. Digital Library of Formative Assessment Resources	19

TASK 3: Technology Services	28

3.1. School Technology Readiness	29

3.2. Assessment Delivery System	29

3.2.A. Project Management Plan	29

3.2.B. System Requirements	32

TASK 4: Test Security	45

4.1. Test Security Plan	45

4.2. Test Administration Monitoring	48

4.3. Investigating Security Breaches	50

TASK 5: Accessibility and Accommodations	52

5.1 Accessibility Plan for Computer-based and Paper-pencil Tests	52

5.1.A. Computer-based Tests	52

5.1.B. Paper-pencil Tests	54

5.2. Individualized Aids	56

TASK 6: Assessment Development	57

6.1. Assessment Design	57

6.2. Item and Task Development	61

6.2.A. Pilot Testing	66

6.2.B. Field Testing	67

6.2.C. Forms Construction	68

6.3. Standard Setting (excluding Smarter Balanced assessments)	68

6.5. Released Test Questions (excluding Smarter Balanced assessments)	73

6.6. Analysis of Test Results	75

6.7. Item Banks	76

6.7.A. California Item Bank	76

6.7.B. ETS Item Banking Information System (IBIS)	76

6.8. Activities in Support of Future Assessment Development	78

TASK 7: Test Administration	82

7.1. CAASPP Test Administration Requirements	83

7.1.A. Manuals	83

7.2. Paper-Pencil Administrations	86

7.3. Computer Based Assessments	95

7.4. Contracting with LEAs for STS for Dual Immersion-Programs	102

TASK 8: Scoring and Analysis	103

8.1. Scoring	103

8.2. Analysis of Test Results	116

TASK 9: Reporting	123

9.1. Reporting to Local Educational Agencies	123

9.2. Reporting to the CDE—Public Reporting Web Site	129

9.3. Data Files	133

9.4. Secure File Transfer System	134

9.5. Technical Report	135

9.6. Other Analyses or Reports	137

Appendixes

Appendix A—Sample Program Schedule

Appendix B—Reporting Expectations for Special Studies and Research Projects

Appendix C—Minimum System Requirements

Appendix D— Summary of Embedded Universal Tools, Designated Supports, and Accommodations Supported by the CAASPP 2015 Test Delivery System

List of Figures

Figure 1.  CAASPP Assessment Technology Platform	28

Figure 2.  CAASPP Assessment Delivery System	33

Figure 3.  Scalable Architecture of the CAASPP Assessment Delivery System	34

Figure 4.  Test Design Team Structure	57

Figure 5.  Overall Schematic of the Test Delivery System	99

Figure 6.  Computer-based Test Delivery — Scoring and Reporting Flow	103

Figure 7.  Paper-pencil Test Delivery—Scoring and Reporting Flow	104

List of Tables

Table 1.  Planned CAASPP Training Workshops and Webcasts	21

Table 2.  Summary of Process for Designing and Developing California Assessments.	61

Table 3.  Summary of Process for Item and Task Development for California Assessments	62

Table 4.  Sample Panel Configuration for Primary Language ALD Workshops	69

Table 5.  Sample Panel Configuration for Alternate Assessment ALD Webinars	69

Table 6.  Sample Panel Configuration for Primary Language Standard Setting Workshops	70

Table 7.  Sample Panel Configuration for Alternate Assessment Standard Setting 
Workshops	71

Table 8.  Distribution Plans for the CAASPP Assessments	82

Table 9.  Estimated CAASPP Test Takers	83

Table 10.  Estimated Print Quantities* for Paper-Pencil Test Booklets, Answer 
Documents, Response Booklets, and School and Grade 
Identification Sheets	88

Table 11a.  Secure Browser Support Policy for Operating Systems	96

Table 11b.  Web Browser Support Policy	96

Table 12.  Supported Operating Systems and Minimum Requirements, 
as of March 30, 2015	97

Table 13.  Summary of Assessment Delivery Components.	98

Table 14.  Online Appeals: Types and Conditions	101

Table 15.  Performance Task and Constructed-Response Scoring by Content 
Area and Grade	106

Table 16.  CAASPP Test Results Provided to LEAs	124

Table 17.  CAASPP Test Results Provided to the Public	130

Table 18.  Planned CAASPP Technical Report by Administration	135

# TASK 1: Comprehensive Plan & Schedule of Deliverables

Task 1 describes the activities, assumptions, and requirements to manage and administer the California Assessment of Student Performance and Progress (CAASPP) assessment system for the 2015–16, 2016–17 and 2017–18 school years. Educational Testing Service (ETS) is the prime contractor and is responsible for the overall management and administration of the services provided to the state under this contract and will work closely with the California Department of Education (CDE) to ensure the success of the CAASPP administrations in the next three years.

While ETS outlines individual roles and responsibilities in greater detail within the Scope of Work (SOW), the following text provides a high-level summary of responsibilities for ETS and its partners:

- ETS will manage the administration, scoring, and reporting activities and have overall responsibility for the constructed-response human scoring and artificial intelligence scoring. In addition, ETS will manage the logistics and coordination of all management meetings, along with the development of all relevant materials. ETS will also provide Help Desk services and psychometric support. ETS will provide item development for all state-specific assessments: the California Next Generation Science Standards (CA NGSS and CA NGSS Alternate) assessments, the primary language assessments, and the California Alternate Assessments (CAA) in English–language arts (ELA) and mathematics. ETS will host and provide support for the Test Operations Management System (TOMS).

- American Institutes for Research (AIR) will provide hosting and support for its test delivery system and online reporting system, a component of the overall CASSPP Assessment Delivery System. These are the same systems used in the successful spring 2014 Field Test and in the current spring 2015 operational administration.

- Measurement Incorporated (MI) will assist ETS in the constructed-response scoring for various grades for all assessments related to Smarter Balanced, including both human scoring and artificial intelligence scoring. These are the same capabilities and systems used in in the Smarter Balanced Field Test activities and in the current spring 2015 operational administration.

- Accenture will publish the printed manuals and paper-pencil assessments, provide fulfillment services, and manage the test materials.

- Center for Assessment will assist with the design of California’s new CA NGSS (including the CA NGSS Alternate), primary language, and CAA tests, as well as to assist with the coordination of activities involving the CDE’s external evaluator.

- Red Dog Records (RDR) will serve as the program’s multimedia experts and provide video (live and animated) production, Web broadcast, and audio-visual support services.

- In-Touch Insight Systems (In-Touch) will continue its role to provide test security site visit audits to CAASPP for this contract.

For simplicity, ETS and its partners will be referred to as ETS in this SOW except where reference to specific proprietary systems or methodologies are noted.

## 1.1. Work Plan, Narrative Schedule, and Timeline

As part of project initiation, ETS will draft a work plan and a supporting project schedule for the delivery of the CAASPP System. During the initial start-up meeting with CDE and State Board of Education (SBE) staff, ETS will review and finalize these draft documents. Each subsequent contract year, ETS will revise the work plan and scheduled documents, focusing on fine-tuning the plans for each coming contract year.

The work plan will include key tasks with dependencies, deliverables with corresponding durations, assigned resources, and responsible staff members. The comprehensive schedule, and accompanying Gantt chart, will clearly identify milestone tasks, resource names, and actual start and finish dates. The most current, approved versions of these documents will reside on a shared, password-protected virtual workspace accessible by both the CDE and ETS. The schedule will also be made available to the CDE in Microsoft Project (MPP) format upon request. For the purposes of initial planning, the proposed work plan is included as Appendix A.

ETS will use a three-step process to develop the work plan for the CAASPP System:

- First, ETS will use Council of Chief State School Officers (CCSSO) operational best practices to detail the plans.

- Second, ETS will develop a program summary—referred to as the scope of work—based on the agreed-upon requirements that outlines the work that ETS will perform and how it will be performed.

- Finally, ETS will use process documents to guide day-to-day activities.

The timeline referenced in Appendix A is a sample to be used for the initial planning discussions. All schedules will be reviewed and approved by the CDE prior to implementation. It is to be a working document that is updated on an ongoing basis throughout the life of the contract.

Regular reviews of the schedule will be conducted during internal weekly meetings and client status meetings. The purpose of these reviews is to discuss recent progress of scheduled tasks, upcoming tasks, and the likelihood of remaining on schedule with key upcoming critical milestones.

The schedule will include detailed information on resource and work associated with the Assessment Delivery System to comply with State Information Technology (IT) Management Guidelines.

## 1.2. Orientation Meeting

Within two weeks of the effective date of the contract, ETS will arrange, attend, and facilitate an orientation meeting with the CDE and SBE staff. ETS will coordinate the agenda with the CDE. ETS staff will include project management, assessment, psychometric, scoring, and technology leads. The purpose of the orientation meeting is to plan for the execution of the full contract, with particular emphasis on the first year. ETS will also focus on the required work and services needed to fulfill the full scope of the CAASPP System activities from planning through reporting. The meeting participants will review the proposed work plan and implementation schedule, obtaining specific information, data, criteria, and/or instructions necessary to finalize that plan. ETS project managers will use their expertise to plan and facilitate this meeting, which will include such tasks as setting an agenda to cover each SOW task as well as producing minutes.

The orientation meeting will be held in downtown Sacramento over two consecutive days. ETS will invite a representative from the Smarter Balanced Assessment Consortium leadership to the orientation meeting to verify that the 2015 administration functioned according to Smarter Balanced’s needs and to discuss any changes needed for 2016.

After the orientation meeting, ETS will submit the meeting minutes via e-mail to the appropriate CDE members as identified by the CDE CAASPP lead administrator for their review and approval. These minutes will address all tasks, with particular emphasis on questions or issues needing resolution, contract implementation timelines, and agreed-upon decisions. ETS also will submit the work plan and schedule that incorporates any changes agreed upon during the orientation meeting no later than ten (10) days following the orientation meeting.

## 1.3. Management Meetings

ETS will schedule and facilitate management meetings with the CDE. ETS will be responsible for the meeting costs, including travel expenses, for its staff. ETS will continue to scope each meeting, develop agendas, and produce appropriate materials. All management meetings will take place in Sacramento, unless otherwise directed by the CDE.

ETS will submit minutes of all meetings via e-mail to the appropriate CDE staff. These minutes will address all tasks, with particular emphasis on questions or issues regarding contract fulfillment, coordination, and scope of work modifications or enhancements. ETS will post these meeting minutes to the Web-based, password-controlled enterprise system.

### 1.3.A. Weekly Meetings

ETS will hold weekly management meetings with the CDE to update and assure that the CDE is informed of all decisions. The weekly management meeting may include managers of:

- California Technical Assistance Center (CalTAC)

- Statistical Analysis

- Information Technology

- Operations

- Test Development

- Appropriate Subcontractor Coordinators

ETS will involve the CDE Contract Monitor and CDE State Project Manager in all meetings that involve the CAASPP Assessment Delivery System. All weekly meetings will be in person at CDE offices with other key staff joining by conference call as appropriate. The CDE reserves the right to require any contractor or subcontractor to attend the meetings in person instead of via telephone or videoconference when the CDE deems it warranted.

ETS will issue a weekly agenda in consultation with the CDE. The agenda will cover the current scope of work in progress. At the beginning of each month, ETS will circulate a calendar for the month based on the project plan agreed upon at the weekly meetings.

During the weekly management meetings, ETS and the CDE may decide to hold separate weekly meetings for specific topics.

For all meetings, including face-to-face and video- or audio-conferences, ETS will facilitate the meeting, record minutes of the meeting, and track completion of assignments. The minutes will be distributed to the CDE and the entire team within two days of the management meetings.

### 1.3.B. Annual Meetings

ETS will annually host a three-day meeting in Sacramento which gathers key ETS CAASPP team members to meet with CDE program managers. Staff members from the SBE and from the Department of Finance (DOF) will be invited to attend the planning meeting. Those who cannot attend in person may attend via video and audio conference. The purpose of the meeting is to plan the upcoming year, including detailing any changes to the scope of work and timeline. ETS will provide a draft timeline in MS-Project for all to review. The outcome of this planning meeting will be an update to the draft timeline and any changes to the SOW requested by the SBE testing liaisons and SBE staff, the CDE CAASPP Program managers, and the DOF. The minutes and updated project documents will be distributed to the CDE and the entire team within ten (10) days of the annual planning meetings.

### 1.3.C. State Board of Education (SBE) Meetings

Every time the SBE conducts public meetings, ETS project managers and relevant ETS officers will attend as required by the CDE. When the SBE is discussing issues that may require ETS’s expertise, such as test development or statistics, the appropriate specialists or subcontractors will also attend the meetings and be available to answer questions or provide background as requested. At the CDE’s and SBE’s direction, ETS will continue to offer special presentations to the SBE, based on ETS’s expertise and experience.

### 1.3.D. Technical Advisory Group (TAG) Meetings

The ETS Executive Director or designee will coordinate with the CDE CAASPP project manager and psychometrics manager on the development of the TAG agenda topics. During the meeting, ETS will facilitate discussion about topics related to ETS activities by bringing the appropriate staff into the discussion and by providing the materials needed by the CDE, TAG members, and the independent evaluator. Additional staff will be available via teleconference as needed. ETS is responsible only for ETS staff travel and material preparation, as required.

For each meeting, ETS will work with the CDE to determine what data and information should be presented, and ETS will provide clear agenda topics and supporting materials to the CDE at least five business days before the meeting. Within five business days of the meeting, ETS will provide proposed studies or analysis plans to the CDE for review and approval.

## 1.4. Coordination, Continuous Improvement, and Independent Evaluation

In addition to the expertise of staff proposed as core members of the ETS team, ETS will provide the CDE with additional support as needed from a group of senior ETS advisors, all of whom were former state assessment directors.

### 1.4.A. Coordination with the Consortium (UCLA) and CDE/SBE Entities and Staff

ETS will coordinate activities to administer the CAASPP assessments with related efforts led by the CDE/SBE, including the CDE Senior Assessment Fellows, and, at the direction of the CDE, involving the CDE communications contractor, the Smarter Balanced Assessment Consortium, the K–12 High Speed Network (K12HSN), and the California Longitudinal Pupil Achievement Data System (CALPADS). Coordination efforts will include the independent project oversight consultant (IPOC) and the independent verification and validation (IV&V) consultant, if available and at the direction of the CDE.

ETS will manage the overall coordination activities with the Smarter Balanced Consortium and with CDE/SBE entities and staff. ETS will assign a project manager to take the lead in developing the coordination plan, handling the logistics of the monthly coordination meetings, and establishing and maintaining the secure coordination Web site.

ETS also will develop a communication plan for each annual administration that will contribute to and coordinate with the efforts by the CDE-led team. Specific activities may include, but are not limited to:

- Operating caaspp.org, the Web site for local educational agencies (LEAs) and their staff that presents information about the administration activities for annual administrations;

- Producing Webcasts and online videos about CAASPP that are geared toward school and LEA staff, test administrators, technology coordinators, and student data coordinators;

- Developing a list of frequently asked questions (FAQs) about the annual administration processes and procedures; and

- Coordinating and staffing communication opportunities at statewide and regional association conferences such as the CDE North/South Assessment and Accountability Meetings, the annual conference for the California Educational Research Association, or Regional Assessment Network meetings.

All content of the communications under the communications plan with LEAs and the public regarding annual CAASPP administrations will be approved by the CDE and the SBE liaison and staff, where appropriate, before being disseminated.

### 1.4.B. Development of Plan for Continuous Improvement

ETS will work with the CDE to create a three-year plan supporting continuous improvement of the CAASPP System. In addition to opportunities for improvement identified in the three-year plan, ETS will propose, based on its experience, opportunities for program improvements that emerge over the course of the contract. ETS will submit the plan to the CDE in an agreed-upon timeline and refine it to reflect feedback from the CDE, SBE staff, the SBE, and the CDE’s external evaluator.

### 1.4.C. Coordination with the Independent Evaluator

The law establishing the CAASPP assessment program called for an independent evaluation of the impact of this requirement and of the quality of the CAASPP assessments. ETS will provide support to the CDE in response to requests from the independent evaluator.

#### Attend Meetings

ETS will participate in meetings convened by the CDE and the independent evaluator for the purposes of identifying and providing the information necessary for the evaluation. The ETS Executive Director and Director of Operations will have access to other ETS and subcontractor staff that may participate in the meetings. ETS assumes that meetings related to the independent evaluation will be held at the CDE offices or by phone.

#### Provide Materials and Data

ETS will provide all necessary materials and data to the independent evaluator. In recognition of the independent evaluator’s need to gather data to further his or her analysis of the CAASPP System, ETS will:

- design test materials (e.g., online surveys, online tests, paper answer documents, and paper test booklets) to include questions that gather these data

- coordinate with the independent evaluator and the CDE to identify desired changes to these questions prior to the annual review of the test materials, detailed later in this SOW

- deliver the questionnaire response data to the independent evaluator and to the CDE on a schedule developed with the evaluator

- continue to provide the evaluator with student demographic information and student item responses, in addition to questionnaire data

ETS will work with the independent evaluator and the CDE to comply with data sharing requests per the independent evaluator’s preference. For example, the independent evaluator may request that ETS send demographic data via CD-ROM and post item responses to a secure file transfer protocol site. At a minimum, ETS will:

- submit a Final Item Analysis and equating file to the independent evaluator following each administration

- submit updated student data files for each administration after annual processing has been run

For each material requested, ETS will work with the independent contractor and the CDE to develop a plan and timeline for submission. ETS assumes that requests will be provided in writing to the ETS Executive Director and Director of Operations and that ETS will have ten (10) business days, at minimum, to respond to the request.

### 1.4.D. Responding to Concerns

ETS assumes that the independent evaluator will submit the first report to the CDE on October 31, 2015, and that an electronic copy of the report will be provided to ETS at the same time. ETS will provide a written response, within four weeks of receipt of the report, to any concerns that may be included in the independent evaluator report. The response will include a process and timeline for resolving each concern reported by the independent evaluator. ETS assumes that any subsequent responses to evaluator comments will be provided in electronic copy to ETS and that ETS will provide written responses within four weeks of receipt of each subsequent request.

## 1.5. Transition of Contracts

As the contractor for the previous CAASPP contract, ETS will ensure the continued operations of CAASPP. ETS will also continue maintaining the comprehensive archive of data and materials from previous CAASPP and Standardized Testing and Reporting (STAR) administrations.

At the end of the contract, ETS will work closely with CDE to develop and implement a plan and schedule for transition to another vendor. ETS will deliver all required materials, including, but not limited to, reports and electronic data files, applications and supporting documents, and other materials developed for the CAASPP System, including test blueprints, item and test specifications, test packages for online tests, and paper-pencil test forms for any assessments under development, on a schedule to be determined by the CDE to the CDE by December 31 of the year following the last test administration. One ETS project management team member will serve as a transition manager to assist the new contractor until the end of the calendar year in which the last administration is completed.

## 1.6. Records and Minutes

At all meetings, including, but not limited to, management meetings and program committee meetings, ETS will take minutes, record information, and document any assignments or tasks for follow up. These notes will be formatted in a format required by the CDE. ETS will keep secure electronic copies of all the records throughout the life of the CAASPP Program.

Each set of minutes will include listings of all those present and their contact information. ETS will review the contact information of attendees to determine if it has changed and update the CDE, if appropriate. At the Orientation Meeting, ETS will propose a format for the meeting minutes for CDE approval.

ETS will distribute minutes from weekly meetings and other conference calls to the CDE for approval within two business days. For all other meetings, ETS will distribute minutes to the CDE for the CDE’s approval within five business days of the meeting. When approved, all relevant CAASPP team members will receive copies.

ETS will keep secure electronic copies of all the records for five years after the final payment of the contract period.

## 1.7. Accomplishments and Monthly Progress Reports

ETS will communicate all accomplishments to demonstrate the CDE expenditures on the CAASPP Program by means of a monthly accomplishments report submitted as part of the invoice. The accomplishments report is to be presented as a detailed narrative attached to each invoice from ETS to the CDE. The accomplishments report is to be sorted by test and test administration and provide a breakdown of the costs invoiced per task or subtask in the scope of work. The summary shall also include a history of invoices previously submitted to date.

ETS will submit this report to the CDE by the fifteenth of the following month. A hardcopy original will be delivered to the CDE. The CDE will share accomplishments reports with SBE staff. In the event that this report will be delayed beyond the fifteenth of the following month, ETS will notify the CDE of the expected date of delivery by the seventh of that month.

In addition, ETS will submit to the CDE by the fifteenth of the following month, a monthly progress report that will provide CDE-required details including the identification of issues, risks, and their resolutions; changes to the program documentation; and flags of the items that are directly related to the CAASPP Assessment Delivery System.

#### Early Identification of Potential Issues

ETS will develop a risk management plan for the CAASPP System with review and approval by the CDE. The plan will also identify what actions ETS can take to offset those risks, along with contingency plans if preventive actions cannot be implemented. The ETS Executive Director, along with staff from the ETS Corporate Project Management Office, in collaboration with the CDE will undertake this process immediately upon award of contract using the following steps.

- Risk identification. ETS will assemble stakeholders to identify possible project risks. ETS will base this identification on prior assessment reports, potential areas of security breach, areas of the project that are not yet well-defined, and areas of known potential for problems. ETS will document possible risks to the defined work plan and include this documentation in a risk register.

- Risk analysis. Once potential risks are identified, ETS will analyze them for their probability, quantitative impact, and qualitative impact. ETS will then translate these into numerical values to accurately determine the outcome of these risks on the cost, time, and resource factors of the project.

- Identify risk triggers. ETS will identify triggers, or warning signs, for risks within their assigned areas of the CAASPP System that might affect the processes for deliverables in the work plan and document the triggers associated with each potential risk.

- Risk resolution. Risks are unknown events that are inherently neutral, but which are categorized as either positive or negative. Each functional area within ETS will identify and document preventive actions for potential negative project risks, or threats, as well as enhancement actions for the positive risks, or opportunities.

- Risk resolution action plan. Based on the collective ideas of the departments, the ETS Executive Director will decide on a plan of action to bring about risk resolution. ETS will rate risks by urgency, based on potential impact to the CAASPP System’s cost, timeline, and deliverables. In many cases where risks have lesser probability or impact, ETS will be able to simply monitor risks without a defined action.

- Responsibility and accountability. ETS will assign responsibility to various teams and team members for carrying out the risk resolution plans for the CAASPP System. Ultimately, the ETS Executive Director will be solely accountable to the CDE for the plans and actions related to the risks of the CAASPP System.

As the project progresses, ETS will monitor the CAASPP System’s initial risk management plan, which will include identifying new risks and dismissing current risks as no longer relevant.

## 1.8. Document Format and Style

ETS will verify that communications and reports sent to the CDE comply with the format and style as specified. ETS will maintain and implement the CDE format and style requirements.

ETS will comply with the CDE Style Manual and the CDE Correspondence Guide, and CDE Web requirements. In addition to the guidelines outlined in the CDE Style Manual, reports for special studies and research will comply with the CDE requirements in Appendix B: Reporting Expectations for Special Studies and Research Projects.

## 1.9. CDE Notification and Approval Schedule

### Issue Escalation Procedure

ETS will make it a priority to keep the CDE informed on all important issues regarding the CAASPP System. ETS will prepare an escalation strategy for notifying the CDE of any issues that may arise during the program. This includes a plan for promptly communicating to the CDE Contract Monitor via telephone, with a follow-up in writing, of any problem that has the potential to impact the quality, timeliness, or other aspect of the project. This follow-up will include the proposed solution and a solution timeline. In addition, subsequent reports to the CDE will contain the issue, the determined solution, and current status within the solution timeline. ETS will work with the CDE to appropriately communicate critical information to the field.

With the CAASPP System, ETS developed multiple key strategies that maintain communications for all team members. These strategies include:

- having all of the ETS management team staff participate in weekly meetings, both internal and client-facing

- making all key managers available by cell phone, e-mail, and voicemail seven days a week, especially during peak periods

- conducting weekly internal meetings among ETS staff

- using e-mail in a disciplined manner to keep ETS managers and the CDE informed of all activities in all components of the scope of work

- distributing a key contact information sheet that provides telephone, e-mail, fax, and cell phone information for all key management or personnel

- maintaining issues logs and risks management logs, and providing access to them to all ETS staff and the CDE

- following an escalation process for routine and emergency issues

- initial discovery of issue or potential scope change

- internal discussion of an issue or potential scope change

- discussion with senior management

- discussion of an issue with the CDE

- root cause analysis

In addition, during the contract period, ETS will enhance these techniques to best suit the needs of the CDE. The goal will be to alert each ETS manager promptly if a deliverable is at risk of falling behind schedule or faces some other type of challenge. ETS will also aim to keep the CDE Contract Monitor apprised of all potential and actual issues that occur and describe how they are being resolved.

#### Approval and Certification Process

ETS will use the information from the Orientation Meeting to finalize a project schedule and detailed scope of work and provide these documents to the CDE for the CDE’s review and approval no later than ten (10) business days following the Orientation Meeting.

This plan will include the refined proposal to describe the deliverables required for each task, which will include a minimum of ten (10) business days for CDE staff to conduct their initial review and provide feedback. ETS’s draft plans will include substantive operational testing opportunities of the CAASPP Assessment Delivery System for the CDE staff to confirm the elimination of sources of error wherever possible, prior to any content or system functionality appearing in a production environment. ETS’s schedule will incorporate the required number of days allocated for the CDE’s review of the initial and subsequent drafts.

For planning purposes, ETS will use the standard deliverable review process outlined below; however, ETS understands and acknowledges the need for flexibility to meet compressed or extended review requirements and will work with the CDE to develop a mutually agreeable review process and schedule for the given deliverable.

- ETS submits the initial draft deliverable to the CDE.

- The CDE reviews the initial draft and provides comments to ETS within ten (10) business days of the ETS submission.

- ETS prepares the revised deliverable and submits the revised deliverable to the CDE within five business days after receipt of the CDE’s written comments to the initial draft.

- The CDE reviews the revised draft and provides one of the following decisions:

- Approval

- Approval with edits

- Edits and revisions required

Deliverables that receive an “Approval” will be finalized by ETS. The finalized deliverable will be submitted to the CDE for archive purposes within five business days. Deliverables that receive an “Approval with edits” will be revised and finalized by ETS while incorporating the additional CDE edits. The finalized deliverable will be submitted to the CDE for archive purposes within 5 business days. Deliverables that have “Edits and revisions required” will be revised by ETS and submitted to the CDE for another review. Prior to revising the deliverable, ETS will meet with the CDE to discuss the required revisions and to ensure that the revisions are clearly understood. The iterative revision and review process will continue until the CDE has approved the deliverable.

Before ETS submits a deliverable to the CDE and at each stage of the review for the deliverable, ETS’s program management representative will submit a signed certification with every deliverable attesting that the deliverable is error-free and meets all requirements. ETS will use a Web-based Project Manager Certification process.

The ETS Gatekeeper will manage the process by which deliverables are submitted to the CDE and will manage feedback received from the CDE. The Gatekeeper will serve as the single point of contact for submitting deliverables to the CDE and notifying the CDE of the submissions. The Gatekeeper will work with the program management representative to verify the completion and inclusion of certification as part of the submission. The Gatekeeper will also be the single point of contact for the CDE to return feedback and/or approval of the deliverable and will confirm that the CDE’s feedback or approval has been communicated to the appropriate ETS program management member. The Gatekeeper may also assist the CDE and ETS in coordinating discussions about the deliverables during the review process.

ETS will not disseminate materials to LEAs or publicly release any materials without the CDE’s prior written approval.

# TASK 2: Program Support Services

ETS is committed to providing superior support services that make it as easy as possible for schools, LEAs, and the CDE to implement the CAASPP System. This section describes how ETS will implement communication activities to help the CDE broaden California’s understanding of both the summative testing system and the interim and formative tools that are available.

## 2.1. Coordinators

##### LEA CAASPP Coordinator and Superintendent Contact Information

TOMS will use the school hierarchy file provided by the CDE to populate its database. By August 18, annually, LEAs will receive communications from ETS requesting that the superintendent of each LEA provide the following information on or before September 30, as required by the testing regulations (California Code of Regulations, Title 5, Section 853. Administration):

- designate from among the employees of the LEA an LEA CAASPP Coordinator;

- identify school(s) with pupils unable to access the computer-based assessment (CBA) version of a CAASPP test(s) in accordance with Education Code (EC) Section 60640(e); and

- report to the CAASPP contractor(s) the number of pupils enrolled in the school identified in subdivision (2) that are unable to access the CBA version of a CAASPP test.

The prior year’s LEA CAASPP Coordinator will also receive a copy of this communication in order to assure receipt and action from the Superintendent. ETS will track the receipt of a completed form for the LEA along with any updates to the data in TOMS. Any changes to the assigned LEA CAASPP Coordinator made during a testing year will require a new Superintendent’s Designation of LEA CAASPP Coordinator form signed by the LEA Superintendent. Representatives from California Technical Assistance Center (CalTAC) will enter the receipt date of these documents into TOMS, triggering LEA access to the system. LEA CAASPP Coordinators will not be able to access TOMS until this form and a Security Agreement have been received from the LEA.

##### Security Agreements

LEA CAASPP and CAASPP Test Site Coordinators receive from ETS the Test (including Field Tests) Security Agreement for LEA and Test Site Coordinators (the “Security Agreement form”). ETS will provide LEA and site CAASPP Coordinators with the Security Agreement form every August, together with the Superintendent’s Designation Form for the appropriate school year. CalTAC tracks receipt of the forms, and the new online version automatically routes Security Agreement forms submitted by CAASPP Test Site Coordinators to the appropriate LEA CAASPP Coordinator.

Upon receipt of this form and the Superintendent’s Designation of LEA CAASPP Coordinator form, the LEA CAASPP Coordinator will receive a user name and temporary password to access TOMS. ETS will conduct follow-up telephone, fax, and e-mail communications in order to obtain completed forms from all school LEAs.

LEA CAASPP Coordinators will be required to sign a CAASPP Test Security Affidavit and to obtain a signed CAASPP Test Security Agreement and signed CAASPP Test Security Affidavit from each CAASPP Test Site Coordinator. In addition, LEA CAASPP Coordinators must obtain signed CAASPP Test Security Affidavits from all test examiners, proctors, and scribes as well as from any other LEA and school staff that will have access to the CAASPP test materials either on paper or electronically. The LEA CAASPP Coordinators must keep the signed agreements and affidavits on file at the LEA office.

## 2.2. Administration Management System LEA Support

The TOMS application will serve as the primary conduit for users of the online system. Administrators and teachers can upload files, retrieve reports, and utilize a long list of other functions. TOMS will use CALPADS data for the LEA/school hierarchy and for enrollment data. The CALPADS enrollment data will be used by TOMS to determine test assignments. ETS will work with the CDE to establish a daily data feed of CALPADS data to TOMS. Additional information about the data feed is described in Task 3.

TOMS will include functionality to collect supplemental ordering information, including overage rules, delivery date options, delivery to school or LEA (LEAs may choose different option for materials versus reports shipment), label options, updates to school and LEA addresses, contacts, rescore requests, and other information. TOMs will also allow LEAs to order accommodated test materials or additional materials and other services that cannot be accommodated by data flows from state level data.

Users will access TOMS via the portal and will have one user ID and password (single sign-on) to perform all required functions to administer and report online and paper tests. Specifically, this includes viewing student information, including test eligibility, and preparing for online testing. Additional information about single sign-on is described in Task 3.

TOMS will be enhanced to manage and track LEA requests for rescores, and AIR’s proprietary TDS system will manage and track LEA requests for appeals, as allowable by state regulations.

ETS will present a complete set of TOMS system requirements for the CDE’s approval before TOMS is configured for the 2016 administration. After the CDE approves this plan, ETS will present a complete project schedule with achievable milestone dates that will include system demonstrations, user acceptance testing by CDE representatives with accompanying system user guides, and built-in time to make any potential system refinements before the published launch date.

## 2.3. Data Driven Improvement

ETS will use a variety of approaches to solicit and use data and information to improve processes and support inclusive of all CAASPP assessments.

Specifically, under the leadership of the CDE, ETS proposes to expand the following data collection actions.

- collect feedback from LEAs across the state at key points and on specific topics using short, well-crafted online surveys

- provide statewide training that allows LEAs plenty of time to conduct local training

- review question logs from live Webcasts for patterns and themes and include Quick Polls during Webcasts to check for understanding

- regularly obtain feedback from CalTAC representatives on the nature of calls and e-mails received to identify key recurring points and questions from the field

ETS will also hold up to 9 in-person focus groups per administration (up to 45 focus groups during the initial contract period). The focus groups will be conducted at the end of each administration cycle to gather additional information from test administrators, special education representatives, primary language stakeholders and LEA CAASPP Coordinators. ETS will work with CDE to determine the purpose, locations, and audience of each session.

## 2.4. Technical Assistance Center

ETS will provide a comprehensive support team to the CDE and LEAs during each annual administration for the support of all CAASPP (including summative assessments, interim assessments, the Digital Library, user provisioning questions, etc.). The CDE and LEAs will have access to ETS program managers, LEA outreach team members, technical assistance center staff, and computer-based testing technology experts.

ETS will provide three-tier help desk support. Support will be provided specifically to LEA CAASPP Coordinators, LEA Technology Coordinators, and other LEA-level staff designated by the LEA CAASPP Coordinator.

The three different tiers of help desk support are as follows:

- Tier 1 – California Technical Assistance Center (CalTAC)

- Tier 2 – xBT

- Tier 3 – Smarter Balanced and/or AIR

### Tier 1: California Technical Assistance Center (CalTAC)

ETS will provide CalTAC services for state- and LEA-level customers throughout the calendar year. CalTAC will:

- operate during the hours of 7 a.m. to 5 p.m. Pacific Time, Monday to Friday, excluding designated California school holidays, with extended hours as needed

- have a dedicated toll-free telephone number handling up to 200 concurrent callers

- have a dedicated e-mail address

- offer real-time chat as an alternative to telephone or e-mail

- operate a fax line to communicate sensitive information (e.g., information that includes student names)

ETS will publish all CalTAC contact information in program materials and on caaspp.org.

In addition, the ETS director of operations will serve as the single point of contact for responding to inquiries from CDE staff and CDE contractors within two (2) business hours. The ETS program manager will serve as the single point of contact on critical Smarter Balanced issues (e.g., Tier 3 Support issues). These points of contact will have the support of ETS’s CAASPP IT Manager.

Response Time. Given how important it is to provide a positive experience for California LEAs, ETS will promptly resolve customer inquiries. ETS will have 30 to 50 customer service representatives dedicated to handling CAASPP inquiries and will answer telephone calls within 60 seconds and respond to e-mail inquiries with a complete answer within two hours of receipt, if received before 3 p.m. during normal business hours. E-mail messages received after 3 p.m. or during non-business hours will receive responses by 9 a.m. the next business day. ETS will post chat feature responses within 90 seconds of receipt during normal business hours and will answer telephone messages received before business hours by 9 a.m. the same business day, telephone messages received after 3 p.m. will be answered by 9 a.m. the next business day. ETS relies on system productivity tools and supervisor interventions to monitor customer response time, and will meet the CDE’s response expectations during the administration window.

ETS will have documented processes to monitor the accuracy of phone and e-mail responses by CalTAC staff through supervisory monitoring, LEA or state feedback, or other methods, and provide retraining as necessary.

ETS will provide weekly customer service summary reports to the CDE. Reports will include volume, wait time, and responses/resolutions by CalTAC staff. The reports will be provided to the Consortium vendor as part of the overall coordination activities with the Consortium.

### Tiers 2 and 3: Technology Support (xBT and AIR)

Tier 2 support will be accomplished through a seamless integration of ETS’ internal technical support team (xBT), a second level that will manage intermediate-plus issues. Two xBT support staff will continue to be based in California to provide Tier 2 technical support. Other xBT support staff will be located in New Jersey to provide additional Tier 2 technical support. In addition, xBT will assist in technical site visits, in-person training workshops, and technology-related Webcasts.

Tier 3 will escalate to the test delivery system (TDS) and reporting vendors AIR or Smarter Balanced for the Digital Library. Escalation to this level will be for technology issues directly related to the TDS or reporting system or the Digital Library. AIR will provide responses back to ETS in a timely manner to allow for information sharing across the platform. In addition, AIR will assist with in-person training workshops and test system-related Webcasts.

Technical issues identified during a testing window that cannot be resolved by CalTAC immediately will be transferred to ETS’s xBT team. If a school LEA is calling with a technical issue and students are in the classroom unable to test, the call is to be moved to technical support immediately for resolution or a recommendation should be provided to have students test at a later time if the problem cannot be resolved. Students should not be kept in a classroom for more than 15 minutes waiting for resolution if not agreed upon by the LEA.

### Training of CalTAC Staff, Training Materials, and Informational Updates

Customer Service Representative Training. ETS will continue to provide training for customer service representatives through an ETS Learning and Development-certified trainer. Training will last for 10 business days, and upon completion of this training all representatives will be able to assist customers with:

- installing secure browsers

- creating users in TOMS and resetting system passwords

- utilizing all CAASPP management functions in TOMS

- processing supplemental orders for paper materials

- understanding summative and interim test administration procedures, including for both computer-based and paper-pencil assessments, where applicable

- using the Digital Library

- accessing student-level and aggregate score reports

- finding answers to questions about upcoming trainings and events

- accessing applicable resources on caaspp.org

Customer Service Representative Training Materials. ETS will use information from CDE-approved sources to develop program training and reference materials. These sources will include:

- administration manuals

- CAASPP PowerPoint presentations

- FAQs

- Standard Operating Procedures

- CAASPP Webcast presentations

- hands-on UAT environments

- caaspp.org

Informational Updates. ETS internal informational updates will follow an established protocol within CalTAC. ETS’s Director of Operations will hold regularly scheduled internal briefing meetings with the CalTAC Manager and senior CalTAC Supervisors to provide the latest program updates. The internal briefings will occur at least weekly and will be scaled up to daily briefings, according to test administration needs.

As new information becomes available from the internal briefings of senior CalTAC Supervisors, ETS will distribute an updated informational flash to customer service representatives via e-mail and through a private, secure social media group used corporate wide. This flash tip sheet will detail the new information, the appropriate strategy for sharing the information with customers, the resolutions required, and the documentation method within ETS contact management tools and system. ETS will include informational flashes in any future training sessions, and will modify material to reflect these updates. As the CAASPP System evolves, ETS will update FAQs and training so that procedures for contact center staff remain up-to-date.

### Annual and Periodic Customer Support Services Reports

CalTAC Annual Reports and Other Available Reports. ETS will continue to provide the CDE with annual reports that help determine the uses of customer support services. ETS will collaborate with the CDE to define views and intervals, and to gain approval on samples.

ETS will continue to distribute reports according to the CDE’s specifications (i.e., posting to a project site or e-mailing to a distribution list), and will work with the CDE and its stakeholders at the Orientation Meeting to determine the most appropriate implementation method for program tracking and resolution.

Customer Contact Tracking System. The ETS customer contact tracking system collects contact information and tracks resolution and ETS will provide the CDE with detailed information on why a contact is calling and the resolution for each contact. ETS can also provide, at CDE request, customer service representative-level detail with a historical view for each time a customer has contacted CalTAC. ETS will collaborate with the CDE to anticipate events before they occur while providing support and resolution to the field with timely and effective information to resolve any emerging issues.

Customer Service Representative Efficiency. CalTAC uses a performance dashboard to view real-time telephone performance. ETS will use this dashboard to track individual performance and determine if additional support for the contact is necessary. ETS also uses the dashboard to make dynamic staffing adjustments as needed to maintain required response times.

## 2.5. Student Accessibility Tool

ETS will support the CA version of the ISAAP tool, including supporting the extract that can be uploaded into TOMS.

ETS will further customize and enhance the California ISAAP tool to include tools, supports, and accommodations that may be needed in order to respond to policy changes from the state, the federal government, or the Smarter Balanced Consortium, or there may be new accessibility components needed specifically for the new non-Smarter Balanced computer-based assessments. ETS will propose annually what changes are required and possible to customize and improve the California ISAAP Tool.

## 2.6. Internet Resource Site

ETS will maintain the web site that will be the central repository for all information regarding the CAASPP assessment program. At the beginning of the new contract period and annually thereafter, ETS will submit the Web site through a WebART review to ensure that the site continues to meet CDE Web standards. The portal will have a section to house accessible manuals, software, item samplers, training materials, etc. that does not require a user ID or password to access. The portal will have search capabilities for public use. The search results will provide links to the pertinent information in the current versions of manuals and documents posted.

The portal will also link to a secure site that will allow for secure posting of data directly to LEAs or accessible by LEAs for retrieval of data. Only authorized users will be able to access the secure site.

ETS will track and report the number of times that resources have been accessed on the portal.

As new Internet and social media resources become available, ETS will consider each to determine whether or not they might be appropriate for CAASPP. ETS will provide recommendations to the CDE for consideration.

ETS will host one annual focus group to specifically solicit input on the web site. ETS will translate this feedback into a Web site enhancement action plan each year for CDE review and approval prior to implementation.

## 2.7. Workshops and Webcasts

ETS will establish and implement a training plan for LEA assessment staff on all aspects of the assessment program. The CDE and ETS, in collaboration with the CDE Senior Fellows and other stakeholders as needed, will determine audience, topics, frequency, and mode (in-person, webcast, videos, modules, etc.) of the training, including such elements as format, participants, and logistics. It is anticipated that the training plan will be implemented in August annually.

ETS plans to conduct between 40-46 sets of workshops and Webcasts for each administration. Planned workshops and Webcasts are included in Table 1 at the end of this task.

ETS will present the names and qualifications of proposed presenters and all associated

Workshop and Webcast materials to the CDE in advance for its review and approval. Following approval by the CDE, materials will be posted for each Webcast on caaspp.org so that viewers may download them no later than the day before the presentation of the Webcast.

### Webcasts

ETS will launch a series of live Webcasts each year starting in September, leading up to the start of summative testing in February, and will conclude each testing cycle with in-person post-test training on testing results and reporting. Webcast viewers will be provided with a method of electronically submitting questions to the presenters during the Webcast. The Webcasts will be closed captioned. The Webcasts will be recorded and archived for on-demand viewing.

### In-person Training

In person trainings will typically be conducted at county offices of education. The first in-person training in a series will always be held in Sacramento. Proposed locations for the in-person training will take into consideration providing convenient locations for as many LEAs as possible while ensuring efficient use of limited staffing resources.

ETS will use an online registration system to track reservations and provide registration confirmation to participants with location, date, and time of their training session.

### Videos and Narrated PowerPoint Presentations

To supplement the live Webcasts and in-person workshops, ETS will produce short “how to” videos and narrated PowerPoint presentations that will be available on caaspp.org. The videos will be provided in multiple formats (e.g., YouTube video, .mov file) and will be closed captioned.

## 2.8.	Local Assessments: Smarter Balanced Interim Assessments and Digital Library

ETS will support California’s K–12 educators in accessing and using Smarter Balanced interim assessments and their results. Additionally, ETS will help educators use Smarter Balanced’s Digital Library. As described in Task 7.3.A.1, the ETS plan for supporting LEAs includes:

- use of a single system sign on for streamlined access

- a unified platform for delivery of all system components

- large-scale teacher training in the scoring of students’ responses to constructed-response and performance task items (discussed in Task 7.3.A.1)

- training and materials to guide use of the interim assessments and accurate interpretations of scores and support effective use of results for instructional purposes (discussed in Task 7.3.A.1)

### 2.8.A. Smarter Balanced Interim Assessments

ETS understands that the intent of California is to have the Smarter Balanced-provided interim assessments available year round to LEAs through the life of the contract. To that end, ETS will deploy the interim assessments using the test delivery system in August of each year or during a timeframe that supports the annual rollover of CALPADS to the next school year. ETS will incorporate any Smarter Balanced-provided updates to the interim assessments by September 1 annually. The CAASPP Assessment Delivery System will deliver both adaptive and fixed form test designs to support core and block interim tests. The system will also allow LEAs to access the on-demand online administration year upon request, and it will provide seamless integration with other CAASPP System components.

ETS will provide the following materials for the Interim assessments:

- System User Guide

- Scoring Guide

- System Infrastructure Guide

- System Training workbook

### 2.8.B. Digital Library of Formative Assessment Resources

CDE-authorized California principals, teachers, and educators will have access to all the instructional and literacy modules, as well as the educational resources, available within the Smarter Balanced Formative Digital Library. ETS will seamlessly integrate this Digital Library sign-on into TOMS.

As an additional benefit a flexible user interface will allow authorized California educators to upload additional instructional modules and resources to the Digital Library, under the specifications and guidelines provided by Smarter Balanced. ETS understands that UCLA will host the Digital Library and may want to manage the process and means by which materials are added to the collection. Depending on how that process is managed, ETS will provide a solution that supports California educators’ contributions to grow the resources available. ETS will also support the collaborative tools provided by the Smarter Balanced Digital Library, including user ratings, feedback, and other evaluation tools.

Table 1.  Planned CAASPP Training Workshops and Webcasts

|  | Name and Description of Training | Type of Training | Audience or Estimated Number of Attendees | Planned # of Sessions | Estimated Durations | Planned Locations | Estimated Timeframe to Provide Training | School Years Provided | SOW Task Reference |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Summer Scoring Institutes Provide thorough training and practice on the scoring of operational items | In-person | 200 California educators per session | 8 | 1 day | TBD – propose: 2 North 2 Central 4 South | July | 2015-16 2016-17 2017-18 | 2.7.B 8.1.A.2 |
| 2 | Using the Smarter Balanced Digital Library Familiarize users with the content and uses of the digital library resources | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 1 | 2 hours | caaspp.org | August | 2015-16 2016-17 2017-18 | 2.7.B |
| 3 | Digital Library & Interim Assessment Clinics Provide information on the access and administration of the interim assessments and general information about access of the Digital Library and available resources | In-person | CAASPP Coordinators + 3 participants per LEA (as space allows) 50-100 participants per session | 8 | 4 ½ hours | TBD – propose: 2 North 2 Central 4 South | August – September | 2015-16 2016-17 2017-18 | 2.7.B |
| 4 | What is Computer Adaptive Testing Provides high-level information on CAT and how it works | Online Presentation | CAASPP Coordinators, Test Administrators, Educators | 1 | 15 minutes | caaspp.org | September | As Smarter Balanced updates | 2.7 |
| 5 | Embedded Universal Tools and Online Features Explains the online tools available to students for testing and how to access and use them | Online Presentation | CAASPP Coordinators, Test Administrators, Educators | 1 | 25 minutes | caaspp.org | September | As Smarter Balanced updates | 2.7 |
| 6 | Performance Task Overview Explains the Smarter Balanced PTs and Classroom Activities and provides examples | Online Presentation | CAASPP Coordinators, Test Administrators, Educators | 1 | 20 minutes | caaspp.org | September | As Smarter Balanced updates | 2.7 |
| 7 | Technology Requirements for Online Testing Provides technology requirements and readiness tasks in preparation for online testing | Online Presentation | CAASPP Coordinators, Technology Coordinators | 1 | 20 minutes | caaspp.org | September | Annual updates as needed | 2.7 |
| 8 | Using the CAASPP Individual Student Assessment Accessibility Profile (ISAAP) Tool Tutorial Instructions for using the tool to create student test settings files | Video and PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 2 | 1 hour | caaspp.org | September | Annual updates as needed | 2.7 |
| 9 | Interim Assessments Hand Scoring System Presentation Instructions for accessing and using the scoring module for hand scored items on the interim assessment | Video, PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 2 | 1 hour | caaspp.org | September | Annual updates as needed | 2.7 |
| 10 | Interim Assessments Reporting System Presentation Familiarize users with available reports, navigation, and tools for the interim reporting system | Video, PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 2 | 30 minutes | caaspp.org | September | Annual updates as needed | 2.7 |
| 11 | Setting up Test Administrations in TOMS Demonstration of functions of TOMS | Video | CAASPP Coordinators, Test Administrators | 1 | 15 minutes | caaspp.org | September | Annual updates as needed | 2.7 |
| 12 | Adding and Managing Users in TOMS Tutorial on how to add and manage users in TOMS/single sign-on | Video | CAASPP Coordinators, Test Administrators | 1 | 15 minutes | caaspp.org | September | Annual updates as needed | 2.7 |
| 13 | Smarter Balanced Interim Assessments Provide an overview of the Interims, planning for them, uses of results and reporting | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 1 | 2 hours | caaspp.org | September | 2015-16 2016-17 2017-18 | 2.7.B |
| 14 | Preparing CALPADS Data Provide overview of CALPADS data elements and the process of loading to TOMS | Webcast (archived), PowerPoint | CAASPP Coordinators, CALPADS Coordinators | 1 | 1 hour | caaspp.org | September | 2015-16 2016-17 2017-18 | 2.7 |
| 15 | TOMS Training Provide introduction to TOMS, logging on, and configuring test administrations | Webcast (archived), PowerPoint | CAASPP Coordinators | 1 | 1 hour | caaspp.org | September | 2015-16 2016-17 2017-18 | 2.7 |
| 16 | Configuring Online Student Test Settings in TOMS Instructions for setting embedded and non-embedded supports and accommodations | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 1 hour | caaspp.org | September – October | Annual updates as needed | 2.7 |
| 17 | CAASPP: Preparing Your LEA’s Technology for Online Testing Review LEA technological resources and requirements and secure browser installation | Webcast (archived), PowerPoint | CAASPP Coordinators Technology Coordinators | 1 | 1 hour | caaspp.org | September – October | 2015-16 2016-17 2017-18 | 2.7 |
| 18 | Interim Assessment Scoring Workshop Train teachers in the effective and consistent use of scoring rubrics | In-person | 100 California educators per session | 8 | 3 hours | TBD – propose: 2 North 2 Central 4 South | September – October | 2015-16 2016-17 2017-18 | 2.7.B 8.1.A.2 |
| 19 | Using the Interim Assessment Reporting System and Interim Assessment Results Interpretation Information to support accurate interpretation and effective use of interim assessment scores | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 1 | 2 hours | caaspp.org | October | 2015-16 2016-17 2017-18 | 2.7.B |
| 20 | Accessibility and Accommodations for CAASPP Purpose and importance of accessibility, available tools, supports and accommodations, process steps | Webcast (archived), PowerPoint | CAASPP Coordinators | 1 | 1 hour | caaspp.org | October | 2015-16 2016-17 | 2.7 |
| 21 | Introduction to new Primary Language Assessment Overview of new assessments and development process | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 1 | 2 hours | caaspp.org | October | 16-17, 17-18 | 2.7.C |
| 22 | Introduction to new CA NGSS Assessment Overview of CA NGSS assessments, development process and a view of sample items | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators, Educators | 1 | 2 hours | caaspp.org | October | 2016-17 2017-18 | 2.7.C |
| 23 | Student Paper-pencil Test Registration in TOMS Instructions for setting up students for paper-pencil testing | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 1 hour | caaspp.org | November | Annual updates as needed | 2.7 |
| 24 | Preparing Your LEA’s Student Paper-pencil Test Registration File Instructions on file specifications and preparation and live demo | Webcast (archived), PowerPoint | CAASPP Coordinators, CALPADS Coordinators | 1 | 1 hour | caaspp.org | November | Annual updates as needed | 2.7 |
| 25 | Using the Online Practice and Training Tests Differences and uses of Practice and Training tests, logging on, tools and layouts, and administration | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 1 hour | caaspp.org | November | 2015-16 2016-17 2017-18 | 2.7 |
| 26 | Paper-Pencil Test Administration Workshop Familiarize coordinators with proper testing procedures, secure material handling, and secure test administration | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 1 hour | caaspp.org | December | Annual updates as needed | 2.7 |
| 27 | Pre-Test Workshop Comprehensive overview of test administration procedures for all CAASPP assessments | Webcast (archived), PowerPoint | CAASPP Coordinators | 1 | 2 hours | Virtual | January | 2015-16 2016-17 2017-18 | 2.7 |
| 28 | Alternate Assessment Training (Math, ELA) Introduction and administration procedures for alternate assessments | Webcast (archived), PowerPoint | Alternate Assessment Test Administrators | 1 | 1 hour | Virtual | January | 2015-16 | 2.7 |
| 29 | Alternate Assessment Training (Math, ELA, CA NGSS) Introduction and administration procedures for alternate assessments | Webcast (archived), PowerPoint | Alternate Assessment Test Administrators | 1 | 1 ½ hours | Virtual | January | 2016-17 2017-18 | 2.7.C |
| 30 | Primary Language Pilot Test Administration Training Introduction and administration of the pilot test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2016-17 | 2.7.C |
| 31 | Primary Language Field Test Administration Training Introduction and administration of the field test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2017-18 | 2.7.C |
| 32 | CA NGSS Pilot Test Administration Training Introduction and administration of the pilot test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2016-17 | 2.7.C |
| 33 | CA NGSS Field Test Administration Training Introduction and administration of the field test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2017-18 | 2.7.C |
| 33 | CA NGSS Alternate Pilot Test Administration Training Introduction and administration of the pilot test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2016-17 | 2.7.C |
| 34 | CA NGSS Alternate Field Test Administration Training Introduction and administration of the field test | Webcast (archived), PowerPoint | CAASPP Coordinators, Test Administrators | 1 | 2 hours | caaspp.org | January | 2017-18 | 2.7.C |
| 35 | Test Security Requirements, test security guidelines for online and paper-pencil administrations, procedures for reporting irregularities | Webcast (archived), PowerPoint | CAASPP Coordinators | 1 | 30 minutes | caaspp.org | January – February | 2015-16 2016-17 2017-18 | 2.7 |
| 36 | Pre-Test Administration Training (includes separate session for Alternate Assessments) In-depth train-the-trainer model on all aspects of test administration with live systems demonstrations with separate hands-on training for alternate assessment administrations | In-person | CAASPP Coordinators and Technology Coordinators 50-100 participants per session | 17 | 4 ½ hours | Butte Humboldt Sacramento Shasta Alameda Fresno Monterey San Joaquin Santa Clara San Francisco Kern Los Angeles (2) Orange Riverside San Diego Santa Barbara | January – February | 2015-16 2016-17 2017-18 | 2.7 |
| 37 | Operational Scoring Weekend Institutes Operational training for scoring summative assessment items, qualifying, and live scoring | In-person and Scoring | 100 California educators per session | 8 | 2 days | TBD – propose: 2 North 2 Central 4 South | March – May | 2015-16 2016-17 2017-18 | 2.7.B 8.1.A.2 |
| 38 | Using the Aggregate Reporting System and Summative Results Interpretation Information to support accurate interpretation and effective use of summative assessment scores | Webcast (archived), PowerPoint | CAASPP Coordinators, Educators | 1 | 2 hours | caaspp.org | May | 2015-16 2016-17 2017-18 | 2.7.B |
| 39 | Post-Test Workshops Review reporting systems and features and provide guidelines for score interpretation Morning session: All CAASPP assessments Afternoon session: Focus on alternate assessments | In-person | CAASPP Coordinators (AM and PM sessions) Special education coordinators (PM sessions only) 50-100 participants per session per location | 8 | 4 ½ hours | TBD – propose: 2 North 2 Central 4 South | May – June | 2015-16 2016-17 2017-18 | 2.7 |
| 40 | Additional Webcast (archived), PowerPoint #1 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |
| 41 | Additional Webcast (archived), PowerPoint #2 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |
| 42 | Additional Webcast (archived), PowerPoint #3 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |
| 43 | Additional Webcast (archived), PowerPoint #4 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |
| 44 | Additional Webcast (archived), PowerPoint #5 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |
| 45 | Additional Webcast (archived), PowerPoint #6 | Webcast (archived), PowerPoint | TBD | 1 | 1 hour | caaspp.org | TBD | 2015-16 2016-17 2017-18 | 2.7.C |

# TASK 3: Technology Services

As part of the Assessment Technology Platform solution for California, the CAASPP Assessment Delivery System includes all components required to deliver the Smarter Balanced and non-Smarter Balanced assessments for the CAASPP System. Figure 1 below provides a diagram of the overall system.

Figure 1.  CAASPP Assessment Technology Platform

ETS will work closely with the CDE to evolve the existing high-capacity CAASPP test delivery system, used for the 2015 administration, to meet future requirements. The CAASPP Assessment Delivery System will, at minimum, deliver the Smarter Balanced summative assessments to approximately 10,000 schools and more than 3.2 million students in over 1,700 LEAs statewide that will use a wide variety of online testing devices (desktop computers, laptop computers, tablets, etc.). Additionally, the CAASPP Assessment Delivery System will deliver the Smarter Balanced Interim Assessments to all participating kindergarten through grade twelve students.

## 3.1. School Technology Readiness

Annually, ETS will work with the CDE to collect information on the technology readiness of schools. This information will include, at minimum:

- Bandwidth availability

- Networking capability

- Available facilities for computer based test administration

- Number of devices available for computer based test administration.

This information is the same as that outlined in the Smarter Balanced Technology Strategy Framework.

#### Collecting the School Technology Readiness Information

During the annual updates from LEA CAASPP Coordinators described in Task 2.1, ETS will incorporate the Technology Readiness Survey, which will be conducted in September of every year. The Technology Readiness Survey will be an online form. Annually in July, ETS will provide the draft Technology Readiness Survey to the CDE for the standard review and approval process described in Task 1.

#### The Annual Report on School Technology Readiness

Once ETS receives the results, they will be compared against the previous year’s information. By November 1 of each year, ETS will submit to the CDE a preliminary report including a summary of the Technology Readiness Survey results. The report will also categorize the listed LEAs in terms of degree of readiness. The preliminary report will be updated and finalized by December 1.

#### Assistance to Schools to Meeting the Technology Requirements

Based on the results of the CAASPP technology readiness survey ETS will proactively reach out to each of these LEAs identified as being less ready, first via phone and subsequently by site visit to assist them in determining what they need to do to become more technologically ready to participate in the CAASPP online assessment. For each such contact, ETS will provide the CDE with a report and recommendation for action it should take. At CDE’s direction, ETS will be available to the LEAs to implement these recommendations.

## 3.2. Assessment Delivery System

The solution supports both summative and interim Smarter Balanced assessments as well as the new succession CA NGSS, CA NGSS Alternate, primary language, and CAA. The solution will employ AIR’s proprietary test delivery system, ETS’s Test Operations Management System (TOMS), scoring systems from ETS and MI, and an online reporting tool from AIR.

### 3.2.A. Project Management Plan

During project initiation, ETS project managers will develop a Project Management Plan (PMP) for CAASPP System, including the Assessment Technology Platform. The PMP will cover the 3-year period of the contract; start-up tasks will be included only in year 1. ETS will ensure that the PMP is in compliance with CA Project Management Methodology (CA-PMM) and the State Information Management Manual (SIMM) and will include all identified schedule elements such as actual and planned start and finish dates. ETS will use a template consistent with the CA-PMM to confirm that all key components are identified and presented in a consistent format. After completion, the PMP will remain accessible on the project SharePoint® site and will be updated annually. ETS will make the schedule available in MPP format for CDE. The ETS Technology Manager and ETS CPMO Project Manager will provide the PMP to the CDE within 30 days of contract start and will work with the CDE, the CDE contract manager, and the CDE state project manager to facilitate a review by Independent Verification and Validation (IV&V) Consultant and by Independent Project Oversight Consultant (IPOC).

The PMP will include, at minimum, the following elements:

- Scope Management Plan—During project initiation, ETS will identify and document scope using the Project Definition document template. The PMP will require the project team to document work in-scope, work out-of-scope, deliverables produced, stakeholders, and interdependencies with other projects.

- Organizational Chart and Governance Model—ETS has created the Project Organization chart as one component of the PMP. ETS’s Project Review Committee will regularly evaluate the CAASPP program activities to ensure that the project team has the support needed to be successful

- Configuration Management Plan—ETS will document the configuration management plan for California and use a configuration management tool to manage changes to the production system, including production environments, software releases and their content, and other production configurations.

- Change Control Management Plan—ETS will manage the scope for development of the Assessment Technology Platform through a structured change management process. First, ETS will establish baselines for scope and schedule at the outset of the project. In the project SharePoint site, ETS will establish a change log to document and track change requests, and will set up a review process to confirm that requests are vetted with the appropriate stakeholders. Project leadership will then review change requests to assess impacts and gain agreement on how to address those impacts in support of a formal approval process. As soon a change request is approved and obtains signoffs, ETS will update the change log, integrate changes into the project plan, and re-baseline schedules if necessary.

- Communications Management Plan—During project initiation, ETS will plan for proper communications so that CDE stakeholders will be aware of not just the type of communications they will receive but also the purpose, frequency, and media (e.g., meeting, e-mail) of each communication.

- Risk Management and Escalation Plan—The ETS CPMO Project Manager will lead the project team and other key stakeholders through a risk identification and analysis session during the project’s planning phase. Identified risks will be added to a risk log which remains accessible on the project’s SharePoint site. In the event that a risk becomes an issue, the ETS CPMO Project Manager will add the issue to the issue log that is always accessible on the project’s SharePoint site. The project manager identifies appropriate owners to remediate issues in a timely fashion to confirm continued project success while reducing the emergence of new issues or risks. Senior management, consisting of ETS’s Project Review Committee and CDE representatives, will regularly review critical project risks and issues.

- Quality Management Plan—The ETS project team will utilize the ETS Quality Plan template to construct a California Quality Plan during the Project Planning phase. The Quality Plan summarizes the quality targets and management processes undertaken during the Project Execution phase. As a result, ETS will be able to consistently reference the Quality Plan throughout the project to monitor and control the level of quality of the deliverables built and processes undertaken on the project.

- Requirements Management Plan—ETS based the requirements management process on best practices of the International Institute of Business Analysis. ETS uses this process to manage solution scope, requirements, and requirements traceability, as well as to maintain requirements for re-use and communicate the requirements. ETS will utilize seasoned business analysts to identify stakeholders; elicit, document, and confirm business needs; and manage traceability and gaps. The requirements management process includes securing approvals, managing issues that emerge during elicitation and analysis, and managing change control of baseline requirements and solution scope. ETS uses requirements traceability to detect missing functionality, assist in scope and change management, and during risk management. ETS analysts will confirm the requirements are clear, concise, accurate, and at the appropriate level of detail so that ETS can effectively communicate the requirements in a way understandable to the stakeholders.

- Schedule Management Plan—ETS will utilize detailed schedules and dashboards built in the Microsoft Project component of the Microsoft® Enterprise® Project Management (EPM) system solution to create and actively manage the project schedule. ETS builds schedules and dashboards based on well-developed scheduling principles and published best practice guidelines. Breakdown structures highlight key task dependencies, critical paths, milestones, deadlines, and resources. ETS then baselines and reviews the schedule on a weekly basis to verify the maintenance of all tasks and timelines. ETS will closely monitor any variance from the schedule baseline to minimize impacts with tasks added, deleted, or updated to reflect changes based on the project team’s input.

- Resource Management Plan—ETS will monitor resources across all project teams and departments to optimize resource capacity, improve productivity, and use analytics to track utilization and reforecast staffing for projects when necessary.

ETS assumes that the CDE will provide comments to the initial PMP within 20 business days of receipt. ETS will respond and provide an updated PMP within 20 business days following receipt of the CDE written comments. Upon approval by the CDE, ETS will implement and monitor the PMP, and will collaborate fully with the CDE and the California Department of Technology (CalTech) to confirm that the plan meets expectations.

ETS will also collaborate with the CDE to determine the technology services summary information required for reporting purposes and will develop and implement a mutually-agreed upon format. ETS understands that the CDE may use the technology services summary to report to the SBE, CalTech, the California Department of Finance, and other stakeholders as needed.

### 3.2.B. System Requirements

ETS will implement the CAASPP Assessment Delivery System for this program according to the expectations of CDE staff, the CDE contract manager, and the CDE state project manager. ETS will plan each meeting to efficiently use the time of the CDE staff, the Independent Verification and Validation consultant, the Independent Project Oversight Consultant, and program management and technology staff to accomplish the tasks identified.

At the start of the contract, ETS will schedule a series of joint requirements sessions to review and discuss the minimum requirements outlined agreed upon by ETS and the CDE (RFS Table 3.1.1. is included as Appendix C for reference). ETS will be responsible for providing the initial requirements document, which will describe the known CAASPP requirements and how ETS handles those requirements. ETS proposes to hold joint requirements sessions before the Orientation Meeting. At each joint requirements session, ETS will use and refine the initial requirements document to establish that the requirements meet or exceed what is needed for the 2016 administration. The revised requirements document will also include a plan by which periodic reviews of the requirements will be conducted to confirm that they continue to meet the functional and technical requirements needed for CAASPP.

From time to time, there may be changes to state or Federal policies or Smarter Balanced requirements that would have an immediate impact on the CAASPP System. The revised requirements also will include a process for ad hoc requirement reviews to address these changes in a flexible but immediate manner.

Within 15 days of the effective date of the contract, ETS will conduct the Orientation Meeting as required in Task 1. ETS program managers will plan and facilitate this meeting, which will include topics under each functional area of the solution such as technology, assessment development, research, delivery, and operations. ETS will review the proposed work plan and implementation schedule and obtain specific information, data, and criteria in order to successfully implement the solution. By August 1, 2015, ETS will also present the revised requirements as defined and agreed to in the joint requirements sessions with the goal of receiving the initial go-ahead to implement the CAASPP Assessment Delivery System. Should additional discussions about the requirements be needed, ETS will schedule and conduct additional joint requirements sessions until the CDE approves the solution for implementation. ETS will submit the final systems requirements, including flow charts and other required artifacts, document to the CDE by August 15, 2015.

ETS’s technology team will also participate in Annual Planning meetings, as described in Task 1.3, in Sacramento to review and confirm the scope of work. The purpose of the meeting will be to plan any changes to the scope of work, system enhancements and fixes, and the timelines to incorporate the changes for the upcoming test administration year. ETS will submit the revised systems requirements document, including flow charts and other required artifacts, to the CDE by August of each subsequent contract year.

In addition to Orientation and Annual Planning meetings, ETS’s technology teams will also participate in weekly management and technical/data exchange meetings, co-facilitated by the ETS Technology Manager and program manager that will anchor communication between all parties and appropriate technical personnel. These weekly meetings will provide the forum for communication with the CDE about project activities and technical items/issues.

ETS will document all business, technical, and functional requirements, new and updated, that are captured in the joint requirements sessions. ETS will then implement these, after the CDE’s approval, following the ETS software development lifecycle methodology.

#### 3.2.B.1. Assessment Delivery System Architecture

The solution on the following seven major domains: assessment planning and development, registration, scheduling and delivery, support, scoring, reporting, and analysis (see Figure 2).

Figure 2.  CAASPP Assessment Delivery System

The ETS solution supports all operational domains, from test development to scoring and reporting. ETS’s system consists of fully integrated individual component services that provide a high performance and robust solution for the administration of Smarter Balanced and non-Smarter Balanced assessments for California.

Figure 3 represents the high level physical architecture of the CAASPP Assessment Delivery System that supports interim and summative Smarter Balanced assessments as well non-Smarter Balanced assessments.

Figure 3.  Scalable Architecture of the CAASPP Assessment Delivery System

The CAASPP Assessment Delivery System will use a single proprietary solution (AIR Test Delivery System) that meets the general Smarter Balanced defined requirements. ETS will further clarify with the CDE that this implementation addresses any California-specific variations allowable through the Smarter Balanced state procedures manual. Where the solution integrates with external Smarter Balanced systems, such as the Digital Library, (e.g. Digital library, UCLA), ETS will use the defined standards and formats for data exchange.

The configuration specifications development process requires making a number of important decisions, often in a short period of time, following contract award. ETS will schedule a series of one- to two-hour meetings over several days to review the provided system configurations and inform any required adjustments. ETS will coordinate with the CDE to schedule the systems configuration meetings to work through the necessary details of the solution specifications.

During these specifications meetings, ETS will work through the configuration decisions needed at one time. When applicable, ETS will provide screen shots and other supporting documentation to allow participants to visualize how different options will look in the various solution components. Decisions to be made during the configuration specifications meetings will include, but are not limited to:

- Test names and the order of tests listed

- the dates during which the student test window will be open, including any scheduled downtime for maintenance and updates

- which test settings that the TA can change in the TA interface at the time the student takes a test, and which test settings must be changed in advance in TOMS

- what values are allowed for each tool

- the content of the messages that will be displayed to the student at various times during a testing session

- which forbidden applications should be included in the check performed on the student’s computer prior to testing

ETS will record all decisions made during the specifications development process. ETS will provide the documentation to the CDE, summarizing major decisions and any issues for which a final decision was not made during the meetings.

#### 3.2.B.2. Interface Requirements

The CAASPP Assessment Delivery System provides a number of touch points with external systems and components as required by the CDE and/or Smarter Balanced policies. To meet those needs, systems will support scalable and reliable integrations with other systems and technologies by utilizing standardized interfaces wherever possible. For Smarter Balanced assessments, ETS will use the plug-and-play XML data exchange for the information about items and test packages needed to support test scoring. Non-Smarter Balanced computer-based assessments will also use the Smarter Balanced test package format whenever possible. If a non-Smarter Balanced computer-based assessment requires a different format to best support the items types developed for those assessments, ETS will work to confirm that the system can support the formats, prior to the item development process.

The CAASPP Assessment Delivery System consists of a series of integrated components. Even still, the CDE, LEAs, and schools will be able to access the features needed to administrate, manage, operate, and conduct test delivery using a single sign-on. This enables these components to appear to users as a single integrated system. ETS will work with Smarter Balanced to provide a solution that allows users to log onto the CAASPP systems and the Smarter Balanced systems using a single sign-on.

##### Smarter Balanced Implementation Readiness Package

ETS has verified that the delivery system conforms with the Smarter Balanced Implementation Readiness Package (IRP) version 1.0, which currently covers capabilities in test administration and item level score results delivery. Annually, and upon a request from the CDE, ETS will provide evidence, including the Summary Performance Report produced by the Implementation Readiness Package as well as electronic access to the simulated assessment to allow the CDE to verify that items and applicable tools, supports and accommodations rendered correctly; items were scored correctly; and results were correctly delivered to the Smarter Balanced data warehouse.

##### CALPADS

ETS will verify with the CDE ETS’s ability to accurately accept data extracts from CALPADS, import that data into the management system, and provide appropriate exception reporting to the CDE. ETS will configure TOMS to process daily CALPADS updates. To be consistent with the 2015 CAASPP System, ETS anticipates receiving two CALPADS extract files nightly via SFTP. One extract file will have organization data, and the other will have student data.

To follow the process for the 2015 CAASPP System, ETS will coordinate with the appropriate CDE staff to facilitate the secure upload of CALPADS data extracts for use in the summative assessments. ETS will also verify the handling procedures for approval of paper-pencil test materials and special forms.

ETS will process the CALPADS files within 24 hours of successful receipt from the CDE. ETS will provide the following notifications when processing the CALPADS data:

- Notify the CDE via e-mail by 8 a.m. PT if one or more of the CALPADS extract files fail to upload to the FTP site.

- Notify the CDE via e-mail within 2 hours of processing whether ETS has received and has processed the file and the number of records processed.

- Notify the field via e-mail and caaspp.org system alert if there are any issues with the files that affects the field.

##### LEA System Compatibility

ETS will continue to propose to the CDE ways to optimize the appropriate data capture from LEAs in the CALPADS interface, so that the regular extracts provided to support CAASPP accurately reflect the CDE-approved supports and accommodations. ETS will also continue working closely with the CDE by providing a TOMS user interface that provides the LEAs with the flexibility to update student support or accommodations needs directly. To be consistent with the 2015 CAASPP System, ETS will consult with the CDE to establish the protocols and permissions needed to allow for this flexibility and configure TOMS accordingly

#### 3.2.B.3 Data Security

ETS maintains dedicated staff with responsibility for information security, physical security, test security, privacy, disaster recovery/business continuity, and internal audit. These staff members communicate and collaborate via a corporate-level Security Steering Committee of leaders responsible for each function, which ETS’s chief information security officer leads.

##### Data Security Plan

ETS will provide all interfaces with the most stringent security considerations in mind, including interfaces for data encryption at rest and in transit for databases that store test items and student data. The CAASPP Assessment Delivery System integrates best security practices, including system-to-system authentication and authorization, and meets the Federal Information Processing Standard Publication 140-2 (FIPS PUB 140-2) issued by the National Institute of Standards and Technology (NIST). All CAASPP data will remain within the continental United States as required by the CDE.

ETS will manage, maintain, transport, and appropriately secure data storage and backup files. Also, ETS will employ industry-standard encryption to protect personally identifiable information both when it is in storage and when it electronically transfers across a public network. ETS will maintain that data in a portable format as agreed upon with CDE.

ETS will meet the CDE’s expectations to develop and execute a data security plan that follows NIST SP 800-15 rev1 to comply with the applicable data security requirements outlined in the final system requirements that may be updated annually. Discussions about the data security plan and user roles and permissions will be an integral part of the joint requirements sessions, and ETS will document decisions in the requirements document for the CDE’s approval.

##### Working with Subcontractors and Vendors

ETS’s company policy mandates an Inter-Enterprise Security Assessment (IESA) of external organizations whenever their work impacts any of the following: sharing sensitive or critical data, communicating sensitive or critical data via non-ETS networks and systems, or interconnecting ETS networks and systems with others. ETS requires subcontractors and vendors by contract to maintain agreed-upon security controls and to provide periodic control assurance.

##### Providing for User Roles and Permissions

The CAASPP System will feature system access control features and authentication of users using industry-standard user access, authentication methods, and encryption. The CAASPP Assessment Delivery System allows for numerous user roles and permissions based on the functions that each user must perform in order to complete their responsibilities for the CAASPP System. ETS will coordinate with the CDE to schedule meetings to review, refine, and add user roles and permissions for finalization within 15 days of the contract start date.

#### 3.2.B.4. System Development Process

At the CDE’s direction, ETS will provide process maps, standard operating procedures, templates, definitions of roles and responsibilities, technical documentation utilizing templates, and project schedules to the CDE’s Independent Verification and Validation consultant and Independent Project Oversight Consultant.

##### Design Process

Led by the ETS Technology Manager, ETS will perform design at two levels:

- Solution Architects will tailor a high-level solution design, designing for innovation and capacity from the start. Their work will provide the big picture, establish that all bases are covered, and confirm that all involved parties are identified and collaborating to make CAASPP successful. The solution architects’ high-level solution design includes: (a) a high-level use case diagram identifying the key capabilities/domains of the solution, (b) activity diagrams depicting flow of responsibilities across software applications, (c) deployment diagrams identifying all participating applications and all interfaces, and (d) other Unified Modeling Language diagrams and text as needed to describe the solution. These solution architects work closely with the various development teams in scope for the solution.

- Application Architects on these development teams then design their respective software applications and interfaces based on the solution design, verifying that their component fits in with the others.

##### Development and Testing Process

ETS’s SDLC teams will continuously improve, support, and enforce smooth and effective operation end-to-end in the technology components of this project. This team will work closely with all IT staff across ETS to establish smooth operation, quality output, and exceptional communication. ETS will perform an analysis at two levels. For the first, at the business level, a specialized team of business analysts will work with the CDE to capture, confirm, and analyze the CDE’s needs; at the second, software level, system analysts will determine the functions of the systems based on the business needs. Through ETS’s documentation practices, ETS will capture and account for all of the CDE’s functions.

##### Validation Process

ETS will follow industry best practices in software development and coding for the CAASPP System. This means ETS will use continuous integration, unit testing, code reviews, separation of environments (e.g., development, various levels of testing, and production), and version control. ETS will use repositories to systematically control all versions. ETS will use reference architecture to guide the use of technologies to keep abreast of the latest technologies, verifying that external support is available and keeping IT focused and efficient. ETS also verify operational readiness of software development by (1) developing knowledge scripts for use by CalTAC personnel on how to route issues raised by end users, (2) documenting/communicating how to operate the software to the operations team, and (3) updating the software’s disaster recovery plan as appropriate.

ETS’s software development teams perform rigorous testing of their developed software, including unit testing, dev-to-dev integration testing, and functional testing. ETS will complement that with additional rigorous testing by a dedicated group specializing in software testing. This group provides a robust suite of testing, including: (1) functional testing, (2) integration testing, (3) performance testing, (4) security testing, and (5) accessibility testing. In particular, in the area of performance and load testing, this group will verify that ETS meets the scalability needs of California through capacity testing, extended period testing, stability testing, stress testing, functional verification under load testing, aggregate testing, and increasing load testing. Dedicated performance testers will tune specialized performance testing tools for the CAASPP System to account for the anticipated load.

ETS’s software testing group will perform progression and regression testing using a combination of commercial, open source, and custom developed tools. This testing will follow a rigorous and robust process. ETS will strictly manage defects and maintain traceability between requirements and test cases in order to verify complete coverage. ETS’s testing group will leverage testing automation through scripting and specialized testing tools in order to bring great efficiencies and value to the CDE by saving on manpower and enabling robust regression testing — all while utilizing highly skilled testers to weed out those issues that tools can overlook.

#### 3.2.B.5. System Implementation

The System Implementation Plan will be part of the PMP, and ETS will discuss this plan as part of the joint requirements sessions before the Orientation meeting. Following the Orientation meeting, ETS will refine the System Implementation Plan for final review and approval by the CDE.

##### Overview of Hosting System

ETS will use two proven hosting providers to meet the CDE’s requirements: Rackspace® and CSC.

##### System Implementation Readiness Assessment Methodology and Schedule

To cover system implementation readiness assessments, or the Operational Readiness Review (ORR), a dedicated team of release managers carry out ETS’s Release Management (RM) process. As the pilots, field tests, and eventually implements new CAASPP computer-based assessments are conducted, ETS will analyze historical test taker estimates as well as survey data from LEAs about the target test taker populations to plan for a capacity that will support continuous systems operations for all CAASPP computer-based assessments.

##### Implementation schedule, including Field Tests and Pilots

ETS will work closely with the CDE and use the RM process to establish the implementation schedule for all administrations, including CA NGSS, CA NGSS Alternate, and primary language pilot tests in 2017 and field tests in 2018.

##### Overall Resources Needed to Support the Implementation Effort, including Hardware, Software, Facilities, Materials, and Personnel

By means of a formal resource planning process, ETS proactively determines and regularly re-assesses anticipated resource capacity based on California’s estimates for computer-based Smarter Balanced summative and interim assessments, test taker volumes, and expected peak volumes. ETS will also use historical resource usage data from the 2014 field test and the 2015 administration to refine capacity estimates. As the pilot tests, field tests, and eventually the implementations of the new CAASPP computer-based assessments are completed, ETS will analyze historical test taker estimates as well as survey data from LEAs about the target test taker populations to plan for a capacity that will support continuous systems operations for all CAASPP computer-based assessments. Capacity planning will enable the right sizing of the infrastructure capacity in order to scale rapidly and handle spikes in demand.

##### Security Features Associated with the System When it is Implemented, Including Security during Implementation

ETS has built security into the production environments and the technologies used and software developed. ETS’s software development process and software testing process includes a comprehensive security framework. This risk-based framework focuses on minimizing vulnerability, increasing awareness, and developing proficiency. In order to establish this level of security, ETS assesses every component of its systems for vulnerability. ETS utilizes Threat Modeling analysis and Attack Tree analysis, which are methods to analyze designs for threats and mitigate them.

Simultaneously, ETS will employ a few different methods of security testing, including vulnerability testing, penetration testing, and vulnerability code review. These methods utilize numerous state-of-the-art automated tools as well as manual security assessment and hacking techniques performed by dedicated and trained security professionals. These methods also involve comprehensive testing and analysis steps.

Driving software development and providing a measurement base for testing, ETS will use tools to generate security requirements tailored to individual systems based on their characteristics. Open Web Application Security Project (OWASP) best practices, the industry leader in security standards, guides software development to verify that the software is secure. ETS also has an Information Protection Office (IPO) group in IT with oversight over all aspects of security, including software, hardware, network, and personnel security.

##### Performance-monitoring Tools and Techniques

ETS will employ a number of strategies to verify ongoing systems performance, including monitoring of system availability and providing reports of online system usage to the CDE. ETS can configure the metrics and thresholds for monitoring based on the CDE’s needs during start-up planning and annual project planning engagements.

ETS will include detailed planning steps identified during project initiation with CDE to identify the most effective parameters for the assessment programs, so that systems is configured to capture and provide reports that are useful for the CDE. During subsequent project meetings, ETS will establish regular reporting practices and periodically review the elements being captured and reported out, providing the most relevant and actionable data possible for the CDE and other stakeholders.

##### Site-specific Implementation Requirements

Outside of preparation of the computer labs at the schools, the test delivery system has no site-specific implementation requirements. ETS will provide a diagnostic tool that may be used by LEAs and schools to verify that they have the bandwidth to support the desired number of testers.

##### System Acceptance and Sign-off Process

To accomplish system acceptance and sign off, ETS will deploy systems to a staging area, which mirrors the final production environment for operational and user acceptance testing by clients such as California. ETS will develop and review the user acceptance testing to confirm that systems meet the CDE’s requirements. Final approval of user acceptance testing triggers final deployment of the system.

#### 3.2.B.6. User Experience

ETS will use a rigorous applications user experience design process, which includes checkpoints during the following phases: architectural design, requirements gathering, user interface (UI) design, usability testing, piloting, and operational delivery. Application design and development will follow industry best practices for delivery on multiple platforms and devices, leveraging World Wide Web Consortium (W3C®), Microsoft®, and Apple® human interface guidelines.

For accessibility, ETS will adhere to the Web Content Accessibility Guidelines (WCAG) 2.0, Level A & AA. ETS will audit and validate application content and interfaces to confirm they are compliant with international Web standards. The WCAG 2.0 guidelines meet or exceed the WCAG 1.0 and Section 508 guidelines set forth in the California Government Code section 11135 and policies included in the CDE’s Web Accessibility Standards. As part of this contract, the development process will incorporate the checklists provided on the CDE Web site (http://www.cde.ca.gov/re/di/ws/webaccessstds.asp) into the development checkpoints.

ETS will include detailed plans for conforming to the User Experience requirements and will include these plans as part of the PMP document described in Task 3.2.B. The User Experience plans will outline the following:

- Consistent look and feel

- Name of Student Displayed on Workstation

- Single Sign-on and Easy Navigation

- Best Practice Standards

- Accessibility Standards

- Online Help

- Identical Interfaces for Administrators and Students

#### 3.2.B.7. Technical Assistance Center (Technology Support)

ETS provides Tier 1, 2 and 3 support for the CAASPP Assessment Delivery System via telephone, e-mail and customer-initiated chat.

For telephone support, ETS uses a Verizon-hosted implementation of Avaya Contact Center v.7.0. The ETS California Technical Assistance Center (CalTAC) can support the staff required to quickly respond to contacts and can shift calls to another ETS Help Desk location if needed for disaster recovery purposes. Additionally ETS will use the Verizon-hosted cloud service to provide additional services. The Avaya and Verizon platforms have back-up technologies in place to continue to route calls in the event of a localized issue. The ETS Help Desk solution includes audio recording of 100 percent of inbound calls and call storage for up to six months.

ETS will use eGain® for e-mail and chat response management. ETS’s e-mail and chat software have the capability to separate Tier 1, 2, and 3 contact types and respond to them based on set timeframes.

ETS will provide escalation to Tier 2 and Tier 3 via telephone, e-mail or chat transfer. ETS logs all contacts and their status as cases into the Customer Relationship Management (CRM) system by institution, district, and individual contact.

ETS will maintain e-mail addresses for various groups such as the LEA and CDE information technology groups to allow for quick dissemination of information. During the Orientation Meeting, and at each Planning Meeting, adding specific groups to the CRM workflow will be discussed.

Cases escalate to Tier 2 and Tier 3 support via a workflow system based on program and issue type, which allows ETS to determine when cases escalate to resolver groups. LEAs or other callers will receive a unique case number that they can reference their case against for all contact methods. The CRM system provides detailed level-reporting for the program overall or down to the school level. Reports on case escalation and case aging are available for review.

#### 3.2.B.8. System Delivery Release Management

ETS will use the RM process for coordinating, tracking, and reporting on software releases, from new release identification through production implementation. The process consists of three phases: release planning, release tracking, and release approval.

ETS will schedule RM planning meetings based on the agreed-upon frequency among the stakeholders, including AIR, MI, and the CDE. These Orientation and Annual Planning meetings will provide a forum for ETS to verify that the California releases are well-understood, that risks are identified, and that mitigation plans in-place. ETS will hold a joint meeting with parties to be identified by the CDE prior to a production release to review the migration steps, address risk, and obtain a consensus approval for the release. ETS will develop the System Delivery Release Management Plan during RM planning, which is the initial starting point of the RM process.

As part of the Release Tracking Process, ETS will have a dedicated RM group that actively coordinates, tracks, and reports on software releases from the initial planning phase through to production deployment/implementation. The RM group will work directly with the ETS IT manager and program manager for CAASPP so that the team effectively coordinates tasks, requirements, and communications with the CDE. ETS will establish communication channels for release of information notification and will determine the stakeholders, communication frequencies, and information the stakeholders should communicate via these channels. RM also obtains the implementation approvals to initiate the production deployment process.

ETS will distribute the release schedule to all identified stakeholders identified, who will then need to review and approve the Release Management Schedule and associated tasks respectively.

Other key Release Management processes and services include the following:

- Processes and procedures for communications, and coordination with internal and external partners, will be a critical component of the process, since ETS includes external partners such as AIR, MI, and the CDE.

- Provide release artifacts that describe release content, testing requirements, and data sourcing to the CDE.

- Closely coordinate system outage management with the CDE so that it occurs when no testing is taking place, at night or on weekends, and will not impact batch processing.

- Provide environments that mirror production to the CDE for end user acceptance testing.

- Provide SDLC Release testing procedures, including regression and integration testing with CALPADS, Smarter Balanced, and other external partners, to the CDE.

- Provide a detailed and complete Migration document that details every step and every piece of information that is needed to deploy it to production from scratch, including application and environment configuration, third-party libraries/software/technologies, system accounts, connection details, complete steps to install the entire environment and the application, as well as rollback procedures.

- Provide the user acceptance testing (UAT) plan, which documents processes and procedures for system delivery acceptance.

- Conduct post-production validation (PPV) using predefined manual and automated scripts to verify that the system is released correctly and that it is operational. ETS will also work with the CDE to develop and review the user validation scripts to verify that users deploy the system properly in the schools and that it remains accessible on all the devices used for accessing the ADS.

- Initiate a roll back to the previous state of the production environment in the unlikely event that the PPV is not successful. Once system engineers roll back the release, the software development team verifies the release once again to verify that the rollback was successful.

#### 3.2.B.9. Performance

The CAASPP Assessment Delivery System will support up to 500,000 concurrent users. Should there be issues with performance during the administration of Smarter Balanced and non-Smarter Balanced computer-based summative assessments, ETS has the capability to “turn off” or throttle back access to the Smarter Balanced Interim Assessments upon direction from the CDE.

The CAASPP Assessment Delivery System also includes existing network optimizations with the California K-12 High Speed Network (K12HSN). ETS will continue the existing optimizations and will work with the CDE and the K12HSN vendor to continue improving performance whenever possible.

##### Performance Testing

ETS will conduct three types of performance testing: 1) load testing to verify customer-facing components function under peak expected loads; 2) verification that back-end processes run in acceptable time frames under all expected conditions; and 3) validation that individual requests are processed to specification, excluding exceptions such as certain administrative reports. ETS will:

- execute tests (with appropriate iteration)

- analyze the results

- implement corrective actions

##### Working with CDE State Project Manager, the Independent Project Oversight Consultant (IPOC), and Independent Verification and Validation (IV&V) consultants

Within 10 business days of the performance report produced by the IV&V contractor, ETS will develop and submit a detailed Systems Performance Plan, in coordination with the CDE contract monitor and the CDE state project manager. The plan will include the most relevant ETS artifacts for monitoring performance, as well as the process that will be used to work collaboratively with the IPOC and IV&V consultants. During subsequent project meetings, ETS will establish and maintain regular reporting practices and issue escalation procedures to the CDE contract monitor, CDE state project Manager, the IPOC, and IV&V consultants.

##### Working with LEAs to Conduct Benchmark Testing

As part of the System Performance Plan, ETS will propose a list of schools to consider for benchmark testing; and will conduct systems benchmark testing with a set of LEAs and schools. The proposed list will include schools that represent the range of school types that participate in the CAASPP System. ETS will also schedule and LEA participation requirements for the benchmark testing; and will submit this list to the CDE for review.

Upon the CDE’s approval, ETS will contact each LEA to obtain permission to conduct benchmark testing. Each LEA will receive detailed information on what is required to participate in the benchmark testing and the goals for the benchmark testing. Within 10 business days upon completion of the benchmark testing, ETS will submit a report of the results, with recommendations for performance improvement where necessary. ETS will work directly with the CDE staff, including the CDE contract monitor and the CDE state program manager, to implement the systems changes needed.

#### 3.2.B.10. Disaster Recovery and Business Continuity

ETS will provide robust and fault-tolerant systems and processes. ETS houses systems in Tier 3 data centers with dual-powered equipment and multiple uplinks to support at least 99.982 percent availability. Additionally, industry-standard backup and recovery procedures are in place. ETS will work with the CDE to document and execute on a formal DR/BC plan that supports the specified uptime and recovery time objectives.

#### 3.2.B.11. Data Policy Retention and Destruction

ETS complies with the data retention, handling, and destruction requirements outlined in the requirements in the California State Administrative Manual (SAM) Section 5305.8; the Department of Education Administrative Manual (DEAM) sections 10120, 10600, and 10601; California Education Code (EC) 60607; and the Family Educational Rights and Privacy Act (FERPA) of 1975.

The ETS solution also meets the Federal Information Processing Standard Publication 140-2 (FIPS PUB 140-2) issued by the National Institute of Standards and Technology (NIST) for data with personally identifiable information and secure test data (e.g., items, score keys), both in transit and at rest.

To comply with the contract transition requirements, ETS will maintain the final data of record as identified in the Requirements document and will confirm the appropriate transfer of the information to the next contract. ETS will securely destroy any data generated by and for CAASPP not considered the data of record. ETS will seek the CDE’s approval prior to the secure destruction of these provisional data.

#### 3.2.B.12. Maintenance and Operations

ETS will manage and coordinate requested changes in an orderly fashion. This will include scoping, at a high level, the amount of overall software changes anticipated for each test administration as well as account for infrastructure and technology upgrades.

As California’s needs change over time, ETS will capture those growing needs as Business Requirements, which will then be allocated to relevant ETS applications for implementation. The application development teams determine Functional Requirements additions/changes that address those changed business needs. The additions/changes will be allocated into releases considering the customer’s timing needs and other constraints.

ETS will establish appropriate communication channels to coordinate and communicate both scheduled and unscheduled releases, to the CDE’s specifications. Every release will contain release notes, including a list of all the functional changes and all the bug fixes that went out with the release.

# TASK 4: Test Security

ETS will provide the CDE with a secure system that is designed to meet the security challenges—both current and emerging—facing today’s LEAs and schools. The system has security checks before, during, and after testing—protecting the integrity of the CAASPP System.

## 4.1. Test Security Plan

Upon commencement of the contract, ETS will review and propose revisions to the CDE for the current test security plan as needed to be specific to the 2016 CAASPP administration. ETS will deliver the draft 2016 test security plan to the CDE at the Orientation Meeting. Then the 2016 test security plan will be revised based on comments from the CDE review and, within three working days after receipt of the CDE’s comments, will be delivered to the CDE. ETS will deliver the final version of the 2016 test security plan to the CDE within three working days after receipt of the revised plan. Upon CDE’s approval, ETS will implement the test security plan and will annually revise the test security plan for each administration.

##### Commitment to Security

ETS shares the CDE’s commitment to the confidentiality of students’ personal data as well as to the security of tests and will strictly enforce ETS’s security process. Every ETS employee must sign and abide by the ETS Code of Ethics, which explicitly describes the personal responsibility of employees to protect personally-identifiable information and intellectual property. ETS subcontractors must also sign documentation acknowledging their understanding of ethical and legal business practices, the need for site security, and expectations for confidentiality policies.

California will have the support of dedicated ETS staff who are responsible for information security, privacy, test security, physical security, disaster recovery/business continuity, and internal audits. These staff members communicate and collaborate via a corporate-level security steering committee, led by ETS’s chief information security officer.

Continual education and certification allow ETS to keep up-to-date in emerging security threats and industry best practices, both of which inform the continuous improvement of security practices and services.

ETS has adopted the International Organization for Standardization’s (ISO’s) 27000 series of standards as both its information security framework and the foundation of its Corporate Information Protection policies. This series of standards for information security management and control drives ETS’s information security program, as well as the manner in which ETS delivers services.

In addition to the ETS Code of Ethics policy noted above, ETS require all employees, agency personnel, consultants, and other work-for-hire staff that use its network services to sign a statement of agreement, verifying that they have read the ETS Corporate Information Protection policy and that they understand and agree to abide by its provisions. In addition, all staff who see or handle secure test items, forms, or booklets must sign a confidentiality agreement as a condition of employment. Information protection policies and the confidentiality agreement form will be provided to the CDE upon request.

ETS’s infrastructure provider holds an ISO 27001 certification for both ETS’s data center, where ETS systems such as servers and the mainframe reside, and ETS’s operations (e.g., network administration and desktop support). This certification covers the systems and internetworks supporting all phases of ETS’s assessment process, including identity, authentication, authorization, registration, test delivery, results collection, scoring, and reporting. An independent firm regularly audits controls and provides an annual SSAE16 Statement of Controls report.

Secured Access. The ETS data center will continue to protect the CAASPP System’s data. Only personnel with functional responsibilities may unlock the doors with their badges, and authorized personnel accompany visitors within the data center at all times. The data center contains extensive smoke detection and alarm systems, as well as a pre-action fire-control system. ETS stores critical files for software, applications, and documentation offsite in a secure location and has a backup site so that operations may continue in the event of a natural disaster.

The Assessment Delivery System is hosted in secure data centers in Chicago, Illinois, and in Ashburn, Virginia, that meet or exceed industry standards, are regularly audited by an independent firm, and provide multiple physical layers of security, including: an integrated proximity card-reader system, a closed circuit monitoring throughout the facility, and security staff available 24 hours a day, seven days a week. Industry standards and best practices — such as file system encryption, host-based firewalls, system hardening, and secure access — are used to enable network, host, and application security.

ETS is in compliance with all applicable legal and regulatory obligations at both the state and federal level. Applicable regulations for information security most often involve the protection of privacy, payment mechanisms, and other sensitive information and systems. Internal and external audits and management reviews grade compliance. Every three years, a team of internal and external auditors, analyze and evaluate, audit the products and services delivered.

##### Item and Test Development Security

ETS will keep materials locked when not in use and will transmit items via ETS’s internal item banking system or secure file transfer protocol sites to maintain security for item development, item field tests, and test form construction. ETS will encrypt databases and backups to meet the standards published in Federal Information and Processing Standard 140-2.

##### Item Bank Security

The measures ETS takes for assuring the security of electronic files are as follows:

- Access to item banks requires secure login identification and passwords, and is restricted to the least amount of privilege required to perform one’s job functions.

- Backups of electronic forms of test content and item banking systems will be kept off-site in order to prevent loss from a system breakdown or a natural disaster.

- The off-site backup files will be kept in secure storage, with access limited to authorized personnel only.

##### Committee Meeting Security Procedures

For committee meetings participants will be required to sign and submit confidentiality forms. For meetings that use paper materials, participants must sign numbered materials in and out.

##### Computer Based Testing Security

ETS designs identity and access management as a set of services, processes, and technologies to securely and consistently manage user identities, privileges, and usage. ETS strictly controls access to the CAASPP Assessment Delivery System based on the assigned user role.

The CDE can direct ETS to change access to data and functionality at any time based on the available user roles. The CAASPP Assessment Delivery System will require users to authenticate themselves by providing a username and password before gaining access. The system’s single sign-on implementation will use industry-proven security standards and best-practice protocols. ETS also will enforce an industry-standard secure password policy every time a user creates a new password or updates an existing one.

The test delivery system will provide a secure browser that locks down the student’s desktop by blocking certain external applications and system hot keys. Any student or item data communicated to and from the test delivery system uses industry-standard encryption to enable secure content delivery. ETS will follow established standards and perform quality inspections so that the data are accurate.

##### Paper Pencil Testing Security

ETS has agreements with more than 60 printing vendors specializing in the production of high-stakes assessment materials, including secure test booklet printing, accessible formats, scannable form production, non-secure materials production, non-standard formats, and other media.

Only those printing vendors who have met the security criteria and who have successfully passed the qualification process will produce secure test materials for the CAASPP System. ETS will use established, secure processes to facilitate the back-and-forth of quality checks during the production cycle. ETS will use a secure courier to ship all test materials to California LEAs in unmarked boxes, bearing only the return address of ETS’s test materials processing center.

ETS will combine bar-code reading technology with a proprietary order tracking system to facilitate closed loop tracking for all secure materials. This process will create a permanent, detailed record of items distributed to each school, which can be matched against returning materials to assess the completeness of each district’s/school’s return.

ETS will systematically match the captured barcode numbers to the outbound shipment barcode numbers’ data files. An output log will be generated that identifies missing test materials by school and LEA. ETS program managers will receive this log, called a “Missing Materials Report,” for follow-up calls to LEA staff to investigate any missing test materials. ETS will provide a document identifying the check-in of all secure materials after each administration.

ETS will use a barcode verification system to account for the secure items received in the warehouse for closed loop tracking.

ETS will obtain written permission from the CDE prior to proceeding with certified, approved destruction at an approved facility after appropriate retention periods. Upon destruction, ETS will present a certificate of destruction of those materials.

##### Encryption of All Test Items and Student Data at Rest and In Transit

ETS will provide all interfaces with security for data encryption at rest and in transit. Encryption at rest primarily applies to any data files that reside on a server that uses the secure File Transfer Protocol (SFTP) waiting to be retrieved. Best security practices, including system-to-system authentication/authorization, are integrated in ETS’s solution design to meet the Federal Information Processing Standard 140-2 issued by the National Institute of Standards and Technology. As the CDE requires, all CAASPP data will remain within the continental United States.

##### Secure Data Transmissions

As a part of implementation, ETS will establish an SFTP service that will manage SFTP transfers to a directory structure. Gatekeepers, generally one in California and one at ETS, will determine access privileges. The ETS gatekeeper will be responsible for approving all users for access.

##### Reporting

The reporting system will produce quality-controlled reports and copy them to a secure location. There, score recipients can access only the information allowed by their security profile.

ETS will store California students’ information on servers that will be encrypted and protected with multiple levels of password protection to prevent unauthorized access. Additionally, ETS will earmark the reports displayed to a particular user for his or her assigned access permissions. The method used to download or electronically transfer files that contain student level data will utilize encryption that meets the standards outlined in Federal Information Processing Standards 140-2. Secure socket layer encryption will protect all data transferred over the Internet, and ETS will maintain data behind a corporate firewall; intrusion-detection software monitors this firewall for breaches 24 hours a day, seven days a week, 365 days a year.

## 4.2. Test Administration Monitoring

ETS will provide the following test administration monitoring activities for the CAASPP System:

- working proactively with LEA CAASPP Coordinators

- social media monitoring

- on-site test security site visits

During a test administration cycle, ETS will meet weekly with the CDE to review test monitoring activities, including the areas described in the following sections. These weekly meetings are separate from the weekly management meetings and will focus specifically on test monitoring activities such as appeals for computer-based tests.

##### Working with LEA CAASPP Coordinators

Prior to the beginning of the test administration window, ETS’s program staff and ETS’s Office of Testing Integrity staff will provide training, through a live Webcast, to LEA CAASPP Coordinators over all required test security procedures for the CAASPP System. ETS will record and post the Webcast to http://www.caaspp.org/ for later viewing. The test security training Webcast will use a train-the-trainer model — that is, in addition to informing LEA CAASPP Coordinators of the test security requirements, ETS will provide them with tools and training materials that they may use in training their LEA staff, CAASPP Test Site Coordinators, Test Administrators and Test Examiners, and even students.

ETS will also provide additional information, tools, and materials on http://www.caaspp.org/ that will assist LEAs in meeting test security requirements. ETS will work with the CDE to provide additional test security materials, as needed, for LEAs.

ETS will also work directly with LEA CAASPP Coordinators and Technology Coordinators as they prepare their local systems, devices, and sites for test administration. ETS will conduct up to 100 on-site visits and up to 200 virtual site visits to LEAs to provide technology and test preparation support as needed.

The CAASPP Assessment Delivery System includes an online method for submitting appeals for computer-based assessments. ETS will work with the CDE to develop the online testing irregularities reporting process, which will include a decision tree to address reported irregularities in a timely fashion.

##### Social Media Monitoring for All CAASPP Tests

ETS will monitor social media and other Web sites throughout each CAASPP administration. Monitoring will begin when the first LEA receives its test materials in January of each administration year and will end upon the closing of the final testing window, in August, or when the last LEA has confirmed completion of testing. ETS will monitor such Web sites as YouTube®, Facebook®, Instagram®, Google+®, Twitter®, and school and LEA Web sites. ETS will include other Web sites identified during the test administration window. ETS will look for any postings — both images and text — that include secure test materials such as test questions or passages, test booklet covers, and answer documents.

For each identified posting, ETS will collect any relevant information, including student name and school or LEA, if possible. ETS will enter this information into a secure online log that is accessible by both ETS and CDE staff. ETS test development and psychometric experts will evaluate each posting identified to be test material and will make recommendations to the CDE on the impact of the items to the validity of the test administration.

##### On-site Test Security Visits

ETS’s Office of Testing Integrity and partner In-Touch Insight will plan and conduct up to 130 on-site test security site visits annually. In-Touch’s team of in-state auditors will conduct the test security site visits.

OTI and CAASPP Program Management staff will provide training to the In-Touch auditors on the expected site visit audit procedures. ETS will conduct the auditor training via live Webcast from the ETS Sacramento office, which will allow participation by CDE staff. ETS will record and post the Webcast on an auditor-only section of http://www.caaspp.org/ for later viewing. Each auditor will complete the provided training; and In-Touch supervisors will not assign auditors to site visits until they verify the completion of training.

The site visits will include audits of both computer-based and paper-pencil test administrations. ETS will conduct before-, during-, and after-testing audits, including:

- 25 pre-test audits (both computer-based and paper-pencil testing)

- 60 during-testing audits (both computer-based and paper-pencil testing)

- 15 post-test audits (paper-pencil testing only)

ETS will submit the proposed test security site visits auditor checklists to the CDE for review and approval. ETS will randomly select 125 LEAs as potential sites, with 100 primary sites plus 25 replacement sites. The proposed list will be representative of California’s diverse LEA demographics. In addition, ETS will include up to 30 additional LEAs at the CDE’s direction. ETS will submit the combined list to the CDE within 60 working days before the first test administration window.

Upon the CDE’s approval of the combined list, the In-Touch auditors will begin scheduling the 130 test security site visits. Auditors will notify the LEA CAASPP Coordinator at least three working days before the scheduled site visit. At the direction of the CDE, a site visit may be scheduled and conducted immediately.

When conducting the site visits, auditors will present a letter of introduction from the ETS Office of Testing Integrity as well as valid government-issued identification. In-Touch will conduct thorough background investigations of each potential auditor before the auditor may complete training and conduct audits for CAASPP.

ETS will report the schedule of site visits weekly to the CDE. As site visits are completed, ETS will also report the preliminary results of the site visits. When a site does not meet the test security requirements, ETS will work with the CDE to determine the next action item, such as instigating a security breach investigation. ETS will submit the final report for a site visit to the CDE within 10 working days after the completion of that site visit.

## 4.3. Investigating Security Breaches

ETS will conduct an investigation of any confirmed test security breach that may compromise the CAASPP administration. An investigator from OTI will be available within 48 hours to handle security concerns related to the CAASPP administration.

Investigations will include interviews with Test Administrators and/or Test Examiners, students (at the discretion of the LEA), CAASPP Test Site Coordinators, and any others who had access to the test materials (online or paper). ETS also analyze data from computer-based incident response and forensic investigation. These investigations will attempt to determine the identity of those involved in the incident, recover any missing material, and assess the extent to which they compromised the test content.

For all reported security breaches, ETS will coordinate and communicate the investigation with the CDE. If the breach involves Smarter Balanced test materials, ETS will work with both the CDE and Smarter Balanced to conduct the investigation and determine the proposed resolution. If the breach occurred in one or more of the member states, ETS assumes that Smarter Balanced will notify the CDE, and will coordinate with both the CDE and Smarter Balanced to mitigate the breach.

When requested, OTI will conduct an immediate on-site investigation in response to security breaches. As required, ETS will obtain the CDE’s approval prior to the investigation. OTI will investigate and report results to CAASPP program management within five days of being informed of a security breach. When necessary, ETS will provide immediate reports through telephone and/or e-mail.

In-Touch auditors will immediately report any breaches to OTI, and OTI will notify CAASPP program management, which will in turn will immediately notify the CDE. ETS requires auditors to file an online site visit form with ETS within three days of the site visit.

ETS will submit a summary report of the investigation within 10 working days following the conclusion of the investigation.

# TASK 5: Accessibility and Accommodations

ETS is committed to establishing that California students have the most accessible user experience with the CAASPP System. In this section, an overview is provided of the appropriate universal tools, designated supports, and accommodations that are available in compliance with Smarter Balanced policies and with the California Code of Regulations, Title 5, sections 853.5 and 853.7.

## 5.1 Accessibility Plan for Computer-based and Paper-pencil Tests

### 5.1.A. Computer-based Tests

ETS will use the AIR proprietary TDS to deliver all CAASPP computer-based assessments including: Smarter Balanced summative assessments, Smarter Balanced interim assessments, CAA, CA NGSS, CA NGSS Alternate, and Primary Language. ETS will provide students access to all of the appropriate universal tools, designated supports, and accommodations needed for the computer-based assessments, which align with the Smarter Balanced Usability, Accessibility, and Accommodations Guidelines (see table in Appendix D). ETS will review the accessibility supports to ensure consistency with Smarter Balanced and as appropriate for the given non-Smarter Balanced CAASPP assessment. California will be able to determine whether Test Administrators may adjust settings at the beginning of the session or whether access to specific features requires higher-level authorization.

ETS intends to work with Smarter Balanced and the state of California to implement new tools or supports in the student interface and secure browser. ETS is committed to working with the CDE and Smarter Balanced to support emergent technologies and accessibility features to the greatest extent possible. As new opportunities arise, ETS will review the technology or feature and make recommendations to the CDE and, if appropriate, Smarter Balanced on the potential systems and impact. ETS will implement new technology or features that are approved in writing by the CDE and ETS.

According to the CDE’s needs and preferences, ETS offers the following choices so that each accommodation can be:

- available to all students

- assigned to students in advance through data upload or through the designated state, LEA, or school administrators

- assigned to students at testing time by the test administrator

At the beginning of the contract and annually thereafter, ETS will make recommendations to the CDE on the assignment of the tools and supports. ETS’s recommendations will be based on experiences from the previous year’s CAASPP administration as well as information from other sources if available such as the California Special Education Management Information System (CASEMIS) and TOMS.

#### 5.1.A.1. Print on Demand

The AIR system will continue to support the print on demand accommodation for items. It is the responsibility of the local test administrators to securely destroy any items that were printed. The test administration manuals developed for each assessment and the test security Webcast will provide full instructions for the secure destruction of locally printed secure test materials. Test security site visit audits, described in Task 4, will include audits of the proper handling of these secure materials.

The TDS will deliver real-time adaptive Braille; large print, AIR’s secure print-on-demand feature, which prints an item or item group to a designated printer, for large print and other paper assessments, or to an embosser for Braille forms. Only the computer-based assessments will be available through the Print-On-Demand feature – paper-pencil assessments will be provided separately to LEAs by ETS.

The print-on-demand function are protected with security controls at three levels:

- embedded security in the print-on-demand function

- authentication, which confirms that only authorized users access information

- policy and test administration procedures, which confirm the proper handling, retrieval, and tracking of secure materials

#### 5.1.A.2. Assistive Technology

The TDS currently supports a wide array of assistive technologies, and ETS continues efforts to expand the classes of these assistive technologies. The system’s streamlined interface adheres to Web Content Accessibility Guidelines 2.0, and AIR is actively working to secure certification of compliance. Permissive mode is built into the system, which relaxes these security restrictions for individual students who need to use such technologies.

The TDS currently works with a variety of refreshable Braille devices, screen readers, on-screen keyboards, and a wide array of input devices.

ETS will collaborative with the CDE to understand the assistive technology needs of California LEAs and students. While it is impossible for any organization to guarantee support for unknown hardware and software, ETS is committed to providing accessibility for all students.

#### 5.1.A.3. Translations

The TDS will support all means of translation access which Smarter Balanced has designed within its assessment system or which the CDE determines to be available for the new CAASPP assessments. The availability of access features, embedded supports, and accommodations is completely configurable, at the CDE’s direction.

##### Translations for Smarter Balanced Assessments

ETS’s system will deliver all Smarter Balanced items with translation tags for all required language translations and the provided translations will remain consistent with Smarter Balanced specifications. These translations include Spanish, Arabic, Vietnamese, Cantonese, Mandarin, Tagalog, Punjabi, Korean, Russian, Ilocano, Ukrainian, and American Sign Language (ASL).

##### Translation Glossaries for CA NGSS

The TDS will also deliver the translations for the CA NGSS assessments (excluding the CA NGSS Alternate). For Spanish stacked translations, ETS assumes that approximately 300-350 words may need to be translated for each of the three grade-level tests developed, for an estimated total of 900-1,050 words.

ETS assessment development specialists will work with EL specialists to identify the words that are recommended for translation. ETS will submit the recommended word lists to the CDE for review and approval. The CDE-approved word lists will then be submitted to ETS’s translations services vendor. ETS will provide the translation glossaries (for stacked translations) in each of the languages supported by Smarter Balanced for CDE review.

In addition, ETS will provide full translations of the CA NGSS Assessments in Spanish. ETS assumes that the CDE will provide its own language experts to conduct the CDE reviews. At the CDE’s direction, ETS will arrange to have an independent review completed.

### 5.1.B. Paper-pencil Tests

ETS assumes that the following assessments will require braille and large print versions in accordance with student IEP requirements:

- Smarter Balanced ELA and mathematics, grades three through eight and grade eleven

- California Standards Tests (CSTs) and California Modified Assessment (CMA) for Science in grades five, eight, and ten

- Standards-based Tests in Spanish (STS) for Reading/Language Arts (RLA) in grades two through eleven

The print quantities of the CST/CMA for Science and the STS RLA braille and large-print test books will be estimated based on usage from previous administrations and take into account any other factors that could influence volumes. The quantities of the Smarter Balanced braille and large-print test books will be based on orders provided by LEAs through TOMS by December 1 annually.

ETS will provide detailed LEA CAASPP Coordinator instructions and test administrator directions to support the test for the special versions.

ETS will produce sufficient quantities of the special version test booklets and supporting answer documents to support the initial orders, any supplemental orders, and any samples necessary to support review and archival processes. ETS will continue to make available the special versions of tests, along with their accompanying test materials, even when the standard paper-pencil version is no longer administered.

#### 5.1.B.1. Braille and Large Print Testing Materials

##### Braille Versions of the CST and CMA Science tests and STS RLA Tests

Braille versions for this contract will be based on existing braille versions of the previously administered assessments. ETS assume that some level of updates and edits to existing braille materials.

If revisions to the existing braille versions are required, ETS will use contracted braille for CST sciences and CMA sciences and uncontracted braille for STS grades two through eleven.

##### Fixed-form, paper Braille Versions of the Smarter Balanced Summative Assessments

ETS assumes that UCLA will provide the fixed-form braille versions of the Summative Assessments for all grades and content areas as a print-ready PDF. ETS will brand the braille versions with CAASPP-specific covers. There will be no other revisions made to the Smarter Balanced braille versions.

##### Large-Print Versions of the CST/CMA Science and STS RLA Tests

Large-print versions for this contract will be based on existing large-print versions of the previously administered assessments. Like the braille versions, ETS assumes that there will be some level of updates and edits to the existing large-print materials.

If revisions are needed to the existing CST for Science, CMA for Science, or STS for RLA large-print versions, ETS test developers will identify those items that require special attention from the staff responsible for producing the large-print forms. The large-print version will be produced in a font format that is equivalent to 20-point Arial.

##### Large-Print Versions of the Smarter Balanced Summative Assessments

ETS assumes that Smarter Balanced will not provide a large-print version of the Smarter Balanced tests. ETS will produce large-print versions that meet the standard state requirements that approximate 14-point font through photo enlargement. ETS will indicate which items cannot be used for scoring because of art or graphics that may be affected by enlargement, and about the spacing of materials that affects performance on items.

ETS will print the large print test forms on 11″ x 17″ paper. The large print test forms will follow the pagination of the standard-size test book.

##### Distribution of Braille and Large Print Testing Materials

ETS will package forms into kits that are ready for distribution to the LEAs on the same schedule as the standard version of the tests. LEAs will use ETS’s system to order braille and large print kits, just as they do for the standard test materials.

Braille kits will include:

- Braille test booklet

- operational test booklet

- Braille response document

- operational response booklet

- directions for administering, transcribing, and returning Braille tests

- boxes and envelopes, along with pre-paid return shipping labels, included in the shipment of all materials to the LEAs

Large print kits will include:

- large print test booklet

- booklet directions for administering, transcribing, and returning large print tests

- boxes and envelopes, along with pre-paid return shipping labels, included in the shipment of all materials to the LEAs

ETS will discuss the proposed plans in the project planning meeting, and ETS will make any adjustments to existing procedures or plans for development of accommodated materials.

##### Scoring of Braille and Large Print Testing Materials

Student responses for the CST/CMA science and STS RLA tests will be marked on a paper-pencil answer document and will be returned to the ETS scoring center for processing.

ETS assumes that the Smarter Balanced paper-pencil Summative Assessments will be available by August 1 annually. Test administrators will use the TDS to transcribe the student responses directly into the system, which will allow for scoring and reporting along the same schedule as the computer-based assessments.

## 5.2. Individualized Aids

All of the universal tools, designated supports, and accommodations currently required by California are supported. That said, ETS also understands that new technology and accessibility features will become available in the future.

To support this, ETS’s secure test delivery system will include a feature by which LEA CAASPP Coordinators could request the use of individualized aids. Using TOMS, the LEA CAASPP Coordinator can select a request button while viewing a student profile. The request would automatically generate a request form linked to that student and would include all required information including:

- LEA name, County-District-School (CDS) code, and mailing address

- LEA CAASPP Coordinator’s name and contact information

- the LEA or site testing window, test, and grade

- the Statewide Student Identifier (SSID) for the student for which the accessibility is requested

The LEA CAASPP Coordinator would then provide information on the individualized aid being requested and description of student need(s) that would be addressed by the individualized aid. If the CDE would like to expand the ability to request individualized aids to others, for example the test administrator, ETS can configure the user roles to allow for this at no additional cost to the CDE.

Annually at the end of each administration, ETS will provide a summary to the CDE of the individual aids requested and the CDE decisions made for each request.

# TASK 6: Assessment Development

ETS will provide a design plan that provides flexibility based on SBE direction and in collaboration with the CDE.  Design and item development through forms construction is performed by ETS Assessment Development with guidance from the lead Psychometrician.

## 6.1. Assessment Design

For the new assessments ETS will establish test design teams that include representatives from ETS internal areas of Assessment Development, Statistical Analysis, Program Management, and Information Technology, as well as representatives from test delivery partner AIR.

ETS will work with the CDE to engage the appropriate national and state-specific experts to participate in these test design teams. Figure 4 provides an overview of ETS’s test design team structure.

Figure 4.  Test Design Team Structure

Once the SBE has approved the design plan for each assessment, ETS will begin the test design process with two steps that are foundational to the evidence-centered design (ECD) process:

- identification (based on the CDE’s guidance) of the specific uses of student scores and the claims that CDE wishes to make based upon those scores

- creation of detailed descriptions of the learning domains to be covered in the assessment

#### CA NGSS-Aligned Science Assessments and Alternate Science Assessments

For planning purposes, ETS assumes that the test development activities for the CA NGSS science assessments, inclusive of the CA NGSS alternate science assessments, focuses on the assessments required to meet federal accountability. ETS will work with CDE to develop new CA NGSS science assessments in three grades to be determined through stakeholder input and approved by the CDE and the SBE. Development activities for the CA NGSS alternate science assessments is described with the California Alternate Assessment activities within this task. The CA NGSS alternate science assessments will be in the same grades approved by the SBE for the CA NGSS science assessments.

ETS will work closely with CDE to develop CA NGSS-aligned assessments that best meet the state’s vision. Other sources of appropriate items may be considered to create the necessary pool for test development and other resources.

#### California Alternate Assessments for ELA and Mathematics

Per EC Section 60640(b)(3), the CAA is limited to the same grades and subject areas assessed by the Smarter Balanced summative assessments (i.e., ELA and mathematics in grades three through eight, inclusive, and grade eleven). ETS will incorporate the ECD test development process with a high-level test design focused on the principles of universal design for learning. Using these concepts to guide test design and item development will allow ETS to create an assessment that is accessible to the widest range of students—and the resulting test scores will accurately reflect the claims of the assessment.

ETS proposes an innovative design that could evolve towards an adaptive assessment at each grade, from three through eight and grade eleven. For ELA and mathematics this design will need to evolve from an initial linear assessment in the 2015–16 administration to potentially an adaptive assessment in the 2017–18 administration. ETS will work with the CDE and with California stakeholders to determine if this proposed design meets the state’s needs.

In this SOW, ETS describes the core elements of the 2015–16 alternate assessments and then discusses how these core elements could evolve towards a multistage adaptive assessment by 2017–18. This multistage assessment would include ELA and mathematics, along with the field test of a CAA NGSS alternate assessment that follows the same test design (e.g., tiered adaptive) and administration procedures. If approved by the CDE and the SBE, this design will allow the CDE to deliver a linear computer-based assessment in 2015–16 for ELA and mathematics and have the potential to evolve towards an adaptive test design. Upon the direction and approval of the CDE and SBE, ETS would incorporate other sources of appropriate items if they become available to create the necessary pool for test development and other resources.

The core elements include:

- test design and item development to allow for students at all achievement levels, from essential understanding to CCC, to show what they know and can do

- incorporating student background characteristics into assessment design and analysis

- accessible and flexible delivery of assessment tasks that allow for the diversity of student communication, attention, and sensory needs to show what they know and can do

Working with the CDE, ETS will identify a plan for an adaptive test design that meets core psychometric requirements and is reasonable in test length and cost. Several options exist, including: adapting within an item or task (e.g., routing students to a related item that measures foundational skills if they answer an item incorrectly), item-level adaptive testing, multistage adaptive testing, and routing students to different difficulty levels using background information.

The ETS item development plan will support the exploration of acquiring and incorporating item banks such as NCSC as those item banks become available to California. This will offer California comparable measurement precision with reduced testing time compared to the 2015 NCSC test design.

##### Incorporate Student Background Characteristics into Assessment Design and Analysis

Recent advances in alternate assessment design recognize the value of using data on student background characteristics to:

- evaluate the fairness of assessments for different groups of students

- document the validity of the assessment based on external criteria

- route students to appropriate test difficulty

- inform standard setting

An efficient way of collecting background information is through the use of a short student inventory that teachers can complete during a student’s first year of testing, with a shorter version for subsequent years. One example of this is the NCSC Learner Characteristic Inventory (LCI). California teachers who completed the NCSC pilot tests completed the LCI, which allowed for deeper analysis of pilot test and field test data. In addition, ETS can use the NCSC LCI along with the NCSC Student Response Check (SRC) to route students in an adaptive assessment, or to determine test stopping rules for students who are unable to respond to test items due to their current functional levels.

ETS will work with the CDE to adapt the LCI or develop a similar inventory that allows administration to either students or teachers to describe a student’s abilities relevant to the constructs that the test measures. Another possible flexibility is to use teacher ratings to inform “stopping rules” (e.g., using teacher ratings in conjunction with a screening assessment to identify students without a foundational level of communicative competency).

Finally, ETS will work with the CDE to include one question (per content area) to allow teachers to rate student abilities in relation to applicable achievement-level descriptors (ALDs) (for example, the Performance Level Descriptors likely available from NCSC for ELA and mathematics and new CA-NGSS Alternate science PLDs) that summarize the grade- and content-specific knowledge and skills expected of students at different levels of proficiency. This additional question would simply ask the teacher to identify the level of proficiency that most closely matches the level of proficiency that the student demonstrates in the classroom. What would emerge is a grouping of students by achievement levels based in part on the recommendations of teachers who have the most knowledge of and experience with the students. Then, once ETS receives each student’s test score information, ETS will have a clear relationship between item and test performance and student ability levels. ETS may apply a contrasting-groups analysis to these data to recommend preliminary or tentative cut scores—the minimum test score needed to enter a proficiency level.

##### Accessible and Flexible Delivery

The third core element of an alternate assessment is accessible and flexible delivery of test content. Students with significant cognitive disabilities use a wide diversity of expressive/receptive communication modes. For example some students use various augmentative and alternative communication (AAC) systems, while others may respond verbally, through sign language, or through gestures, verbalizations, or facial expressions. To accommodate this diversity, ETS will use an online delivery platform along with individualized administration that allows for print-on-demand paper or tactile delivery and scribe/reader facilitated administrations for students for whom these accommodations are appropriate.

#### California Primary Language Assessment

ETS will work with the CDE to develop a careful and collaborative design process. ETS will work with the CDE to develop new primary language assessments in Spanish in grades to be determined through stakeholder input and approved by the CDE and the SBE. ETS understands that Spanish is the leading primary language in California. For planning purposes, ETS will work with the CDE to develop primary-language tests in Spanish.

For planning purposes, ETS assumes that the California primary language assessment focuses on reading and writing, though of course the final decision rests with the CDE. ETS assumes that the CDE would like to create a test that covers reading and writing.

The new primary language assessment will align with the literacy standard and expectations that mark the CCSS. Therefore, one logical approach is to build an assessment that utilizes the same sorts of items and performance tasks which the Smarter Balanced ELA assessment uses, including: items on short and longer texts, as well as questions that require selected responses, interactions with texts (such as highlighting and table creation), and written responses. Additional sources for appropriate items will be considered if necessary.

While ETS will support development of an assessment that will use the sorts of tasks used in Smarter Balanced, this test is in no way meant to be a translation or adaptation of Smarter Balanced. Rather, ETS will develop the assessment as a primary language assessment in the primary language while meeting CCSS ELA/Literacy standards. In other words, it will be a Spanish RLA test developed in Spanish—not a translation or adaptation of an ELA measure.

## Process for Working with the CDE and its Stakeholders in Designing and Developing Test Designs

ETS will implement the following plan to help California design forward-looking yet practical assessments for CA NGSS science, primary language, and alternate assessments. ETS understands that the state will undergo a thorough process by which the State Superintendent of Public Instruction (SSPI) will provide assessment recommendations to the SBE and legislature for consideration. Test development activities for the CA NGSS, CA NGSS alternate, and the primary language assessments will commence upon direction by the CDE. The work will proceed in the following stages and on the schedule described below in Table 2.

Table 2.  Summary of Process for Designing and Developing California Assessments.

| Process Step | Associated Tasks | Deliverables to the CDE for Review and Approval |
| --- | --- | --- |
| Step 1: Create a Draft High-Level Design Document for the CDE’s Consideration | - convene ETS and external subject matter experts - develop draft claims and propose evidence to support those claims - identify items, tasks, stimuli, passages and simulations to provide evidence - determine test format | Draft High-Level Design Document |
| Step 2: Review Initial Draft of High-Level Design Document | - stakeholders meet throughout the state | High-level Design |
| Step 3: Produce Detailed Task and Test Specification Documents | - develop specifications for items and tasks - develop specifications for test forms - draft initial achievement-level descriptors (ALDs) - draft plan for producing operational results of assessment | Detailed Specifications Documents |
| Step 4: Conduct Reviews of Detailed Item and Test Specifications and ALDs | - review with the CDE staff - conduct stakeholder outreach | Revised Test Design and Specifications Documents |
| Step 5: Finalize Design and Specifications Documents | - finalize documents based on input collected in Step 4 | Final Design and Test Specifications Documents. |

## 6.2. Item and Task Development

All items that ETS develops will meet the technical criteria established in the American Educational Research Association (AERA), the American Psychological Association (APA), and the National Council on Measurement in Education (NCME) Standards for Educational and Psychological Testing.

#### ETS Item and Task Development Processes

In Table 3, ETS describes the standard item and task development processes, which ETS will use for the CAASPP System. Note that ETS discusses both standard processes for more traditional items, as well as the robust processes ETS uses for the development of more complex items types (e.g., interactive and scenario-based tasks).

Table 3.  Summary of Process for Item and Task Development for California Assessments

| Process Step | Associated Tasks | Deliverables to the CDE for Review and Approval |
| --- | --- | --- |
| Step 1: Review Existing Item Pools | Existing items will be evaluated and placed into one of the following categories: - Item aligns with the test specifications and can be used in the assessment as is - Item can be used in the assessment with modification - Item cannot be used in the assessment | Analysis Report |
| Step 2: Create and Submit Annual Development Plans | - Detailed development targets by content classification, item type and grade - Identification of all deliverables, including items, rationales, rubrics, stimuli, copyright permission, etc. - Definition of metadata that will be associated with all items and tasks - Description of major review steps - A detailed schedule for the development process | Item Development Plan |
| Step 3: Recruit and Train Item Writers | - Selection and training of item writers - Item writing assignments | Item Writing Workshop Plan |
| Step 4: Creation of Items and Tasks | - draft quality items ranging from the simpler to the most complex and innovative - develop associated metadata establishing item alignments to the framework targets - utilize Agile Development | Deliverable in Step 6 |
| Step 5: Internal Reviews at ETS | - Three internal content reviews - An internal editorial review - An internal bias and sensitivity review | Deliverable in Step 6 |
| Step 6: Submission of Tasks to CDE and CDE Review | - Performance Task Development - Technology-Enhanced Item Development - Traditional Item Development | Draft Item Development |
| Step 7: External reviews with content and bias and sensitivity review panels | - Recruit Committees - Prepare the Necessary Materials - Facilitate Review - Record results | Meeting Summary Report |
| Step 8: Alternate Test Formats | - Follow American Printing House for the Blind (APH) and ETS guidelines |  |

- Step 1: Review Existing Item Pools

Once ETS has completed test designs, ETS will review any relevant existing items or passages in the California pools for appropriateness for the tests. ETS understands that it is not sufficient that an item can be “classified” according to a standard. For example, for CA-NGSS, items must truly measure the core ideas, practices, and cross-cutting concepts of CA-NGSS, and must fit the new assessment specifications.

- Step 2: Create and Submit Annual Development Plans

After completing the review of the existing pools (where appropriate), ETS will complete a plan for item and task development for each new assessment.

Since CAA will be an operational assessment beginning with the 2015-16 administration, the initial development plan will be constructed to allow for embedded field-testing in 2015-16. ETS will submit the initial item development plans for alternate ELA and mathematics by December 2015, and the schedules for Steps 3 through 8 will be based on a December 2015 approval date by the CDE.

For planning purposes for CA NGSS science, CA NGSS alternate science, and primary language, the plan will be constructed to allow for pilot testing in the 2016–17 school year. ETS understands that the development plans and schedules for Steps 3 through 8 below will be dependent on SBE approval and directions provided by the CDE to ETS on the assessments to be developed for these areas.

- Step 3: Recruit and Train Item Writers

To achieve a strong representation of educators from California in the item development process, ETS with the guidance of CDE will recruit California educators. When each new development cycle begins, ETS will conduct in‐person and virtual item writing workshops that provide an overview of the subject framework, subject‐specific guidelines, item writing techniques, factors that influence item difficulty, criteria for selecting stimulus materials, accessibility considerations, determination of appropriate item types to target specific measurement goals, translatability considerations, and bias/sensitivity guidelines.

ETS will give item writers assignments that include item target attributes, such as difficulty level and assessment goals. Assignments will include additional desired item attributes such as difficulty level, use of specific stimuli including media elements, accessibility guidelines, and tools and simulations. Outside item writers will sign and submit standard confidentiality agreement forms and will submit draft items to ETS electronically using appropriate security measures.

- Step 4: Creation of Items and Tasks

Central to the development of items are the standards for which CDE wants to collect evidence of student understanding. For many standards, the selection of passages and stimuli is a key component to ensuring items and tasks are aligned to the standards. For example, the CCSS for English Language Arts places an emphasis on text complexity as the major differentiator of standards across the grades, and the CCSS for Math and the CA-NGSS emphasize the application and generalization of knowledge and skills in a variety of settings.

Similarly, the creation of items involves more than the item content. Part of the ETS item development process includes the development of rationales (e.g., for incorrect answer options in selected response items) and scoring information and/or rubrics (for constructed response items).

- Agile Development

ETS will ensure that traditional items (such as selected response, technology-enabled items, and constructed response items) are created to measure accurately specific content and to provide meaningful information based on student responses. ETS also has processes in place for developing more innovative items and tasks such as those required to address CA-NGSS next-generation task development.

An Agile Software Development approach will be used for the development of all technology-based performance tasks under this proposal, as used by ETS on NAEP science development for NCES performance tasks. Agile Development involves iterative stages of development with clear targets for the development goals and functionality at each stage of the development. Each stage is informed by data collection procedures and review commentary that improves the quality and usability of the final product, so that the critical investments that are needed for sophisticated and complex measurement tasks can be made appropriately at each stage shown below.

Task Outline Agreement Review. For science performance tasks, the task concept involves an outline with key elements that will be incorporated into the tasks, including standard item development characteristics such as framework targets and overall formats but also performance-specific elements such as the inquiry question to be addressed, the independent and dependent variables to be included.

Alpha Draft Task Agreement Review. The next stage of review by CDE will be of a programmed version of the task called the “alpha” build, with final text and all item content in place and mockups of graphics, animation and functionality.

Certification Review. This is a Keep-or-Drop review by CDE. During this review, the performance tasks are reviewed for their fidelity to the final text agreed upon at the Alpha draft task build text (see above) and for the final functionality as agreed in the Alpha draft task build functionality mockup.

- Step 5: Internal Reviews at ETS

ETS has well-established procedures for reviewing all items to ensure they meet California’s expectations. Throughout this multi-step item review process, ETS assessment specialists continuously evaluate the match of the items to the standards, the appropriateness of the items to the population being assessed, the importance of the information being assessed, and the implications for instruction. Another key aspect of item reviews is ensuring conformity with California Test Item Specifications and the California Style Guide. If an item is deemed to be unrelated to the content standards, to not be age appropriate, or to provide inappropriate models for instruction, it is revised or eliminated.

- Step 6: Submission of Tasks to CDE and CDE Review

ETS is committed to providing CDE sufficient time to review and approve all content materials prior to assessment review panels. For Performance Task Development, ETS proposes a schedule where CDE review of traditional items coincide with the Alpha Draft Task Agreement Review of Performance Tasks. CDE review of Technology-Enhanced items will follow an approach similar to selected response and constructed response items. All items and tasks for year one development will be submitted to CDE for review.

- Step 7: External reviews with content and bias and sensitivity review panels

ETS will present its plan for CDE review followed by field review of the items and associated scoring rubrics. All assessment items are to be reviewed upon the completion of item editing. Each item must be reviewed by a Content and Bias/Sensitivity Review Committee in each content area to confirm that the item is of high quality, that it has accurate content alignment for that content area, that it measures the skill in a sound manner, and that the item does not unfairly advantage/disadvantage any student, and that it is not offensive to students, parents, or the public.

- ETS Will Prepare the Necessary Materials and Facilitate Review

For each meeting, ETS will prepare and provide all required review materials. ETS facilitators will record all committee input in master item books, with a location to mark the committee’s judgment of “Accept as is,” “Accept with edits,” or “Reject.” At the conclusion of each meeting, ETS and CDE representatives will discuss issues or discrepancies in notes or committee recommendations. For performance tasks, see the review criteria recording for each stage of review described above (Accept/Decline followed by revise to Accept for Outline and Alpha Build reviews; Keep/Drop for Certification review stage).

Recruitment of content and bias/sensitivity committee members

ETS will seek applications from California educators by emailing the application form and process to LEAs.  Applicants are vetted by ETS content staff to ensure minimum qualifications; criteria include degree in the appropriate field and teaching experience in the subject assessed.  Those applicants who are qualified based on these criteria are forwarded to CDE, and CDE makes final selections from the pool of qualified applicants.

Role of committees:

Content review committees are convened to validate the content appropriateness of all items, passages, and scenario-based tasks prior to inclusion in the bank.  ETS facilitators meet with content review committee (either in person, or in a moderated online review) to discuss each item.  Committee members consider the following questions as they review assessment materials:

- Is the content of the item accurate?

- Is the item correctly aligned to the standard?

- Is the item an appropriate measure of student ability?

Based on these questions, the committee may decide to accept, revise, or reject an item, passage, or task from the bank.  All items must complete this committee review prior to selection for use.

Bias/Sensitivity review committees are convened to ensure that the content of assessment materials are free of any information or subject matter that may favor one group of students over another (criteria for group differences include gender, race/ethnicity, urban/rural, and socioeconomic status), or that may be disturbing or provoke an emotional response that could affect student performance.  In committee recruitment, ETS recommends seeking teacher representatives reflecting the broad diversity of the state’s population to ensure that many perspectives are represented in committee deliberations.  ETS will provide facilitators with special training in facilitating bias and sensitivity reviews.  Bias/Sensitivity committees are asked to consider the following questions as they review assessment materials:

- Does the item, passage, or task contain information that may favor one group over another?

- Does the item, passage, or task contain information that may be disturbing, controversial, or provoke an emotional response among some test takers?

If the answer to either question is yes, the committee will be asked to consider whether the item, passage, or task is an appropriate measure of student ability for the given standard.  Based on discussion around this last question, the committee may recommend edits to the item, or may recommend it be rejected.

Finally, the bias/sensitivity committee will evaluate the set of items as a whole to determine whether the items, passages, and tasks are representative of the gender, racial/ethnic, socioeconomic, and urban/rural makeup of the state.

Following the meetings. At the conclusion of each meeting, ETS and CDE representatives will discuss issues or discrepancies in notes or committee recommendations. For performance tasks, see the review criteria recording for each stage of review described above (Accept/Decline followed by revise to Accept for Outline and Alpha Build reviews; Keep/Drop for Certification review stage).ETS will provide summary results from the review meetings, including the total number of items accepted as is, the number of items with revision, and the number of items rejected.

- Step 8: Alternate Test Formats

ETS recognizes that some students will require alternate test formats to access test content, even with the focus on universal design and accessible testing platforms. All alternate testing formats will be developed by a specialized unit within ETS’s Assessment Development division, called the Alternate Test Formats (ATF) group. The ATF group is devoted to the development of alternate test forms. ETS assessment specialists work closely with the ATF group throughout the entire process to establish content validity in the adaptations. The Alternate Test Format group collaborates with approved braille vendors to produce embossed Braille materials. ETS has experience working with several braille vendors, including but not limited to National Braille Press, Associated Services for the Blind, Region IV, Clovernook, and GH Braille. In addition the ATF group works with assessment specialists to review APIP tagging of items. APIP tagging standardizes the process for embedding accessibility features for test accommodations, including Braille, audio forms, and language accommodations.

### 6.2.A. Pilot Testing

As part of the annual development plans described in Task 6.1 above for CA NGSS science, CA NGSS alternate science, and primary language, ETS will develop piloting plans with the CDE that best suit the advancement of the CAASPP System. In this process, ETS researchers will share measurement advances with the CDE. A pilot testing plan will be provided for each assessment developed.

In general for planning purposes, ETS assumes that a pilot test plan will describe the following:

- Purpose of the pilot and base criteria for evaluating pilot results

- Process by which relevant test administrator observations and student comments can be collected from post-test administration questionnaires

- Preparation, review, and production process for all materials for pilot testing, whether the materials are computer-based or paper

- Sampling plan and proposed sample size

- Pilot test administration directions

- Proposed schedule of tasks, deliverables, and pilot test activities

- Planned Analysis and pilot test report

- Communication and training plan to LEAs

ETS will collaborate with the CDE to finalize each pilot test plan and to schedule the pilot administrations in order to minimize disruption to instructional activities and to avoid conflicts with accountability assessment administrations.

### 6.2.B. Field Testing

ETS understands that the CDE expects the administration of a stand-alone field test for each of the following: CA NGSS science, CA NGSS alternate science, and primary language. ETS also understand the expectation of every eligible student to take part in these field tests, which is similar to the successful model that the CDE utilized in 2014 for the Smarter Balanced field test.

As part of the annual development plans described in Task 6.1 above for CA NGSS science, CA NGSS alternate science, and primary language, ETS will develop field testing plans with the CDE that best suit the advancement of the CAASPP System. In this process, ETS researchers will share measurement advances with the CDE. A field test plan will be provided for each assessment developed.

In general for planning purposes, ETS assumes that a field test plan will describe the following:

- Purpose of the field test and base criteria for evaluating field test results

- Process by which relevant test administrator observations and student comments can be collected from post-test administration questionnaires

- Preparation, review, and production process for all materials for field testing, whether the materials are computer-based or paper

- Sampling plan and proposed sample size

- Field test administration directions

- Proposed schedule of tasks, deliverables, and field test activities

- Scoring, including rangefinding, activities

- Planned Analysis and field test report

- Communication and training plan to LEAs

ETS will collaborate with the CDE to finalize each field test plan and to schedule the field test administrations in order to minimize disruption to instructional activities and to avoid conflicts with accountability assessment administrations.

- Smarter Balanced

AIR’s TDS supports embedded field-testing of newly developed Smarter Balanced items. ETS has assumed that all items will be provided by Smarter Balanced. ETS anticipates including five to eight additional items in the computer-based tests only. ETS has not included costs for the development, scoring, or analyses of these field-test items. UCLA will develop, score, and analyze the Smarter Balanced field test items as part of the UCLA contract CN140236.

### 6.2.C. Forms Construction

ETS will employ the IBIS platform for test construction activities. ETS will work hand-in-hand with the CDE during the test construction process. Additional details of the forms constructions requirements will be included in the annual development plans. ETS will acquire the CDE’s approval before the test specifications and blueprints are finalized and before any item pool or form moves forward in the process.

## 6.3. Standard Setting (excluding Smarter Balanced assessments)

ETS will meet the needs of the CDE by providing a sound and defensible standard setting process for the alternate assessments in ELA and mathematics in grades three through eight and grade eleven, and for the primary language assessments in grades determined by the SBE (assumed to be for grades three through eleven). ETS will collaborate with the CDE, and as appropriate with the TAG, to provide the necessary plans and materials for approval. ETS understands the needs of the CDE regarding ALDs and standard setting, and will deliver reports in a timely manner to gain input from the CDE and the California public prior to SBE approval.

#### Development of Achievement-Level Descriptors

ETS will propose and implement a process to develop the ALDs for each assessment on a timeline that will allow review and revision by the CDE and SBE staff as needed, and will produce final approved ALDs for use in final form development and for use at the standard setting workshops.

For both the CAA and primary language assessments, ETS will facilitate ALD workshops, panel meetings of California educators, parents/guardians, and community representatives prior to the standard setting workshops. The panels will identify and discuss the knowledge and skills required of students in each grade and subject area for each level. The majority of participants will be teachers currently teaching the population of students taking the assessment, currently licensed in the subject and grades, and with five or more years of teaching experience. Teachers will have practice working with the California standards. Prior to the ALD workshop, participants will be provided with a pre-workshop assignment on the California standards, which will prepare them for the activities of the workshop. The ALD workshops will occur as soon as the blueprints are approved. Final blueprints and standards are essential elements of the ALD process.

The workshop for the primary language assessments will be a face-to-face meeting at a location approved by the CDE. However, because ETS assumes the NCSC ALDs to be a starting point for the CAA, ETS proposes completing this ALD work through a series of Webinars. Participants in the alternate ALD Webinars will receive overall training first; grade-specific Webinars will focus on the alignment between the new alternate assessments and the existing NCSC ALDs. Each panelist will participate in one orientation Webinar, three two-hour grade- and content-specific Webinars, and one cross-grade content-specific Webinar. ETS staff with content knowledge and distance-based facilitation experience will conduct all training and facilitation. Prior to the start of the ALD workshops, ETS will conduct a walkthrough with the CDE of the ALD plans for both the primary language and CAA in Sacramento, California.

ETS understands the challenges associated with recruiting from this specialized pool of educators and will include utilizing contact lists of known California educators from this population to establish necessary representation. ETS proposes, for costing purposes, a four-panel workshop for the primary language assessments, which will include two or three grades in each grade-based panel, including four representatives at each grade, and parent/guardian and community representatives. ETS anticipates a three-day workshop. The resulting ALD documents will be edited and a draft provided to the CDE for review prior to preparing a final document for SBE review. ETS will recruit a similar configuration of panelists for the Web-based CAA ALD meetings; however, ETS anticipates that teachers on the CAA panels will have experience teaching both ELA and mathematics, which allows for more flexibility in recruiting and assignment. Representatives will participate in the grade-band and content area for which they have experience. Each panel will work in a small group to review grade- and content-specific NCSC ALDs, alternate assessment blueprints, and additional materials such as exemplar items. All available panelists will join the last Webinar for each content area to finalize the CAA ALDs. ETS will provide this final document to the CDE for review and approval prior to presentation to the SBE for approval. Sample panel configurations for ALD workshops and Webinars are included as Table 4 and Table 5 below.

Table 4.  Sample Panel Configuration for Primary Language ALD Workshops

| Grades | Number of Panelists |
| --- | --- |
| 3-4 | 10 |
| 5-6 | 10 |
| 7-8, 11 | 14 |
| Total | 34 |

Table 5.  Sample Panel Configuration for CAA ALD Webinars

| Grades | Number of Panelists (ELA) | Number of Panelists (math) |
| --- | --- | --- |
| 3-4 | 10 | 10 |
| 5-6 | 10 | 10 |
| 7-8, 11 | 14 | 14 |
| Total | 34 | 34 |

#### Standard Setting Methods

ETS proposes to use the bookmark method (Karantonis & Sireci, 2006; Lewis, Mitzel, & Green, 1996; Zieky, Perie, & Livingston, 2008; Tannenbaum & Cho, 2014) for the primary language assessments. ETS used this method to set standards for the STAR CMA and STS assessments, and it is appropriate given the test design and psychometric calibration and scaling method.

For the CAA, ETS believes that a holistic approach, such as the Performance Profile Method, is most appropriate to these performance-based assessment types, in which the rubric score for each task includes descriptive, measurement criteria, and the administration of the assessment occurs one-on-one. ETS’s plan for the CAA includes external data collected in the early stages of assessment development. Teachers will consider the ALDs adapted from the NCSC ALDs and aligned to the NCSC Core Content Connectors and rate their own students based on in-class observation and experience. A contrasting groups analysis of the initial teacher-based ratings of students and student scores will inform the standard setting panelists’ judgments as part of feedback included in the standard setting workshop. If the CDE determines that an adaptive test design is feasible and desired, ETS will propose an additional standard setting plan that takes this into account. The proposed costs represent standard setting on the linear form of the alternate assessment in year one.

#### Panel Composition

The standard setting workshop participants will include state-nominated educators as well as parent/guardian and community representatives. The composition of the panels will be primarily teachers with at least five years of experience working with students aligned with the assessments, and who are familiar with the state-approved content standards appropriate to the assessment. The goal in recruiting is to select a group of educators, representative of the demographics in California, within each subject area and grade level. ETS will work with the CDE to select and finalize each standard setting panel. ETS anticipates a three-day face-to-face workshop; and the results from the workshop will include documentation of the panel composition. Sample panel configurations for standard setting workshops are included as Table 6 and Table 7 below.

Table 6.  Sample Panel Configuration for Primary Language Standard Setting Workshops

| Grades | Number of Panelists |
| --- | --- |
| 3-4 | 14 |
| 5-6 | 14 |
| 7-8, 11 | 14 |
| Total | 42 |

Table 7.  Sample Panel Configuration for CAA Standard Setting Workshops

| Grades | Number of Panelists (ELA) | Number of Panelists (math) |
| --- | --- | --- |
| 3-4 | 10 | 10 |
| 5-6 | 10 | 10 |
| 7-8, 11 | 10 | 10 |
| Total | 30 | 30 |

#### Bookmark Method

ETS welcomes the opportunity to discuss with the CDE and the TAG the types of standard setting methods most appropriate for each assessment type. Because of the appropriateness of the Bookmark method, and its use in the standard setting procedures for the California STS in recent years, (e.g., ETS 2009; ETS 2010; ETS 2011), ETS proposes the Bookmark method for standard setting of the new CAASPP primary language assessment.

#### Standard Setting Process

Prior to the panel meeting, panelists will receive a pre-workshop assignment to familiarize them with the CCC Standards and the ALDs for the subject and grade for which they have been recruited. Once assembled at the workshop, panelists undergo a general session overview and training.

After the panelists indicate that they understand the process, they make their first round of independent standard setting judgments. Panelists will complete the bookmark task three times over three rounds. Between rounds, discussions and feedback take place both at the table-level and the room-level, allowing panelists ample time and information for reflection. Panelists also receive their individual judgments. Between the second and third rounds the panelists will also discuss impact data — the percentage of students, based on the current administration of this assessment, who would be classified at each performance level, if the panel’s cut-score recommendations were to be accepted at that point. Panelists may, but are not required, to make changes to their individual judgments at each round.

The bookmark study can occur after the tests have been administered and test scores are available, Item Response Theory (IRT) analyses are completed, and materials have been prepared for the panel meetings. ETS anticipates each panel meeting requiring three days, and ETS will run four panels concurrently for each subject area.

ETS will provide the CDE with the formal standard setting plan for review six weeks prior to the workshop, and will include a draft of the materials to be used in standard setting, an annotated agenda of the three-day workshop, and the review of the plan and materials in the overall project schedule, allowing adequate time for review, discussion, and revisions.

#### Assessment Score Data in Standard Setting

ETS recognizes the need for careful attention to training and evaluation of panelists’ understanding of both appropriate use and limitations of data in the judgment process. ETS proposes to discuss with the CDE and the TAG regarding inclusion of external data as part of the feedback to the panel.

#### Holistic Standard Setting Methods for Alternate Assessment

To develop a standard setting process for the CAA, ETS proposes to discuss with the CDE and the TAG the nature of information available from these tasks and the use of the scores and classification levels over the course of the school year. For this process, ETS will recruit a diverse and representative group of educators, with appropriate experience and expertise in the grade-level and content area of the students taking these assessments. For the CAA, the panel would become familiar with the assessment tasks, scoring rubrics, and the meaning of the performance levels, and discuss the student performance expectations at each of the levels. At the end of the CAA standard setting workshop, ETS will present the resulting recommended cut scores to the CDE.

#### Technical Report

ETS will provide the CDE and the TAGs with a complete report of the standard setting process, panelists’ recommendations, evaluations, and other relevant data. The report will meet the NCLB peer review requirements (USDOE, 2007). In addition, the CDE may require an executive summary report, in order to meet time-sensitive deadlines. ETS will provide a brief report, oriented toward audiences such as the SBE. Because there are multiple score users, with differing backgrounds and needs, clear communication of score meaning must be deliberate. ETS will be happy to collaborate with the CDE to create useful score interpretive materials for multiple stakeholders.

#### Schedule for Standard Setting

ETS understands the need to hold the standard setting workshops for the CAA as soon as data are available after the operational launch in spring 2015–16; and ETS will similarly hold standard setting workshops for the primary language assessment soon after the field test in spring 2017–18. For both types of standard setting workshops proposed, there are important milestones. ETS acknowledges the need for clear communication and planning in order to be successful in these tasks.

#### Logistics

ETS will provide the CDE with recommendations for site locations which will accommodate each workshop. Once panel participants and locations have been approved, accommodations will include lodging and meals for panelists and meeting space. ETS will arrange for substitute teacher reimbursement and will cover the costs of lodging and meetings, in accordance with current CDE guidelines.

- 6.4. Test Administration System Familiarization

ETS offers several opportunities for students and Test Administrators to become familiar with the test delivery system (including TOMS and TDS). ETS also provides multiple training opportunities to support the LEA CAASPP Coordinator, the LEA Technology Coordinator, and other designated staff as they prepare the infrastructure used for the test administration process.

#### CAASPP Test Administration Portal

ETS will provide access to the test administration components with the broadest range of users in mind. The site itself provides a one-stop shop for access to all things CAASPP including access to the TDS, training videos, test administration manuals, and live Webcasts, among other things. A user can quickly go to a certain section or test administration tool and ETS designed the links to be interlaced yet intuitive.

#### Practice and Training Tests

The ETS Team will provide practice and training tests for the operational summative assessments administered in this contract. Practice tests will be available for the Smarter Balanced summative assessments and the Alternate Assessments in ELA and mathematics.

For subsequent school years prior to their release on September 1 and November 1, respectively, the ETS Team will ensure that the practice and training tests are updated to reflect current tools and item types. For the Smarter Balanced assessments, ETS will work with Smarter Balanced to obtain access to the latest practice and training test materials. For the Alternate Assessments, ETS will ensure that assessment development and AIR staff have provided the latest updates to the practice and training tests before they are made available.

The practice and training tests will be accessed via a Web browser using a guest login or through the secure browser. ETS will provide training materials and resources, such as classroom activities and scoring rubrics, on the CAASPP Portal. The practice and training tests will be available for each grade and content area being tested and will include functionality for all approved universal tools, designated supports, and accommodations.

#### Training for LEA CAASPP Coordinators and LEA Technology Coordinators

ETS’s training plan begins in September for each administration when ETS proposes to conduct a training session to introduce the test administration setup process. At this session, ETS will review the required testing windows for each type of assessment and provide guidelines and considerations for scheduling the testing. ETS also will provide detailed information on system requirements, including minimum requirements for hardware, software, and bandwidth.

ETS will conduct ten (10) regularly scheduled Webcasts and in-person workshops and release training videos and manuals throughout the school year and leading up to the start of the summative test administration window.

## 6.5. Released Test Questions (excluding Smarter Balanced assessments)

ETS will work with the CDE to release and make available to stakeholders a subset of the CDE-owned operational test items each year for the CAA, CA NGSS, CA NGSS alternate, and primary language components of the CAASPP System. Because the assessments for CA NGSS, CA NGSS alternate, and primary language will not be operational during this contract period, ETS includes releasing items for the CAA ELA and mathematics only. Smarter Balanced released items are available through the Smarter Balanced Web site. ETS will include a link to the Smarter Balanced Web Site on the RTQ site to make it easy for users to locate.

#### Procedure

For each assessment and grade level, ETS assessment specialists will work with CDE content experts to select and release an annual RTQ sample equaling 10 percent of the items appearing on the prior year’s test form.

- ETS assessment specialists will select 10 percent of the core items from each administration for each grade and subject area of the CDE-owned alternate ELA and mathematics items for release annually.

- ETS assessment specialists will select and review each set of items for release to confirm that each set of RTQs is representative of the broad content, difficulty, and overall blueprint distribution of standards measured by items on the operational tests.

- After the initial selection of the RTQs, ETS assessment specialists will establish that items undergo careful review following a thorough content and editorial review process.

- After the content and editorial review process, ETS will submit the selected RTQs to the CDE for review and approval. Ultimately, the CDE will have the final authority to accept or reject any items selected for release. Historically this has been a collaborative process, with ETS assessment specialists working in cooperation with CDE counterparts to review, revise, and finalize RTQ selections.

- Once the CDE confirms the RTQ selections, ETS assessment specialists will prepare the RTQs and other necessary materials for review and approval by a California content review panel. The CDE will review the input from the content review panel and make the final determination of acceptance.

- Upon finalization of the RTQs, ETS will update the item status in the item bank to indicate the item as released. This will make the item unavailable for selection in the future.

- After the CDE makes final determination of acceptance, ETS will export RTQs from the item bank and convert them to an agreed-upon HTML format for posting on the CDE Web site.

#### Selection Criteria for RTQs

To confirm strong representation of the breadth and depth of the skills and concepts addressed by the items on each assessment, ETS assessment specialists will use the following criteria to select the RTQs:

- variety of item types, which may include selected-response items, constructed-response items, technology-enhanced items, and performance tasks

- statistical reliability of the item based on most recent administration

- range of item difficulty and complexity

- items that exemplify the level of knowledge and skills students are expected to demonstrate to meet expectations at each performance level

- adequate representation of standard and blueprint distribution

- representation of the various components of the standards

- representation of a variety of ways each standard can be assessed

In the event there is a problem securing permission for a passage or stimulus during the RTQ selection process, ETS will work with the CDE to find a solution which may include providing only the citations, rather than the complete text, for copyrighted material along with the associated items or replacing those RTQs related to materials for which permissions are not granted.

#### Communication Plan for RTQs

To increase and support parent, student, and teacher understanding of the CAASPP System, ETS will collaborate with the CDE to select a subset set of the RTQs, exemplars, that represent the concepts and skills students performing at the different proficiency levels are expected to demonstrate at each grade level assessed.

## 6.6. Analysis of Test Results

Following each field test form, ETS will perform classical item, IRT, and test analyses. Classical item analyses involve computing a set of statistics for every item in each form of the test. Each statistic provides key information about the quality of each item from an empirical perspective. This is also a quality control step to verify answer keys. ETS uses this information for item reviews, test construction, test revisions, technical reports, and other psychometric analyses and documentation.

After receiving all of the student response data, implementing scoring rules, checking the data files and applying agreed-upon valid case criteria rules to the data, the next step will include a classical item analysis. This analysis evaluates item difficulty, item discrimination, and student raw score performance of selected response (SR) items and hand-scored constructed-response (CR) items. These analyses help identify any items that might not have performed as expected.

ETS will conduct and provide the following:

- Item difficulty (p-values)

- Item-total correlation (SR and CR items)

- Proportion of students choosing each response option (SR items)

- Percentage of students omitting an item (SR and CR items)

- Score point distribution (CR items)

In addition to the classical analyses described previously, ETS will carefully review each item for differential item functioning. In addition to providing classical item statistics for each field test, ETS will provide IRT parameter estimates for all items. The specific IRT model selected will be based on collaboration between the CDE and ETS. In addition, ETS will work with the CDE in investigating the feasibility of creating a vertical scale for both the primary language assessments and the CAA.

In addition to the item statistics ETS will estimate the reliability of each of the field test versions and use these estimates to advise the CDE concerning the estimated numbers of items that need to be administered to reach various levels of reliability. ETS will also examine additional data collected relevant to computer-based testing with innovative item types. Since California has expressed interest in moving towards an adaptive test, ETS will also evaluate the characteristics of the item pool to determine whether it was large enough in terms of range of difficulties, discriminations, and content covered without introducing exposure issues. In addition ETS shall evaluate other characteristics of items and item performance that need to be analyzed e.g., how long student spend on the items, the time it takes for the items to render, the time it take the system to present a new item, item utilization rates, accuracy of CAT engine in building aligned assessments for every student.

Following each field test, ETS will deliver a report within eight weeks of the completion of the field testing.

As part of the test development process, ETS proposes to conduct alignment studies that will inform the task selection for final forms of the newly developed assessments. ETS’s plan is a modification of the alignment procedures suggested by Webb, and include in the process measures of the alignment of the overall test to the standards, by considering the test specifications and blueprints, as well as task or question-level alignment judgments. ETS suggests the alignment process be completed as part of the field test analyses.

## 6.7. Item Banks

### 6.7.A. California Item Bank

ETS currently provides and maintains the electronic item bank for several of the California paper-pencil assessments, including the California High School Exit Examination (CAHSEE), CSTs, CMA, California Alternate Performance Assessment (CAPA), STS, and the California English Language Development Test (CELDT). While the California item bank is not used to produce the CST, CMA, CAPA, and STS forms, the CAHSEE or CELDT program may be using the California item bank for its forms construction process.

The consolidated item bank will house all CST, CMA, CAPA, STS, CAHSEE, and CELDT items and associated statistics by assessment. While ETS will retain ownership of its proprietary software, the CDE will own and copyright both the item bank and the customized version of the item bank. The enhanced item banking software will support the full functionality that is described below.

ETS will provide updated versions of the item bank to the CDE on an ongoing basis. ETS will work with the CDE to determine the optimum process if a change in databases is desired.

### 6.7.B. ETS Item Banking Information System (IBIS)

The items that will be developed for the new assessments will include a variety of item types such as technology-enhanced items, graphing, and technology-enhanced simulations. The structure of the California Item Bank cannot handle these new item types. In order to provide the CDE with a data warehouse for the new CAASPP assessments, ETS will use its proprietary item banking system, IBIS, during the development and reviews of the new CAASPP assessments. ETS does not include activities to provide customization of IBIS.

Using IBIS, CDE staff and approved California item reviewers shall have direct access to the item bank through a secure Web-based interface. User authentication, controlled by ETS-managed credentials, secures access through the interface. To establish the complete security of all data moving across the Internet, ETS implements a 128-bit secure socket layer (SSL) encryption.

Controlled Access. ETS will grant the CDE staff and California item reviewers with access to IBIS consistent with their roles in the item development process. These reviewers will be able to comment on items during steps in the workflow process customized for CAASPP. ETS will establish access policies with California and manage the granting of access for appropriate staff and educators.

IBIS will hold searchable, sortable, and printable data (e.g. item cards) and properties, including, but not limited to:

- unique identification number for item components (question, stimulus, graphics, animations, sound files, etc.)

- UIN links between all item components

- titles for stimuli (e.g. passage, scenario, scene)

- all and any alignment attributes (e.g. test family, item type, subject, grade, strand, substrand, standard, benchmark, cognitive level)

- properties (keys, distractor rationales, item type, stimulus type [e.g. passage genre, scenario vs. simulation]), stimulus graphic indicator (yes/no), passage word count, Lexile, rubrics

- source documentation, copyright permissions information, and related documentation (e.g. contract) for science scenarios, reading passages, graphics and items, if applicable

- item images (item as it appeared during administration) including functional animations or simulations

- blind/visual impairment review notes

- item development and administration status

- administration history for the life of the item, scenario or passage for non-Smarter Balanced items

- performance data (p-value, pbis correlation, IRT parameters, tertiles, DIF, etc.)

System flexibility and interoperability. CDE will have the ability to customize features of IBIS for CAASPP development. This activity will involve meetings to determine the most desirable means for configuring the item bank and user interface. The ETS will use the QTI standard as the basis for building the XML formats of items with capability for APIP standard tagging. QTI enables routine exports to most third-party online platforms including the AIR online platform. APIP tagging standardizes the process for embedding accessibility features for test accommodations, including Braille, audio forms, and language accommodations.

Smarter Balanced Assessments. ETS plans to import the metadata and scoring information for Smarter Balanced items into IBIS to accomplish the following activities: (1) access to CR items in the scoring system; (2) scoring of the paper forms; and (3) psychometric analyses. ETS will receive an annual feed of items and metadata from Smarter Balanced in interoperable QTI format.

Item Bank Export. IBIS uses the QTI standard as the basis for building the XML formats for items, data, and metadata. This feature will confirm a smooth transition at the end of the contract period. ETS employs industry standard formats and routinely has handed off data feeds of items, test packets, data, and metadata to numerous partner organizations. As a comprehensive item database, IBIS includes all reading passages, artwork, stems, distractors, form identifiers, item keys, rationales and scoring rubrics. Copyright permissions records are also housed in IBIS, and using the dynamic reporting functions in IBIS, a report containing copyright permissions, and expiration dates can be generated for the CDE.

## 6.8. Activities in Support of Future Assessment Development

ETS understands that California law includes provisions for expanding the CAASPP System to include assessments in areas such as history/social sciences, technology, and the arts, as well as new end-of-course tests in science, ELA, and mathematics. ETS further understands that these assessments would be based on State Superintendent of Public Instruction (SSPI) recommendations made no later than March 1, 2016, and will require SBE approval, legislative action, and funding. Therefore, no specific plans or budget for work on any additional assessments has been included in this scope of work.

References

Hanson, B. A.,& Beguin, A. A. (2002). Obtaining a common scale for item response theory item parameters using separate versus concurrent estimation in the common-item equating design. Applied Psychological Measurement, 26 (1), 3 – 24.

Kolen, M. J., & Brennan, R.L. (2004). Test Equating: Methods and Practices. (2nd ed.). New York, NY: Springer-Verlag.

Stocking, M. L., & Lord, F. M. (1983). Developing a common metric in item response theory. Applied Psychological Measurement, 7, 201 – 210.

Yen, W.M. (1986). The choice of scale for educational measurement: An IRT perspective. Journal of Educational Measurement, 23(4), 299 – 325.

American Educational Research Association, American Psychological Association, & National Council on Measurement in Education. (1999). Standards for educational and psychological testing. Washington, DC: American Educational Research Association.

American Institutes for Research, (2008). Ohio Achievement Tests Summer 2006 Standard Setting: Setting Standards in Grades 5 and 8 Science, Grades 5 and 8 Social Studies, and Grade 7 Writing Technical Report (Technical Report No. 2008-07). Retrieved from http://www.ohiodocs.org/technical_reports.htm

Baron, P. A., & Papageorgiou, S. (2014). Mapping the TOEFL® Primary™ Test Onto the Common European Framework of Reference. RM-14-05. Educational Testing Service, Princeton NJ.

Buckendahl, C. W., Smith, R. W., Impara, J. C. and Plake, B. S. (2002), A Comparison of Angoff and Bookmark Standard Setting Methods. Journal of Educational Measurement, 39: 253–263. doi: 10.1111/j.1745-3984.2002.tb01177.x

Bunch, M. B., Inman, E., & Miles, J. (2008). Ohio graduation tests standard setting report for Science, Social studies, and Writing (Technical Report No. 2008-14). Retrieved from http://www.ohiodocs.org/technical_reports.htm

Educational Testing Service (2002). ETS standards for quality and fairness. Princeton, NJ.

Educational Testing Service (2010). ETS using unique approach to setting cut-scores on teacher licensure assessments. K-12 Education News. Retrieved from http://www.ets.org/k12/news/unique_approach_set_cutscores_teacher_licensure

Educational Testing Service. (2009). Technical report on the standard setting workshop for the California Standards-based Tests in Spanish: RLA grades two through four, mathematics grades two through four, March 20, 2009 (California Department of Education Contract Number 5417). Princeton, NJ: Educational Testing Service.

Educational Testing Service. (2010). Technical report on the standard setting workshop for the California Standards-based Tests in Spanish: RLA grades five through seven, mathematics grades five through seven, January 15, 2010 (California Department of Education Contract Number 5417).Princeton, NJ: Educational Testing Service.

Egan, K. L. (2001). Validity and defensibility of cutscores established by the Bookmark standard setting method. Paper presented at the 2001 Council of Chief State School Officers Conference on Large-Scale Assessment, Houston.

Kane, M. T. (2006). Validation. In R. L. Brennan (Ed.), Educational measurement (4 ed., pp. 17-64). Westport, CT: American Council on Education/Praeger.

Kannan, P. (2014). Content and Performance Standard Articulation Practices Across the States: Report Summarizing the Results From a Survey of the State Departments of Education (ETS Research Memorandum RM-14-09). Princeton, NJ: Educational Testing Service.

Karantonis, A., & Sireci, S.G. (2006). The bookmark standard-setting method: A literature review. Educational Measurement: Issues and Practice, 25(1), 4 – 12.

Katz, I. R., Tannenbaum, R. J., & Kannan, P. (2009). Virtual Standard-setting. Clear exam review, 20(2), 19 – 27.

Katz, I.R, & Tannenbaum, R.J. (2014). Comparision of web-based and face-to-face standard setting using the Angoff method. Journal of Applied Testing Technology, 15, 1 – 17.

Kingston, N.M., Kahl,S.R., Sweeney, K, & Bay, L. (2001). Setting performance standards using the body of work method. In G.J.Cizek (Ed.), Setting performance standards: Concepts, methods, and perspectives (pp. 219-248). Mahwah, NJ: Lawrence Erlbaum.

Laitusis, C. C., Buzick, H. M., Cook, L. L., & Stone, E. (2011). Adaptive Testing Options for Accountability Assessments. In M. Russell and Kavanaugh, (Eds.) Assessing Students in the Margins: Challenges, Strategies, and Techniques. Retrieved from: http://www.infoagepub.com/products/Assessing-Students-in-the-Margins

Lewis, D. M., Mitzel, H. C., & Green, D. (1996). Standard-setting: A bookmark approach. In D. R. Green (Chair), IRT-based standard-setting procedures utilizing behavioral anchoring. Symposium conducted at the Council of Chief State School Officers National Conference on Large-Scale Assessment, Phoenix, AZ.

O’Neill, T. R., Tannenbaum, R. J., & Tiffen, J. T. (2005). Recommending a minimum English proficiency standard for entry-level nursing. Journal of Nursing Measurement, 13, 129-146.

Papageorgiou, S, & Tannenbaum, R.J. (in press). Situating standard setting within argument-based validity. Language Assessment Quarterly.

Phillips, G.W. (2012). The benchmark method of standard setting. on complex performance assessments. In G.J. Cizek (Ed.), Setting performance standards: Foundations, methods, and innovations, (pp. 323–346). Mahwah, NJ: Lawrence Erlbaum Associates, Inc.

Plake, B. S., & Hamilton, R.K. (2001). The analytic judgment method for setting standards on complex performance assessments. In G.J. Cizek (Ed.), Setting performance standards: Concepts, methods, and perspectives, (pp. 283–312). Mahwah, NJ: Lawrence Erlbaum Associates, Inc.

Plake, B., Hamilton, R., & Jaeger, R.M. (1997). A new standard setting method for performance assessments: The dominant profile judgment method and some field-test results. Educational and Psychological Measurement, 57, 400 – 411.

Stone, E., Cook, L.L., & Laitusis, C.C. (2013). Evaluation of a Condition-Adaptive Test of Reading Comprehension for Students with Reading-Based Learning Disabilities. (ETS Research Report RR-13-20). Princeton, NJ: Educational Testing Service.

Stone, E., & Davey, T. (2011). Computer-adaptive testing for students with disabilities: A review of the literature. ETS Research Report 11 – 32.

Tannenbaum, R.J. (2012). A Multistate Approach to Setting Standards: An Application to Teacher Licensure Tests. CLEAR Exam Review, 23, 18 – 24.

Tannenbaum, R.J., & Katz, I.R. (2013). Standard setting. In K.F. Geisinger (Ed.), APA handbook of testing and assessment in psychology: Vol 3. Testing and assessment in school psychology and education (pp. 455-477). Washington, DC: American Psychological Association

Tannenbaum, R.J., & Cho, Y. (2014). Critical factors to consider in evaluating standard-setting studies to map language test scores to frameworks of language proficiency. Language Assessment Quarterly, 11, 233 – 249.

US Department of Education. (2007). Standards and Assessments Peer Review Guidance: Information and Examples for Meeting Requirements of the No Child Left Behind Act of 2001. Retrieved from: https://w ww2.ed.gov/policy/elsec/guid/saaprguidance.pdf.

Zieky, M. J., Perie, M., Livingston, S. A. (2008). Cutscores: A manual for setting standards of performance on educational and occupational tests. Princeton, NJ: Educational Testing Service.

Baron, P. A., Tannenbaum, R.J, and Bailey, S. (2013). Evaluation of the Alignment between CBAL Periodic Accountability Assessments and the Common Core State Standards: A Confirmatory Study. Presented at the annual meeting of American Educational Research Association, April, Philadelphia, PA.

Bola, D., Impala, J.C., & Buckendahl, C.W. (2003). Aligning tests with states’ content standards: Methods and Issues. Educational Measurement: Issues and Practice, 22, 21 – 29.

Eckhout, T.J., Place, B.S., Smith, D.L., & Larsen, A. (2007). Aligning a state’s alternative standards to regular core content standards in reading and mathematics: A case study. Applied Measurement in Education, 20, 79 – 100.

Herman, J.L., Webb, N.M., & Zuniga, S.A. (2007). Measurement issues in the alignment of standards and assessments: A case study. Applied Measurement in Education, 20, 101 – 126.

Porter, A.C. (2002). Measuring the content of instruction: Uses in research and practice. Educational Researcher, 31, 3 – 14.

Porter, A., McMaken, J., Hwang, J, & Yang, R. (2011). Common core standards: The new U.S. intended curriculum. Educational Researcher, 40, 103 – 116.

Tannenbaum, R.J, Baron, P. A. and Kannan, P. (2012). Evaluation of the Alignment between CBAL Periodic Accountability Assessments and the Common Core State Standards. (Final Report). Princeton, NJ: Educational Testing Service.

Webb, N.L. (1999). Alignment of science and mathematics standards and assessments in four states. Council of Chief State School Officers and National Institute for Science Education. Madison, WI: Wisconsin Center for Education Research, University of Wisconsin.

Webb, N.L. (2007). Issues related to judging the alignment of curriculum standards and assessments. . Applied Measurement in Education, 20, 7 – 25.

Webb, N.M., Herman, J.L., & Webb, N.L. (2007). Alignment of mathematics state-level standards and assessments: The role of reviewer agreement. Educational Measurement: Issues and Practice, 26, 17 – 29.

# TASK 7: Test Administration

ETS offers the CDE a comprehensive computer-based CAASPP Assessment Delivery System that allows LEAs to manage and administer all CAASPP assessments. While fewer California assessments are paper-pencil, ETS will deliver an efficient and secure paper-pencil test for students for whom these assessments are most appropriate. The CAASPP Assessment Delivery System includes both the Test Operations Management System (TOMS) and AIR’s test delivery system. These key components integrate together to produce, deliver, and administer both computer-based and paper-pencil assessments. Table 8 provides an overview of the test administration distribution plans.

Table 8.  Distribution Plans for the CAASPP Assessments

| Assessment | Online | Paper | Paper Accommodations |
| --- | --- | --- | --- |
| Smarter Balanced |  |  | Braille, Large Print, Spanish-Mathematics |
| CST, CMA, CAPA Science* |  |  (2015 – 2016 and 2016 – 2017 Only) | Braille and Large Print for CST and CMA Science |
| STS RLA* |  |  (2015 – 2016 and 2016 – 2017 Only) | Braille and Large Print |
| California Alternate Assessments for ELA and Mathematics |  |  |  |
| CA NGSS Pilot and Field Test |  (2016–2017 and 2017–2018 only) |  |  |
| CA NGSS Alternate Pilot and Field Test |  (2016–2017 and 2017–2018 only) |  |  |
| Primary Language Pilot and Field Test |  (2016–2017 and 2017–2018 only) |  |  |

* CST: California Standardized Test; CMA: California Modified Assessment; CAPA: California Alternate Performance Assessment; STS RLA: Standards-based Test in Spanish for Reading/Language Arts

For planning purposes, ETS used the information from Table 9 provided by the CDE.

Table 9.  Estimated CAASPP Test Takers

| Current Assessments in State Law |  |  |  |  |
| --- | --- | --- | --- | --- |
| Assessment | Subject | Grade | School Year(s) | Estimated Test Takers |
| Smarter Balanced Summative | ELA and mathematics | 3–8, 11 | 2015–16 2016–17 2017–18 | 3,200,000 3,200,000 3,200,000 |
| CSTs and CMA | Science | 5, 8, 10 | 2015–16 2016–17 | 1,380,000 1,380,000 |
| CAPA | Science | 5, 8, 10 | 2015–16 2016–17 | 15,000 15,000 |
| CAPA | ELA and | mathematics | See Alternate Assessment below |  |
| STS | Reading/ language arts | 2–11 | 2015–16 2016–17 | 45,000 45,000 |
| Successor Assessments in State Law |  |  |  |  |
| Alternate Assessment | ELA and mathematics | 3–8, 11 | 2015–16 2016–17 2017–18 | 39,000 39,000 39,000 |
| California NGSS-aligned (including Alternate) ESEA-Required Science | Science | Three grades TBD2 | Develop: 2015–16 Pilot:2016–17 Field Test: 2017–18 | 1,395,000 |
| CCSS-aligned Primary Language | Reading/ language arts | 3–112 | Develop: 2015–16 Pilot:2016–17 Field Test: 2017–18 | 45,000 |

## 7.1. CAASPP Test Administration Requirements

ETS will create manuals, user guides, and other supporting materials so that the LEAs have the information they need to effectively and efficiently administer the CAASPP System.

### 7.1.A. Manuals

ETS will produce high-quality manuals that will give California the exact information needed in ways that are accurate and efficient. To increase the efficiency of communications between the LEAs and schools during the test administration, and to assure that tests are administered in a consistent manner, ETS will review with the CDE all CAASPP System documentation and update the materials based on the needs of the CDE and LEA CAASPP Coordinators, revised academic standards, and other requirements. In addition, ETS will analyze information collected as part of data-driven improvement activities. ETS will solicit feedback specifically from the LEA Advisory Group to confirm that manuals and other ancillary materials meet the needs of the field.

General Specifications for Developing Manuals. ETS will use the previous administration’s manuals as the starting point for the current administration. Prior to the development and production of a manual, ETS will provide the CDE with a list of recommended revisions including those from the data-driven improvement process. When appropriate, ETS will also make recommendations to re-conceptualize existing manuals for increased usability, create new or additional manuals, or even retire existing manuals.

ETS will schedule sufficient time for the thorough review and approval of the manuals prior to posting or publishing. In addition, ETS will implement a process by which an ETS editor will conduct inter-manual consistency checks so that there is consistent tone, language, and directions between the manuals. The production schedule for each manual will follow the CDE approval requirements.

Posting Manuals to http://www.caaspp.org/. ETS will print all manuals and convert them to PDF and/or HTML files. The PDFs will include the appropriate accessibility tagging that meets or exceeds the CDE Web requirements. ETS will post only non-secure materials or materials edited to remove secure sections.

Based on feedback from the LEA Advisory Group, ETS will propose recommendations to the CDE for ways to make information about the test administration process more accessible.

ETS will post all final approved manuals to http://www.caaspp.org/ by November 1st annually. Given this required posting deadline, ETS anticipates that there may be changes or updates to policy or administration procedures that may impact the manuals. During the initial planning phase of each manual, ETS will propose processes and contingencies. In the event that a policy or administrative change is required after ETS publishes a manual, ETS will work with the CDE to determine which contingencies ETS should consider and what impact the contingencies have to LEA activities and the overall program schedule, if any.

Printing Quality Control Procedures. ETS will provide printed copies of the Test Administration Manual and the Post-Test Guide. Upon approval of the final draft by the CDE, the manuals will go through printing quality control procedures, which require that a printing quality control specialist be on-site through all stages of production to confirm the quality of all products. The general process requires all print vendors perform a quality check on all materials produced at all stages of print manufacturing. These quality checks occur at the prepress, press, bindery, and packaging/shipping stages. ETS will use a required quality control checklist to verify the vendors’ adherence to quality procedures.

#### Test Administration Manual (TAM)

ETS will make sure that California-specific revisions still adhere to the Smarter Balanced test administration procedures and policies.

Separate TAMs will cover other CAASPP content areas and assessments, including science, alternate, and primary language assessments, as well as the existing paper-pencil assessments. These TAMs will be coordinated and consolidated whenever possible to confirm ease-of-use in the field. The manuals’ interior font size will be 11 points or larger, printed with black ink.

In addition to posting the final PDF to http://www.caaspp.org/ by November 1 of each year, ETS will produce and deliver each TAM a minimum of 30 days prior to an LEA’s testing window. For each TAM, ETS will provide one copy for the LEA CAASPP Coordinator and one copy for each CAASPP Test Site Coordinator. ETS will deliver all printed copies to the LEA CAASPP Coordinators, who will be responsible for distribution to their schools. Additional TAMS are available for order through CalTAC at no additional cost to the LEA or the CDE. ETS will confirm that the final PDF version of the appropriate TAM is available for training sessions.

#### LEA CAASPP Test Coordinator Manual (LEA TCM)

As a companion document to the TAMs, but with a focus on the tasks that are the responsibility of the LEA CAASPP Coordinators, ETS will develop an LEA Test Coordinator Manual (LEA TCM). If possible, a single manual will cover all summative CAASPP testing for a particular administration year. In the event that more than one manual is needed to properly cover the information, ETS will revise the schedule and plans to ensure that the manuals are properly reviewed and provided to the field in a timely manner.

Where necessary, text will reflect any applicable grade-level differences. Because paper-pencil testing should be minimal in California, ETS will focus the content of the administrator’s guide primarily on the computer-based testing while clearly identifying sections that are for the paper-pencil test administration. Also, ETS will not include proprietary information in the administrators’ guide. This way, electronic posting will not require a separate version.

ETS will propose and collaborate with the CDE to determine the content of the administrators’ guide, and ETS will provide the initial draft to the CDE in accordance with the program schedule for each administration year and with the goal of posting the final version by November 1 to caaspp.org. ETS will make the manual available for the pre-test training sessions in January and February of each administration year.

#### CAASPP Test Site Coordinator Manual (SCM)

Similar to the LEA TCM, ETS will develop a manual for coordinating testing at the school-site level: the CAASPP Test Site Coordinator Manual (SCM). This manual will focus on the tasks that are the responsibility of the CAASPP Test Site Coordinators. If possible, a single manual will cover all summative CAASPP testing for a particular administration year.

#### Test Administrator’s Manual (TAM)

To complete the set of role-specific CAASPP coordination and administration manuals, ETS will develop a Test Administrator’s Manual (TAM) for Test Administrators. If possible, a single manual will cover all summative CAASPP testing for a particular administration year. In compliance with CDE requirements, this manual will include:

- an overview of the CAASPP System, and the various test management, registration, and delivery systems

- LEA CAASPP Coordinator responsibilities

- LEA responsibility and activity checklist

- CAASPP Test Site Coordinator responsibility and activity checklist

- test administrator responsibility and activity checklist

- appropriate processes for handling accessibility and accommodations for both computer-based and paper-pencil tests

- appropriate measures for protecting test security and confidentiality at the LEA level

- estimated test duration charts for planning purposes, and suggestions for LEA-level test scheduling

- appropriate processes for including special populations of students in testing

- important dates leading up to, during, and after the testing window(s)

- how to handle student absences and other unique testing situations (e.g., testing of homebound students, students moving into and/or out of the LEA during the testing window, etc.)

- how to report irregularities/security breaches

- how to determine whether an appeal is necessary

- toll-free telephone number and e-mail for CalTAC Help Desk support

#### Technology Services Coordinator’s Manual (TSCM)

ETS will develop a manual for use by LEA- and site-level Technology Coordinators, a crucial role now that California administers a majority of tests online.

#### CAASPP Test Management System Manual (CTMSM)

ETS also produces documentation that shows procedures for using TOMS, the CAASPP Assessment Delivery System component that allows authorized users to configure testing for students, order materials, submit test setting files, and complete other tasks. ETS can develop and release this documentation in task-specific editions, or as a single manual covering all system functionalities.

#### CAASPP Post-Test Guides

ETS will develop a CAASPP Post-Test Guide each year that will provide a single reference document for all reporting-related information, for all users. The manual will provide an overview of the assessments, a description and guide to both online reporting tools and paper reports, and guidelines for interpreting reports. Also, ETS will include clear standards for interpreting the intended use of the test scores. ETS will develop these standards as part of the psychometric review of the test items and forms. ETS will clearly delimit the addressed population and describe the constructs that the assessments should measure. The goal of this manual will be to guide all CAASPP reporting stakeholders in understanding the scores provided, what they represent, and how they can use them to improve curricular programs in the schools.

ETS will post the Post-Test Guide to caaspp.org by November 1 annually. ETS will deliver one printed copy to each LEA CAASPP Coordinator at least one month prior to the beginning of student summative testing each year. Additional printed copies are available for order from CalTAC at no additional cost to the LEA or the CDE.

## 7.2. Paper-Pencil Administrations

There are existing CAASPP tests that are available only as paper-pencil assessments. In addition, not all students in California will be able to test on a computer. Therefore, ETS will offer an efficient and secure process for providing a paper-pencil assessment for students who require this mode of testing. ETS will manage and provide the paper-delivered tests from ETS’s Ewing, New Jersey, location, where ETS owns publishing, distribution, and scoring facilities. Currently, ETS is using these capabilities and facilities to deliver the printed materials for the 2015 CAASPP administration, and ETS will use these same capabilities and facilities in future CAASPP administrations.

ETS will produce:

- non-scannable test booklets with separate scannable answer documents for CST/CMA/CAPA for Science Assessments in grades five, eight, and ten, and STS for RLA in grades four through eleven

- scannable test booklets for the STS for RLA booklets for grades two and three

- non-scannable test booklets with a scannable response booklet for the paper-pencil versions of the Smarter Balanced Summative Assessments in grades three through eight and grade eleven

- secure directions for administration (that include assessment items) for alternate assessments in ELA and mathematics in grades three through eight and grade eleven

- non-scannable test booklets for the braille and large print versions of all CAASPP assessments

- non-scannable test booklets for the Spanish version of the Smarter Balanced mathematics assessments in grades three through eight and grade eleven

ETS will provide the CDE with final documents for review and approval following the certification process.

With California’s input, ETS will develop a detailed project plan to track the completion of the sequence of tasks and will incorporate the detailed project plan into the master project plan. ETS will put each document through the same rigorous process of review, proofreading, accuracy checking, CDE approval, document tracking and version control, and quality inspection that are used with all secure test materials.

#### 7.2.A.1. Paper Test Booklets and Answer Documents

ETS will develop and print secure non-scannable test booklets and scannable answer documents for the CAASPP paper-pencil tests. In producing these versions, ETS will establish that all content and formatting within the test booklets and answer documents maintains consistency with the CAASPP test materials in the 2015 administration. ETS will discuss any changes in format or content for the non-Smarter Balanced paper-pencil assessments with the CDE for the CDE’s approval prior to implementation. For the Smarter Balanced paper-pencil assessments, ETS assumes that Smarter Balanced will provide print-ready PDFs that may be used for the CAASPP administration.

Test booklets will have adequate space for student identification and demographic information, as well as space for the placement of a student barcode label. Barcodes, along with the human-readable number, will appear on the front and back covers of each test booklet, to maintain test security. Estimated print quantities for the paper-pencil test materials is included in Table 10.

Table 10.  Estimated Print Quantities* for Paper-Pencil Test Booklets, Answer Documents, Response Booklets, and School and Grade Identification Sheets

| Document | Document Type | Estimated 2016 Print Quantity | Estimated 2017 Print Quantity | Estimated 2018 Print Quantity** |
| --- | --- | --- | --- | --- |
| CST Science Grade 5 Test Booklet | Non-scannable | 536,000 | 536,000 | 0 |
| CST Science Grade 8 Test Booklet | Non-scannable | 541,000 | 541,000 | 0 |
| CST Science Grade 10 Test Booklet | Non-scannable | 555,000 | 555,000 | 0 |
| CMA Science Grade 5 Test Booklet | Non-scannable | 35,000 | 35,000 | 0 |
| CMA Science Grade 8 Test Booklet | Non-scannable | 31,000 | 31,000 | 0 |
| CMA Science Grade 10 Test Booklet | Non-scannable | 20,000 | 20,000 | 0 |
| CST/CMA Answer Document—Grade 5, 8, & 10 | Scannable | 1,718,000 | 1,718,000 | 0 |
| CAPA For Science Examiner’s Manual | Non-scannable | 7,500 | 7,500 | 0 |
| CAPA For Science Answer Document | Scannable | 15,000 | 15,000 | 0 |
| STS RLA Grade 2 Test Booklet | Scannable | 17,000 | 17,000 | 0 |
| STS RLA Grade 3 Test Booklet | Scannable | 17,000 | 17,000 | 0 |
| STS RLA Grade 4 Test Booklet | Non-scannable | 11,000 | 11,000 | 0 |
| STS RLA Grade 5 Test Booklet | Non-scannable | 7,000 | 7,000 | 0 |
| STS RLA Grade 6 Test Booklet | Non-scannable | 5,000 | 5,000 | 0 |
| STS RLA Grade 7 Test Booklet | Non-scannable | 3,000 | 3,000 | 0 |
| STS RLA Grade 8 Test Booklet | Non-scannable | 3,000 | 3,000 | 0 |
| STS RLA Grade 9 Test Booklet | Non-scannable | 2,000 | 2,000 | 0 |
| STS RLA Grade 10 Test Booklet | Non-scannable | 2,000 | 2,000 | 0 |
| STS RLA Grade 11 Test Booklet | Non-scannable | 2,000 | 2,000 | 0 |
| STS RLA Grade Answer Document — Grades 4-11 | Scannable | 35,000 | 35,000 | 0 |
| Smarter Balanced ELA Grade 3 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 3 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 3 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 3 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 4 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 4 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 4 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 4 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 5 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 5 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 5 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 5 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 6 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 6 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 6 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 6 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 7 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 7 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 7 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 7 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 8 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 8 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 8 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 8 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 11 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 11 Test Booklet | Non-scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced ELA Grade 11 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Smarter Balanced Math Grade 11 Response Booklet | Scannable | 45,700 | 45,700 | 1,000 |
| Alternate Assessment For ELA and Mathematics Secure Directions for Administration — Grades 3–8 and 11*** | Non-scannable | 4,000 | 4,000 | 4,000 |
| School And Grade ID Sheet (SGID) | Scannable | 570,000 | 570,000 | 570,000 |

*The estimated print quantities include the estimated test taker count as indicated in RFS Addendum 1, Table 3.1, plus the estimated overage materials included in the LEA shipments, the materials needed to support the special versions, and the estimated materials for ETS inventory to fulfill supplemental orders requested by LEAs.
**The estimated print quantities for the Smarter Balanced paper-pencil assessments for the 2018 administration are to support the continued administration of the Braille and large print and minimal regular versions. 
***The administration of the alternate assessments do not require test booklets and answer documents. Test questions are included in the secure Directions for Administration and test administrators will enter student responses into the TDS.

Test booklets will contain the following information on their covers:

- form identification

- content area

- administration date

- security warning

- copyright information on the inside front cover

- CDE logo and CAASPP logo on the front cover

ETS is prepared to customize the information on the cover annually, and ETS will design answer books to provide:

- space for scannable, pre-printed student barcode labels; or information can be printed if the LEA opted to receive pre-ID’d materials as an ancillary service

- space for students to write and grid-in information specified above, such as name, grade level, and gender

- space for test administrators to indicate special testing conditions or student test settings used during testing

Each test booklet page will contain a unique scannable identifier on each page. This identifier will aid in locating any pages separated from the books. Each California test booklet will also have a six-digit sequential number, known as a litho code, which are used in the distribution and collection process as well as for CDE edit checks. Each page will identify the session number and form designation for ease of viewing during test monitoring.

Each test booklet will contain a barcode, which ETS will scan before sending the test booklets to schools and LEAs. ETS will scan these barcodes again once those schools and LEAs return the test booklets. This will occur immediately upon receipt at the ETS facility following the return of paper test materials. ETS will document scanned data into both the inventory and a closed-loop tracking system. This system will track inventory and determine, by school and LEA, any missing test booklets or secure test materials.

After the last pick-up, ETS will provide an initial missing secure materials report. This report will include a complete accounting of all materials, identifying the school, LEA, content area, form identifier, quantity of test booklets sent, quantity of test booklets returned, and the number of missing materials. ETS will also provide a separate summary for each LEA and confer with the contracted courier service provider to obtain details about the delivery of returned shipments. ETS will update the report and inform California and each LEA of subsequent returns.

#### 7.2.A.2. Special Versions (Braille and Large-Print)

ETS will estimate the print quantities of the CST/CMA for science and the STS RLA Braille and large print test books based on usage from previous administrations and take into account any other factors that could influence volumes. ETS will base the quantities of the Smarter Balanced Braille and large print test books on orders provided by LEAs through TOMS by December 1 annually.

##### Procedures for Producing Braille Versions of the Tests

ETS production staff will develop and produce Braille versions of each assessment for each test administration window. Materials will include a page for transcriber’s notes and a special symbols page, as well as a special Instructions for Use document for administering the Braille tests. ETS will provide detailed instructions and examiner directions to support the test for the Braille versions. They will reflect any special instructions for test administration specific to the Braille version of the assessment.

##### Procedures for Producing Large-Print Versions of the Tests

ETS will provide the large print booklets — in black ink — and related materials for each test administration. ETS will produce these booklets by submitting the document copy to the printer on electronic media. Before producing the camera copy, ETS will electronically enlarge the type size. It is important to do this, rather than enlarging the copy via a photocopier, to yield documents with sharp and distinct images that are vital to visually impaired students.

ETS will present pages in portrait format and spiral bind the booklets so that the pages will lie flat when fully opened. For the modification of graphics for the large print booklets, ETS will remove any background shading or screens during the composition process. Such shading or screens could hinder a student’s ability to interpret and respond to the item. ETS proposes reproducing any graphics that the developer purposely drew to scale at the same size and will only modify items from the original size that are solely represented by color or contrast.

The directions for administration specific to the large print edition will be similar to those used for the regular print, operational version of the test.

Students will respond directly in the special version test booklets or response booklets, and test administrators will transcribe their responses into the test delivery system.

#### 7.2.A.3. Paper-Pencil Test Administration

ETS has detailed plans in place for the printing, packing and packaging, shipping, and retrieval and processing of the 2015 CAASPP test administration materials, and ETS will continue using the same processes, refining elements to improve efficiencies and to address any policy or programmatic changes required for a given administration.

##### Printing and Packaging

ETS will print and package assessment materials according to the requirements of the RFS. The shrink-wrap, overage, and packaging specifications will support the goal of efficient handling by the CAASPP Test Site Coordinators, also allowing ETS to effectively bundle the necessary quantities of test materials.

ETS proposes the following baseline packaging assumptions:

- ETS will provide test booklets in packages of 10.

- Test books will be spiraled for assessments with multiple test versions with the package to help facilitate equal distribution of forms across the student population.

- ETS will provide accommodated versions of the test booklets in individual packages with accompanying materials.

- ETS will individually package manuals and ancillary materials to meet the CDE’s requirements.

- Secure materials will be in shrink-wrapped packages that will have an affixed barcode indicating the items contained within the package.

ETS will ship all paper-pencil test materials — CST/CMA/CAPA Science, STS RLA, Smarter Balanced, and Alternate Assessments — for a test administration window at one time. If the LEA ordered pre-ID labels, then ETS will also package the labels with the test materials. ETS will package all materials for each school and ship those packages to the appropriate LEA. Because many LEAs have multitrack calendars that require testing in more than one test administration window, it will be necessary to make more than one shipment to some LEAs.

ETS will develop and maintain the materials list for each administration, as ETS does for the CAASPP 2015 administration. This list is a requirements document that specifies anticipated page counts, order quantities, distribution quantities, and processing quantities for each item type by year. ETS will provide the list to the CDE upon request.

ETS will use distribution rules to calculate material quantities and overages. ETS’s costs assume 10 percent overage for every school testing, as well as a five percent overage for every LEA based on the LEA’s total order for each grade.

##### Shipping

ETS will meet the CDE’s timelines and requirements, producing detailed packing lists for each order and tracking sheets for test administrators. For barcode-tracked materials, ETS will produce shipping lists that itemize each piece of the shipment and individual boxes. ETS will provide electronic flat text files of the security barcodes at the time of shipping for the CDE and each LEA.

ETS will package boxes by assessment and grade for each test site and send them to the LEA, and ETS will clearly label the contents of each shipment. ETS ships all test materials, bearing the return address of ETS’s test materials processing center, by a secure courier.

Box 1 of each LEA- or county-office shipment will include:

- return freight kits for scorable and non-scorable materials

- directions for inventorying the materials and for notifying CalTAC of any missing materials or shortages

- a set of packing lists for all school shipments within the LEA or county office

- a packing list for the LEA or county overage materials listed in the order in which they are packed

- a pallet detail report for those shipments that include two or more pallets

Box 1 of each school shipment will include:

- return freight kits for scorable and non-scorable materials

- a packing list with materials listed in the order in which they are packed

- pre-ID student labels

ETS will numerically label the boxes to correspond with the packing list (i.e., Box 1 of 20, Box 2 of 20, Box 20 of 20), to make materials for a particular assessment and grade level identifiable upon receipt at the test site.

Box Specifications. ETS will use specifications for box construction so that the boxes used for shipping test materials are extremely sturdy and durable. ETS will use double-walled, reusable boxes to both withstand the rigors of handling by the carriers during distribution to LEAs, and to protect the test materials shipped back to ETS for processing.

LEAs receive many shipments of materials during the school year. Although ETS will label the boxes with program information, it is critical that the LEA CAASPP Coordinator be able to locate Box 1 of each shipment as soon as possible, as Box 1 contains the packing list and other important information needed to facilitate handling. For that reason, ETS will mark Box 1 so that LEAs easily recognize it.

Special Services to LEAs. Where possible, ETS will provide the following fee-based special services to LEAs:

- accommodations for special LEA requested arrangements and space

- pallet jack or other equipment necessary for LEAs without a dock or proper equipment

- alternate carrier arrangements at the request of the LEA so that testing materials reach the more remote areas of the state on time

ETS will provide the CDE a proposed price list for review and approval. The price list will include all special services and other fee-based ancillary services (e.g., rescoring of constructed response test questions) available to LEAs.

ETS will use TOMS to capture requests for proper delivery (e.g., no dock, need assistance). If there are any questions about special services in the enrollment order, CalTAC will follow up with the LEA CAASPP Coordinator before ETS ships test materials for that LEA.

Additional Orders. When LEAs need additional materials, ETS will process requests for additional materials as long as there are not delays with shipments to other LEAs. Having the additional orders fulfilled using the main packaging and distribution system will allow ETS to consistently and effectively respond to requests for additional materials to LEAs within two business days of notification.

Packaging and Distribution System. ETS will utilize a state-of-the-art Packaging and Distribution system, which uses barcode-identified packaging components. Barcodes will identify item type, boxes, orders, pallets, and shipments.

ETS will establish a high level of quality through such steps as applying unique shipping labels for each package associated with a school’s order. Each package will have a tracking number associated with it. ETS will load this order and shipment tracking information into TOMS, where LEA CAASPP Coordinators placed their orders. Since TOMS contains e-mail addresses tied to each order’s school and LEA hierarchy, the system-generated e-mails will go to LEA CAASPP Coordinators upon shipment of their order. Information on their order is available for LEA personnel to view and track in the system.

All materials for the test administration will arrive in schools no earlier than 10 working days and no later than five working days prior to the start of testing. ETS will use closed-loop tracking to make sure that ETS sends the correct materials ordered, and that the school or LEA receives and accounts for those materials.

##### Collection and Processing

LEAs must return scorable and non-scorable materials within five working days after the last day for each test administration period. ETS project management will closely monitor the return of materials and will notify the Help Desk, CalTAC, of any LEAs that have not returned their materials. CalTAC will contact the LEA CAASPP Coordinators and work with them to facilitate the return of the test materials. ETS will work onsite with LEAs, collaborating with County Offices of Education, to verify the return materials in a timely manner.

In the packaging process, ETS will include freight return kits for scorable and non-scorable materials for use by the LEA CAASPP and scorable materials. The label will also contain bar-coded information identifying the school and LEA. When CAASPP Test Site Coordinators pack their materials for return to the LEA, they are required to apply the appropriate labels and number the cartons (e.g., 1 of 2, 2 of 2). Upon receipt of the materials at the LEA, the LEA CAASPP Coordinator is required to complete the “total shipment from this LEA” information on the label.

The use of the color-coded labels streamlines the return process. LEAs will deliver all scorable and non-scorable materials to ETS’s scanning and scoring facilities in Ewing, New Jersey.

Processing of Returned Materials. Upon receipt of the test materials, ETS will utilize a precise inventory and test processing system in conjunction with quality assurance procedures to maintain an up-to-date accounting of all the testing materials within ETS facilities.

As ETS receives test materials, personnel remove the materials from the shipping cartons and carefully examine each shipment for a number of conditions, including physical damage, shipping errors, and omissions.

As materials are batched for scanning, personnel also conduct a visual inspection to compare the number of students recorded on the school and grade identification (SGID) sheet to the number of answer documents in the stack.

ETS’s image scanning process provides the ability to capture security information electronically and to perform the following tasks:

- compare scorable material quantities reported on header sheets to actual documents scored

- follow up on any missing shipments or quantities appearing to be less than expected with a phone call by ETS’s Program Management Team to the school LEA

  - CalTAC staff will contact the LEA for further resolution.

ETS will check in all secure materials by scanning the barcode label on each of the returned cartons. ETS will then count and return the materials in each box to the original box for storage. ETS will compare the quantity of test booklets that received, including the scanned counts of STS grades 2 and 3 scorable documents, and compare that to the quantity that are assigned and sent to each LEA and school.

Notifying LEAs of Discrepancies in the Quantities of Secure Materials. ETS will send reports detailing secure materials received back from the LEAs or schools to CalTAC, who will follow-up with LEAs. ETS will provide the CDE with an electronic file showing the final resolutions of discrepancies no later than September 20th of each year. The format of the file will be similar to the file format used in the 2014 administration.

Procedures for the Secure Destruction of Secure Materials. After secure materials (including test booklets and examiner’s manuals) are processed, ETS will return them to their original boxes for storage and palletize and place them in ETS’s secure warehouse facilities. Once all resolution is complete, ETS will request approval from the CDE to securely destroy the materials. For the purposes of this bid, ETS will request approval from the CDE on October 31st annually following the administration to securely destroy test materials.

## 7.3. Computer Based Assessments

AIR’s test delivery system will be used as part of a continued offering for CAASPP. The proposed system has the proven operational capabilities to deliver the full range of assessments.

#### AIR-Proprietary Test Delivery System

ETS and its subcontractor, AIR, will host and support the AIR-proprietary test delivery system (TDS) for the administration of all online California-specific and Smarter Balanced assessments (summative and interim) for California.

A summary of the system features:

- Provides advanced security protocols and techniques to protect both test content and student data

- Provides educators with a robust set of tools to manage and monitor testing. The system displays each student’s progress through the test. Additionally, intuitive, user-friendly icons indicate each student’s testing status. Customized student grouping rules can be applied to easily help manage student data.

- Uses current industry-recognized standards (SIF, IMS, etc.).

- Is flexible to accommodate the varying technological capabilities that exist in state school LEAs.

- Accommodates virtual networks and/or thin client environments and supports administration within a secure wireless environment on tablets or other mobile devices.

- Includes a rich set of tools to enhance the student’s computerized-testing experience

- Tools are highly customizable and can be configured for each computerized test and test taker as set by the testing procedures and PMP.

- Provides a workflow that makes pre-registration for specific online testing sessions unnecessary.

- Shows online testing metrics, by assessment and state/LEA/school, immediately upon inquiry. Daily completion status reports summarized across state and by LEA are available

The test delivery system is a purely Internet-based system that supports operating systems and browsers longer than their original manufacturers. This covers almost all the computers currently found in schools. While inside schools, there can be technology schools, technology is advancing rapidly outside. ETS will not only to keep up with those advances across all technology proposed for CAASPP, but leverage them to make test content more meaningful and accessible. Therefore, ETS needs to confirm that their system always has forward browser compatibility with the latest operating systems, including iOS®, Androids, and Chromebook™ devices, as well as assistive technology devices. a below describes the secure browser support policy for new operating system releases. Table 11b describes the Web browser support policy for new releases.

Table 11a.  Secure Browser Support Policy for Operating Systems

| Release of 3rd party software | Compatibility | Description |
| --- | --- | --- |
| Currently supported operating systems | 90 days after release | AIR intends to support a new version of a currently supported operating system within 90 days of official release. |
| Google ChromeOS | presumptive support | AIR does not block new versions from accessing the site. |

Table 12b.  Web Browser Support Policy

| Release of 3rd party software | Compatibility | Description |
| --- | --- | --- |
| Apple Safari and Microsoft Internet Explorer browsers | 90 days after release | AIR does block new versions of these browsers from accessing the site until they are tested and all issues are resolved. |
| Google Chrome | presumptive support | AIR does not block new versions of these browsers from accessing the site. |

Table 13 below provides a list of supported operating systems and recommended specifications as of the submission of this SOW. ETS will update this list annually as part of the Smarter Balanced Implementation Readiness Package described in Task 3.ETS will provide the CDE with advance notice when a secure browser update will be released. AIR will continue to work closely with the major operating system vendors to ensure that the secure browsers will work on any new operating system updates.

Table 13.  Supported Operating Systems and Minimum Requirements, as of March 30, 2015

| Operating System | Supported Devices | Secure Browser | Related Requirements* |
| --- | --- | --- | --- |
| Desktop |  |  |  |
| Windows XP (Service Pack 3), Vista, 7, 8.0, and 8.1 Server 2003, and 2008 | Desktops/Laptops | Windows Secure Browser 7.2 | Disable fast user switching. Server 2003 and 2008 are supported when using a thin client. |
| Mac OS X 10.5 (Power PC) | Desktops/Laptops | Mac Secure Browser 5.6 | Disable fast user switching and Launchpad. |
| Mac OS X 10.5 (Intel) | Desktops/Laptops | Mac Secure Browser 6.5 | Disable fast user switching and Launchpad. |
| Mac OS X 10.6 – 10.10 | Desktops/Laptops | Mac Secure Browser 7.2 | Disable Spaces (10.7 – 10.10). |
| Linux Fedora 16 –20 openSUSE 13.1 Red Hat Enterprise 6.5 Ubuntu (LTS) 10.04, 12.04, and 14.04 | Desktops/Laptops | Linux Secure Browser 6.5 | Install required libraries. Install Festival and SoX. Install Verdana TrueType font. |
| Mobile |  |  |  |
| iOS 6.0 – 8.1 | iPad 2 iPad 3 4th Generation (Retina Display) iPad Air | AIRSecureTest Mobile Secure Browser | Enable Guided Access. (Note: Single App Mode is not the same as Guided Access.) |
| Android 4.0.4 – 4.4 | Google Nexus 10 Motorola Xoom Samsung Galaxy Note (10.1) Samsung Galaxy Tab (10.1) LearnPad Quarto | AIRSecureTest Mobile Secure Browser | Enable the secure browser keyboard. |
| Chrome OS 31 – 40 | Chromebooks | AIRSecureTest Kiosk Application | Chromebooks must be in kiosk mode. |
| Windows 8.0, and 8.1 | AIR supports any tablet running Windows 8.0 and 8.1 Pro. However, AIR has done extensive testing only on Surface Pro, Asus Transformer, and Dell Venue. | Windows Secure Browser 7.2 | Disable fast user switching. |

Note: The CAASPP end-of-support date for operating systems will be consistent with the Smarter Balanced end-of-support plan (www.smarterbalanced.org)

The CAASPP Assessment Delivery System contains a series of integrated modules that appear to users as a single, integrated system. Once logged in, users can navigate the various components of the system securely. The CAASPP Assessment Delivery system has four components: TOMS, the test delivery system, the quality monitor system, and participation reports. Table 14 provides an overview of each component.

Table 14.  Summary of Assessment Delivery Components.

| System | Description |
| --- | --- |
| Test Operations Management System (TOMS) | TOMS is responsible for: - student registration - gathering of demographic data - materials ordering |
| Test delivery system Test administrator interface | The test delivery system’s test administrator interface provides the interface through which test administrators establish and monitor testing sessions and authenticate student users. The student interface is the testing system as it appears to the student, on which students take tests. The test delivery system delivers tests to students, records responses, and forwards data to downstream systems. Available for CAASPP computer-based tests beginning with the 2015-16 administration: Smarter Balanced summative assessments, Smarter Balanced interim assessments, CAA. Planned availability for CAASPP computer-based tests beginning with 2017-18 Field Test administration: CA NGSS, CA NGSS Alternate, and Primary Language. |
| Quality monitor system | The quality monitor system receives the data, verifies the validity of the test administered and the item-level scores assigned, and gathers statistical data for ongoing quality reports. Data are then provided to ETS for test-level scoring and reporting. |
| Completion Status | The online reporting system for participation reports provides a secure interface to participation data and associated demographic information. Available for CAASPP computer-based tests beginning with the 2015-16 administration: Smarter Balanced summative assessments, Smarter Balanced interim assessments, CAA. Planned availability for CAASPP computer-based tests beginning with 2017-18 Field Test administration: CA NGSS, CA NGSS Alternate, and Primary Language. |

#### System Description and Capabilities

To administer tests, the test delivery system needs information about students and test administrators, including authentication information. TOMS gathers data from districts, schools, or the state, and transfers those data to AIR’s roster tracking system, a flexible database system shared by the test delivery system and the AIR reporting systems utilized for completion status. The roster tracking system will house TOMS-provided data provided about the educational networks in California, such as which schools are in which LEAs, which teachers are in which schools, and which students are in which classrooms.

After the test delivery system administers the test to a student, the system passes the resulting data to the quality monitor system. The quality monitor system rescores tests, checks that the tests meet the blueprint, captures statistics on items, and runs a host of extensive quality checks. The quality monitor system also runs a suite of analyses designed to detect cheating, which ETS can make accessible to psychometric personnel at any time. The entire quality checking process occurs in milliseconds. The system then transfers item-level score data to ETS for test-level scoring and population within the electronic reporting systems. In the rare event that the quality monitor system identifies an anomalous test result, the system promptly notifies members of the project team and ETS holds the results until they can be verified.

The interfaces comply with the application programming interfaces and data interoperability standards established by the Smarter Balanced Consortium. Figure 5 provides a schematic of the overall system.

Figure 5.  Overall Schematic of the Test Delivery System

Activities related to system requirements are described in Task 3.

#### 7.3.A.1 Interim Assessments

ETS will build on the implementation of the 2015 Smarter Balanced interim assessments for LEAs to include:

- the capacity to limit the number of testing opportunities

- educator access to all grade levels of interims using a user-friendly presentation of the available interim assessments

- a visual difference from the summative assessments (e.g., different search or filtering process, different graphic screen element)

- streamlined access to the Smarter Balanced interim assessment component for educators, using the same systems and protocols used for the summative assessments

- training and certification of LEA-based trainers in the scoring of student responses to constructed-response and performance-task items, using workshops, webinars, and supportive ancillary documents and materials

- training and materials to guide accurate interpretations of scores and support effective use of interim assessment results to improve instruction

- a method for reporting scores to the Smarter Balanced data warehouse for reporting purposes

As part of this contract, ETS and its subcontractor, AIR, will provide services that will incorporate access to the Interim Assessments via single sign-on functionality through TOMS. Access to the Interim Assessments will be available year round beginning in August 2015. ETS will update the interim assessments by September annually with materials provided by Smarter Balanced. ETS will work with the CDE to develop appropriate roles for administration of summative and interim assessments that limit access as appropriate.

The Interim Assessments will share the same servers as the Summative Assessment. It is estimated that approximately 6.3 million students in kindergarten through grade twelve will have access to the Interim Assessments. This estimate includes the students in grades three through eight and grade eleven who also will have access to the Summative Assessments. ETS and AIR will host a server infrastructure with sufficient bandwidth, hardware, and software to provide the Smarter Balanced assessments and tools to up to approximately 6.3 million students.

##### Training Educators in the Scoring of Student Responses to CR Items

As part of the plan to improve educators’ access to interim assessments — and to train them to effectively use them — ETS will use its expertise and provide opportunities for educators to learn how to accurately and reliably score student responses to constructed response and performance task items. Educators training is described in Task 2.

##### Reporting Interim Assessment Scores to Smarter Balanced Data Warehouse

Following the administration of an interim assessment, ETS will securely transfer information to the Smarter Balanced Data Warehouse for prompt reporting via the Smarter Balanced Reporting System. ETS will work with Smarter Balanced to allow for single sign on access to the Smarter Balanced Reporting System to make it seamless for educators to use all components.

#### 7.3.A.2. Appeals for Computer Based Assessments

The test delivery system provides an online method by which LEA CAASPP Coordinators may submit an appeal for a computer-based assessment. The system handles all of the current appeals types and conditions required by the CDE and Smarter Balanced. ETS will confirm with the appeals types and conditions for each administration during the Orientation and Annual Planning Meetings.

A team of trained ETS representatives, in conjunction with the CDE, will be responsible for monitoring the appeals queue via the online appeals system. Monitoring and processing of the outstanding appeals will take place throughout the day, Monday through Friday, during the test administration period. The designated team will review each request and approve or deny the appeal based upon the requirements documented for each type of appeal. Based on experiences from the 2014 Smarter Balanced Field Test and preparations for the 2015 CAASPP administration, a recommended decision tree is included in Table 15. The decision tree indicates who is handling the request and describes each type of request, reasons for the request, and results of an approved request.

Table 15.  Online Appeals: Types and Conditions

- Appeals Handled by the CDE

| Type of Appeal | Reasons for Appeal | Results of Approved Appeal |
| --- | --- | --- |
| Invalidate a test | - Test security breach - Test administered inconsistently with the TAM - Student deliberately did not attempt to respond appropriately to items | Invalidated tests WILL be scored. |
| Restore a test that has been reset | - A test was inadvertently or inappropriately reset | A test that has been reset in error can be restored to its previous status and restarted where the student left off. |
| Grace Period Extension | - Loss of Internet access | Allows the student to review previously answered questions upon logging back in to the test following expiration of the pause rule period. |

- Appeals Handled by ETS

| Type of Appeal | Reasons for Appeal | Results of Approved Appeal |
| --- | --- | --- |
| Reset a test | - Student started test without the designated supports or accommodations in his or her individualized education program or Section 504 plan - Correct test was not available - Incorrect test originally opened | Resetting a student’s test removes that test from the system and enables the student to start a new test from the beginning. |
| Reopen a test | - Student became ill and the test expired - Technological difficulty resulted in expiration of the test - Unanticipated excused absence or school closure resulted in expiration of test(s) | Reopening a test allows a student to access a test that has already been expired or submitted: - Expired – Test opens where student left off - Submitted – Test opens at the last page of the test; student can review items in the current segment, but cannot return to previous segments |

After ETS enters and reviews an appeal within the system, the LEA will receive a status of the appeal, whether it has been approved or denied. The LEA can review reasons for denying an appeal in the appeals database.

ETS will report weekly on the status of all appeals, whether they be approved, rejected, or outstanding appeals that are still in the queue to be processed. ETS will be prepared to report daily or on demand as needed by the CDE.

ETS will maintain a log of appeals that includes at least the following data elements:

- Date of appeal

- Name of LEA

- Type of Appeal

- Appeal Decision

## 7.4. Contracting with LEAs for STS for Dual Immersion-Programs

STS is currently available via the process agreed to by CDE and ETS. The STS is optionally available for students enrolled in a dual-language immersion program and who are either non-limited English proficient or re-designated fluent English proficient (the STS for Non-ELs in Dual-immersion Programs). ETS will enter into agreements with LEA’s that are interested in this service.

Non-English Learner (EL) students in dual-immersion programs may take the STS for RLA and/or the STS for mathematics for which they meet the grade-level or end-of-course (EOC) eligibility requirements. However, because ETS will not report results for the STS for non-ELs, students do not have to take both content-area tests.

ETS has a process in place to allow these students to take a previous version of the STS at a minimal cost to the LEA. This cost is uniform across the state and is designed to recoup the marginal cost of the assessment.

LEAs will be able to download and/or order printed copies of these tests via a secure Web site. Prior to accessing the Web site, the LEA must sign and return a license and administration agreement that covers all security and privacy requirements.

ETS documents materials regarding test administration and instructions for scoring in detail, and makes these materials available to the LEA for download or in a printed format.

ETS will include the fees for these STS services as part of the CAASPP Ancillary Services Price List for CDE review and approval.

# TASK 8: Scoring and Analysis

ETS will work with the CDE to lay out and document the scoring procedures. ETS will follow existing quality assurance processes to confirm and validate the results. Finally, ETS will perform a series of tests, which will include processing sample data through an end-to-end sequence that verifies accuracy.

## 8.1. Scoring

ETS will take an integrated approach to planning and accurately scoring the assessments using Smarter Balanced- and California-required methodologies and procedures. ETS will work with the CDE to lay out and document the scoring procedures and will follow the quality assurance process to confirm and validate the results. Finally, ETS will perform a series of tests, which will include processing sample data through an end-to-end sequence that verifies accuracy.

- Scoring Process Flowcharts

For computer-based assessments, ETS will deliver test results within two-three weeks after a student completes testing in a given content area. Figure 6 below illustrates the process ETS will use for scoring computer-based CAASPP assessments.

Figure 6.  Computer-based Test Delivery — Scoring and Reporting Flow

For all paper-pencil tests, ETS will deliver test results within six (6) weeks after receipt of materials to confirm complete and accurate processing. Figure 7 below illustrates the process ETS will use for scoring paper-pencil CAASPP assessments.

Figure 7.  Paper-pencil Test Delivery—Scoring and Reporting Flow

- Rescore Requests

Request for a rescore will be provided to districts following a CDE-approved procedure for requesting the rescoring of an individual student’s responses or a set of classroom-level responses. ETS will provide results of any such rescores to the requesting district within 30 working days of receipt of the request. In the case that the rescore indicates any anomalies, ETS will verify the correct scores and reissue affected score reports. In such an event, there will be no charge to the district. ETS will also conduct CDE rescore requests at no charge to the CDE. If any such CDE-requested rescoring requires updating and/or distribution of new data and score reports, there will be no charge to the CDE or to the CAASPP contract.

- 8.1.A. Methods of Scoring

ETS will utilize all necessary scoring methods for each of the following item types:

- Selected-response Item Scoring. For computer-adaptive testing (CAT), the AIR test delivery system will administer, score, and subsequently pass items through the CAT algorithm to determine which item to administer next. The system scores machine-scored items automatically in real-time. ETS will house student results in the ETS-maintained database of record. This private and secure state-specific database will contain CAASPP student results and assessment registration information.

- Technology-Enhanced Item Scoring. Technology-enhanced items (TEIs) offer an advantage over traditional selected-response items. TEIs more closely simulate what students do in the classroom and the real world, as students can actually create their own responses rather than choosing from four preselected responses. Although scoring such items presents new challenges, ETS has significant experience and demonstrated competence in this area.

- Constructed Response Item Scoring. Constructed-response items require students to provide written responses, from simple fill-in-the-blank items with comprehensive lists of possible answers to full essay responses. Scoring approaches for these items generally fall into three categories:

  - Deterministic Scoring. This includes machine-scored items basic TEIs (such as matching items, hot spots, etc.), or simple fill-in-the-blank items with comprehensive lists of possible answers.

  - Human-scored Responses. As the name suggests, these items involve constructs that require human scoring.

  - Artificial Intelligence (AI) Scoring. ETS has developed rater engines that make it possible to automatically score more complex constructed-response items—such as items that ETS can score by matching a mathematical function (plot a line, use an equation, etc.), or longer constructed-response items that move beyond simple fill-in-the-blank types — that expand the possibilities for constructed-response items. AI scoring often requires some level of human scoring, in order to train the scoring engine and validate the scores.

- 8.1.A.1. Deterministic or Machine-Scoring

ETS’s system will maintain each unique scoring key used to score the programs. All Smarter Balanced machine-scored items will be rendered into ETS’s systems.

ETS will score the multiple-choice, gridded responses, and computer-scored technology-enhanced items using the production keys or scoring rules.

- 8.1.A.2. Performance Task and Constructed-response Scoring

ETS will score Performance Task and constructed-response student responses (including mathematics responses in Spanish) to maximize validity and reliability while incorporating efficiencies wherever possible. Table 16 represents the division of labor between ETS and MI.

Table 16.  Performance Task and Constructed-Response Scoring by Content Area and Grade

|  | Smarter Balanced ELA | Smarter Balanced Mathematics | California NGSS | Primary Language | CAA and CA NGSS Alternate |
| --- | --- | --- | --- | --- | --- |
| Grade 3 | ETS | MI | - | ETS | Proctor |
| Grade 4 | ETS | MI | - | ETS | Proctor |
| Grade 5 | ETS | MI | ETS | ETS | Proctor |
| Grade 6 | MI | ETS | - | ETS | Proctor |
| Grade 7 | MI | ETS | - | ETS | Proctor |
| Grade 8 | MI | ETS | ETS | ETS | Proctor |
| Grade 9 | - | - | - | ETS | Proctor |
| Grade 10 | - | - | - | ETS | Proctor |
| Grade 11 | ETS | ETS | ETS | ETS | Proctor |

The procedures ETS proposes for California include:

- careful recruiting of raters utilizing ETS best practice hiring process

- extensive training of all levels of scoring leadership, not only on the prompts, rubrics, and related scoring material but on how best to monitor the quality of the scoring

- rigorous training of the raters in appropriately applying the rubric for each prompt type, following the generic sample responses that exemplify the quality required for each score point so that every prompt is scored on the same general criteria

- requiring new raters to demonstrate their accuracy by passing a “certification” test before being assigned to score a specific assessment and then by passing a shorter, more focused “calibration” test before each new prompt type

- using scoring leaders to read behind and monitor raters; scoring leaders have the option of evaluating responses a rater previously scored, with or without the knowledge of the score he or she gave (“informed” versus “blind” back rating)

- using scoring system’s live operational data to identify (and, for scoring leaders, then counsel) raters who are reading at unusually slow (or overly fast) rates

- using content scoring leaders to monitor the scoring leaders and their virtual teams

- including pre-scored validity responses (sometimes called monitor papers) within each rater’s set of assigned responses in order to evaluate ongoing accuracy while scoring

- regularly analyzing inter-rater reliability (IRR) statistics to verify that raters are scoring consistently (scoring system produces real-time IRR and validity response scoring statistics)

- Using Hand Scoring of CAASPP Constructed Response Items for Teacher Professional Development

ETS remains committed to maximizing the involvement of California teachers in scoring student responses to CAASPP items and in increasing the professional development opportunities to the greatest extent possible. ETS will follow best practices as recommended by Smarter Balanced for using scoring as a professional development tool for teachers in California.

ETS will involve teachers in five types of large-scale scoring activities: 1) Interim Assessment Scoring Workshops, 2) Summer Scoring Institutes, 3) Range-Finding Meetings, 4) Constructed Response Scoring Modules, and 5) Live Operational Scoring.

Interim Assessment Scoring Workshops will train teachers in the effective and consistent use of scoring rubrics and materials so that they may accurately score their students’ interim assessments.

These workshops, detailed in Table 1 in Task 2, will include:

- Training that will increase teacher effectiveness in teaching and evaluating writing.

- Feedback to teachers that will support improvement in student performance.

- Online posting of videotapes of these workshops.

- Support for the recruitment and training of California teachers to score Smarter Balanced summative assessments.

- Pre-scored constructed-response samples in the scoring training sessions

- Preparation of workshop participants for the certification test required for CAASPP Smarter Balanced summative raters.

- Access to the scoring system with the opportunity to take an online certification test.

- Opportunities for teachers not qualified for the summative scoring.

Summer Scoring Institutes will provide training on the scoring of released operational items from both the summative and interim administrations from the previous year.

These workshops will include:

- Live training materials that raters use for operational scoring.

- Student responses from the summative and interim administrations for certified teachers.

- Items and responses from the pool of AI-scored responses that receive additional human back-reads.

- Opportunity for teachers to rate responses using the same systems and processes used for operational scoring.

Range-Finding Meetings for the new assessments in CA NGSS and Primary Language will take place after the pilot and field tests. The grade- and subject-specific committees will contain teachers, district/school curriculum staff, district/school administrators, and higher education staff as specified by the CDE. These range-finding meetings will provide input into score ranges for each item, scoring rationales, and identify anchor sets with exemplar responses.

Constructed Response Scoring Modules will work with the Beginning Teacher Support and Assessment (BTSA) Induction to engage preliminary credentialed teachers in a job-embedded formative assessment system of support and professional growth. ETS will suggest opportunities to including modules on constructed response scoring in these locally implemented programs with the goal of improving classroom practice. With this professional development, beginning teachers will be able to hand score both interim and summative performance tasks, and engage in the system of assessments to improve teaching and learning. ETS will reach out to interested BTSA providers to gauge their interest.

Live Operational Scoring will provide current California teachers, to the maximum extent possible, the option to engage in operational scoring of CAASPP English Language Arts and Mathematics student responses. To achieve this, ETS will employ the following strategies:

  - Weekend Scoring Institutes will be available to California teachers who have applied and have been accepted for the operational pool. ETS will hold scoring institutes on alternating weekends in March, April, and May for the purposes of training and certifying California teachers in a face-to-face setting. Teachers that qualify during these weekend sessions will score for the remainder of the weekend and will be certified to score via a distributed model at the end of the institute session.

  - Recruitment Tactics to Maximize CA Teacher Involvement. In order to encourage California teachers to participate in distributed scoring, ETS proposes the following:

    - reach out to the Education Coalition, as a collection of educator stakeholders, for assistance

    - offer teachers professional development or continuing education credit – ETS will explore the possibility with the appropriate state offices to offer continuing education credits to teachers

    - offer California teachers priority processing over other raters and provide them with their own link through the CDE and California teachers associations Websites

      - Priority processing means that, as applications come in to the scoring centers, applications from California teachers will be placed at the very front of the queue, guaranteeing them priority in the training, certification, and hiring process.

    - reach out to Teacher Education Programs throughout the State to target pre-service teachers

      - ETS will suggest criteria or possible pilot programs for consideration of the CDE and SBE to expand the pool of potential raters beyond the current requirement of a bachelor’s degree.

    - Beginning Teacher Support and Assessment (BTSA) Induction—in addition to providing the modules described above, ETS will propose to BTSA providers that they include information regarding the CR scoring opportunities and perhaps a link to the application site

- Rates:

    - Hourly:

At the time of hiring, all reviewers are expected to make a reasonable commitment to participate in summative scoring, as defined annually by CDE and SBE staff.

        - The hourly rate for scoring in the program is $13 an hour.

        - The hourly rate for scoring by certified California educators is $20 per hour, retroactive to the time of hiring. ETS will work with the CDE to operationalize the process and will submit the process for review and approval by the CDE and SBE staff.

    - Weekend institutes:

      - $150 stipend plus travel expenses for attendance at a weekend institute

      - California teachers who qualify to score after the institute will receive $20 an hour for any scoring they provide after the institute.

- Scoring Preparation and Execution for California

- Rater Recruitment

ETS will recruit and hire the necessary number of qualified raters to meet the scoring timelines. A qualified rater must meet the following eligibility requirements: (1) has, at minimum, an undergraduate degree from an accredited college or university; (2) is preferably a practicing or former teacher; (3) resides in the continental United States, Alaska, or Hawaii; and (4) is eligible to work in the United States. ETS will require verification of rater credentials including college degrees or other qualifications as determined in cooperation with the CDE and SBE staff. ETS will specifically recruit California teachers and educators and plan to hire as many qualified applicants from California as possible. In addition, recruitment outreach will include prior raters who are currently scoring or have successfully scored responses for one or more large-scale constructed-response programs.

ETS will appoint a team of highly experienced human resources professionals to recruit and achieve the CDE’s stated program requirements. This dedicated team will be responsible for vetting and hiring the required number of qualified raters and leaders to meet the volumes specified by Smarter Balanced as well as the volumes required to score the pilot and field test items for the proposed new assessments.

- Organizational Scoring Structure

The organizational structure for CAASPP will encompass:

- Content scoring leaders. These team members have overall responsibility for one or more assessments, working under the supervision of ETS’s assessment development content experts. Working across the leadership team for their domain, such as the ELA Upper Level grades, the content scoring leader will escalate non-routine issues (e.g., test security cases), review the performance of the group scoring leaders, and oversee the quality and progress of the scoring, working closely with assessment developers, scoring experts, and human resources professionals.

- Group scoring leaders. These team members provide key leadership and feedback to scoring leaders, carefully monitoring the overall quality and progress of the scoring. They score complex, non-routine responses and resolve any content-related issues raised by leaders.

- Scoring leaders. Scoring leaders’ primary duties will include monitoring and reporting on a team of raters. Leaders back-read their teams throughout the scoring process, offering feedback and resolving selected non-routine responses.

- Raters. Based on their given availability, ETS schedules these members to calibrate and then score assigned responses.

During rater recruitment, ETS evaluates, trains, and tests raters to determine their ability to read responses and score to the required accuracy level. If an applicant meets all of the specifications, then ETS will certify him or her as a rater.

- Scoring Plan

Number of Responses for Human and Artificial Intelligence (AI) Scoring

ETS will use specific assumptions regarding the number of items and the scoring mode for each item. Based on information provided on http://www.smarterapp.org regarding the type of student response elicited, and the potential of that items to provide quality professional development, ETS will base scoring solutions on the following assumptions regarding the number of items that can be AI scored, and ETS will work with the CDE to adjust inclusion of additional items for AI scoring to reflect their potential and appropriately include more human scoring by California teachers. In all cases AI scoring will only be applied to items that meet the most rigorous technical specifications for scoring that equal or exceed standards for human raters.

ETS will only expand AI scoring beyond the 2014-15 levels in accordance with the following criteria and with prior approval of the CDE.

- ETS will target for AI scoring only those constructed response (CR) items that are designed to elicit a specific correct answer from students. These items require test-takers to enter a single word, phrase, sentence, number, or set of numbers and are technical and repetitive. They typically take students 1-5 minutes and do not require complex scoring rubrics. These are items that are not particularly useful or appropriate for trained educators and professional development.

- ETS will target for Teacher Scoring and Professional Development Extended Response (ER) items that are designed to elicit more complex and elaborate student responses. These items allow students to demonstrate the use of complex thinking skills that are consistent with evidence based conclusions for interpreting information and developing explanations. These items typically take students 5-20 minutes to complete and require multi-level scoring rubrics. These item types are much more suitable for scoring by human scorers and for focused professional development.

- ETS will only expand AI scoring to any identified ER items after engaging input from teacher stakeholder groups to determine the best item types to use for professional development and teacher scoring.

- Development of Scoring Training Materials for New Assessments

Following rangefinding, the scoring team will create the various sets needed to train, qualify, and monitor raters for the CA NGSS and CA NGSS Alternate assessments (scored by Test Examiners) and primary language pilot and field tests.

ETS will include a set of decision papers which will be identified during rangefinding that represent the fine lines at the top and bottom of each score descriptor on the rubric. ETS will select these responses based on their scoring “difficulty” (e.g., is the response a high 2 or a low 3?).

- Training

The Scoring Trainers will use Smarter Balanced training materials for each grade level and train by item type, to develop a strong foundation to score a variety of items within the type for which they qualify. ETS will leverage the Smarter Balanced-based infrastructure in place to allow for ongoing trainings as ETS brings on raters to handle any fluctuations in scoring demands. ETS will complete scoring on a rolling basis and return the results within the window specified.

ETS will train the raters to evaluate types of items within a specific grade and content area. By focusing on a specific type of response, the rater will develop specialization in understanding and applying the nuances of the rubric criteria for the item type. This internalization of the rubric by type will allow raters to apply the general scoring criteria to multiple items accurately. For mathematics performance tasks (PTs), when scoring criteria for PTs within a family is generalizable across the PT type, raters will train across all PTs in the type as a unit. ETS anticipates that the training and qualifying sets from Smarter Balanced will consist of items and responses most representative of the type that ETS will score. Scoring trainers will use the latest Smarter Balanced training materials to help the raters learn to apply the criteria illustrated in the Scoring Guide, confirm the raters become familiar with the process of scoring student responses, and assess the raters’ understanding of the scoring criteria before they can begin live scoring.

ETS will employ flexible and secure online training interfaces for the rater training in the scoring sites and with distributive scoring activities. ETS will use the online training interfaces to allow ETS to lead interactive training sessions that emulate the best characteristics of face-to-face training. Using these same systems, the CDE will be able to actively monitor all of hand-scoring training and scoring activities without travel.

ETS raters will utilize the identification of condition codes, unusual prompt treatment, and Alert situations (e.g., child-in-danger); as well as other particular types of responses that they should forward to the Scoring Leaders during live scoring.

Qualification. Each member of ETS scoring staff will qualify for the scoring of student responses based on established California standards following a rigorous training process. ETS will maintain a consistent level of scoring quality throughout the scoring effort. ETS will submit documentation of all training processes and results to the CDE at the conclusion of scoring.

- Scoring Systems

The ETS online distributed scoring platform contains the key features, functionality, and related benefits that California needs for effective, high quality scoring.

To satisfy California’s need for rapid scoring turnaround, ETS will use this platform to:

- use selected criteria to prioritize the scoring of responses in queue

- stratify response scoring, based on the alignment of student and rater demographic data, to reduce potential scoring bias

- randomly distribute responses

- reconfigure pre-set scoring rules in a prioritized order, when necessary, to achieve scoring deadlines

- Quality Control

ETS will utilize a variety of procedures for controlling rating quality along with the monitoring of the raters.

These procedures include:

- Rigorous training of the scoring leadership. Content scoring leaders, group scoring leaders, and scoring leaders will receive training respectively on their assigned grade level(s) and prompt types prior to the annual scoring period. In subsequent years, top leadership will conduct refresher sessions.

- Extensive training of raters. Raters will go through a training period where they learn to appropriately apply the rubric for each prompt, following the Smarter Balanced-provided and CDE-developed benchmark sample responses that exemplify the quality required for each score point. ETS online scoring platforms will support rater training with a full-service menu of training options, including orientation materials, program-specific information, training on how to use the platform, and interactive training that includes practice scoring for both potential and qualified raters.

- Rater Reliability

ETS will conduct a 10 percent second reads for all hand scored responses without adjudication. The second read will be used as a quality assurance measure to validate the consistency of the scoring and measure the accuracy of the scoring.

ETS’s scoring systems will capture and report the quality monitoring data that are available to scoring supervisors. These data include: the number and percent of exact matches for each rater; the number and percent of adjacent scores. ETS will confer with the CDE to outline requirements for rater reliability reports so that ETS can provide this information with the necessary level of detail. MI will transfer the quality data from their system to ETS on a daily basis for consolidation of reporting.

The scoring specifications will include the requirement to maintain an average inter-rater reliability of 70 percent or higher.

ETS considers scores captured within the distributed scoring systems to be raw scores. ETS exports these scores, once acceptable according to the California rules, to the final scoring and reporting system, which will report the scores on appropriate scale for each prompt.

- Questionable Content and Confidentiality

ETS will implement a formal process for informing the CDE when student responses reflect a possible dangerous situation for the student. For possible dangerous situations, scoring project management and staff will employ a set of Alert procedures to notify the CDE of responses indicating endangerment, abuse, or psychological and/or emotional difficulties. If a rater identifies a response which may require an Alert, then they flag or note that response as a possible Alert and transfer the image to the scoring manager. Scoring leadership will then decide if they need to forward the response to the CDE for further review and action.

ETS will provide an SFTP site to send the alerted student’s response in a unique file with student identification information to the CDE. ETS will attach a detailed description of the unusual situation to the student response. ETS will make any other adjustments to the process based on CDE-specific requirements. ETS will communicate weekly—or more often, if required—with updates on posted alert papers to CDE jurisdiction through e-mail.

- Condition Codes

ETS will assign student responses a score or a condition code according to the final set of scoring specifications developed in conjunction with the CDE. Smarter Balanced already has assigned a set of condition codes which ETS proposes to use with approval of the CDE. ETS will assign scores as requested by the CDE and include scores of zero in the computed statistics.

ETS will verify blank responses for either the multiple-choice or constructed-response items as a routine step in the scoring process. Additionally, ETS will visually check returned paper materials for any separate papers that many contain student written responses.

- Reporting

ETS’s online scoring system provides on-demand reports on scoring activities. The CDE will be able to view both aggregate scoring statistics for the entire pool of raters as well as individual raters in real time.

The scoring system offers many data elements, such as:

- total number of responses for responses read

- hourly rate of responses read

- mean score awarded overall

- percentage of scores awarded at each score point

- number and percentage of exact scores

- number and percentage of adjacent scores

- number and percentage of non-adjacent scores

- number and percentage of responses deferred

- rater performance statistics

- rater productivity metrics

- Scoring Student Responses with AI (Artificial Intelligence)

ETS will deliver AI scoring technologies that meet the demand for student reports and scoring data that is not only fast and efficient, but that also meets the rigorous standards of validity and reliability necessary for large-scale state assessments. ETS will follow the same considerations of for teacher scoring and professional development as outlined in the Scoring Plan.

The scope for both the Smarter Balanced and CA NGSS components, includes the following:

- initial AI scoring model building and evaluation for CR items or PTs

- operational deployment of AI scoring models for CR items or PTs

- periodic operational quality control for monitoring AI scoring model performance for CR items or PTs

- development of client reports that document AI model development, deployment, and performance

- Timeline for Model Building, Evaluation, and Deployment

For Smarter Balanced items, ETS will utilize AI scoring and incorporate both ETS and MI engines for scoring in a complementary fashion.

For CA NGSS items, ETS will complete the development of an initial item pool in the first year of development. A pilot test will be in the spring of 2017 and a field test for the spring of 2018. Once the data from the field test become available in the summer of 2018, ETS will conduct AI-scoring model building and evaluation during the second half of 2018.

ETS will use a broad range of evaluation criteria during model development, which consider statistical performance criteria as well as construct-representation considerations, to compare the performance of candidate models.

ETS will conduct ongoing quality-control (QC) efforts to monitor the performance of the AI scoring models during deployment. Therefore, if the structure of the student (sub-) populations and their associated performance characteristics change significantly, ETS will be able to detect and recalibrate the scoring models in time for future administrations.

- Long-term Partnership Model

ETS will consult with the CDE in the longer-term development and deployment of novel AI models. ETS will utilize existing and emerging capabilities to produce statistically reliable, substantively defensible, and practically useful automated scores for an increasing number of items over the years.

- 8.1.B. Interim Assessment Scoring

ETS will deliver the interim assessments through the same test delivery system as the summative assessments. ETS will meet all of the mandatory requirements in the same way as is done in the summative assessment.

This system will provide the same features available on the summative assessments, assuming that Smarter Balanced provides the same content supports (such as alternate language glossaries) that they will provide for the operational summative assessment.

The test delivery system has an automated routing feature which sends items that require human scoring to a designated scoring system. Local scoring occurs through the Open Source Teacher Scoring System, which routes student responses to performance items back to the local test administrator for scoring or further routing.

- Local Scoring

The test delivery system will make student performance responses available for local scoring of interim assessments. The teacher scoring system allows teachers to score any performance items requiring hand-scoring administered as part of the interim assessments, including extended responses and writing essays. Hand-scoring via the teacher scoring system differs significantly from the hand-scoring procedures described for the high-stakes summative assessments. First, those procedures route student responses randomly to trained professional raters. Second, they typically require additional read behind requirements. Third, those procedures typically route validation papers through the scoring queue to monitor scoring behavior.

Student responses for performance task items on the interim assessments will flow into the teacher scoring system in real time after a student completes and submits an online test. Scoring rubrics, exemplar responses, and anchor papers for each item will be accessible in the teacher scoring system by the teacher. In the event the teacher needs to transfer his or her queue, the teacher or a higher-level authority (such as a principal) is able to assign student responses to other raters.

Once teachers submit performance scores to the teacher scoring system, student test records will be uploaded to AIR’s test integration system, where they will be processed in real time. Uploads from the teacher scoring system to the test integration system will be regularly scheduled, within 24 hours after performance scores are submitted. The test integration system merges human scores with machine scores and sends the complete test result through the Quality Monitor (QM) system for final test scoring. Results then transfer to ETS for routing to the Smarter Balanced reporting system. The Database of Record (DoR) maintains the authoritative record of tests administered and completed.

- Training Local Raters to Score Interim Assessments

ETS will provide training materials that will guide teachers through the process, including accessing the teacher scoring system, retrieving student responses for scoring, training and refreshing on scoring rubrics and exemplar responses, and entering scores into the system for reporting.

Teachers will be able to train to use the teacher scoring system using a combination of training materials:

- a detailed user guide on the teacher scoring system that includes screenshots and step-by-step instructions on how to use the teacher scoring system, how to complete critical tasks in the teacher scoring system, and how to address common issues encountered in the system

- training and certification of LEA-based trainers in the scoring of student’s responses to constructed-response and performance task items

- User Guide for Teacher Scoring System

The purpose of the user guide for the teacher scoring system is to train users on the system functionality. ETS will work closely with the CDE to confirm that the user guide clearly explains all relevant functions. The user guide will be available in PDF format for users to retrieve from a designated location on http://www.caaspp.org/.

- Scoring Training

In addition to the user guide, ETS will develop a training presentation for teachers and schools to learn how to score students’ responses.

- Additional Training

ETS will consult with the CDE to design and implement additional training for teacher scoring. Should additional training for teacher scoring be identified beyond what has been agreed to in this SOW, ETS will provide a cost estimate to the CDE.

- 8.1.C. Cumulative Scores

ETS’s enterprise scoring platform will coordinate all scoring. The scoring platform will integrate both objective item scores and constructed-response item ratings to produce final cumulative score data, which can be scaled or converted as needed. Custom quality control processes, will be based on the Statistical Analysis System® (SAS), verify that score data meet ETS data quality requirements.

- Student Database of Record

ETS will maintain a student Oracle database that houses all student biographical, demographic, and assessment results. Will be of sufficient size and scope to accommodate the entire California suite of assessment programs. Information associated with each student has a database relationship to the LEA, school, and teacher/class codes as ETS collects the data during the operational chain of events.

Statewide Student Identification Number. ETS assumes that the CDE-issued statewide student identification (SSID) number provided in CALPADS will serve as the unique student identifier. ETS will maintain the SSID for all records produced throughout the life of the contract.

## 8.2. Analysis of Test Results

ETS will use commercially available software for all statistical analyses. In particular, ETS will use the Statistical Analysis System (SAS) to develop an open-source solution to support item analyses and DIF analyses, scoring, and any statistical and psychometric analysis for technical reports, research studies, and any data analysis based on the CDE’s requests. For IRT calibration, ETS will use a commercially available version of PARSCALE or an equivalent version (e.g. FLEXMIRT); and, if needed, ETS will use STUIRT for equating and scaling.

Final scores. The test delivery system will deliver the Smarter Balanced and newly developed computer-based assessments. The ETS scoring system will create a record for each test taker. For each test response submission, the system will receives all machine scored item scores and holds them in the record along with the number of constructed responses pending hand scoring. When the system receives constructed response scores, it will update the student record. Once both adaptive and performance task test response submissions are received and all expected constructed response scores are received, final scoring is invoked and all required test scores (overall and claims) are calculated. ETS will base all scaled scores produced on the maximum likelihood estimation (MLE) approach. Once all required scores are calculated, ETS send the scored test record to the quality validation system. Once this is complete, ETS’s Statistical Analysis Group receives a data extract to verify the scoring. ETS will sign-off on the release of scores into downstream systems.

For the paper-pencil assessments, ETS will use ETS systems for scoring and other psychometric analysis. As with computer-based assessments, once scoring and validation is complete, ETS’s Statistical Analysis Group will analyze scores and release for downstream reporting.

Routine procedures. ETS will perform data cleaning, item analyses, DIF for newly developed assessments, IRT calibration for newly developed assessments, and scaling and equating for newly developed assessments prior to producing scoring tables. For each of these steps in the process, two psychometricians and two data analysts will independently review the results using a psychometric procedure checklist. For newly developed forms, which require scaling and equating, ETS will conduct one final executive review after the psychometric and data analysis team has verified the analyses. This final review will involve the psychometric director and senior psychometric advisors, who have extensive operational and theoretical psychometric experience. They will provide an independent evaluation of the psychometric analyses and determine whether all results are technically defensible. After securing final approval in the executive review, ETS will share results with the CDE for final approval before producing the scoring tables. ETS will thoroughly review these scoring tables as a quality step before passing them on to downstream systems for scoring and reporting.

Audit procedures. ETS will use both the ETS internal audit process and detailed documentation of each assessment to evaluate the assessments and assessment system. ETS performs an audit of its testing programs at least once every three years, and ETS will report the audit results of the tests in the CAASPP to the CDE. The ETS Office of Corporate Quality Assurance (OCQA) will be responsible for conducting these audits.

Performance tracking. For each assessment, regardless of whether or not there is new test development, ETS will track performance over time, focusing specifically over the years on scaled score means, scaled score standard deviations, and percentage of students meeting each performance level both for the overall population as well as for each subgroup. In addition, within each year, in the event of an administration of multiple test forms within a grade level, ETS will evaluate whether the scores and psychometric properties (e.g. reliability) were comparable. In instances where unusual performance patterns appear, ETS will communicate these issues with the CDE and provide recommendations for resolving them.

New assessments. For assessments with new test development, ETS will develop psychometric criteria to support new test form construction based on results from field test studies or information from well-established item pools. Specifically, ETS will establish target test characteristic curves, targeted difficulty, and targeted discrimination levels in order to achieve parallel forms. In terms of the psychometric process, ETS will document all psychometric characteristics of all test forms developed. Particularly, ETS will document test form difficulty (based on IRT), characteristics of the populations when form was created and scaled (e.g. demographics, average test performance, percentage of examinees at each performance level), linking coefficients used to scale new test to base scale, and final conversion tables. ETS will compare the documentation associated with the newly developed test forms against documentation from prior versions of a particular assessment to evaluate the coherence of all forms constructed. If any new form created deviates from historical psychometric characteristics, then ETS will perform additional analyses to identify potential causes. ETS will share the results of such analyses with the CDE.

Technical report. ES will develop a technical report, summarizing the entire end-to-end process, to provide the technical evidence of the quality and overall performance of each assessment. The key components of the assessment include test design, test development and form assembly, test administration, scoring and reporting, calibration, equating and scaling, standard-setting, scoring reliability and validity, quality control procedure, and historical comparisons and special studies.

ETS will readily provide further data analyses in order to confirm the validity of test scores, federal peer review, programmatic review, program evaluation, or any additional inquiries regarding the operation of the CAASPP System.

- 8.2.A. Item Analysis

- Smarter Balanced Assessments

Analysis of the Smarter Balanced Assessment will be performed by the Smarter Balanced Consortium. ETS will fully cooperate with the development of appropriate reports, and ETS psychometricians will document relevant technical information to provide the CDE with additional information and analyses, as necessary, for the maintenance of the Smarter Balanced ELA and mathematics assessments.

- Continuing CAASPP Assessments

CAASPP involves the administration of linear forms of current paper-pencil assessments. For each item on these forms, ETS will provide the following information:

- the proportion of examinees selecting the correct response

- the IRT difficulty parameter (b)

- point-biserial and biserial correlation coefficients used to measure item discrimination

- the test characteristic curve

- the IRT item fit classification for each item

- plots of item difficulties (as measured by the b parameter) estimated in prior administrations, and the b parameter estimated in the current population

- raw score to scale score conversion tables with frequencies and the associated conditional standard errors of measurement for each raw score

- New Assessments

After ETS receives all of the student response data for the new assessments, implements scoring rules, checks the data files, and applies agreed-upon valid case criteria rules to the data, ETS will conduct item analyses. The item analyses compute important statistics for every item of the test. The statistics provide key information about the quality of each item from an empirical perspective.

ETS will perform this analysis to evaluate item difficulty, item discrimination, and student raw score performance of selected response (SR) items and hand-scored constructed response (CR) items. These analyses help identify any items that might not have performed as expected.

Summary Analyses

ETS will provide the CDE with summary analyses at the end of each test administration. The purpose of the summary analyses is to provide the CDE with a preliminary summary of the statewide test results. Typical summary analyses include percent at proficient or above, mean scale scores, and comparisons to selected LEAs. By May annually, ETS will work with the CDE to agree upon the summary analyses that will be provided.

- 8.2.B. Summary Analysis

ETS will produce analyses that provide summary evidence of test score accuracy and validity. Both during and after completion of the item analyses, ETS will conduct analyses specific to summarizing the performance of the students taking each assessment and the psychometric qualities of each assessment.

The CAASPP System includes both online and paper-pencil assessments, as well as both linear assessments and computer adaptive assessments. For all assessments, ETS will provide distributions of tests scores by grade and subgroup within grade, descriptive statistics concerning test scores, and where applicable, descriptive statics for performance task scores and subscores where possible. In addition, for each assessment ETS will provide the test characteristic curve, the overall test score reliability, overall and conditional standard errors of measurement, and, where applicable, decision accuracy and decision consistency estimates. At the item level, ETS will summarize item difficulty and item discrimination measures for both CR and SR item types. For online assessments ETS will also provide the distribution of the time to complete the assessment, as well as descriptive statistics summarizing the time to complete the assessment. For tests that may have variable-length assessments ETS will provide the distribution of the number of items administered, as well as descriptive statistics summarizing the number of items administered to each student. For CR items ETS will summarize reader reliability information and provide information concerning the degree of relationship among CR items and, where applicable, the relationship between CR and SR scores.

- Continuing CAASPP Paper-Pencil Summative Assessments

As part of the CAASPP System, ETS will administer current paper-pencil assessments for the CAPA for Science, CST for Science, CMA for Science, and STS for Reading/Language Arts. ETS will conduct analyses for the populations of students who take each form at both the item and the test level, and will summarize them in CDE technical reports.

For the population of students who take selected-response tests, ETS will first conduct an item analysis estimating the percentage correct and the biserial and point biserial correlations. For constructed-response test items, ETS will first conduct item analyses estimating the average item scores and the polyserial correlations, and ETS will examine the frequency distribution for each item. ETS will review items flagged for extreme difficulty or low item discrimination for inclusion in scoring. Because ETS will not develop new items to support the existing tests, there will be no need to perform DIF analyses or item model fit, as the items have already undergone review. At the test level, ETS will determine the overall internal consistency reliability of the test and the overall standard error of measurement, and ETS will provide conditional standard errors of measurement. In addition, ETS will also examine the internal consistency reliability estimates for various subgroups of the student population. ETS will also provide decision classification information for score classifications.

For all intact forms without any edits or replacement of items, ETS will apply the conversion tables from the previous administration to the current administration. If new or edited items are used or removed as the result of an item security breach, then ETS will generate conversion tables using the true-score equating through the Rasch model. The item parameters used for true-score equating are post-equated item parameters from the intact forms for the unchanged items and the post-equated item parameters from the most recent administration for the replacement or edited items.

Summary analyses will include overall distributions of test scores, as well as distributions by grade level and by subgroups. These tables will group students by demographic characteristics such as gender, ethnicity, English-language fluency, need for special education services, and economic status. For each demographic group, the tables will show the numbers of valid cases, scale score means, standard deviations, minimums, maximums, and the percentages of students in each performance level.

#### Smarter Balanced

- ETS assumes that the CDE will rely on the analyses conducted by Smarter Balanced/UCLA for the Smarter Balanced summative assessments and no additional activities will be planned for the analysis of Smarter Balanced data except for the purposes of special studies approved by the CDE.

- New Non-Smarter Balanced Online Summative Assessments

If the new online CAASPP assessments are linear forms, ETS will utilize a multi-stage adaptive testing (MST) model (or an item-level adaptive), or begin with a linear assessment and morph to a MST model (or item level adaptive).

Regardless of whether ETS implements a linear test, item-level adaptive, or MST, ETS will provide distributions of tests scores by grade and subgroup within grade and descriptive statistics concerning test scores. These tables will group students by demographic characteristics such as gender, ethnicity, English-language fluency, need for special education services, and economic status. For each demographic group, the tables will show the numbers of valid cases, scale score means, standard deviations, minimums, maximums, and the percentages of students in each performance level.

ETS will provide the test characteristic curve, the overall test score reliability, and overall and conditional standard errors of measurement (CSEM). At the item level, ETS will summarize item difficulty and item discrimination measures for both CR and SR item types. The estimation procedures used for statistics such as CSEM will depend on whether the assessment uses a linear, item-level adaptive or a MST design. ETS will also provide the distribution of the time to complete the assessment, as well as descriptive statistics summarizing the time to complete the assessment. If the assessments follow the MST model and the results have variable-length assessment, ETS will provide the distribution of the number of items administered, as well as descriptive statistics summarizing the number of items administered to each student. For SR items, ETS will summarize reader reliability information and provide information concerning the degree of relationship among CR items. For an MST, ETS would provide routing rates, ranges of scores for each route, and IRT parameter levels by each route.

ETS will conduct DIF analyses as part of the item development process in which the items are identified as potentially biased in the item bank as not ready for operational use.

If ETS uses an MST, ETS will conduct extensive monitoring and quality control analyses. ETS will concentrate on the characteristics of the MST panels developed to measure whether earlier panels obtained similar measurement outcomes and whether ETS should adjust to the initial assembly configuration implemented to optimize the routing rates.

- 8.2.C. Replication of Analyses

ETS will work with the CDE and the external evaluator to determine the format and the layout of the student-level data files; and will have psychometricians, data analysts, assessment developers, and IT professionals available to answer questions on the statistical and content properties of the items as well as any technical questions concerning the data structure.

The student data for replication will provide all student demographic information, including level of student support or accommodation. ETS will provide all test level scores, including raw scores, cluster scores claim level scores, and all scaled scores. The student-level data file will also contain all item responses for selected-response items, all scores for performance task items, and all associated item identifications. In addition, ETS will provide the latency between items and the time to answer each item.

ETS will supply the CDE and to the external evaluator with the entire vector of student-level information for each student, including identification of any accommodations the student used. If there is any information that the CDE believes is not necessary in the replication of item statistics and test characteristics, ETS will create and send an abridged file to the CDE and the external evaluator. In addition, should the CDE require additional documentation to assist in replications, then ETS will provide any supplementation information needed.

- Interim Assessment Analyses

When final claim and test level scores are available, ETS will receive the interim assessment results for both the Interim Comprehensive Assessments (ICAs) and the Interim Assessment Blocks (IABs). When the last LEA completes summative testing, ETS will produce a complete electronic file containing interim assessment information for all those who took an interim assessment. This file will contain student identifiers, student test scores on the interim (not reported to the CDE) and summative assessments, school information, testing dates, and student demographics. As a result, ETS will be able to provide the CDE with a comprehensive report documenting the usage of the computer-based, interim assessments.

The report will include:

- Overall utilization rates by grade and subject

- Overall utilization rates by subject and grade by LEA and school

- Tables providing interim assessment usage over the course of the school year

These tables will also include summary statistics on how many times students took each assessment.

# TASK 9: Reporting

ETS will deliver a full range of reports and reporting formats that the CDE requires for the CAASPP System, which will include merging results from both paper‐pencil formats and computer‐based tests. ETS will provide reports in both formats and ETS will confirm security, confidentiality, and ease of use for CDE‐approved users. This Online Reporting System is the same system that was using for the 2015 CAASPP administration. ETS will continue to improve the reporting system in 2016, based on user feedback in 2015.

## 9.1. Reporting to Local Educational Agencies

ETS will implement a comprehensive and secure online reporting system for interactive reporting that allows users to create customized reports to display data at the state, county, LEA, school, and student level.

ETS will delivers reports in both PDF and Microsoft Excel (CSV) formats for convenience and flexibility in printing and sharing. ETS will send documents to e-mail addresses as determined by the LEA CAASPP Coordinator or the CDE.

ETS will consult with the CDE on the expansion of these reports to support additional summative, interim, and formative reporting needs. Initially the system will report test results only for the Smarter Balanced and non-Smarter Balanced summative assessments. Reports for the interim assessments will occur through the Smarter Balanced Data Warehouse.

#### Requirements for Reporting to LEAs

ETS will follow the reporting requirements as outlined in Education Code Section 60643. ETS’s system for reporting results to LEAs will include the following features:

- integration of student demographic data from CALPADS with student test results from the assessments

- real-time online completion reports for students taking the computer-based summative assessments, with completion reports available at the school and LEA level

- online student rosters with test results by grade level for each school and LEA, where the LEA may print or download student rosters locally through the reporting system

- online individual student results for all CAASPP assessments that the LEA may print or download locally

Table 17 below describes the test results provided to LEAs by type of report, test, timeframe, and mode of delivery.

Table 17.  CAASPP Test Results Provided to LEAs

| Type of Report | Tests/Content | When | Who |
| --- | --- | --- | --- |
| The individual student results for a content area | Computer-based assessments (both Smarter Balanced and non-Smarter Balanced) | Two to three (2-3) weeks after the student has completed all components of the assessment for that content area and scores are merged. | LEA and Site Coordinators, teachers have access through TOMS |
| Individual student results | CAASPP paper-pencil tests (e.g., CST/CMA/CAPA Science and STS RLA) and for the new CAASPP assessments that have paper-pencil versions | Within six (6) weeks after our scoring center receives a complete, clean set of answer documents for processing and scoring | LEA and Site Coordinators, teachers have access through TOMS |
| Individual student results | Smarter Balanced paper-pencil assessments | Within six (6) weeks after our scoring center receives a complete, clean set of answer documents for processing and scoring and after receipt of the Smarter Balanced score keys and conversion tables. | LEA and Site Coordinators, teachers have access through TOMS |
| Online aggregate reports of test results | All assessments results summaries by subgroups | Aggregate results for a school available when at least 90 percent of the students in the school have completed testing. This will be done by content area. The same will apply to results aggregated for an LEA. Results for some schools in an LEA may available before results for that LEA meets the 90 percent level. | LEA and Site Coordinators, teachers have access through TOMS |
| LEA created aggregate reports, based on the data available and as CDE allows. | All assessments | Aggregate results for a school available when at least 90 percent of the students in the school have completed testing. This will be done by content area. The same will apply to results aggregated for an LEA. Results for some schools in an LEA may available before results for that LEA meets the 90 percent level. | LEA and Site Coordinators, teachers have access through TOMS |
| ISR in electronic format online individual student results for all CAASPP assessments that the LEA may print or download locally | Computer-based assessments (both Smarter Balanced and non-Smarter Balanced), | Within four (4) weeks | LEA and Site Coordinators have access through TOMS |
| Paper ISR | All assessments | Within five (5) weeks after test results for all content areas are available for the given LEA. | LEAs will receive two (2) copies of each ISR |
| Downloadable Data File | All assessments | Within five (5) weeks after test results for all content areas are available for the given LEA. | LEA and Site Coordinators have access through TOMS |
| ETS Data Manager | All assessments through a dynamic, interactive data tool that offers the ability to access data through pre-developed report templates and an environment for the creation of custom reports | Starting in 2016 | CDE and LEA users, if approved by CDE |

#### Individual Student Reports (ISR) in Paper Format Delivered to LEAs

  - The ISR will include test results of all CAASPP assessments that a student took. For example, an 8th grader will have taken the Smarter Balanced summative assessments in ELA and mathematics, as well as the CST or CMA Science assessment.

  - The student’s ISR will include results from all three assessments on a single ISR. ETS assumes that the ISR is a single-page report with dynamic text options and the student test results printed on one side with CAASPP and EAP information printed on the other side.

  - ETS will provide an option for an ISR to be reproduced in Spanish if an LEA marks in TOMS that the student comes from a Spanish-speaking home

  - ETS will provide an option for an ISR opt out  for an English ISR if an LEA marks in TOMS that the student comes from a Spanish-speaking home

  - In addition, to help parents/guardians understand the ISR, ETS will develop and post a printable PDF of the ISR interpretation guide. The interpretation guide will describe the key elements of the ISR. ETS will post it and a Spanish translation to http://www.caaspp.org/ for LEAs to print.

LEAs will log into the reporting system through the TOMS component of the CAASPP Assessment Delivery System, which employs a single sign on solution. In addition, for the Smarter Balanced interim test results, ETS will deliver the data files annually to Smarter Balanced so that the results are included in the Smarter Balanced Data Warehouse and Reporting systems. LEAs will be able to access the Smarter Balanced systems by logging into TOMS via the single sign on access.

ETS will deliver California’s Smarter Balanced data to the Smarter Balanced Data Warehouse on a schedule agreed upon by the CDE and ETS. The data will be in the format specified by Smarter Balanced.

##### Online Reporting System

###### LEA Access to the Online Reporting System

Similar to the security protocol for TOMS and the test delivery system components, LEAs will access the reporting features based on the level of access in their roles. The hierarchy operates so that a user has access to reports for their role level and all levels below.

- CDE-assigned staff can view the test result reports within the state.

- An LEA user can view test result reports within their LEA drill‐downs to school- and student‐level reports.

- School administrators can view test result reports within their school.

California users will have access to ETS’s report portal 24 hours a day, seven days a week. After completing scoring procedures for summative assessments, ETS’s system will promptly provide data for static and dynamic reports.

###### Report Types

Based on the Smarter Balanced reporting requirements for mathematics and ELA, the summative reports will contain information outlining student knowledge and skills as well as achievement levels aligned to the assessment-specific claims as defined by Smarter Balanced and as adopted and adapted by the California State Board of Education (SBE). These reports define and present test scores for users in multiple ways. The online reports offer drill-down functionality — from the overall claim to the content claim — at the state, county, LEA, school, and student levels. The individual student report outlines student performance on the Smarter Balanced summative assessments in a static version supported by extensive text.

For the non-Smarter Balanced computer-based assessments that will be operational during the initial contract period (i.e., alternate assessments for ELA and mathematics), the summative reports will contain information outlining student knowledge and skills as well as SBE-adopted achievement levels. ETS’s reporting system is capable of expanding to include new CAASPP computer-based assessments as they are implemented.

ETS’s interactive reporting suite will produce customized reports showing preliminary individual and group-level results for online assessments. These reports are real-time and cumulative, and provide student listings with relevant score measures.

ETS’s reporting solution provides static reports, while supporting user-specific needs with a report builder. Static reports include scaled-score distribution, performance-level distribution, standard- and indicator-level performance, claim level, and target information based on user permissions.

By default, the filtering variables will align with CDE-outlined student demographic variables while taking into account the Smarter Balanced requirements. The CDE will have the opportunity to outline access rules and functionality as well as variable availability and labeling.

##### Additional Information about Report Distribution

###### Electronic Test Results

The aggregate and results for the Smarter Balanced Summative Assessments, CAA, CST/CMA/CAPA Sciences, and STS RLA will be provided as electronic reports via TOMS.

All Interim reports will be available via the Smarter Balanced Reporting System.

###### Paper ISRs

Test results provided on the ISR will include scale scores, performance levels, and, where available, performance by claim or reporting cluster.

For ease of handling by the LEAs, the ISR will be printed on a single sheet of 8.5 inch x 11 inch paper. The student address will be on the left side of the report to accommodate the use of left-windowed envelopes by LEAs. A POSTNET barcode will appear above the student address; the barcode will allow LEAs to qualify for postage lower rates and take advantage of faster, more efficient mail processing.

ETS will provide two color copies of each student’s ISR to the student’s LEA. One copy will be packaged for the LEA and the second copy will be packaged for the school at which the student was tested. Color schemes will be chosen so that the LEA report can be easily photocopied as a black-and-white copy.

Additional information on the test results may be available on the online reporting system. ETS will propose ISR formats and additional online information for the CDE’s consideration and approval.

Printing

When ETS prints paper ISRs, ETS will:

- Print each page as original, thus producing easy-to-read reports that do not smudge; and

- Utilize a sophisticated report collation process combined with high-speed laser printing technologies to print all report types in continuous print streams.

Packaging

Each shipment of reports for schools, LEAs, and counties will include a specific letter enclosed with the package describing what they are receiving in their shipment. All reports will be assembled by grade, school, and LEA. School sets of reports will be assembled and shipped to the LEA for distribution to schools.

The following packaging processes will be employed to provide LEAs with clearly organized shipments:

- All reports will be assembled and placed in report folders. One color of folder will be used for LEA reports; another color will be used for school reports. The ISRs will be grouped in accordance with the information provided on the packing list and placed in folders.

- Reports will be boxed and labeled by school, with the boxes for all schools within each LEA shipped to the LEA CAASPP Coordinator for distribution. The LEA reports will be boxed separately.

- Enclosed in each shipment of reports will be a specific letter describing what the LEA is receiving in the shipment.

- A pallet map will be included with each report shipment for LEAs that receive more than one pallet of reports.

- Prior to shipment, quality control specialists will perform a final quality check of reports and check for complete units of work, correct assembly, and the correct use of mailing labels.

Delivery

ETS and its subcontractors will work with the CDE to design reports and reporting systems that provide accurate results to all stakeholders in a timely manner.

ETS will distribute all paper reports so that LEAs receive them according to the approved timeline. For those LEAs that test grade levels in multiple testing windows/ administrations, they will receive ISRs as processing and scoring is completed for each test administration.

Box 1 of each LEA shipment, which contains the letter explaining what is included in the shipment, will be white, so it will be easy for the LEA CAASPP Coordinator to distinguish this box from other boxes in the shipment.

Trained shipping personnel will determine the most reliable and rapid means of delivering each shipment of reports. Each LEA’s reports will be entered in the shipping manifest system as they are shipped. ETS’s barcode technology, combined with distribution partners’ (UPS, for example) tracking systems, will allow ETS to provide instant updates about the location and status of report packages should any problems arise. Upon receipt of reports at the LEA, LEA personnel signatures will be required to provide for secure delivery.

ETS will track where a LEA is at a given point in the reporting process and will provide the following status information to the CDE during the weekly management meetings: Reports printed, Reports shipped, and LEA complete.

##### Correcting Errors Due to Changes to the Data

Anytime there are changes to the data that require reports to be reprinted, CalTAC staff will contact Publications to print and ship revised reports. All of the reports will be clearly identified as “revised” with the appropriate revision date.

In any such event, ETS staff will take the following steps:

- Initially analyze the situation;

- Inform the CDE immediately;

- Further analyze the impact of the error;

- Discuss solution options with the CDE; and

- Deliver an expedient resolution that best mitigates program risk.

##### Correcting Demographic and Special Testing Conditions Data

Since CALPADS is the source of record for student demographic data, LEAs will be instructed to make demographic data corrections in CALPADS. The corrected demographic data will be uploaded to the online reporting system through the process established and described in Test Administration.

LEAs will be instructed to use TOMS to make corrections to special testing conditions information and other test-specific data that may be correctable, such as parent exemptions or accommodations used by the student.

All corrections should be submitted by the LEA on or before the end of their test administration window. There will be no cost to LEAs for making either demographic data corrections or changes to other testing condition information that may be correctable. If the LEA makes corrections after the end of its test administration window, the corrections may not be received in time to be reflected in the LEA’s aggregate and student reports.

##### Rescore Requests for Paper-Pencil Tests and for Responses That Were Hand Scored

ETS will establish a process by which an LEA may request that a student’s test be rescored as a fee-based ancillary service paid by the LEA. ETS will provide a price list for ancillary services to the CDE for review and approval. Rescore requests will be restricted to the paper-pencil tests that have bearing on Federal or state accountability and to responses to Smarter Balanced Summative Assessments that were hand scored. Rescoring will not be available for the CAPA Science and the CAAs, since the answer documents are completed by the examiner; or for the STS RLA tests, since these tests are not part of accountability.

ETS scoring experts will review each original student response in question along with the original score assigned. For responses that were hand scored by human raters, the original score assigned to the student response will be reviewed in close comparison to the original anchor papers used in training. If ETS’s scoring experts determine that the original score assigned was incorrect, a new score will be issued.

ETS will work with the CDE to establish criteria by which LEAs may request rescoring and to determine the fee for rescore requests.

## 9.2. Reporting to the CDE—Public Reporting Web Site

ETS will design and develop, utilizing responsive Web design, an updated CAASPP results reporting Web site that the CDE can host. Development will follow ETS software development standards, as described in Task 3, while also adhering to the CDE Web Application Development Standards and CDE Web Standards. ETS’s design staff will consult with the CDE to document detailed requirements for aggregation of the data per EC Section 60641, as well as display of the data in the Web reporting site. ETS will supply installation documentation and functional requirements to the CDE. Table 18 shows the results that will appear on this Web site.

Table 18.  CAASPP Test Results Provided to the Public

| Type of Report | Tests | Content | When |
| --- | --- | --- | --- |
| Web site hosted by CDE | Smarter Balanced summative and non-Smarter Balanced online summative assessments | Aggregate results at school, grade, LEA, county, and state levels and will allow for selection of further breakdowns based on the required demographic data (e.g. race, English language proficiency, gender, ethnicity) identified by the CDE. The application will also allow for comparison of multiple schools or LEAs and will incorporate a data-visualization design approach. | August annually, to be determined by CDE |
| Web site hosted by CDE | CAASPP paper-pencil tests (e.g., CST/CMA/CAPA Science and STS RLA) and for the new CAASPP assessments that have paper-pencil versions | Aggregate results at school, grade, LEA, county, and state levels and will allow for selection of further breakdowns based on the required demographic data (e.g. race, English language proficiency, gender, ethnicity) identified by the CDE. | August annually, to be determined by CDE |

ETS will deliver the CAASPP reporting data to the CDE in coordination with the calculation for Federal and state accountability programs.

ETS will protect the platform or application itself by user authentication during the “LEA preview period” prior to being publically available.

ETS will put in place quality controls of the application and the data displayed. Also, ETS will test software developed by ETS for quality and performance, and the CDE will also have user acceptance signoff. ETS’s Data Quality group (DQS) and statistical analysis department will review aggregate data files for accuracy. Additionally, ETS will install data files into ETS’s user acceptance testing environment to confirm that ETS completes the data load without error. ETS will turn over data files and application code to the CDE per an agreed-upon schedule.

To protect student privacy, the Web reporting site will implement the CDE-required suppression rules. ETS will use an asterisk or similar mark to suppress data where someone could ascertain a student’s identity. For example, if a grade includes 10 or fewer students, an asterisk or similar will appear in the reporting rows to indicate that the data were suppressed.

To speed delivery of Web pages during times of peak demand or when the site is performing sub-optimally, ETS will support static versions of all the Web pages. Since the Web reporting site will reside on the CDE servers, the CDE will monitor Web site performance. ETS will provide technical support to the CDE Technology Services Division as needed to optimize the Web reporting site.

##### Requirements for the Reporting Web Site

ETS will work with the CDE and the SBE on the timeline for the delivery of the Reporting Web site. For planning purposes, ETS will assume that the CDE will publicly release statewide test results in late summer, annually. To accomplish this, only those test materials that are received by the scoring center before July 1, annually, will be included in the state’s initial release.

ETS will work with the CDE to comply with the CDE’s Web standards. The CDE will continue to host the Reporting Web site.

To speed delivery of Web pages during times of peak demand or when the site is performing sub-optimally, static versions of all the Web pages are also supported. ETS will monitor Web site performance and work with the CDE to assure that the site meets performance specifications.

The design of the Reporting Web site will be data driven so the user can very efficiently select particular parameters to see the desired reporting of results. The design will be a scalable design to accommodate additional servers. The database will use MS-SQL Server technology. While there are many combinations of summary reports that will be accessible, the summary data will be pre-calculated. While this may limit the dynamic nature of the site, it will prevent inappropriate summaries that could lead to inappropriate interpretation of results by users.

The software application behind the Reporting Web site will allow the site administrator to load new iterations of data into the database and to generate new research files based on the refreshed data. As the data are refreshed, notes added by the CDE from the previous iteration will be preserved.

Summaries by counties, LEAs, schools, and the state will be provided. The site will support all CAASPP assessments—Smarter Balanced Summative Assessments, the CSTs, CMA, CAA, and STS.

##### Student Privacy

ETS will deliver the Reporting Web site in accordance with these requirements:

- Use of an asterisk to suppress data where a student’s identity could be ascertained

- Reporting of all performance levels and a combined proficiency level which totals the sum of the proficient and above

- Allowance for the selective inclusion of either all available performance levels or the combined proficiency level on Web pages

##### Delivery of Aggregate Summary Data Files That Are Synchronous with the Delivery of the Student Data Files

The Web site will provide for aggregate summary data files that are synchronous with the delivery of the student data files. These aggregate summary data files include aggregations by schools, LEAs, counties, and the state. Independent charters are represented as separate LEAs within a county. The summaries will also be compiled by individual assessment and by grade within each assessment. They will include statistical data for the various assessments reflecting performance levels, quarters, or CAPA levels. These data will include the number of test takers, the average scale score, and derived scores as appropriate.

##### Requirements for the Aggregate Summary Data

ETS will deliver report pages and research files that include aggregate summary data. The summary data and the Web site will support the reporting by claim or cluster. This claim/cluster reporting will include such information as average percent correct and mean-scale score reported by grade (or by course for non-grade specific courses). ETS will work with the CDE to define this new requirement more precisely in order to optimize value to the CAASPP assessment system constituencies.

##### Summary Data

ETS will work with the CDE annually to determine the subgroup categories to be supported by the Reporting Web site

ETS will include the ethnicity by economic status data in the CAASPP Summary Data submitted to CDE for Web reporting purposes. For Web reporting purposes, the ethnicity subgroups will include: African American or Black, American Indian or Alaskan Native, Asian, Filipino, Hispanic or Latino, Pacific Islander, and White. Economic Status analysis will include Economically Disadvantaged and Not Economically Disadvantaged. ETS will work with the CDE to incorporate changes to the required subgroup reporting categories.

##### Research Files

The Web reporting application supports the following research file requirements:

- State-level research file that contains all county, LEA, and school results for all demographic subgroups

- State-level research file that contains all county, LEA, and school results for the “all students” demographic subgroup

- State-level–only research file that contains results for all demographic subgroups

- Limited research files that contain all data for selected counties, LEAs and schools

- Research files containing all assessment data

- A research file containing all reporting claim or reporting cluster results data

- Suppression of results where the reported group totals 10 or fewer students or where the number of student reports in any individual cell may allow identification of an individual student

- Compressed (zipped) research files formatted as fixed-length ASCII and comma-delimited (including column names) files

- An Access 2003 (or a more recent version of Access) database shell that can be used to import comma-delimited research files along with all instructions for use of the database shell

- A load utility that will facilitate the easy importation of comma-delimited research files into the database shell

##### Administrative Functionality

ETS will incorporate extensive administrative functionality into the Internet design to include:

- Notes. Allow for the inclusion of “notes” that may be dynamically added to any selected report page. For example, notes may be added to one or all schools in a LEA and to one or all of the subgroups. Notes must be capable of being retained when report data are updated.

- Embargo Reports. Allow for the selected exclusion of Internet report pages. For example, all reporting claim reports may be excluded, or a report page may be embargoed for subgroup reports at the school level while the combined proficiency report (combined total of proficient and above students) is accessible. In addition, all state reports are embargoed until the site is opened to the public.

- Research File Generation. Allow for the generation of new research files when new aggregate data are loaded to the site. Which files are generated and the sequence of that generation must be part of the research-file generation function.

##### CDE Web Delivery Requirements

The key to successful deliveries of the Web reporting application and data files is to plan for preliminary iterations. This strategy allows CDE data management staff to be involved in early review of the site and the data. By delivering early, issues are identified and remedied earlier, before the critical public deadlines.

Annually, ETS will propose a timeline for site development and data deliverables for CDE approval.

## 9.3. Data Files

ETS will maintain a student database to house all student demographic data and assessment results. This database will accommodate millions of records of the size and scope of the CAASPP System. Information associated with each student has a database relationship to the LEA, school, and grade codes as data are collected during the operational chain of events. Integral to this database is the maintenance of a student identification system, which confirms that each student is uniquely identified within the test delivery system so all assessment information can easily be associated with that student. ETS assumes that the CDE-issued statewide student identification (SSID) number provided in CALPADS will serve as the unique student identifier. ETS will maintain the SSID for all records produced throughout the life of the incumbent contract.

ETS recognizes that CALPADS is the state database of record for managing and maintaining the longitudinal student data. The scoring capabilities and procedures described in Task 8 outline ETS’s robust process for both scannable answer documents and assessments delivered online. ETS’s scoring process will utilize the SSID number to provide the linkage information that maps directly to the database. Whether a student uses a pre-ID label or a pre-printed answer document, receives a unique login user ID and password, or takes multiple modes of assessments — each of the delivery modes will direct the resulting data for that student to a central repository for scoring and reporting.

ETS will deliver student data files and corresponding aggregate files on the delivery schedule agreed upon with the CDE. ETS recognizes that delivery dates will be dependent on the requirements for the state and federal accountability programs.

ETS will prepare the data in a format that the CDE can access. Due to the large numbers of records produced for CAASPP annually, ETS will deliver fixed record-length data files. ETS will consult with the CDE to determine if data delivery in a different format (e.g., XML file or delimited file), is necessary.

ETS will deliver student data files in three formats:

- compressed layout with demographic information only

- a layout with item response data and demographic information

- a file that contains all student data available

ETS’s systems will maintain two types of files for CAASPP: a complete student response file for each CAASPP test administration, and a history file for all students who have participated in CAASPP testing. ETS will maintain a cumulative repository of individual test results for all students who have participated in CAASPP testing. The history file will include student-identification and performance data, as specified by the CDE, as well as other information necessary for merging with files of any other test administration in which the student participated. The CAASPP history will allow the tracking of previous test administrations for individual students. The history file will maintain compatibility with files developed under previous contracts and with files developed by contractors awarded contracts under the terms of this SOW.

## 9.4. Secure File Transfer System

Due to the confidential nature of test results, ETS uses secure file transfer protocol (SFTP) and encryption for all student data files. SFTP offers an efficient mechanism for transferring large-scale data. In addition, ETS uses .ZIP archive file format technology to reduce the disk space requirements on all files. This method applies to all data file transfers.

ETS supports most secure transfer protocols, including Web-service-based technologies, to exchange data with clients and file-based transfers using Tumbleweed® Communications Corp., a provider of security solutions. This enables ETS to effectively manage and protect business-critical Internet communications. These processes allow simplified data exchanges with secure and easy-to-use architecture, which provides management of files and large documents over the Internet. One standard, easy-to-use mechanism is an SFTP.

As a part of implementation, ETS will establish an SFTP service which will manage SFTP transfers to a directory structure between ETS and the CDE. Gatekeepers, generally one in California and one at ETS, will determine access privileges. The ETS gatekeeper will be responsible for approving all users for access.

ETS will provide all interfaces with the most stringent security considerations in mind, including interfaces for data encryption at rest and in transit for databases that store test items and student data. Encryption at rest primarily applies to any data files that reside on a server that uses the SFTP waiting to be retrieved. ETS integrates best security practices, including system-to-system authentication and authorization, in ETS’s solution design. These practices meet the Federal Information Processing Standard Publication 140-2 (FIPS PUB 140-2) issued by the National Institute of Standards and Technology (NIST). All CAASPP data will remain within the continental United States, as the CDE requires.

## 9.5. Technical Report

ETS will consult with the CDE and recommend suggestions in organization, style, and specificity that would improve the readability and overall usefulness of technical reports. Furthermore, ETS will partner with the CDE to determine what standard elements of the technical report overlap with the elements supplied by Smarter Balanced and need not be a part of the reports for CAASPP. ETS will confirm that generated reports include what is necessary for the CDE and the corresponding Technical Advisory Committees in producing the final versions of the technical reports.

ETS will produce a technical report for each administered summative assessment, including pilot or field test assessments. Table 19 below lists the planned technical reports for each administration.

Table 19.  Planned CAASPP Technical Report by Administration

|  | 2016 Administration | 2017 Administration | 2018 Administration |
| --- | --- | --- | --- |
| Smarter Balanced for ELA and Mathematics |  |  |  |
| CST for Science |  |  | Not Applicable |
| CMA for Science |  |  | Not Applicable |
| CAPA for Science |  |  | Not Applicable |
| STS RLA |  |  | Not Applicable |
| Alternate Assessments for ELA and Mathematics |  |  |  |
| CA NGSS (General Assessment) | Not Applicable |  for the Pilot Test |  for the Field Test |
| CA NGSS Alternate Assessment | Not Applicable |  for the Pilot Test |  for the Field Test |
| Primary Language | Not Applicable |  for the Pilot Test |  for the Field Test |

For the Smarter Balanced technical report, unless critically important to the narrative, ETS will not duplicate requirements already supplied by the Smarter Balanced consortium.

ETS will deliver drafts of the technical manuals by November 1st annually and at the end of the contract. The following bullets outline the proposed organization of the technical reports. ETS will work with the CDE to determine any additional chapters or analyses as needed.

- Executive Summary. This summary section can stand alone for public distribution, and ETS will write it for an informed lay audience (e.g., school principals). It will highlight key findings from each chapter of the technical report.

- Chapter 1. Introduction. This chapter provides an introduction to the technical manual, gives the purposes of the assessment, and describes the uses of the assessment information.

- Chapter 2. Overview of the Assessment. This chapter describes the item formats and item specifications, as well as test assembly, test administration, scoring, and an equating overview.

- Chapter 3. Item Development. This chapter describes the procedures followed during item development. For the Smarter Balanced assessments, only a very brief overview of the process will be included, as ETS expects that the Smarter Balanced consortium will include a thorough discussion in their report.

- Chapter 4. Test Assembly. This chapter provides a description of the content being measured and detailed descriptions of how the content is being measured (i.e., test blueprints). This chapter provides a rationale for how blueprints were constructed and the construct being measured. For the Smarter Balanced assessments, only a very brief overview of the process will be included.

- Chapter 5. Test Administration. This chapter details the processes involved in the actual administration with emphasis on efforts made to confirm standardization of the tests. It also details procedures to confirm test security.

- Chapter 6. Performance Standards. This section will overview the cutpoint validation and the standard setting methodologies and describe the process conducted to establish cut scores for the assessments based on their first operational administration. For the Smarter Balanced assessments, this section will link to the report supplied by the Smarter Balanced consortium.

- Chapter 7. Scoring. This chapter provides information on the scoring processes and describes the types of scores and score reports produced at the end of each administration. The section will include scale score distribution tables and demographic summaries, as well as summary reports of how the automated scoring systems performed.

- Chapter 8. Psychometric Analyses. This chapter provides detailed information on the psychometric analyses of the operational test data. It presents and describes the results of the item and test analyses, differential item functioning results, calibration and scaling process, linking and equating methods, and deriving scale scores. It includes explanations for all statistical procedures implemented during the psychometric analyses; interpretations of the data and the analyses; and IRT analyses, standard errors of measurement, and reliability estimates (including for subgroups). For the Smarter Balanced assessments, ETS will base the statistics only on students from California.

- Chapter 9. Quality Control Procedures. This chapter describes quality control procedures of various aspects of the testing process — from control of item development, to scoring procedures and psychometric processes, to score reporting.

- Chapter 10. Historical Results. This chapter provides yearly results for each assessment, at both the item and test levels. ETS will maintain longitudinal results in this chapter.

ETS will provide the CDE sufficient time to review each technical report and verify the accuracy of analyses. ETS will provide at least 20 business days for the CDE to review the first drafts and 10 business days for the CDE to review the revised draft. ETS scheduled five business days for the CDE review of the final draft.

ETS will deliver five bound copies of the each final technical report. In addition, ETS will deliver electronic formats of each technical report — in Microsoft Word, PDF, and HTML — that will meet the CDE's Web accessibility requirements, and ETS will deliver the tables included in the technical reports as Microsoft Excel files.

## 9.6. Other Analyses or Reports

ETS will partner with the CDE and SBE staff/liaisons to identify and expand on research questions and develop instruments for CDE’s approval. Together, ETS will make recommendations for all data collection instruments, such as interview protocols, observation protocols, surveys, and cognitive labs. ETS will then deliver the instruments within the test delivery system in order to link responses to student performance and student demographic data from CALPADS.

Studies to be included are:

- Analytic research on the impact of AI scoring at the sub-group level to determine if any group is disadvantaged by the new technology.

- Statistical analysis of the necessary N size and aggregation of sub-claim score for assessments at the LEA level.

- Efficacy or impact of extended response items types as a tool to provide professional development in both summative scoring modality and various interim scoring situations.

- Effect(s) of any universal tools, designated supports, and/or accommodations used by students (particularly students with disabilities and English learners) on the CAA.

Once each year during the term of the contract with the CDE, ETS will propose additional studies and analyses to support the validity of the CAASPP program, evaluate new initiatives, or address relevant policy issues. ETS will recommend additional studies either proactively or upon request. ETS will work with the CDE to support the technical quality of the CAASPP System, which includes validity, reliability, fairness and accessibility, and comparability.

A global view of the process would be that ETS and the CDE and SBE staff and liaisons would meet at least once a year to discuss special studies. Should CDE request any special studies, ETS will meet with researchers who have specific expertise in the study area requested. ETS would present the research study plans, along with a statement of cost, to the CDE. Together, the CDE, SBE staff and liaisons, and ETS staff would discuss the specific plans and make necessary modifications before agreeing on final costs. All special studies and research will adhere to the requirements outlined in Appendix B, Reporting Expectations for Special Studies and Research Projects.

# Appendix A—Sample Program Schedule

The program schedule is a living document. The program schedule included in this appendix is a sample for planning purposes only. ETS will present a revised schedule to the CDE prior to the Orientation Meeting. ETS will present a proposed schedule each year prior to the Annual Planning Meeting. At minimum, the agreed upon schedule will be reviewed with the CDE during the Weekly Management Meetings, and more often as determined by the needs of the program.

| ID | Task Name | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- |
| 1 | Contract Begins | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 2 | Administration Year One (July 2015 - December 2016) | 897 days | Wed 7/1/15 | Fri 12/28/18 |  |
| 3 | Begin administration year one | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 4 | Project Management | 277 days | Wed 7/1/15 | Fri 8/5/16 |  |
| 5 | Project Management Begins | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 6 | Orientation Meeting | 14 days | Wed 7/1/15 | Tue 7/21/15 |  |
| 7 | Conduct internal ETS planning meeting | 1 day | Wed 7/1/15 | Wed 7/1/15 | ETS,AIR,MI |
| 8 | Schedule and prepare/ship materials for orientation meeting | 5 days | Wed 7/1/15 | Wed 7/8/15 | ETS |
| 9 | Conduct orientation meeting | 2 days | Mon 7/13/15 | Tue 7/14/15 | MI,CDE,ETS,AIR |
| 10 | Prepare meeting minutes/participant list and deliver to CDE | 5 days | Wed 7/15/15 | Tue 7/21/15 | ETS |
| 11 | Program Meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 12 | Conduct weekly internal status meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 | ETS |
| 13 | Conduct weekly CDE management meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 | CDE,AIR,MI,ETS |
| 14 | Conduct weekly CDE technical meeting | 252 days | Wed 7/1/15 | Thu 6/30/16 | CDE,AIR,MI,ETS |
| 15 | State Board Meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 16 | Attend State Board meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 | CDE,ETS |
| 17 | Technical Advisory Group (TAG) Meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 18 | Work with the CDE to develop TAG agendas | 252 days | Wed 7/1/15 | Thu 6/30/16 | CDE,ETS |
| 19 | Attend TAG meetings | 252 days | Wed 7/1/15 | Thu 6/30/16 | CDE,ETS |
| 20 | Monthly Progress Reports | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 21 | Deliver monthly progress reports to CDE | 252 days | Wed 7/1/15 | Thu 6/30/16 | ETS |
| 22 | Project Management Plan (PMP) & Project Definitions Document | 80 days | Wed 7/1/15 | Thu 10/22/15 |  |
| 23 | Project Management Plan for Overall CAASPP Activities | 70 days | Wed 7/1/15 | Thu 10/8/15 |  |
| 24 | Establish project SharePoint site | 1 day | Thu 7/9/15 | Thu 7/9/15 | ETS |
| 25 | Complete Work Breakdown Structure | 10 days | Wed 7/1/15 | Wed 7/15/15 | ETS |
| 26 | Develop draft project management plan for overall CAASPP activities | 30 days | Wed 7/1/15 | Wed 8/12/15 | ETS |
| 27 | CDE reviews project management plan for overall CAASPP activities | 20 days | Thu 8/13/15 | Thu 9/10/15 | CDE |
| 28 | Finalize project management plan for overall CAASPP activities | 20 days | Fri 9/11/15 | Thu 10/8/15 | ETS |
| 29 | Project Definitions Document for the Assessment Delivery System | 70 days | Wed 7/1/15 | Thu 10/8/15 |  |
| 30 | Develop draft project management plan for the Assessment Delivery System | 30 days | Wed 7/1/15 | Wed 8/12/15 | ETS,AIR |
| 31 | CDE reviews project management plan for the Assessment Delivery System | 20 days | Thu 8/13/15 | Thu 9/10/15 | CDE |
| 32 | Finalize project management plan for the Assessment Delivery System | 20 days | Fri 9/11/15 | Thu 10/8/15 | ETS,AIR |
| 33 | Integrated Comprehensive Work plan & Project Schedule | 10 days | Fri 10/9/15 | Thu 10/22/15 |  |
| 34 | CDE reviews comprehensive integrated project schedule | 10 days | Fri 10/9/15 | Thu 10/22/15 | CDE |
| 35 | CDE project schedule review complete | 0 days | Thu 10/22/15 | Thu 10/22/15 | CDE |
| 36 | Test Security | 277 days | Wed 7/1/15 | Fri 8/5/16 |  |
| 37 | Update the Test Security Plan for the 2016 administration | 7 days | Wed 7/1/15 | Fri 7/10/15 | ETS |
| 38 | Deliver the Test Security Plan to CDE for review | 1 day | Mon 7/13/15 | Mon 7/13/15 | ETS |
| 39 | CDE reviews the Test Security Plan | 10 days | Tue 7/14/15 | Mon 7/27/15 | CDE |
| 40 | Apply CDE edits to the Test Security Plan | 3 days | Tue 7/28/15 | Thu 7/30/15 | ETS |
| 41 | CDE 2nd review of the Test Security Plan | 5 days | Fri 7/31/15 | Thu 8/6/15 | CDE |
| 42 | Apply updates and deliver the final Test Security Plan to CDE for approval | 3 days | Fri 8/7/15 | Tue 8/11/15 | ETS |
| 43 | Monitor social media sites for test security breaches | 252 days | Wed 7/1/15 | Thu 6/30/16 | ETS |
| 44 | Perform on-site security audit visits | 125 days | Wed 2/3/16 | Fri 7/29/16 | ETS |
| 45 | Investigate test security breaches as needed | 125 days | Wed 2/3/16 | Fri 7/29/16 | ETS |
| 46 | Deliver audit reports to CDE | 125 days | Wed 2/10/16 | Fri 8/5/16 | ETS |
| 47 | Data Driven Improvement | 237 days | Wed 7/1/15 | Thu 6/9/16 |  |
| 48 | Pre-Testing Data Collection | 77 days | Fri 10/23/15 | Wed 2/17/16 |  |
| 49 | Pre-Test Survey | 77 days | Fri 10/23/15 | Wed 2/17/16 |  |
| 50 | Develop Pre-Test Survey | 20 days | Fri 10/23/15 | Thu 11/19/15 | ETS |
| 51 | CDE reviews Pre-Test Survey | 10 days | Fri 11/20/15 | Mon 12/7/15 | CDE |
| 52 | Revise Pre-Test Survey | 3 days | Tue 12/8/15 | Thu 12/10/15 | ETS |
| 53 | CDE 2nd review of Pre-Test Survey | 5 days | Fri 12/11/15 | Thu 12/17/15 | CDE |
| 54 | Apply updates and deliver final Pre-Test Survey to CDE for approval | 3 days | Fri 12/18/15 | Tue 12/22/15 | ETS |
| 55 | Administer Pre-Test Survey | 20 days | Mon 1/4/16 | Mon 2/1/16 | ETS |
| 56 | Analyze survey results | 10 days | Tue 2/2/16 | Tue 2/16/16 | ETS |
| 57 | Deliver survey results & recommended program improvements to CDE | 1 day | Wed 2/17/16 | Wed 2/17/16 | ETS |
| 58 | Post-Testing Data Collection | 237 days | Wed 7/1/15 | Thu 6/9/16 |  |
| 59 | Post-Test Survey | 67 days | Tue 3/8/16 | Thu 6/9/16 |  |
| 60 | Develop Post-Test Survey | 20 days | Tue 3/8/16 | Mon 4/4/16 | ETS |
| 61 | CDE reviews Post-Test Survey | 10 days | Tue 4/5/16 | Mon 4/18/16 | CDE |
| 62 | Revise Post-Test Survey | 3 days | Tue 4/19/16 | Thu 4/21/16 | ETS |
| 63 | CDE 2nd review of Post-Test Survey | 5 days | Fri 4/22/16 | Thu 4/28/16 | CDE |
| 64 | Apply updates and deliver final Post-Test Survey to CDE for approval | 3 days | Fri 4/29/16 | Tue 5/3/16 | ETS |
| 65 | Administer Post-Test Survey | 20 days | Wed 5/11/16 | Wed 6/8/16 | ETS |
| 66 | Deliver survey results & recommended program improvements to CDE | 1 day | Thu 6/9/16 | Thu 6/9/16 | ETS |
| 67 | Post-Test Focus Groups for Administrators | 60 days | Wed 7/1/15 | Thu 9/24/15 |  |
| 68 | Prepare materials for Post-Test Focus Groups | 9 days | Wed 7/1/15 | Tue 7/14/15 | ETS |
| 69 | Conduct Sacramento focus group | 2 days | Wed 7/15/15 | Thu 7/16/15 | ETS |
| 70 | Conduct Southern CA focus group | 2 days | Tue 7/28/15 | Wed 7/29/15 | ETS |
| 71 | Compile results and recommended program improvements to CDE | 40 days | Thu 7/30/15 | Thu 9/24/15 | ETS |
| 72 | Test Coordinator Advisory Group | 162 days | Tue 8/18/15 | Mon 4/11/16 |  |
| 73 | Prepare materials for Test Coordinator Advisory Group 1 | 20 days | Tue 8/18/15 | Tue 9/15/15 | ETS |
| 74 | Conduct September Advisory Group 1 | 1 day | Wed 9/16/15 | Wed 9/16/15 | ETS |
| 75 | Compile results and recommended program improvements to CDE | 40 days | Thu 9/17/15 | Wed 11/11/15 | ETS |
| 76 | Prepare materials for Test Coordinator Advisory Group 2 | 20 days | Thu 1/14/16 | Thu 2/11/16 | ETS |
| 77 | Conduct February Advisory Group 2 | 1 day | Fri 2/12/16 | Fri 2/12/16 | ETS |
| 78 | Compile results and recommended program improvements to CDE | 40 days | Tue 2/16/16 | Mon 4/11/16 | ETS |
| 79 | caaspp.org User Focus Group | 62 days | Mon 8/24/15 | Wed 11/18/15 |  |
| 80 | Prepare materials for caaspp.org Focus Groups | 20 days | Mon 8/24/15 | Mon 9/21/15 | ETS |
| 81 | Conduct caaspp.org User Focus group | 2 days | Tue 9/22/15 | Wed 9/23/15 | ETS |
| 82 | Compile results and recommended program improvements to CDE | 40 days | Thu 9/24/15 | Wed 11/18/15 | ETS |
| 83 | Project Management Complete | 0 days | Fri 8/5/16 | Fri 8/5/16 |  |
| 84 | Training & LEA Support | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 85 | Training & LEA Support Begins | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 86 | CalTAC | 252 days | Wed 7/1/15 | Thu 6/30/16 |  |
| 87 | Train CalTAC staff on the CAASPP program | 10 days | Wed 7/1/15 | Wed 7/15/15 | ETS |
| 88 | Establish help desk technical phone, web chat and e-mail support | 10 days | Wed 7/1/15 | Wed 7/15/15 | ETS |
| 89 | Perform technology support site visits as needed | 242 days | Thu 7/16/15 | Thu 6/30/16 | ETS |
| 90 | LEA CAASPP Coordinator Designation Forms & Security Agreements | 64 days | Wed 7/1/15 | Wed 9/30/15 |  |
| 91 | Collect LEA CAASPP coordinator designation forms and security agreements | 50 days | Wed 7/1/15 | Thu 9/10/15 | ETS |
| 92 | Input updates into the LEA CAASPP coordinator database | 43 days | Thu 7/30/15 | Tue 9/29/15 | ETS |
| 93 | Provide CDE access to the CAASPP coordinator database | 1 day | Wed 9/30/15 | Wed 9/30/15 | ETS |
| 94 | LEA Technology Readiness | 91 days | Thu 7/30/15 | Tue 12/8/15 |  |
| 95 | Develop technology readiness information collection methodologies | 30 days | Thu 7/30/15 | Thu 9/10/15 | ETS |
| 96 | Collect technology readiness information from LEAs | 40 days | Fri 9/11/15 | Thu 11/5/15 | ETS |
| 97 | Conduct outreach campaign to non-responsive LEAs | 20 days | Fri 11/6/15 | Mon 12/7/15 | ETS |
| 98 | Present readiness results to CDE | 1 day | Tue 12/8/15 | Tue 12/8/15 | ETS |
| 99 | Summative Assessment Test Administration Training Manuals | 216 days | Wed 7/1/15 | Tue 5/10/16 |  |
| 100 | Smarter Balanced Test Administration Manual (TAM) | 111 days | Wed 7/1/15 | Tue 12/8/15 |  |
| 101 | TAM available from Smarter Balanced | 0 days | Wed 7/1/15 | Wed 7/1/15 | Smarter Balanced |
| 102 | Adapt Smarter Balanced TAM for California | 15 days | Fri 9/11/15 | Thu 10/1/15 | ETS |
| 103 | CDE reviews Smarter Balanced TAM | 10 days | Fri 10/2/15 | Thu 10/15/15 | CDE |
| 104 | Apply CDE edits to Smarter Balanced TAM | 3 days | Fri 10/16/15 | Tue 10/20/15 | ETS |
| 105 | CDE 2nd review of Smarter Balanced TAM | 5 days | Wed 10/21/15 | Tue 10/27/15 | CDE |
| 106 | Apply updates and deliver final Smarter Balanced TAM to CDE for approval | 3 days | Wed 10/28/15 | Fri 10/30/15 | ETS |
| 107 | Post Smarter Balanced TAM to caaspp.org | 1 day | Mon 11/2/15 | Mon 11/2/15 | ETS |
| 108 | Print Smarter Balanced TAM | 20 days | Mon 11/2/15 | Tue 12/1/15 | ETS |
| 109 | Distribute Smarter Balanced TAM to LEAs | 5 days | Wed 12/2/15 | Tue 12/8/15 | ETS |
| 110 | Alternate Assessment Test Administration Manual (TAM) | 72 days | Thu 8/13/15 | Mon 11/23/15 |  |
| 111 | Develop Alternate Assessment TAM | 25 days | Thu 8/13/15 | Thu 9/17/15 | ETS |
| 112 | CDE reviews Alternate Assessment TAM | 10 days | Fri 9/18/15 | Thu 10/1/15 | CDE |
| 113 | Apply CDE edits to Alternate Assessment TAM | 3 days | Fri 10/2/15 | Tue 10/6/15 | ETS |
| 114 | CDE 2nd review of Alternate Assessment TAM | 5 days | Wed 10/7/15 | Tue 10/13/15 | CDE |
| 115 | Apply updates and deliver final Alternate Assessment TAM to CDE for approval | 3 days | Wed 10/14/15 | Fri 10/16/15 | ETS |
| 116 | Post Alternate Assessment TAM to caaspp.org | 1 day | Mon 10/19/15 | Mon 10/19/15 | ETS |
| 117 | Print Alternate Assessment TAM | 20 days | Tue 10/20/15 | Mon 11/16/15 | ETS |
| 118 | Distribute Alternate Assessment TAM to LEAs | 5 days | Tue 11/17/15 | Mon 11/23/15 | ETS |
| 119 | CST, CMA, CAPA Science, STS Paper/Pencil TAM | 56 days | Thu 8/6/15 | Fri 10/23/15 |  |
| 120 | Develop CST, CMA, CAPA Science & STS Paper/Pencil TAM | 10 days | Thu 8/6/15 | Wed 8/19/15 | ETS |
| 121 | CDE reviews CST, CMA, CAPA Science & STS Paper/Pencil TAM | 10 days | Thu 8/20/15 | Wed 9/2/15 | CDE |
| 122 | Apply CDE edits to CST, CMA, CAPA Science & STS Paper/Pencil TAM | 3 days | Thu 9/3/15 | Tue 9/8/15 | ETS |
| 123 | CDE 2nd review of CST, CMA, CAPA Science & STS Paper/Pencil TAM | 5 days | Wed 9/9/15 | Tue 9/15/15 | CDE |
| 124 | Apply updates and deliver final CST, CMA, CAPA Science & STS Paper/Pencil TAM to CDE for approval | 3 days | Wed 9/16/15 | Fri 9/18/15 | ETS |
| 125 | Post CST, CMA, CAPA Science & STS Paper/Pencil TAM to caaspp.org | 1 day | Mon 9/21/15 | Mon 9/21/15 | ETS |
| 126 | Print CST, CMA, CAPA Science & STS Paper/Pencil TAM | 20 days | Mon 9/21/15 | Fri 10/16/15 | ETS |
| 127 | Distribute CST, CMA, CAPA Science & STS Paper/Pencil TAM to LEAs | 5 days | Mon 10/19/15 | Fri 10/23/15 | ETS |
| 128 | LEA CAASPP Test Coordinators Manual (LEA TCM) | 47 days | Wed 10/28/15 | Thu 1/7/16 |  |
| 129 | Develop LEA TCM | 25 days | Wed 10/28/15 | Thu 12/3/15 | ETS |
| 130 | CDE reviews LEA TCM | 10 days | Fri 12/4/15 | Thu 12/17/15 | CDE |
| 131 | Apply CDE edits to LEA TCM | 3 days | Fri 12/18/15 | Tue 12/22/15 | ETS |
| 132 | CDE 2nd review of LEA TCM | 5 days | Wed 12/23/15 | Thu 12/31/15 | CDE |
| 133 | Apply updates and deliver final LEA TCM to CDE for approval | 3 days | Mon 1/4/16 | Wed 1/6/16 | ETS |
| 134 | Post LEA TCM to caaspp.org | 1 day | Thu 1/7/16 | Thu 1/7/16 | ETS |
| 135 | Test Site Coordinators Manual (SCM) | 47 days | Wed 10/28/15 | Thu 1/7/16 |  |
| 136 | Develop SCM | 25 days | Wed 10/28/15 | Thu 12/3/15 | ETS |
| 137 | CDE reviews SCM | 10 days | Fri 12/4/15 | Thu 12/17/15 | CDE |
| 138 | Apply CDE edits to SCM | 3 days | Fri 12/18/15 | Tue 12/22/15 | ETS |
| 139 | CDE 2nd review of SCM | 5 days | Wed 12/23/15 | Thu 12/31/15 | CDE |
| 140 | Apply updates and deliver final SCM to CDE for approval | 3 days | Mon 1/4/16 | Wed 1/6/16 | ETS |
| 141 | Post SCM to caaspp.org | 1 day | Thu 1/7/16 | Thu 1/7/16 | ETS |
| 142 | Test Examiners Manual (TEM) | 47 days | Wed 11/4/15 | Thu 1/14/16 |  |
| 143 | Develop TEM | 25 days | Wed 11/4/15 | Thu 12/10/15 | ETS |
| 144 | CDE reviews TEM | 10 days | Fri 12/11/15 | Mon 12/28/15 | CDE |
| 145 | Apply CDE edits to TEM | 3 days | Tue 12/29/15 | Thu 12/31/15 | ETS |
| 146 | CDE 2nd review of TEM | 5 days | Mon 1/4/16 | Fri 1/8/16 | CDE |
| 147 | Apply updates and deliver final TEM to CDE for approval | 3 days | Mon 1/11/16 | Wed 1/13/16 | ETS |
| 148 | Post TEM to caaspp.org | 1 day | Thu 1/14/16 | Thu 1/14/16 | ETS |
| 149 | Technology Services Coordinators Manual (TSCM) | 47 days | Wed 11/4/15 | Thu 1/14/16 |  |
| 150 | Develop TSCM | 25 days | Wed 11/4/15 | Thu 12/10/15 | ETS |
| 151 | CDE reviews TSCM | 10 days | Fri 12/11/15 | Mon 12/28/15 | CDE |
| 152 | Apply CDE edits to TSCM | 3 days | Tue 12/29/15 | Thu 12/31/15 | ETS |
| 153 | CDE 2nd review of TSCM | 5 days | Mon 1/4/16 | Fri 1/8/16 | CDE |
| 154 | Apply updates and deliver final TSCM to CDE for approval | 3 days | Mon 1/11/16 | Wed 1/13/16 | ETS |
| 155 | Post TSCM to caaspp.org | 1 day | Thu 1/14/16 | Thu 1/14/16 | ETS |
| 156 | CAASPP Test Operations Management System Manual (TOMS) | 47 days | Thu 8/13/15 | Mon 10/19/15 |  |
| 157 | Develop TOMS manual | 25 days | Thu 8/13/15 | Thu 9/17/15 | ETS |
| 158 | CDE reviews TOMS manual | 10 days | Fri 9/18/15 | Thu 10/1/15 | CDE |
| 159 | Apply CDE edits to TOMS manual | 3 days | Fri 10/2/15 | Tue 10/6/15 | ETS |
| 160 | CDE 2nd review of TOMS manual | 5 days | Wed 10/7/15 | Tue 10/13/15 | CDE |
| 161 | Apply updates and deliver final TOMS manual to CDE for approval | 3 days | Wed 10/14/15 | Fri 10/16/15 | ETS |
| 162 | Post TOMS manual to caaspp.org | 1 day | Mon 10/19/15 | Mon 10/19/15 | ETS |
| 163 | STS for Dual Immersion Students Manual | 47 days | Fri 9/11/15 | Mon 11/16/15 |  |
| 164 | Develop STS manual | 25 days | Fri 9/11/15 | Thu 10/15/15 | ETS |
| 165 | CDE reviews STS manual | 10 days | Fri 10/16/15 | Thu 10/29/15 | CDE |
| 166 | Apply CDE edits to STS manual | 3 days | Fri 10/30/15 | Tue 11/3/15 | ETS |
| 167 | CDE 2nd review of STS manual | 5 days | Wed 11/4/15 | Tue 11/10/15 | CDE |
| 168 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Wed 11/11/15 | Fri 11/13/15 | ETS |
| 169 | Post STS manual to caaspp.org | 1 day | Mon 11/16/15 | Mon 11/16/15 | ETS |
| 170 | Test Administrator Quick Start Guide | 47 days | Fri 9/25/15 | Wed 12/2/15 |  |
| 171 | Develop STS manual | 25 days | Fri 9/25/15 | Thu 10/29/15 | ETS |
| 172 | CDE reviews STS manual | 10 days | Fri 10/30/15 | Thu 11/12/15 | CDE |
| 173 | Apply CDE edits to STS manual | 3 days | Fri 11/13/15 | Tue 11/17/15 | ETS |
| 174 | CDE 2nd review of STS manual | 5 days | Wed 11/18/15 | Tue 11/24/15 | CDE |
| 175 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Wed 11/25/15 | Tue 12/1/15 | ETS |
| 176 | Post STS manual to caaspp.org | 1 day | Wed 12/2/15 | Wed 12/2/15 | ETS |
| 177 | Online Reporting Guide | 52 days | Tue 12/22/15 | Wed 3/9/16 |  |
| 178 | Develop Online Reporting Guide manual | 30 days | Tue 12/22/15 | Fri 2/5/16 | ETS |
| 179 | CDE reviews Online Reporting Guide manual | 10 days | Mon 2/8/16 | Mon 2/22/16 | CDE |
| 180 | Apply CDE edits to Online Reporting Guide manual | 3 days | Tue 2/23/16 | Thu 2/25/16 | ETS |
| 181 | CDE 2nd review of Online Reporting Guide manual | 5 days | Fri 2/26/16 | Thu 3/3/16 | CDE |
| 182 | Apply updates and deliver final Online Reporting Guide manual to CDE for approval | 3 days | Fri 3/4/16 | Tue 3/8/16 | ETS |
| 183 | Post Online Reporting Guide to caaspp.org | 1 day | Wed 3/9/16 | Wed 3/9/16 | ETS |
| 184 | CAASPP Post-Test Guide | 76 days | Mon 1/25/16 | Tue 5/10/16 |  |
| 185 | Develop Post-Test Guide | 30 days | Mon 1/25/16 | Mon 3/7/16 | ETS |
| 186 | CDE reviews Post-Test Guide | 10 days | Tue 3/8/16 | Mon 3/21/16 | CDE |
| 187 | Apply CDE edits to Post-Test Guide | 3 days | Tue 3/22/16 | Thu 3/24/16 | ETS |
| 188 | CDE 2nd review of Post-Test Guide | 5 days | Fri 3/25/16 | Thu 3/31/16 | CDE |
| 189 | Apply updates and deliver final Post-Test Guide to CDE for approval | 3 days | Fri 4/1/16 | Tue 4/5/16 | ETS |
| 190 | Post Post-Test Guide to caaspp.org | 1 day | Wed 4/6/16 | Wed 4/6/16 | ETS |
| 191 | Print Post-Test Guide | 20 days | Wed 4/6/16 | Tue 5/3/16 | ETS |
| 192 | Distribute Post-Test Guide to LEAs | 5 days | Wed 5/4/16 | Tue 5/10/16 | ETS |
| 193 | Training Webcasts and Workshops | 193 days | Wed 8/19/15 | Wed 5/25/16 |  |
| 194 | Training Webcasts | 188 days | Wed 8/19/15 | Wed 5/18/16 |  |
| 195 | Present and archive Using the Digital Library webcast | 1 day | Wed 8/19/15 | Wed 8/19/15 | ETS |
| 196 | Present and archive Using Interim Assessments webcast | 1 day | Wed 9/9/15 | Wed 9/9/15 | ETS |
| 197 | Present and archive Preparing CALPADS Data for Testing webcast | 1 day | Wed 9/16/15 | Wed 9/16/15 | ETS |
| 198 | Present and archive Test Operations Management System (TOMS) Training webcast | 1 day | Wed 9/23/15 | Wed 9/23/15 | ETS |
| 199 | Present and archive Preparing Technology for Online Testing webcast | 1 day | Wed 10/14/15 | Wed 10/14/15 | ETS |
| 200 | Present and archive Accessibility and Accommodations webcast | 1 day | Wed 10/21/15 | Wed 10/21/15 | ETS |
| 201 | Present and archive Using the Online Practice Tests and Training Tests webcast | 1 day | Wed 11/18/15 | Wed 11/18/15 | ETS |
| 202 | Present and archive Pre-Test webcast | 1 day | Tue 1/12/16 | Tue 1/12/16 | ETS,AIR |
| 203 | Present and archive Alternate Assessment training webcast | 1 day | Wed 1/13/16 | Wed 1/13/16 | ETS |
| 204 | Present and archive Test Security LEA Training webcast | 1 day | Wed 1/20/16 | Wed 1/20/16 | ETS |
| 205 | Present and archive Post-Test webcast | 1 day | Wed 5/18/16 | Wed 5/18/16 | ETS |
| 206 | Regional Training Workshops | 178 days | Thu 9/10/15 | Wed 5/25/16 |  |
| 207 | Present regional Digital Library and Interim workshops | 5 days | Thu 9/10/15 | Wed 9/16/15 | ETS |
| 208 | Present regional Pre-Test Workshops | 22 days | Wed 1/13/16 | Fri 2/12/16 | ETS,AIR |
| 209 | Present regional Post-Test Workshops | 5 days | Thu 5/19/16 | Wed 5/25/16 | ETS |
| 210 | Interim CR Scoring Training | 101 days | Tue 10/13/15 | Thu 3/10/16 |  |
| 211 | Receive CR scoring methodology and procedures from Smarter Balanced | 1 day | Tue 10/13/15 | Tue 10/13/15 | Smarter Balanced |
| 212 | Produce workshop slides and e-mail announcement | 20 days | Thu 1/21/16 | Thu 2/18/16 | ETS |
| 213 | Deliver summative and interim CR scoring training workshops | 15 days | Fri 2/19/16 | Thu 3/10/16 | ETS |
| 214 | Training & LEA Support Complete | 0 days | Thu 6/30/16 | Thu 6/30/16 |  |
| 215 | Test Development | 392 days | Wed 7/1/15 | Fri 1/20/17 |  |
| 216 | Test Development Begins | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 217 | NGSS and Primary Language Design | 121 days | Wed 7/1/15 | Tue 12/22/15 |  |
| 218 | Create a draft high level design document & submit to CDE | 40 days | Wed 7/1/15 | Wed 8/26/15 | ETS |
| 219 | CDE reviews initial draft of high level design document | 10 days | Thu 8/27/15 | Thu 9/10/15 | CDE |
| 220 | Produce detailed tasks and test specification documents | 40 days | Fri 9/11/15 | Thu 11/5/15 | ETS |
| 221 | Conduct review of detailed item and test specifications and ALDs with stakeholders | 1 day | Fri 11/20/15 | Fri 11/20/15 | ETS,CDE |
| 222 | Finalize design and specifications documents | 20 days | Mon 11/23/15 | Tue 12/22/15 | ETS |
| 223 | Alternate Assessment ELA/Math Design | 71 days | Wed 7/1/15 | Fri 10/9/15 |  |
| 224 | Create a draft high level design document & submit to CDE | 10 days | Wed 7/1/15 | Wed 7/15/15 | ETS |
| 225 | CDE reviews initial draft of high level design document | 10 days | Thu 7/16/15 | Wed 7/29/15 | CDE |
| 226 | Produce detailed tasks and test specification documents | 30 days | Thu 7/30/15 | Thu 9/10/15 | CDE |
| 227 | Conduct review of detailed item and test specifications and ALDs with stakeholders | 1 day | Fri 9/11/15 | Fri 9/11/15 | ETS,CDE |
| 228 | Finalize design and specifications documents | 20 days | Mon 9/14/15 | Fri 10/9/15 | ETS |
| 229 | Alternate Assessment ELA/Math | 52 days | Mon 10/12/15 | Mon 12/28/15 |  |
| 230 | Develop draft blueprints | 5 days | Mon 10/12/15 | Fri 10/16/15 | ETS |
| 231 | CDE reviews Alternate Assessment ELA/Math draft blueprints | 10 days | Mon 10/19/15 | Fri 10/30/15 | CDE |
| 232 | External committee blueprint review meeting | 2 days | Mon 11/2/15 | Tue 11/3/15 | External Committee,CDE,ETS |
| 233 | CDE reviews and approves blueprints | 5 days | Wed 11/4/15 | Tue 11/10/15 | CDE |
| 234 | Develop Alternate Assessment ELA/Math Assessment items | 13 days | Wed 11/11/15 | Tue 12/1/15 | ETS |
| 235 | CDE reviews new Alternate Assessment ELA/Math items | 10 days | Wed 12/2/15 | Tue 12/15/15 | CDE |
| 236 | External committee item review meetings | 2 days | Wed 12/16/15 | Thu 12/17/15 | External Committee,CDE,ETS |
| 237 | CDE reviews and approves new items | 5 days | Fri 12/18/15 | Mon 12/28/15 | CDE |
| 238 | Primary Language | 309 days | Mon 9/28/15 | Mon 12/19/16 |  |
| 239 | Review existing passages | 40 days | Mon 9/28/15 | Fri 11/20/15 | ETS |
| 240 | Create a development plan | 10 days | Mon 11/23/15 | Tue 12/8/15 | ETS |
| 241 | CDE reviews and approves development plan | 15 days | Wed 12/9/15 | Thu 12/31/15 | CDE |
| 242 | Conduct Item Writer Training workshop | 2 days | Mon 1/4/16 | Tue 1/5/16 | ETS |
| 243 | Develop Primary Language Assessment items | 60 days | Wed 1/6/16 | Thu 3/31/16 | ETS |
| 244 | CDE reviews new Primary Language items | 10 days | Fri 4/1/16 | Thu 4/14/16 | CDE |
| 245 | ETS revises Primary Language items | 40 days | Fri 4/15/16 | Fri 6/10/16 | ETS |
| 246 | External committee item review meetings | 2 days | Mon 6/13/16 | Tue 6/14/16 | External Committee,CDE,ETS |
| 247 | CDE reviews and approves new items | 5 days | Wed 6/15/16 | Tue 6/21/16 | CDE |
| 248 | Finalize items and develop pilot test forms | 40 days | Wed 6/22/16 | Wed 8/17/16 | ETS |
| 249 | Prepare for online test delivery | 85 days | Thu 8/18/16 | Mon 12/19/16 | ETS |
| 250 | NGSS Science (Including Alt NGSS) | 296 days | Mon 11/16/15 | Fri 1/20/17 |  |
| 251 | Conduct additional stakeholder meetings | 5 days | Mon 11/16/15 | Fri 11/20/15 | ETS |
| 252 | Finalize development plan | 5 days | Mon 11/23/15 | Tue 12/1/15 | ETS |
| 253 | CDE reviews and approves development plan | 15 days | Wed 12/2/15 | Tue 12/22/15 | CDE |
| 254 | Task outline agreement review | 5 days | Wed 12/23/15 | Thu 12/31/15 | ETS,CDE |
| 255 | Finalize, review and approve blueprints in collaboration with CDE partners | 15 days | Mon 1/4/16 | Mon 1/25/16 | ETS,CDE |
| 256 | External committee blueprint review meeting | 2 days | Tue 1/26/16 | Wed 1/27/16 | External Committee,CDE,ETS |
| 257 | CDE approves blueprints | 5 days | Thu 1/28/16 | Wed 2/3/16 | CDE |
| 258 | Develop NGSS Science items | 65 days | Thu 2/4/16 | Thu 5/5/16 | ETS |
| 259 | CDE reviews new NGSS discreet items and alpha draft task agreement | 10 days | Fri 5/6/16 | Thu 5/19/16 | CDE |
| 260 | External committee item review meetings | 3 days | Mon 5/23/16 | Wed 5/25/16 | External Committee,CDE,ETS |
| 261 | Task certification review, finalize items, and develop pilot test forms | 100 days | Thu 5/26/16 | Mon 10/17/16 | ETS |
| 262 | Prepare for online test delivery | 65 days | Tue 10/18/16 | Fri 1/20/17 | ETS |
| 263 | Test Development Complete | 0 days | Fri 1/20/17 | Fri 1/20/17 |  |
| 264 | Operational Test Administration | 769 days | Wed 7/1/15 | Tue 7/3/18 |  |
| 265 | Operational Test Administration Begins | 0 days | Wed 7/1/15 | Wed 7/1/15 |  |
| 266 | CAASPP Assessments | 510 days | Wed 7/1/15 | Wed 7/5/17 |  |
| 267 | Testing Systems | 151 days | Wed 7/1/15 | Mon 2/8/16 |  |
| 268 | Minimum System Requirements Document | 20 days | Wed 7/1/15 | Wed 7/29/15 |  |
| 269 | Develop Minimum System Requirements Document | 5 days | Wed 7/1/15 | Wed 7/8/15 | ETS |
| 270 | CDE reviews and approves Minimum System Requirements Document | 15 days | Thu 7/9/15 | Wed 7/29/15 | CDE |
| 271 | System Configurations | 20 days | Wed 7/1/15 | Wed 7/29/15 |  |
| 272 | Develop list of system configurations | 5 days | Wed 7/1/15 | Wed 7/8/15 | ETS |
| 273 | CDE reviews and approves system configurations | 15 days | Thu 7/9/15 | Wed 7/29/15 | CDE |
| 274 | Item Transfer | 40 days | Fri 11/13/15 | Thu 1/14/16 |  |
| 275 | Receive Interim items from Smarter Balanced | 1 day | Fri 11/13/15 | Fri 11/13/15 | Smarter Balanced |
| 276 | Import Interim field test items from Smarter Balanced | 10 days | Mon 11/16/15 | Tue 12/1/15 | ETS |
| 277 | Receive Summative pools from Smarter Balanced | 1 day | Wed 12/30/15 | Wed 12/30/15 | Smarter Balanced |
| 278 | Import items from Smarter Balanced and embed new field test items into testing system | 10 days | Thu 12/31/15 | Thu 1/14/16 | ETS |
| 279 | Test Operations Management System (TOMS) | 76 days | Wed 7/1/15 | Fri 10/16/15 |  |
| 280 | CDE confirms CALPADS information and list of designated supports/accommodations | 1 day | Wed 7/1/15 | Wed 7/1/15 | CDE |
| 281 | Confirm business requirements for pre-test delivery reporting and application enhancements | 1 day | Thu 7/2/15 | Thu 7/2/15 | ETS |
| 282 | Update CALPADS import function | 20 days | Thu 7/2/15 | Thu 7/30/15 | ETS |
| 283 | Develop and deliver TOMS implementation plan to CDE | 5 days | Mon 7/6/15 | Fri 7/10/15 | ETS |
| 284 | CDE reviews TOMS implementation plan | 10 days | Mon 7/13/15 | Fri 7/24/15 | CDE |
| 285 | Incorporate CDE recommendations to TOMS implementation plan | 3 days | Mon 7/27/15 | Wed 7/29/15 | ETS |
| 286 | CDE approves TOMS implementation plan | 5 days | Thu 7/30/15 | Wed 8/5/15 | CDE |
| 287 | Configure TOMS enhancements for the 2016 CAASPP administration | 15 days | Thu 8/6/15 | Wed 8/26/15 | ETS |
| 288 | Begin daily updates of district and school user contact information | 1 day | Thu 8/27/15 | Thu 8/27/15 | ETS |
| 289 | Functional testing | 10 days | Thu 8/27/15 | Thu 9/10/15 | ETS |
| 290 | Dev-2-Dev Testing | 5 days | Fri 9/11/15 | Thu 9/17/15 | ETS |
| 291 | Integration testing | 10 days | Fri 9/18/15 | Thu 10/1/15 | ETS |
| 292 | Load testing | 10 days | Fri 9/18/15 | Thu 10/1/15 | ETS |
| 293 | CDE UAT of TOMS enhancements | 5 days | Fri 10/2/15 | Thu 10/8/15 | CDE |
| 294 | Apply fixes to TOMS enhancements | 5 days | Fri 10/9/15 | Thu 10/15/15 | ETS |
| 295 | Deploy enhancements to TOMS | 1 day | Fri 10/16/15 | Fri 10/16/15 | ETS |
| 296 | CA ISAAP Tool | 21 days | Thu 8/6/15 | Thu 9/3/15 |  |
| 297 | Gather business requirements for CA ISAAP tool enhancements | 5 days | Thu 8/6/15 | Wed 8/12/15 | ETS |
| 298 | Configure CA ISAAP tool for the 2016 administration | 5 days | Thu 8/13/15 | Wed 8/19/15 | ETS |
| 299 | CDE UAT of CA ISAAP Tool | 5 days | Thu 8/20/15 | Wed 8/26/15 | CDE |
| 300 | Apply fixes to CA ISAPP | 5 days | Thu 8/27/15 | Wed 9/2/15 | ETS |
| 301 | Deploy CA ISAAP Tool | 1 day | Thu 9/3/15 | Thu 9/3/15 | ETS |
| 302 | Test Delivery System (TDS) | 150 days | Thu 7/2/15 | Mon 2/8/16 |  |
| 303 | Update Secure Browsers | 25 days | Fri 9/25/15 | Thu 10/29/15 | AIR |
| 304 | Gather business requirements for application enhancements | 10 days | Thu 7/2/15 | Thu 7/16/15 | ETS,AIR |
| 305 | Configure TDS for the 2016 CAASPP administration | 40 days | Thu 7/30/15 | Thu 9/24/15 | AIR |
| 306 | TDS Testing for Interim Assessments | 62 days | Fri 9/25/15 | Wed 12/23/15 |  |
| 307 | Functional testing | 10 days | Fri 9/25/15 | Thu 10/8/15 | AIR,ETS |
| 308 | Dev-2-Dev Testing | 5 days | Fri 10/9/15 | Thu 10/15/15 | ETS,AIR |
| 309 | Integration testing | 5 days | Fri 10/16/15 | Thu 10/22/15 | ETS,AIR |
| 310 | Load testing | 5 days | Fri 10/23/15 | Thu 10/29/15 | ETS,AIR |
| 311 | CDE UAT | 10 days | Fri 10/16/15 | Thu 10/29/15 | CDE |
| 312 | End-to-End (E2E) Testing | 15 days | Wed 12/2/15 | Tue 12/22/15 | ETS,AIR |
| 313 | Deploy TDS for Interim Assessments including Teacher Hand Scoring | 1 day | Wed 12/23/15 | Wed 12/23/15 | AIR |
| 314 | TDS Testing for Summative Assessments | 41 days | Tue 12/8/15 | Mon 2/8/16 |  |
| 315 | Functional testing | 10 days | Tue 12/8/15 | Mon 12/21/15 | AIR,ETS |
| 316 | Dev-2-Dev Testing | 5 days | Tue 12/22/15 | Wed 12/30/15 | ETS,AIR |
| 317 | Integration testing | 5 days | Fri 1/15/16 | Fri 1/22/16 | ETS,AIR |
| 318 | Load testing | 5 days | Mon 1/25/16 | Fri 1/29/16 | ETS,AIR |
| 319 | CDE UAT | 10 days | Thu 12/31/15 | Thu 1/14/16 | CDE |
| 320 | End-to-End (E2E) Testing | 15 days | Fri 1/15/16 | Fri 2/5/16 | ETS,AIR |
| 321 | Deploy TDS for Summative Assessments including Online Reporting System and Participation Reports | 1 day | Mon 2/8/16 | Mon 2/8/16 | AIR |
| 322 | Formative Digital Library | 116 days | Fri 9/11/15 | Tue 3/1/16 |  |
| 323 | Provide access to Digital Library | 116 days | Fri 9/11/15 | Tue 3/1/16 | ETS |
| 324 | Interim Assessment Registration, Test Content and Ancillaries | 170 days | Wed 7/1/15 | Mon 3/7/16 |  |
| 325 | Current Interim Assessments available | 0 days | Wed 7/1/15 | Wed 7/1/15 | Smarter Balanced |
| 326 | Update enrollment/test administration information | 50 days | Fri 9/25/15 | Mon 12/7/15 | ETS |
| 327 | New enhanced test packages available from Smarter Balanced | 0 days | Fri 2/5/16 | Fri 2/5/16 | Smarter Balanced |
| 328 | Process new test packages | 20 days | Fri 2/5/16 | Fri 3/4/16 | AIR |
| 329 | Updated Interim Comprehensive Assessment (summative clone) (ICA) launched | 1 day | Mon 3/7/16 | Mon 3/7/16 | AIR |
| 330 | Updated Interim Assessment Blocks (IAB) launched | 1 day | Mon 3/7/16 | Mon 3/7/16 | AIR |
| 331 | Configure Smarter Balanced System User Guide for CA | 40 days | Wed 7/1/15 | Wed 8/26/15 | ETS,AIR |
| 332 | Configure Smarter Balanced Scoring Guide for CA | 40 days | Wed 7/1/15 | Wed 8/26/15 | ETS,AIR |
| 333 | Configure Smarter Balanced System Infrastructure Guide for CA | 40 days | Wed 7/1/15 | Wed 8/26/15 | ETS,AIR |
| 334 | Configure Smarter Balanced System Training Workbook for CA | 40 days | Wed 7/1/15 | Wed 8/26/15 | ETS,AIR |
| 335 | Interim Assessment Reporting | 101 days | Tue 2/9/16 | Thu 6/30/16 |  |
| 336 | Deliver Interim Results to Smarter Balanced | 101 days | Tue 2/9/16 | Thu 6/30/16 | ETS,AIR |
| 337 | Summative Computer Based Assessments | 165 days | Tue 11/17/15 | Fri 7/15/16 |  |
| 338 | Summative content packages available for CAT | 0 days | Tue 11/17/15 | Tue 11/17/15 | Smarter Balanced |
| 339 | Summative content packages available for PT | 0 days | Tue 12/1/15 | Tue 12/1/15 | Smarter Balanced |
| 340 | Summative test packages available for CAT and PT | 0 days | Mon 1/11/16 | Mon 1/11/16 | Smarter Balanced |
| 341 | Import and QC test packages | 20 days | Mon 1/11/16 | Mon 2/8/16 | ETS |
| 342 | Update enrollment/test administration information | 20 days | Tue 1/12/16 | Tue 2/9/16 | ETS |
| 343 | Administer summative assessments (Smarter Balanced ELA/Math, ELA/Math Alternate) | 90 days | Thu 3/10/16 | Fri 7/15/16 | ETS |
| 344 | Summative Paper/Pencil Testing | 418 days | Tue 11/10/15 | Wed 7/5/17 |  |
| 345 | Reprint CST/CMA/CAPA Science & STS paper test | 30 days | Tue 11/10/15 | Wed 12/23/15 | ETS |
| 346 | Receive material orders | 15 days | Mon 11/16/15 | Tue 12/8/15 | ETS |
| 347 | Receive paper-based tests from Smarter Balanced | 1 day | Mon 12/5/16 | Mon 12/5/16 | Smarter Balanced |
| 348 | Add covers | 10 days | Tue 12/6/16 | Mon 12/19/16 | ETS |
| 349 | Print all summative operational paper tests | 30 days | Tue 12/20/16 | Wed 2/1/17 | ETS |
| 350 | Distribute paper tests as needed | 88 days | Thu 2/16/17 | Mon 6/19/17 | ETS |
| 351 | Receive paper tests | 75 days | Thu 3/17/16 | Thu 6/30/16 | ETS |
| 352 | Scan paper tests | 76 days | Thu 3/17/16 | Fri 7/1/16 | ETS |
| 353 | Conduct resolutions on paper tests | 90 days | Thu 3/17/16 | Fri 7/22/16 | ETS |
| 354 | Special Versions | 150 days | Tue 12/6/16 | Wed 7/5/17 |  |
| 355 | Produce large print & Braille | 40 days | Tue 12/6/16 | Wed 2/1/17 | ETS |
| 356 | Deliver large print and Braille as requested | 100 days | Thu 2/16/17 | Wed 7/5/17 | ETS |
| 357 | Scoring | 90 days | Thu 3/24/16 | Fri 7/29/16 |  |
| 358 | Summative Computer Based Assessments | 90 days | Thu 3/24/16 | Fri 7/29/16 |  |
| 359 | Hand and AI scoring occurs | 90 days | Thu 3/24/16 | Fri 7/29/16 | ETS,MI |
| 360 | Perform scoring QC | 90 days | Thu 3/24/16 | Fri 7/29/16 | ETS |
| 361 | Final scoring occurs | 90 days | Thu 3/24/16 | Fri 7/29/16 | ETS |
| 362 | Psychometric Analysis | 18 days | Thu 5/19/16 | Tue 6/14/16 |  |
| 363 | Conduct Item Analysis of CAASPP Summative assessments | 16 days | Thu 5/19/16 | Fri 6/10/16 | ETS |
| 364 | Item Analysis Files delivered to CDE | 1 day | Mon 6/13/16 | Mon 6/13/16 | ETS |
| 365 | Facilitate Alternate Assessment Data Review meeting | 1 day | Tue 6/14/16 | Tue 6/14/16 | ETS |
| 366 | Standard Setting for Alternate Assessment ELA/Math | 4 days | Tue 7/12/16 | Fri 7/15/16 |  |
| 367 | Conduct Standard Setting for Alternate Assessment ELA/Math | 4 days | Tue 7/12/16 | Fri 7/15/16 | ETS,CDE |
| 368 | Reporting | 724 days | Thu 9/3/15 | Tue 7/3/18 |  |
| 369 | Summative Assessment | 724 days | Thu 9/3/15 | Tue 7/3/18 |  |
| 370 | Delivery of Data Files to CDE and Smarter Balanced | 117 days | Thu 3/24/16 | Wed 9/7/16 |  |
| 371 | Prepare student data files | 90 days | Thu 3/24/16 | Fri 7/29/16 | ETS |
| 372 | Post initial student data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Mon 8/1/16 | Mon 8/1/16 | ETS |
| 373 | Post final data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Wed 9/7/16 | Wed 9/7/16 | ETS |
| 374 | Online Reporting Systems | 724 days | Thu 9/3/15 | Tue 7/3/18 |  |
| 375 | Online Reporting Systems Setup | 37 days | Thu 9/3/15 | Mon 10/26/15 |  |
| 376 | Gather specifications for AIR online reporting systems | 5 days | Thu 9/3/15 | Thu 9/10/15 | ETS |
| 377 | CDE reviews online reporting system specifications | 10 days | Fri 9/11/15 | Thu 9/24/15 | CDE |
| 378 | Configure online reporting systems | 20 days | Fri 9/25/15 | Thu 10/22/15 | ETS,AIR |
| 379 | Demonstrate online reporting systems to CDE | 1 day | Fri 10/23/15 | Fri 10/23/15 | ETS,AIR |
| 380 | Deploy online reporting system | 1 day | Mon 10/26/15 | Mon 10/26/15 | ETS,AIR |
| 381 | Student Level Reporting | 627 days | Wed 1/27/16 | Tue 7/3/18 |  |
| 382 | Provide final individual scores within 4 weeks of student online test completion | 90 days | Wed 2/28/18 | Tue 7/3/18 | ETS,AIR |
| 383 | Launch ISR availability within online reporting system | 1 day | Wed 1/27/16 | Wed 1/27/16 | ETS,AIR |
| 384 | School Level Reporting | 1 day | Fri 4/8/16 | Fri 4/8/16 |  |
| 385 | Launch school level reporting functionality | 1 day | Fri 4/8/16 | Fri 4/8/16 | ETS,AIR |
| 386 | LEA Level Reporting | 1 day | Mon 4/25/16 | Mon 4/25/16 |  |
| 387 | Launch LEA level reporting functionality | 1 day | Mon 4/25/16 | Mon 4/25/16 | ETS,AIR |
| 388 | State Level Reporting | 188 days | Fri 10/23/15 | Mon 7/25/16 |  |
| 389 | State Aggregate Reporting Website | 188 days | Fri 10/23/15 | Mon 7/25/16 |  |
| 390 | Develop business requirements | 45 days | Fri 10/23/15 | Wed 12/30/15 | ETS |
| 391 | CDE provides text for site | 1 day | Tue 3/29/16 | Tue 3/29/16 | CDE |
| 392 | Construct web reporting site | 30 days | Wed 3/30/16 | Tue 5/10/16 | ETS |
| 393 | CDE UAT of Web Reporting Site | 10 days | Wed 5/11/16 | Tue 5/24/16 | CDE |
| 394 | CDE provides feedback on changes needed | 10 days | Wed 5/25/16 | Wed 6/8/16 | CDE |
| 395 | Apply changes | 5 days | Thu 6/9/16 | Wed 6/15/16 | ETS |
| 396 | CDE second UAT | 5 days | Thu 6/16/16 | Wed 6/22/16 | CDE |
| 397 | Finalize site with CDE updates | 5 days | Thu 6/23/16 | Wed 6/29/16 | ETS |
| 398 | Deploy State level reporting website | 1 day | Mon 7/25/16 | Mon 7/25/16 | ETS |
| 399 | Individual Student Report | 172 days | Fri 11/20/15 | Fri 7/29/16 |  |
| 400 | Develop individual student report | 40 days | Fri 11/20/15 | Fri 1/22/16 | ETS |
| 401 | CDE reviews individual student report | 10 days | Mon 1/25/16 | Fri 2/5/16 | CDE |
| 402 | Update individual student report | 3 days | Mon 2/8/16 | Wed 2/10/16 | ETS |
| 403 | CDE 2nd review of individual student report | 5 days | Thu 2/11/16 | Thu 2/18/16 | CDE |
| 404 | Apply updates & submit to CDE for approval | 3 days | Fri 2/19/16 | Tue 2/23/16 | ETS |
| 405 | Provide electronic student roster reports to LEAs | 20 days | Fri 7/1/16 | Fri 7/29/16 | ETS |
| 406 | Print and ship Individual Student Reports (ISR) to LEAs | 20 days | Fri 7/1/16 | Fri 7/29/16 | ETS |
| 407 | Rescore Process | 120 days | Thu 3/24/16 | Mon 9/12/16 |  |
| 408 | LEAs request rescores | 90 days | Thu 3/24/16 | Fri 7/29/16 | LEAs |
| 409 | Provide rescore results | 90 days | Thu 5/5/16 | Mon 9/12/16 | ETS |
| 410 | Invoicing for rescores occurs | 10 days | Thu 5/12/16 | Wed 5/25/16 | ETS |
| 411 | Interpretive Guides | 31 days | Tue 3/22/16 | Tue 5/3/16 |  |
| 412 | Produce interpretive guides | 30 days | Tue 3/22/16 | Mon 5/2/16 | ETS |
| 413 | Post interpretive guides | 1 day | Tue 5/3/16 | Tue 5/3/16 | ETS |
| 414 | Technical Report | 61 days | Thu 9/8/16 | Mon 12/5/16 |  |
| 415 | Develop Technical Manual | 40 days | Thu 9/8/16 | Wed 11/2/16 | ETS |
| 416 | CDE reviews Technical Report and returns edits to ETS | 10 days | Thu 11/3/16 | Wed 11/16/16 | CDE |
| 417 | ETS applies edits and delivers final Technical Report to CDE | 3 days | Thu 11/17/16 | Mon 11/21/16 | ETS |
| 418 | CDE 2nd review of Technical Report | 5 days | Tue 11/22/16 | Wed 11/30/16 | CDE |
| 419 | Apply updates and deliver Technical Manual to CDE for approval | 3 days | Thu 12/1/16 | Mon 12/5/16 | ETS |
| 420 | Operational Test Administration Complete | 0 days | Tue 7/3/18 | Tue 7/3/18 |  |
| 421 | Year one Complete | 0 days | Fri 12/28/18 | Fri 12/28/18 |  |
| 422 | Administration Year Two (July 2016 - December 2017) | 523 days | Thu 6/23/16 | Tue 7/3/18 |  |
| 423 | Begin administration year two | 0 days | Fri 7/1/16 | Fri 7/1/16 |  |
| 424 | Project Management | 283 days | Thu 6/23/16 | Tue 8/1/17 |  |
| 425 | Project Management Begins | 0 days | Fri 7/1/16 | Fri 7/1/16 |  |
| 426 | Annual Planning Meetings | 35 days | Thu 6/23/16 | Thu 8/11/16 |  |
| 427 | Schedule and prepare/ship materials for annual planning meeting | 3 days | Thu 6/23/16 | Mon 6/27/16 | ETS |
| 428 | Conduct annual planning meeting | 3 days | Tue 7/5/16 | Thu 7/7/16 | CDE,AIR,MI,ETS |
| 429 | Update project documentation and management plan | 15 days | Fri 7/8/16 | Thu 7/28/16 | ETS |
| 430 | Prepare meeting minutes/participant list and deliver to CDE | 10 days | Fri 7/29/16 | Thu 8/11/16 | ETS |
| 431 | Program Meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 |  |
| 432 | Conduct weekly internal status meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 | ETS |
| 433 | Conduct weekly CDE management meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 | CDE,AIR,MI,ETS |
| 434 | Conduct weekly CDE technical meeting | 255 days | Fri 7/1/16 | Fri 6/30/17 | CDE,AIR,MI,ETS |
| 435 | State Board Meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 |  |
| 436 | Attend State Board meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 | CDE,ETS |
| 437 | Technical Advisory Group (TAG) Meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 |  |
| 438 | Work with the CDE to develop TAG agendas | 255 days | Fri 7/1/16 | Fri 6/30/17 | CDE,ETS |
| 439 | Attend TAG meetings | 255 days | Fri 7/1/16 | Fri 6/30/17 | CDE,ETS |
| 440 | Monthly Progress Reports | 255 days | Fri 7/1/16 | Fri 6/30/17 |  |
| 441 | Deliver monthly progress reports to CDE | 255 days | Fri 7/1/16 | Fri 6/30/17 | ETS |
| 442 | Project Management Plan (PMP) & Project Definitions Document | 80 days | Fri 7/1/16 | Mon 10/24/16 |  |
| 443 | Project Management Plan for Overall CAASPP Activities | 70 days | Fri 7/1/16 | Mon 10/10/16 |  |
| 444 | Update Work Breakdown Structure as needed | 10 days | Fri 7/8/16 | Thu 7/21/16 | ETS |
| 445 | Update project management plan for overall CAASPP activities as needed | 30 days | Fri 7/1/16 | Fri 8/12/16 | ETS |
| 446 | CDE reviews project management plan for overall CAASPP activities | 20 days | Mon 8/15/16 | Mon 9/12/16 | CDE |
| 447 | Finalize updates to the project management plan for overall CAASPP activities | 20 days | Tue 9/13/16 | Mon 10/10/16 | ETS |
| 448 | Project Definitions Document for the Assessment Delivery System | 70 days | Fri 7/1/16 | Mon 10/10/16 |  |
| 449 | Develop draft project management plan for the Assessment Delivery System | 30 days | Fri 7/1/16 | Fri 8/12/16 | ETS,AIR |
| 450 | CDE reviews project management plan for the Assessment Delivery System | 20 days | Mon 8/15/16 | Mon 9/12/16 | CDE |
| 451 | Finalize project management plan for the Assessment Delivery System | 20 days | Tue 9/13/16 | Mon 10/10/16 | ETS,AIR |
| 452 | Integrated Comprehensive Work plan & Project Schedule | 10 days | Tue 10/11/16 | Mon 10/24/16 |  |
| 453 | CDE reviews comprehensive integrated project schedule | 10 days | Tue 10/11/16 | Mon 10/24/16 | CDE |
| 454 | CDE project schedule review complete | 0 days | Mon 10/24/16 | Mon 10/24/16 | CDE |
| 455 | Test Security | 277 days | Fri 7/1/16 | Tue 8/1/17 |  |
| 456 | Update the Test Security Plan for the 2017 administration | 3 days | Fri 7/1/16 | Wed 7/6/16 | ETS |
| 457 | Deliver the Test Security Plan to CDE for review | 1 day | Thu 7/7/16 | Thu 7/7/16 | ETS |
| 458 | CDE reviews the Test Security Plan | 10 days | Fri 7/8/16 | Thu 7/21/16 | CDE |
| 459 | Apply CDE edits to the Test Security Plan | 3 days | Fri 7/22/16 | Tue 7/26/16 | ETS |
| 460 | CDE 2nd review of the Test Security Plan | 5 days | Wed 7/27/16 | Tue 8/2/16 | CDE |
| 461 | Apply updates and deliver the final Test Security Plan to CDE for approval | 3 days | Wed 8/3/16 | Fri 8/5/16 | ETS |
| 462 | Monitor social media sites for test security breaches | 255 days | Fri 7/1/16 | Fri 6/30/17 | ETS |
| 463 | Perform on-site security audit visits | 125 days | Wed 2/1/17 | Tue 7/25/17 | ETS |
| 464 | Investigate test security breaches as needed | 125 days | Wed 2/1/17 | Tue 7/25/17 | ETS |
| 465 | Deliver audit reports to CDE | 125 days | Wed 2/8/17 | Tue 8/1/17 | ETS |
| 466 | Data Driven Improvement | 237 days | Fri 7/1/16 | Tue 6/6/17 |  |
| 467 | Pre-Testing Data Collection | 77 days | Tue 10/25/16 | Tue 2/14/17 |  |
| 468 | Pre-Test Survey | 77 days | Tue 10/25/16 | Tue 2/14/17 |  |
| 469 | Develop Pre-Test Survey | 20 days | Tue 10/25/16 | Mon 11/21/16 | ETS |
| 470 | CDE reviews Pre-Test Survey | 10 days | Tue 11/22/16 | Wed 12/7/16 | CDE |
| 471 | Revise Pre-Test Survey | 3 days | Thu 12/8/16 | Mon 12/12/16 | ETS |
| 472 | CDE 2nd review of Pre-Test Survey | 5 days | Tue 12/13/16 | Mon 12/19/16 | CDE |
| 473 | Apply updates and deliver final Pre-Test Survey to CDE for approval | 3 days | Tue 12/20/16 | Thu 12/22/16 | ETS |
| 474 | Administer Pre-Test Survey | 20 days | Tue 1/3/17 | Mon 1/30/17 | ETS |
| 475 | Analyze survey results | 10 days | Tue 1/31/17 | Mon 2/13/17 | ETS |
| 476 | Deliver survey results & recommended program improvements to CDE | 1 day | Tue 2/14/17 | Tue 2/14/17 | ETS |
| 477 | Post-Testing Data Collection | 237 days | Fri 7/1/16 | Tue 6/6/17 |  |
| 478 | Post-Test Survey | 67 days | Mon 3/6/17 | Tue 6/6/17 |  |
| 479 | Develop Post-Test Survey | 20 days | Mon 3/6/17 | Fri 3/31/17 | ETS |
| 480 | CDE reviews Post-Test Survey | 10 days | Mon 4/3/17 | Fri 4/14/17 | CDE |
| 481 | Revise Post-Test Survey | 3 days | Mon 4/17/17 | Wed 4/19/17 | ETS |
| 482 | CDE 2nd review of Post-Test Survey | 5 days | Thu 4/20/17 | Wed 4/26/17 | CDE |
| 483 | Apply updates and deliver final Post-Test Survey to CDE for approval | 3 days | Thu 4/27/17 | Mon 5/1/17 | ETS |
| 484 | Administer Post-Test Survey | 20 days | Tue 5/9/17 | Mon 6/5/17 | ETS |
| 485 | Deliver survey results & recommended program improvements to CDE | 1 day | Tue 6/6/17 | Tue 6/6/17 | ETS |
| 486 | Post-Test Focus Groups for Administrators | 60 days | Fri 7/1/16 | Mon 9/26/16 |  |
| 487 | Prepare materials for Post-Test Focus Groups | 9 days | Fri 7/1/16 | Thu 7/14/16 | ETS |
| 488 | Conduct Sacramento focus group | 2 days | Fri 7/15/16 | Mon 7/18/16 | ETS |
| 489 | Conduct Southern CA focus group | 2 days | Thu 7/28/16 | Fri 7/29/16 | ETS |
| 490 | Compile results and recommended program improvements to CDE | 40 days | Mon 8/1/16 | Mon 9/26/16 | ETS |
| 491 | Test Coordinator Advisory Group | 162 days | Thu 8/18/16 | Fri 4/7/17 |  |
| 492 | Prepare materials for Test Coordinator Advisory Group 1 | 20 days | Thu 8/18/16 | Thu 9/15/16 | ETS |
| 493 | Conduct September Advisory Group 1 | 1 day | Fri 9/16/16 | Fri 9/16/16 | ETS |
| 494 | Compile results and recommended program improvements to CDE | 40 days | Mon 9/19/16 | Fri 11/11/16 | ETS |
| 495 | Prepare materials for Test Coordinator Advisory Group 2 | 20 days | Fri 1/13/17 | Thu 2/9/17 | ETS |
| 496 | Conduct February Advisory Group 2 | 1 day | Fri 2/10/17 | Fri 2/10/17 | ETS |
| 497 | Compile results and recommended program improvements to CDE | 40 days | Mon 2/13/17 | Fri 4/7/17 | ETS |
| 498 | caaspp.org User Focus Group | 62 days | Wed 8/24/16 | Fri 11/18/16 |  |
| 499 | Prepare materials for caaspp.org Focus Groups | 20 days | Wed 8/24/16 | Wed 9/21/16 | ETS |
| 500 | Conduct caaspp.org User Focus group | 2 days | Thu 9/22/16 | Fri 9/23/16 | ETS |
| 501 | Compile results and recommended program improvements to CDE | 40 days | Mon 9/26/16 | Fri 11/18/16 | ETS |
| 502 | Project Management Complete | 0 days | Tue 8/1/17 | Tue 8/1/17 |  |
| 503 | Training & LEA Support | 252 days | Fri 7/1/16 | Tue 6/27/17 |  |
| 504 | Training & LEA Support Begins | 0 days | Fri 7/1/16 | Fri 7/1/16 |  |
| 505 | CalTAC | 252 days | Fri 7/1/16 | Tue 6/27/17 |  |
| 506 | Train CalTAC staff on the CAASPP program | 10 days | Fri 7/1/16 | Fri 7/15/16 | ETS |
| 507 | Establish help desk technical phone, web chat and e-mail support | 10 days | Fri 7/1/16 | Fri 7/15/16 | ETS |
| 508 | Perform technology support site visits as needed | 242 days | Mon 7/18/16 | Tue 6/27/17 | ETS |
| 509 | LEA CAASPP Coordinator Designation Forms & Security Agreements | 64 days | Fri 7/1/16 | Fri 9/30/16 |  |
| 510 | Collect LEA CAASPP coordinator designation forms and security agreements | 50 days | Fri 7/1/16 | Mon 9/12/16 | ETS |
| 511 | Input updates into the LEA CAASPP coordinator database | 43 days | Mon 8/1/16 | Thu 9/29/16 | ETS |
| 512 | Provide CDE access to the CAASPP coordinator database | 1 day | Fri 9/30/16 | Fri 9/30/16 | ETS |
| 513 | LEA Technology Readiness | 91 days | Mon 8/1/16 | Thu 12/8/16 |  |
| 514 | Develop technology readiness information collection methodologies | 30 days | Mon 8/1/16 | Mon 9/12/16 | ETS |
| 515 | Collect technology readiness information from LEAs | 40 days | Tue 9/13/16 | Mon 11/7/16 | ETS |
| 516 | Conduct outreach campaign to non-responsive LEAs | 20 days | Tue 11/8/16 | Wed 12/7/16 | ETS |
| 517 | Present readiness results to CDE | 1 day | Thu 12/8/16 | Thu 12/8/16 | ETS |
| 518 | Summative Assessment Test Administration Training Manuals | 216 days | Fri 7/1/16 | Mon 5/8/17 |  |
| 519 | Smarter Balanced Test Administration Manual (TAM) | 111 days | Fri 7/1/16 | Thu 12/8/16 |  |
| 520 | TAM available from Smarter Balanced | 0 days | Fri 7/1/16 | Fri 7/1/16 | Smarter Balanced |
| 521 | Adapt Smarter Balanced TAM for California | 15 days | Tue 9/13/16 | Mon 10/3/16 | ETS |
| 522 | CDE reviews Smarter Balanced TAM | 10 days | Tue 10/4/16 | Mon 10/17/16 | CDE |
| 523 | Apply CDE edits to Smarter Balanced TAM | 3 days | Tue 10/18/16 | Thu 10/20/16 | ETS |
| 524 | CDE 2nd review of Smarter Balanced TAM | 5 days | Fri 10/21/16 | Thu 10/27/16 | CDE |
| 525 | Apply updates and deliver final Smarter Balanced TAM to CDE for approval | 3 days | Fri 10/28/16 | Tue 11/1/16 | ETS |
| 526 | Post Smarter Balanced TAM to caaspp.org | 1 day | Wed 11/2/16 | Wed 11/2/16 | ETS |
| 527 | Print Smarter Balanced TAM | 20 days | Wed 11/2/16 | Thu 12/1/16 | ETS |
| 528 | Distribute Smarter Balanced TAM to LEAs | 5 days | Fri 12/2/16 | Thu 12/8/16 | ETS |
| 529 | Alternate Assessment Test Administration Manual (TAM) | 72 days | Mon 8/15/16 | Wed 11/23/16 |  |
| 530 | Develop Alternate Assessment TAM | 25 days | Mon 8/15/16 | Mon 9/19/16 | ETS |
| 531 | CDE reviews Alternate Assessment TAM | 10 days | Tue 9/20/16 | Mon 10/3/16 | CDE |
| 532 | Apply CDE edits to Alternate Assessment TAM | 3 days | Tue 10/4/16 | Thu 10/6/16 | ETS |
| 533 | CDE 2nd review of Alternate Assessment TAM | 5 days | Fri 10/7/16 | Thu 10/13/16 | CDE |
| 534 | Apply updates and deliver final Alternate Assessment TAM to CDE for approval | 3 days | Fri 10/14/16 | Tue 10/18/16 | ETS |
| 535 | Post Alternate Assessment TAM to caaspp.org | 1 day | Wed 10/19/16 | Wed 10/19/16 | ETS |
| 536 | Print Alternate Assessment TAM | 20 days | Thu 10/20/16 | Wed 11/16/16 | ETS |
| 537 | Distribute Alternate Assessment TAM to LEAs | 5 days | Thu 11/17/16 | Wed 11/23/16 | ETS |
| 538 | CST, CMA, CAPA Science, STS Paper/Pencil TAM | 56 days | Mon 8/8/16 | Tue 10/25/16 |  |
| 539 | Develop CST, CMA, CAPA Science & STS Paper/Pencil TAM | 10 days | Mon 8/8/16 | Fri 8/19/16 | ETS |
| 540 | CDE reviews CST, CMA, CAPA Science & STS Paper/Pencil TAM | 10 days | Mon 8/22/16 | Fri 9/2/16 | CDE |
| 541 | Apply CDE edits to CST, CMA, CAPA Science & STS Paper/Pencil TAM | 3 days | Tue 9/6/16 | Thu 9/8/16 | ETS |
| 542 | CDE 2nd review of CST, CMA, CAPA Science & STS Paper/Pencil TAM | 5 days | Fri 9/9/16 | Thu 9/15/16 | CDE |
| 543 | Apply updates and deliver final CST, CMA, CAPA Science & STS Paper/Pencil TAM to CDE for approval | 3 days | Fri 9/16/16 | Tue 9/20/16 | ETS |
| 544 | Post CST, CMA, CAPA Science & STS Paper/Pencil TAM to caaspp.org | 1 day | Wed 9/21/16 | Wed 9/21/16 | ETS |
| 545 | Print CST, CMA, CAPA Science & STS Paper/Pencil TAM | 20 days | Wed 9/21/16 | Tue 10/18/16 | ETS |
| 546 | Distribute CST, CMA, CAPA Science & STS Paper/Pencil TAM to LEAs | 5 days | Wed 10/19/16 | Tue 10/25/16 | ETS |
| 547 | LEA CAASPP Test Coordinators Manual (LEA TCM) | 47 days | Fri 10/28/16 | Fri 1/6/17 |  |
| 548 | Develop LEA TCM | 25 days | Fri 10/28/16 | Mon 12/5/16 | ETS |
| 549 | CDE reviews LEA TCM | 10 days | Tue 12/6/16 | Mon 12/19/16 | CDE |
| 550 | Apply CDE edits to LEA TCM | 3 days | Tue 12/20/16 | Thu 12/22/16 | ETS |
| 551 | CDE 2nd review of LEA TCM | 5 days | Tue 12/27/16 | Mon 1/2/17 | CDE |
| 552 | Apply updates and deliver final LEA TCM to CDE for approval | 3 days | Tue 1/3/17 | Thu 1/5/17 | ETS |
| 553 | Post LEA TCM to caaspp.org | 1 day | Fri 1/6/17 | Fri 1/6/17 | ETS |
| 554 | Test Site Coordinators Manual (SCM) | 47 days | Fri 10/28/16 | Fri 1/6/17 |  |
| 555 | Develop SCM | 25 days | Fri 10/28/16 | Mon 12/5/16 | ETS |
| 556 | CDE reviews SCM | 10 days | Tue 12/6/16 | Mon 12/19/16 | CDE |
| 557 | Apply CDE edits to SCM | 3 days | Tue 12/20/16 | Thu 12/22/16 | ETS |
| 558 | CDE 2nd review of SCM | 5 days | Tue 12/27/16 | Mon 1/2/17 | CDE |
| 559 | Apply updates and deliver final SCM to CDE for approval | 3 days | Tue 1/3/17 | Thu 1/5/17 | ETS |
| 560 | Post SCM to caaspp.org | 1 day | Fri 1/6/17 | Fri 1/6/17 | ETS |
| 561 | Test Examiners Manual (TEM) | 47 days | Fri 11/4/16 | Fri 1/13/17 |  |
| 562 | Develop TEM | 25 days | Fri 11/4/16 | Mon 12/12/16 | ETS |
| 563 | CDE reviews TEM | 10 days | Tue 12/13/16 | Wed 12/28/16 | CDE |
| 564 | Apply CDE edits to TEM | 3 days | Thu 12/29/16 | Mon 1/2/17 | ETS |
| 565 | CDE 2nd review of TEM | 5 days | Tue 1/3/17 | Mon 1/9/17 | CDE |
| 566 | Apply updates and deliver final TEM to CDE for approval | 3 days | Tue 1/10/17 | Thu 1/12/17 | ETS |
| 567 | Post TEM to caaspp.org | 1 day | Fri 1/13/17 | Fri 1/13/17 | ETS |
| 568 | Technology Services Coordinators Manual (TSCM) | 47 days | Fri 11/4/16 | Fri 1/13/17 |  |
| 569 | Develop TSCM | 25 days | Fri 11/4/16 | Mon 12/12/16 | ETS |
| 570 | CDE reviews TSCM | 10 days | Tue 12/13/16 | Wed 12/28/16 | CDE |
| 571 | Apply CDE edits to TSCM | 3 days | Thu 12/29/16 | Mon 1/2/17 | ETS |
| 572 | CDE 2nd review of TSCM | 5 days | Tue 1/3/17 | Mon 1/9/17 | CDE |
| 573 | Apply updates and deliver final TSCM to CDE for approval | 3 days | Tue 1/10/17 | Thu 1/12/17 | ETS |
| 574 | Post TSCM to caaspp.org | 1 day | Fri 1/13/17 | Fri 1/13/17 | ETS |
| 575 | CAASPP Test Operations Management System Manual (TOMS) | 47 days | Mon 8/15/16 | Wed 10/19/16 |  |
| 576 | Develop TOMS manual | 25 days | Mon 8/15/16 | Mon 9/19/16 | ETS |
| 577 | CDE reviews TOMS manual | 10 days | Tue 9/20/16 | Mon 10/3/16 | CDE |
| 578 | Apply CDE edits to TOMS manual | 3 days | Tue 10/4/16 | Thu 10/6/16 | ETS |
| 579 | CDE 2nd review of TOMS manual | 5 days | Fri 10/7/16 | Thu 10/13/16 | CDE |
| 580 | Apply updates and deliver final TOMS manual to CDE for approval | 3 days | Fri 10/14/16 | Tue 10/18/16 | ETS |
| 581 | Post TOMS manual to caaspp.org | 1 day | Wed 10/19/16 | Wed 10/19/16 | ETS |
| 582 | STS for Dual Immersion Students Manual | 47 days | Tue 9/13/16 | Wed 11/16/16 |  |
| 583 | Develop STS manual | 25 days | Tue 9/13/16 | Mon 10/17/16 | ETS |
| 584 | CDE reviews STS manual | 10 days | Tue 10/18/16 | Mon 10/31/16 | CDE |
| 585 | Apply CDE edits to STS manual | 3 days | Tue 11/1/16 | Thu 11/3/16 | ETS |
| 586 | CDE 2nd review of STS manual | 5 days | Fri 11/4/16 | Thu 11/10/16 | CDE |
| 587 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Fri 11/11/16 | Tue 11/15/16 | ETS |
| 588 | Post STS manual to caaspp.org | 1 day | Wed 11/16/16 | Wed 11/16/16 | ETS |
| 589 | Test Administrator Quick Start Guide | 47 days | Tue 9/27/16 | Fri 12/2/16 |  |
| 590 | Develop STS manual | 25 days | Tue 9/27/16 | Mon 10/31/16 | ETS |
| 591 | CDE reviews STS manual | 10 days | Tue 11/1/16 | Mon 11/14/16 | CDE |
| 592 | Apply CDE edits to STS manual | 3 days | Tue 11/15/16 | Thu 11/17/16 | ETS |
| 593 | CDE 2nd review of STS manual | 5 days | Fri 11/18/16 | Mon 11/28/16 | CDE |
| 594 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Tue 11/29/16 | Thu 12/1/16 | ETS |
| 595 | Post STS manual to caaspp.org | 1 day | Fri 12/2/16 | Fri 12/2/16 | ETS |
| 596 | Online Reporting Guide | 52 days | Thu 12/22/16 | Tue 3/7/17 |  |
| 597 | Develop Online Reporting Guide manual | 30 days | Thu 12/22/16 | Fri 2/3/17 | ETS |
| 598 | CDE reviews Online Reporting Guide manual | 10 days | Mon 2/6/17 | Fri 2/17/17 | CDE |
| 599 | Apply CDE edits to Online Reporting Guide manual | 3 days | Mon 2/20/17 | Wed 2/22/17 | ETS |
| 600 | CDE 2nd review of Online Reporting Guide manual | 5 days | Thu 2/23/17 | Wed 3/1/17 | CDE |
| 601 | Apply updates and deliver final Online Reporting Guide manual to CDE for approval | 3 days | Thu 3/2/17 | Mon 3/6/17 | ETS |
| 602 | Post Online Reporting Guide to caaspp.org | 1 day | Tue 3/7/17 | Tue 3/7/17 | ETS |
| 603 | CAASPP Post-Test Guide | 76 days | Mon 1/23/17 | Mon 5/8/17 |  |
| 604 | Develop Post-Test Guide | 30 days | Mon 1/23/17 | Fri 3/3/17 | ETS |
| 605 | CDE reviews Post-Test Guide | 10 days | Mon 3/6/17 | Fri 3/17/17 | CDE |
| 606 | Apply CDE edits to Post-Test Guide | 3 days | Mon 3/20/17 | Wed 3/22/17 | ETS |
| 607 | CDE 2nd review of Post-Test Guide | 5 days | Thu 3/23/17 | Wed 3/29/17 | CDE |
| 608 | Apply updates and deliver final Post-Test Guide to CDE for approval | 3 days | Thu 3/30/17 | Mon 4/3/17 | ETS |
| 609 | Post Post-Test Guide to caaspp.org | 1 day | Tue 4/4/17 | Tue 4/4/17 | ETS |
| 610 | Print Post-Test Guide | 20 days | Tue 4/4/17 | Mon 5/1/17 | ETS |
| 611 | Distribute Post-Test Guide to LEAs | 5 days | Tue 5/2/17 | Mon 5/8/17 | ETS |
| 612 | Training Webcasts and Workshops | 193 days | Fri 8/19/16 | Tue 5/23/17 |  |
| 613 | Training Webcasts | 188 days | Fri 8/19/16 | Tue 5/16/17 |  |
| 614 | Present and archive Using the Digital Library webcast | 1 day | Fri 8/19/16 | Fri 8/19/16 | ETS |
| 615 | Present and archive Using Interim Assessments webcast | 1 day | Fri 9/9/16 | Fri 9/9/16 | ETS |
| 616 | Present and archive Preparing CALPADS Data for Testing webcast | 1 day | Fri 9/16/16 | Fri 9/16/16 | ETS |
| 617 | Present and archive Test Operations Management System (TOMS) Training webcast | 1 day | Fri 9/23/16 | Fri 9/23/16 | ETS |
| 618 | Present and archive Preparing Technology for Online Testing webcast | 1 day | Fri 10/14/16 | Fri 10/14/16 | ETS |
| 619 | Present and archive Accessibility and Accommodations webcast | 1 day | Fri 10/21/16 | Fri 10/21/16 | ETS |
| 620 | Present and archive Using the Online Practice Tests and Training Tests webcast | 1 day | Fri 11/18/16 | Fri 11/18/16 | ETS |
| 621 | Present and archive Pre-Test webcast | 1 day | Wed 1/11/17 | Wed 1/11/17 | ETS,AIR |
| 622 | Present and archive Alternate Assessment training webcast | 1 day | Thu 1/12/17 | Thu 1/12/17 | ETS |
| 623 | Present and archive Test Security LEA Training webcast | 1 day | Wed 1/18/17 | Wed 1/18/17 | ETS |
| 624 | Present and archive Post-Test webcast | 1 day | Tue 5/16/17 | Tue 5/16/17 | ETS |
| 625 | Regional Training Workshops | 178 days | Mon 9/12/16 | Tue 5/23/17 |  |
| 626 | Present regional Digital Library and Interim workshops | 5 days | Mon 9/12/16 | Fri 9/16/16 | ETS |
| 627 | Present regional Pre-Test Workshops | 22 days | Mon 1/16/17 | Tue 2/14/17 | ETS,AIR |
| 628 | Present regional Post-Test Workshops | 5 days | Wed 5/17/17 | Tue 5/23/17 | ETS |
| 629 | Interim CR Scoring Training | 101 days | Thu 10/13/16 | Wed 3/8/17 |  |
| 630 | Receive CR scoring methodology and procedures from Smarter Balanced | 1 day | Thu 10/13/16 | Thu 10/13/16 | Smarter Balanced |
| 631 | Produce workshop slides and e-mail announcement | 20 days | Thu 1/19/17 | Wed 2/15/17 | ETS |
| 632 | Deliver summative and interim CR scoring training workshops | 15 days | Thu 2/16/17 | Wed 3/8/17 | ETS |
| 633 | Training & LEA Support Complete | 0 days | Tue 6/27/17 | Tue 6/27/17 |  |
| 634 | Test Development | 402 days | Fri 7/1/16 | Tue 1/23/18 |  |
| 635 | Begin Test Development | 0 days | Fri 7/1/16 | Fri 7/1/16 |  |
| 636 | Primary Language Pilot Test | 93 days | Mon 2/6/17 | Wed 6/14/17 |  |
| 637 | Administer Primary Language Pilot Test | 30 days | Mon 2/6/17 | Fri 3/17/17 | ETS |
| 638 | Conduct range finding external committee meeting | 2 days | Mon 4/17/17 | Tue 4/18/17 | ETS,CDE,External Committee |
| 639 | CDE approves training scoring sets | 10 days | Wed 4/19/17 | Tue 5/2/17 | CDE |
| 640 | Perform analysis on pilot test data | 20 days | Wed 4/26/17 | Tue 5/23/17 | ETS |
| 641 | CDE reviews pilot test data | 10 days | Wed 5/24/17 | Tue 6/6/17 | CDE |
| 642 | Conduct data review external committee meeting | 1 day | Wed 6/7/17 | Wed 6/7/17 | ETS,CDE,External Committee |
| 643 | CDE approval of data review results | 5 days | Thu 6/8/17 | Wed 6/14/17 | CDE |
| 644 | NGSS Pilot Test (Including Alt NGSS) | 73 days | Mon 2/6/17 | Wed 5/17/17 |  |
| 645 | Administer NGSS Pilot Test | 30 days | Mon 2/6/17 | Fri 3/17/17 | ETS |
| 646 | Conduct range finding external committee meeting | 2 days | Mon 4/17/17 | Tue 4/18/17 | ETS,CDE,External Committee |
| 647 | Perform analysis on pilot test data | 20 days | Wed 4/19/17 | Tue 5/16/17 | ETS |
| 648 | Conduct data review external committee meeting | 1 day | Wed 5/17/17 | Wed 5/17/17 | ETS,CDE,External Committee |
| 649 | Alternate Assessment ELA/Math Embedded Field Test Item Development | 43 days | Fri 7/1/16 | Wed 8/31/16 |  |
| 650 | Develop Alternate Assessment ELA/Math Assessment items | 26 days | Fri 7/1/16 | Mon 8/8/16 | ETS |
| 651 | CDE reviews new items | 10 days | Tue 8/9/16 | Mon 8/22/16 | CDE |
| 652 | External committee item review meetings | 2 days | Tue 8/23/16 | Wed 8/24/16 | ETS,CDE,External Committee |
| 653 | CDE approves new items | 5 days | Thu 8/25/16 | Wed 8/31/16 | CDE |
| 654 | Primary Language Standalone Census Field Test Preparation | 284 days | Tue 12/20/16 | Tue 1/23/18 |  |
| 655 | Revise Primary Language Assessment items as needed | 81 days | Tue 12/20/16 | Thu 4/13/17 | ETS |
| 656 | CDE reviews new Primary Language items | 15 days | Fri 4/14/17 | Thu 5/4/17 | CDE |
| 657 | Update items based on CDE review | 3 days | Fri 5/5/17 | Tue 5/9/17 | ETS |
| 658 | CDE approves new items | 5 days | Wed 5/10/17 | Tue 5/16/17 | CDE |
| 659 | Finalize items and develop field test forms | 83 days | Wed 5/17/17 | Fri 9/8/17 | ETS |
| 660 | CDE reviews field test forms | 18 days | Mon 9/11/17 | Wed 10/4/17 | CDE |
| 661 | External committee field test forms review meeting | 2 days | Thu 10/5/17 | Fri 10/6/17 | ETS,CDE,External Committee |
| 662 | CDE approves field test forms | 5 days | Mon 10/9/17 | Fri 10/13/17 | CDE |
| 663 | Prepare for online test delivery | 72 days | Mon 10/16/17 | Tue 1/23/18 | ETS |
| 664 | NGSS Science (Including Alt NGSS) Standalone Census Field Test Preparation | 320 days | Tue 9/27/16 | Fri 12/22/17 |  |
| 665 | Revise NGSS Science items as needed | 152 days | Tue 9/27/16 | Tue 5/2/17 | ETS |
| 666 | External committee item review meetings | 3 days | Wed 5/3/17 | Fri 5/5/17 | External Committee,CDE,ETS |
| 667 | Develop pilot test forms & CDE review/approval | 100 days | Mon 5/8/17 | Fri 9/22/17 | ETS,CDE |
| 668 | Prepare for online test delivery | 65 days | Mon 9/25/17 | Fri 12/22/17 | ETS |
| 669 | Test Development Complete | 0 days | Tue 1/23/18 | Tue 1/23/18 |  |
| 670 | Operational Test Administration | 517 days | Fri 7/1/16 | Tue 7/3/18 |  |
| 671 | Operational Test Administration Begins | 0 days | Fri 7/1/16 | Fri 7/1/16 |  |
| 672 | CAASPP Assessments | 270 days | Fri 7/1/16 | Fri 7/21/17 |  |
| 673 | Testing Systems | 156 days | Fri 7/1/16 | Mon 2/13/17 |  |
| 674 | Minimum System Requirements Document | 20 days | Fri 7/1/16 | Fri 7/29/16 |  |
| 675 | Develop Minimum System Requirements Document | 5 days | Fri 7/1/16 | Fri 7/8/16 | ETS |
| 676 | CDE reviews and approves Minimum System Requirements Document | 15 days | Mon 7/11/16 | Fri 7/29/16 | CDE |
| 677 | System Configurations | 20 days | Fri 7/1/16 | Fri 7/29/16 |  |
| 678 | Develop list of system configurations | 5 days | Fri 7/1/16 | Fri 7/8/16 | ETS |
| 679 | CDE reviews and approves system configurations | 15 days | Mon 7/11/16 | Fri 7/29/16 | CDE |
| 680 | Item Transfer | 11 days | Fri 7/1/16 | Mon 7/18/16 |  |
| 681 | Receive Interim items from Smarter Balanced | 1 day | Fri 7/1/16 | Fri 7/1/16 | Smarter Balanced |
| 682 | Import Interim field test items from Smarter Balanced | 10 days | Tue 7/5/16 | Mon 7/18/16 | ETS |
| 683 | Receive Summative pools from Smarter Balanced | 1 day | Fri 7/1/16 | Fri 7/1/16 | Smarter Balanced |
| 684 | Import items from Smarter Balanced and embed new field test items into testing system | 10 days | Tue 7/5/16 | Mon 7/18/16 | ETS |
| 685 | Test Operations Management System (TOMS) | 71 days | Fri 7/1/16 | Tue 10/11/16 |  |
| 686 | CDE confirms CALPADS information and list of designated supports/accommodations | 1 day | Fri 7/1/16 | Fri 7/1/16 | CDE |
| 687 | Confirm business requirements for pre-test delivery reporting and application enhancements | 1 day | Tue 7/5/16 | Tue 7/5/16 | ETS |
| 688 | Update CALPADS import function | 20 days | Tue 7/5/16 | Mon 8/1/16 | ETS |
| 689 | Configure TOMS enhancements for the 2017 CAASPP administration | 15 days | Mon 8/1/16 | Fri 8/19/16 | ETS |
| 690 | Begin daily updates of district and school user contact information | 1 day | Mon 8/22/16 | Mon 8/22/16 | ETS |
| 691 | Functional testing | 10 days | Mon 8/22/16 | Fri 9/2/16 | ETS |
| 692 | Dev-2-Dev Testing | 5 days | Tue 9/6/16 | Mon 9/12/16 | ETS |
| 693 | Integration testing | 10 days | Tue 9/13/16 | Mon 9/26/16 | ETS |
| 694 | Load testing | 10 days | Tue 9/13/16 | Mon 9/26/16 | ETS |
| 695 | CDE UAT of TOMS enhancements | 5 days | Tue 9/27/16 | Mon 10/3/16 | CDE |
| 696 | Apply fixes to TOMS enhancements | 5 days | Tue 10/4/16 | Mon 10/10/16 | ETS |
| 697 | Deploy enhancements to TOMS | 1 day | Tue 10/11/16 | Tue 10/11/16 | ETS |
| 698 | CA ISAAP Tool | 49 days | Wed 7/6/16 | Tue 9/13/16 |  |
| 699 | Gather business requirements for CA ISAAP tool enhancements | 20 days | Wed 7/6/16 | Tue 8/2/16 | ETS |
| 700 | Configure CA ISAAP tool for the 2017 administration | 5 days | Mon 8/22/16 | Fri 8/26/16 | ETS |
| 701 | CDE UAT of CA ISAAP Tool | 5 days | Mon 8/29/16 | Fri 9/2/16 | CDE |
| 702 | Apply fixes to CA ISAPP | 5 days | Tue 9/6/16 | Mon 9/12/16 | ETS |
| 703 | Deploy CA ISAAP Tool | 1 day | Tue 9/13/16 | Tue 9/13/16 | ETS |
| 704 | Test Delivery System (TDS) | 121 days | Mon 8/22/16 | Mon 2/13/17 |  |
| 705 | Update Secure Browsers | 25 days | Tue 9/27/16 | Mon 10/31/16 | AIR |
| 706 | Gather business requirements for application enhancements | 10 days | Mon 8/22/16 | Fri 9/2/16 | ETS,AIR |
| 707 | Configure TDS for the 2017 CAASPP administration | 40 days | Tue 9/6/16 | Mon 10/31/16 | AIR |
| 708 | TDS Testing for Interim Assessments | 41 days | Tue 11/1/16 | Mon 1/2/17 |  |
| 709 | Functional testing | 10 days | Tue 11/1/16 | Mon 11/14/16 | AIR,ETS |
| 710 | Dev-2-Dev Testing | 5 days | Tue 11/15/16 | Mon 11/21/16 | ETS,AIR |
| 711 | Integration testing | 5 days | Tue 11/22/16 | Wed 11/30/16 | ETS,AIR |
| 712 | Load testing | 5 days | Thu 12/1/16 | Wed 12/7/16 | ETS,AIR |
| 713 | CDE UAT | 10 days | Tue 11/22/16 | Wed 12/7/16 | CDE |
| 714 | End-to-End (E2E) Testing | 15 days | Thu 12/8/16 | Fri 12/30/16 | ETS,AIR |
| 715 | Deploy TDS for Interim Assessments including Teacher Hand Scoring | 1 day | Mon 1/2/17 | Mon 1/2/17 | AIR |
| 716 | TDS Testing for Summative Assessments | 41 days | Thu 12/15/16 | Mon 2/13/17 |  |
| 717 | Functional testing | 10 days | Thu 12/15/16 | Fri 12/30/16 | AIR,ETS |
| 718 | Dev-2-Dev Testing | 5 days | Mon 1/2/17 | Fri 1/6/17 | ETS,AIR |
| 719 | Integration testing | 5 days | Mon 1/9/17 | Fri 1/13/17 | ETS,AIR |
| 720 | Load testing | 5 days | Mon 1/16/17 | Fri 1/20/17 | ETS,AIR |
| 721 | CDE UAT | 10 days | Mon 1/9/17 | Fri 1/20/17 | CDE |
| 722 | End-to-End (E2E) Testing | 15 days | Mon 1/23/17 | Fri 2/10/17 | ETS,AIR |
| 723 | Deploy TDS for Summative Assessments including Online Reporting System and Participation Reports | 1 day | Mon 2/13/17 | Mon 2/13/17 | AIR |
| 724 | Formative Digital Library | 116 days | Tue 9/13/16 | Mon 2/27/17 |  |
| 725 | Provide access to Digital Library | 116 days | Tue 9/13/16 | Mon 2/27/17 | ETS |
| 726 | Interim Assessment Registration, Test Content and Ancillaries | 171 days | Fri 7/1/16 | Mon 3/6/17 |  |
| 727 | Current Interim Assessments available | 0 days | Fri 7/1/16 | Fri 7/1/16 | Smarter Balanced |
| 728 | Update enrollment/test administration information | 50 days | Tue 9/27/16 | Wed 12/7/16 | ETS |
| 729 | New enhanced test packages available from Smarter Balanced | 0 days | Mon 2/6/17 | Mon 2/6/17 | Smarter Balanced |
| 730 | Process new test packages | 20 days | Mon 2/6/17 | Fri 3/3/17 | AIR |
| 731 | Updated Interim Comprehensive Assessment (summative clone) (ICA) launched | 1 day | Mon 3/6/17 | Mon 3/6/17 | AIR |
| 732 | Updated Interim Assessment Blocks (IAB) launched | 1 day | Mon 3/6/17 | Mon 3/6/17 | AIR |
| 733 | Configure Smarter Balanced System User Guide for CA | 40 days | Fri 7/1/16 | Fri 8/26/16 | ETS,AIR |
| 734 | Configure Smarter Balanced Scoring Guide for CA | 40 days | Fri 7/1/16 | Fri 8/26/16 | ETS,AIR |
| 735 | Configure Smarter Balanced System Infrastructure Guide for CA | 40 days | Fri 7/1/16 | Fri 8/26/16 | ETS,AIR |
| 736 | Configure Smarter Balanced System Training Workbook for CA | 40 days | Fri 7/1/16 | Fri 8/26/16 | ETS,AIR |
| 737 | Interim Assessment Reporting | 101 days | Tue 2/14/17 | Tue 7/4/17 |  |
| 738 | Deliver Interim Results to Smarter Balanced | 101 days | Tue 2/14/17 | Tue 7/4/17 | ETS,AIR |
| 739 | Summative Computer Based Assessments | 171 days | Mon 11/14/16 | Fri 7/14/17 |  |
| 740 | Summative content packages available for CAT | 0 days | Mon 11/14/16 | Mon 11/14/16 | Smarter Balanced |
| 741 | Summative content packages available for PT | 0 days | Thu 12/1/16 | Thu 12/1/16 | Smarter Balanced |
| 742 | Summative test packages available for CAT and PT | 0 days | Mon 1/9/17 | Mon 1/9/17 | Smarter Balanced |
| 743 | Import and QC test packages | 20 days | Mon 1/9/17 | Fri 2/3/17 | ETS |
| 744 | Update enrollment/test administration information | 20 days | Mon 1/16/17 | Fri 2/10/17 | ETS |
| 745 | Administer summative assessments (Smarter Balanced ELA/Math, ELA/Math Alternate) | 90 days | Mon 3/13/17 | Fri 7/14/17 | ETS |
| 746 | Summative Paper/Pencil Testing | 199 days | Wed 10/12/16 | Fri 7/21/17 |  |
| 747 | Reprint CST/CMA/CAPA Science & STS paper test | 30 days | Tue 11/15/16 | Fri 12/30/16 | ETS |
| 748 | Receive material orders | 35 days | Wed 10/12/16 | Thu 12/1/16 | ETS |
| 749 | Receive paper-based tests from Smarter Balanced | 1 day | Mon 12/5/16 | Mon 12/5/16 | Smarter Balanced |
| 750 | Add covers | 10 days | Tue 12/6/16 | Mon 12/19/16 | ETS |
| 751 | Print all summative operational paper tests | 30 days | Tue 12/20/16 | Wed 2/1/17 | ETS |
| 752 | Distribute paper tests as needed | 88 days | Thu 2/16/17 | Mon 6/19/17 | ETS |
| 753 | Receive paper tests | 75 days | Mon 3/20/17 | Fri 6/30/17 | ETS |
| 754 | Scan paper tests | 76 days | Mon 3/20/17 | Mon 7/3/17 | ETS |
| 755 | Conduct resolutions on paper tests | 90 days | Mon 3/20/17 | Fri 7/21/17 | ETS |
| 756 | Special Versions | 150 days | Tue 12/6/16 | Wed 7/5/17 |  |
| 757 | Produce large print & Braille | 40 days | Tue 12/6/16 | Wed 2/1/17 | ETS |
| 758 | Deliver large print and Braille as requested | 100 days | Thu 2/16/17 | Wed 7/5/17 | ETS |
| 759 | Scoring | 90 days | Mon 3/27/17 | Fri 7/28/17 |  |
| 760 | Summative Computer Based Assessments | 90 days | Mon 3/27/17 | Fri 7/28/17 |  |
| 761 | Hand and AI scoring occurs | 90 days | Mon 3/27/17 | Fri 7/28/17 | ETS,MI |
| 762 | Perform scoring QC | 90 days | Mon 3/27/17 | Fri 7/28/17 | ETS |
| 763 | Final scoring occurs | 90 days | Mon 3/27/17 | Fri 7/28/17 | ETS |
| 764 | Psychometric Analysis | 38 days | Mon 5/22/17 | Wed 7/12/17 |  |
| 765 | Conduct Item Analysis of CAASPP Summative assessments | 16 days | Mon 5/22/17 | Mon 6/12/17 | ETS |
| 766 | Item Analysis Files delivered to CDE | 1 day | Tue 6/13/17 | Tue 6/13/17 | ETS |
| 767 | Facilitate Alternate Assessment Data Review meeting | 1 day | Wed 7/12/17 | Wed 7/12/17 | ETS |
| 768 | Reporting | 472 days | Tue 9/6/16 | Tue 7/3/18 |  |
| 769 | Summative Assessment | 472 days | Tue 9/6/16 | Tue 7/3/18 |  |
| 770 | Delivery of Data Files to CDE and Smarter Balanced | 117 days | Mon 3/27/17 | Tue 9/5/17 |  |
| 771 | Prepare student data files | 90 days | Mon 3/27/17 | Fri 7/28/17 | ETS |
| 772 | Post initial student data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Mon 7/31/17 | Mon 7/31/17 | ETS |
| 773 | Post final data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Tue 9/5/17 | Tue 9/5/17 | ETS |
| 774 | Online Reporting Systems | 472 days | Tue 9/6/16 | Tue 7/3/18 |  |
| 775 | Online Reporting Systems Setup | 37 days | Tue 9/6/16 | Wed 10/26/16 |  |
| 776 | Gather specifications for AIR online reporting systems | 5 days | Tue 9/6/16 | Mon 9/12/16 | ETS,AIR |
| 777 | CDE reviews online reporting system specifications | 10 days | Tue 9/13/16 | Mon 9/26/16 | CDE |
| 778 | Configure online reporting systems | 20 days | Tue 9/27/16 | Mon 10/24/16 | ETS,AIR |
| 779 | Demonstrate online reporting systems to CDE | 1 day | Tue 10/25/16 | Tue 10/25/16 | ETS,AIR |
| 780 | Deploy online reporting system | 1 day | Wed 10/26/16 | Wed 10/26/16 | ETS,AIR |
| 781 | Student Level Reporting | 375 days | Wed 1/25/17 | Tue 7/3/18 |  |
| 782 | Provide final individual scores within 4 weeks of student online test completion | 90 days | Wed 2/28/18 | Tue 7/3/18 | ETS,AIR |
| 783 | Launch ISR availability within online reporting system | 1 day | Wed 1/25/17 | Wed 1/25/17 | ETS,AIR |
| 784 | School Level Reporting | 1 day | Thu 4/13/17 | Thu 4/13/17 |  |
| 785 | Launch school level reporting functionality | 1 day | Thu 4/13/17 | Thu 4/13/17 | ETS,AIR |
| 786 | LEA Level Reporting | 1 day | Fri 4/28/17 | Fri 4/28/17 |  |
| 787 | Launch LEA level reporting functionality | 1 day | Fri 4/28/17 | Fri 4/28/17 | ETS,AIR |
| 788 | State Level Reporting | 188 days | Tue 10/25/16 | Wed 7/19/17 |  |
| 789 | State Aggregate Reporting Website | 188 days | Tue 10/25/16 | Wed 7/19/17 |  |
| 790 | Develop business requirements | 45 days | Tue 10/25/16 | Fri 12/30/16 | ETS |
| 791 | CDE provides text for site | 1 day | Mon 3/27/17 | Mon 3/27/17 | CDE |
| 792 | Construct web reporting site | 30 days | Tue 3/28/17 | Mon 5/8/17 | ETS |
| 793 | CDE UAT of Web Reporting Site | 10 days | Tue 5/9/17 | Mon 5/22/17 | CDE |
| 794 | CDE provides feedback on changes needed | 10 days | Tue 5/23/17 | Mon 6/5/17 | CDE |
| 795 | Apply changes | 5 days | Tue 6/6/17 | Mon 6/12/17 | ETS |
| 796 | CDE second UAT | 5 days | Tue 6/13/17 | Mon 6/19/17 | CDE |
| 797 | Finalize site with CDE updates | 5 days | Tue 6/20/17 | Mon 6/26/17 | ETS |
| 798 | Deploy State level reporting website | 1 day | Wed 7/19/17 | Wed 7/19/17 | ETS |
| 799 | Individual Student Report | 195 days | Tue 10/25/16 | Fri 7/28/17 |  |
| 800 | Develop individual student report | 40 days | Tue 10/25/16 | Wed 12/21/16 | ETS |
| 801 | CDE reviews individual student report | 10 days | Thu 12/22/16 | Fri 1/6/17 | CDE |
| 802 | Update individual student report | 3 days | Mon 1/9/17 | Wed 1/11/17 | ETS |
| 803 | CDE 2nd review of individual student report | 5 days | Thu 1/12/17 | Wed 1/18/17 | CDE |
| 804 | Apply updates & submit to CDE for approval | 3 days | Thu 1/19/17 | Mon 1/23/17 | ETS |
| 805 | Provide electronic student roster reports to LEAs | 20 days | Mon 7/3/17 | Fri 7/28/17 | ETS |
| 806 | Print and ship Individual Student Reports (ISR) to LEAs | 20 days | Mon 7/3/17 | Fri 7/28/17 | ETS |
| 807 | Rescore Process | 120 days | Mon 3/27/17 | Fri 9/8/17 |  |
| 808 | LEAs request rescores | 90 days | Mon 3/27/17 | Fri 7/28/17 | LEAs |
| 809 | Provide rescore results | 90 days | Mon 5/8/17 | Fri 9/8/17 | ETS |
| 810 | Invoicing for rescores occurs | 10 days | Mon 5/15/17 | Fri 5/26/17 | ETS |
| 811 | Interpretive Guides | 31 days | Mon 3/20/17 | Mon 5/1/17 |  |
| 812 | Produce interpretive guides | 30 days | Mon 3/20/17 | Fri 4/28/17 | ETS |
| 813 | Post interpretive guides | 1 day | Mon 5/1/17 | Mon 5/1/17 | ETS |
| 814 | Technical Report | 61 days | Wed 9/6/17 | Wed 11/29/17 |  |
| 815 | Develop Technical Manual | 40 days | Wed 9/6/17 | Tue 10/31/17 | ETS |
| 816 | CDE reviews Technical Report and returns edits to ETS | 10 days | Wed 11/1/17 | Tue 11/14/17 | CDE |
| 817 | ETS applies edits and delivers final Technical Report to CDE | 3 days | Wed 11/15/17 | Fri 11/17/17 | ETS |
| 818 | CDE 2nd review of Technical Report | 5 days | Mon 11/20/17 | Fri 11/24/17 | CDE |
| 819 | Apply updates and deliver Technical Manual to CDE for approval | 3 days | Mon 11/27/17 | Wed 11/29/17 | ETS |
| 820 | Operational Test Administration Complete | 0 days | Tue 7/3/18 | Tue 7/3/18 |  |
| 821 | Year two complete | 0 days | Tue 1/23/18 | Tue 1/23/18 |  |
| 822 | Administration Year Three (July 2017 - December 2018) | 397 days | Thu 6/22/17 | Fri 12/28/18 |  |
| 823 | Begin administration year three | 0 days | Mon 7/3/17 | Mon 7/3/17 |  |
| 824 | Project Management | 397 days | Thu 6/22/17 | Fri 12/28/18 |  |
| 825 | Project Management Begins | 0 days | Mon 7/3/17 | Mon 7/3/17 |  |
| 826 | Annual Planning Meetings | 35 days | Thu 6/22/17 | Wed 8/9/17 |  |
| 827 | Schedule and prepare/ship materials for annual planning meeting | 3 days | Thu 6/22/17 | Mon 6/26/17 | ETS |
| 828 | Conduct annual planning meeting | 3 days | Mon 7/3/17 | Wed 7/5/17 | CDE,AIR,MI,ETS |
| 829 | Update project documentation and management plan | 15 days | Thu 7/6/17 | Wed 7/26/17 | ETS |
| 830 | Prepare meeting minutes/participant list and deliver to CDE | 10 days | Thu 7/27/17 | Wed 8/9/17 | ETS |
| 831 | Program Meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 |  |
| 832 | Conduct weekly internal status meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 | ETS |
| 833 | Conduct weekly CDE management meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 | CDE,AIR,MI,ETS |
| 834 | Conduct weekly CDE technical meeting | 390 days | Mon 7/3/17 | Fri 12/28/18 | CDE,AIR,MI,ETS |
| 835 | State Board Meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 |  |
| 836 | Attend State Board meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 | CDE,ETS |
| 837 | Technical Advisory Group (TAG) Meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 |  |
| 838 | Work with the CDE to develop TAG agendas | 390 days | Mon 7/3/17 | Fri 12/28/18 | CDE,ETS |
| 839 | Attend TAG meetings | 390 days | Mon 7/3/17 | Fri 12/28/18 | CDE,ETS |
| 840 | Monthly Progress Reports | 390 days | Mon 7/3/17 | Fri 12/28/18 |  |
| 841 | Deliver monthly progress reports to CDE | 390 days | Mon 7/3/17 | Fri 12/28/18 | ETS |
| 842 | Project Management Plan (PMP) & Project Definitions Document | 80 days | Mon 7/3/17 | Fri 10/20/17 |  |
| 843 | Project Management Plan for Overall CAASPP Activities | 70 days | Mon 7/3/17 | Fri 10/6/17 |  |
| 844 | Update Work Breakdown Structure as needed | 10 days | Thu 7/6/17 | Wed 7/19/17 | ETS |
| 845 | Update project management plan for overall CAASPP activities as needed | 30 days | Mon 7/3/17 | Fri 8/11/17 | ETS |
| 846 | CDE reviews updates to the project management plan for overall CAASPP activities | 20 days | Mon 8/14/17 | Fri 9/8/17 | CDE |
| 847 | Finalize updates to the project management plan for overall CAASPP activities | 20 days | Mon 9/11/17 | Fri 10/6/17 | ETS |
| 848 | Project Definitions Document for the Assessment Delivery System | 70 days | Mon 7/3/17 | Fri 10/6/17 |  |
| 849 | Develop draft project management plan for the Assessment Delivery System | 30 days | Mon 7/3/17 | Fri 8/11/17 | ETS,AIR |
| 850 | CDE reviews project management plan for the Assessment Delivery System | 20 days | Mon 8/14/17 | Fri 9/8/17 | CDE |
| 851 | Finalize project management plan for the Assessment Delivery System | 20 days | Mon 9/11/17 | Fri 10/6/17 | ETS,AIR |
| 852 | Integrated Comprehensive Work plan & Project Schedule | 10 days | Mon 10/9/17 | Fri 10/20/17 |  |
| 853 | CDE reviews comprehensive integrated project schedule | 10 days | Mon 10/9/17 | Fri 10/20/17 | CDE |
| 854 | CDE project schedule review complete | 0 days | Fri 10/20/17 | Fri 10/20/17 | CDE |
| 855 | Test Security | 390 days | Mon 7/3/17 | Fri 12/28/18 |  |
| 856 | Update the Test Security Plan for the 2018 administration | 2 days | Mon 7/3/17 | Tue 7/4/17 | ETS |
| 857 | Deliver the Test Security Plan to CDE for review | 1 day | Wed 7/5/17 | Wed 7/5/17 | ETS |
| 858 | CDE reviews the Test Security Plan | 10 days | Thu 7/6/17 | Wed 7/19/17 | CDE |
| 859 | Apply CDE edits to the Test Security Plan | 3 days | Thu 7/20/17 | Mon 7/24/17 | ETS |
| 860 | CDE 2nd review of the Test Security Plan | 5 days | Tue 7/25/17 | Mon 7/31/17 | CDE |
| 861 | Apply updates and deliver the final Test Security Plan to CDE for approval | 3 days | Tue 8/1/17 | Thu 8/3/17 | ETS |
| 862 | Monitor social media sites for test security breaches | 390 days | Mon 7/3/17 | Fri 12/28/18 | ETS |
| 863 | Perform on-site security audit visits | 125 days | Wed 1/24/18 | Tue 7/17/18 | ETS |
| 864 | Investigate test security breaches as needed | 125 days | Wed 1/24/18 | Tue 7/17/18 | ETS |
| 865 | Deliver audit reports to CDE | 125 days | Wed 1/31/18 | Tue 7/24/18 | ETS |
| 866 | Data Driven Improvement | 237 days | Mon 7/3/17 | Tue 5/29/18 |  |
| 867 | Pre-Testing Data Collection | 77 days | Mon 10/23/17 | Tue 2/6/18 |  |
| 868 | Pre-Test Survey | 77 days | Mon 10/23/17 | Tue 2/6/18 |  |
| 869 | Develop Pre-Test Survey | 20 days | Mon 10/23/17 | Fri 11/17/17 | ETS |
| 870 | CDE reviews Pre-Test Survey | 10 days | Mon 11/20/17 | Fri 12/1/17 | CDE |
| 871 | Revise Pre-Test Survey | 3 days | Mon 12/4/17 | Wed 12/6/17 | ETS |
| 872 | CDE 2nd review of Pre-Test Survey | 5 days | Thu 12/7/17 | Wed 12/13/17 | CDE |
| 873 | Apply updates and deliver final Pre-Test Survey to CDE for approval | 3 days | Thu 12/14/17 | Mon 12/18/17 | ETS |
| 874 | Administer Pre-Test Survey | 20 days | Tue 12/26/17 | Mon 1/22/18 | ETS |
| 875 | Analyze survey results | 10 days | Tue 1/23/18 | Mon 2/5/18 | ETS |
| 876 | Deliver survey results & recommended program improvements to CDE | 1 day | Tue 2/6/18 | Tue 2/6/18 | ETS |
| 877 | Post-Testing Data Collection | 237 days | Mon 7/3/17 | Tue 5/29/18 |  |
| 878 | Post-Test Survey | 67 days | Mon 2/26/18 | Tue 5/29/18 |  |
| 879 | Develop Post-Test Survey | 20 days | Mon 2/26/18 | Fri 3/23/18 | ETS |
| 880 | CDE reviews Post-Test Survey | 10 days | Mon 3/26/18 | Fri 4/6/18 | CDE |
| 881 | Revise Post-Test Survey | 3 days | Mon 4/9/18 | Wed 4/11/18 | ETS |
| 882 | CDE 2nd review of Post-Test Survey | 5 days | Thu 4/12/18 | Wed 4/18/18 | CDE |
| 883 | Apply updates and deliver final Post-Test Survey to CDE for approval | 3 days | Thu 4/19/18 | Mon 4/23/18 | ETS |
| 884 | Administer Post-Test Survey | 20 days | Tue 5/1/18 | Mon 5/28/18 | ETS |
| 885 | Deliver survey results & recommended program improvements to CDE | 1 day | Tue 5/29/18 | Tue 5/29/18 | ETS |
| 886 | Post-Test Focus Groups for Administrators | 60 days | Mon 7/3/17 | Fri 9/22/17 |  |
| 887 | Prepare materials for Post-Test Focus Groups | 9 days | Mon 7/3/17 | Thu 7/13/17 | ETS |
| 888 | Conduct Sacramento focus group | 2 days | Fri 7/14/17 | Mon 7/17/17 | ETS |
| 889 | Conduct Southern CA focus group | 2 days | Thu 7/27/17 | Fri 7/28/17 | ETS |
| 890 | Compile results and recommended program improvements to CDE | 40 days | Mon 7/31/17 | Fri 9/22/17 | ETS |
| 891 | Test Coordinator Advisory Group | 162 days | Thu 8/17/17 | Fri 3/30/18 |  |
| 892 | Prepare materials for Test Coordinator Advisory Group 1 | 20 days | Thu 8/17/17 | Wed 9/13/17 | ETS |
| 893 | Conduct September Advisory Group 1 | 1 day | Thu 9/14/17 | Thu 9/14/17 | ETS |
| 894 | Compile results and recommended program improvements to CDE | 40 days | Fri 9/15/17 | Thu 11/9/17 | ETS |
| 895 | Prepare materials for Test Coordinator Advisory Group 2 | 20 days | Fri 1/5/18 | Thu 2/1/18 | ETS |
| 896 | Conduct February Advisory Group 2 | 1 day | Fri 2/2/18 | Fri 2/2/18 | ETS |
| 897 | Compile results and recommended program improvements to CDE | 40 days | Mon 2/5/18 | Fri 3/30/18 | ETS |
| 898 | caaspp.org User Focus Group | 62 days | Wed 8/23/17 | Thu 11/16/17 |  |
| 899 | Prepare materials for caaspp.org Focus Groups | 20 days | Wed 8/23/17 | Tue 9/19/17 | ETS |
| 900 | Conduct caaspp.org User Focus group | 2 days | Wed 9/20/17 | Thu 9/21/17 | ETS |
| 901 | Compile results and recommended program improvements to CDE | 40 days | Fri 9/22/17 | Thu 11/16/17 | ETS |
| 902 | Project Management Complete | 0 days | Fri 12/28/18 | Fri 12/28/18 |  |
| 903 | Training & LEA Support | 252 days | Mon 7/3/17 | Tue 6/19/18 |  |
| 904 | Training & LEA Support Begins | 0 days | Mon 7/3/17 | Mon 7/3/17 |  |
| 905 | CalTAC | 252 days | Mon 7/3/17 | Tue 6/19/18 |  |
| 906 | Train CalTAC staff on the CAASPP program | 10 days | Mon 7/3/17 | Fri 7/14/17 | ETS |
| 907 | Establish help desk technical phone, web chat and e-mail support | 10 days | Mon 7/3/17 | Fri 7/14/17 | ETS |
| 908 | Perform technology support site visits as needed | 242 days | Mon 7/17/17 | Tue 6/19/18 | ETS |
| 909 | LEA CAASPP Coordinator Designation Forms & Security Agreements | 64 days | Mon 7/3/17 | Thu 9/28/17 |  |
| 910 | Collect LEA CAASPP coordinator designation forms and security agreements | 50 days | Mon 7/3/17 | Fri 9/8/17 | ETS |
| 911 | Input updates into the LEA CAASPP coordinator database | 43 days | Mon 7/31/17 | Wed 9/27/17 | ETS |
| 912 | Provide CDE access to the CAASPP coordinator database | 1 day | Thu 9/28/17 | Thu 9/28/17 | ETS |
| 913 | LEA Technology Readiness | 91 days | Mon 7/31/17 | Mon 12/4/17 |  |
| 914 | Develop technology readiness information collection methodologies | 30 days | Mon 7/31/17 | Fri 9/8/17 | ETS |
| 915 | Collect technology readiness information from LEAs | 40 days | Mon 9/11/17 | Fri 11/3/17 | ETS |
| 916 | Conduct outreach campaign to non-responsive LEAs | 20 days | Mon 11/6/17 | Fri 12/1/17 | ETS |
| 917 | Present readiness results to CDE | 1 day | Mon 12/4/17 | Mon 12/4/17 | ETS |
| 918 | Summative Assessment Test Administration Training Manuals | 216 days | Mon 7/3/17 | Mon 4/30/18 |  |
| 919 | Smarter Balanced Test Administration Manual (TAM) | 111 days | Mon 7/3/17 | Mon 12/4/17 |  |
| 920 | TAM available from Smarter Balanced | 0 days | Mon 7/3/17 | Mon 7/3/17 | Smarter Balanced |
| 921 | Adapt Smarter Balanced TAM for California | 15 days | Mon 9/11/17 | Fri 9/29/17 | ETS |
| 922 | CDE reviews Smarter Balanced TAM | 10 days | Mon 10/2/17 | Fri 10/13/17 | CDE |
| 923 | Apply CDE edits to Smarter Balanced TAM | 3 days | Mon 10/16/17 | Wed 10/18/17 | ETS |
| 924 | CDE 2nd review of Smarter Balanced TAM | 5 days | Thu 10/19/17 | Wed 10/25/17 | CDE |
| 925 | Apply updates and deliver final Smarter Balanced TAM to CDE for approval | 3 days | Thu 10/26/17 | Mon 10/30/17 | ETS |
| 926 | Post Smarter Balanced TAM to caaspp.org | 1 day | Tue 10/31/17 | Tue 10/31/17 | ETS |
| 927 | Print Smarter Balanced TAM | 20 days | Tue 10/31/17 | Mon 11/27/17 | ETS |
| 928 | Distribute Smarter Balanced TAM to LEAs | 5 days | Tue 11/28/17 | Mon 12/4/17 | ETS |
| 929 | Alternate Assessment Test Administration Manual (TAM) | 72 days | Mon 8/14/17 | Tue 11/21/17 |  |
| 930 | Develop Alternate Assessment TAM | 25 days | Mon 8/14/17 | Fri 9/15/17 | ETS |
| 931 | CDE reviews Alternate Assessment TAM | 10 days | Mon 9/18/17 | Fri 9/29/17 | CDE |
| 932 | Apply CDE edits to Alternate Assessment TAM | 3 days | Mon 10/2/17 | Wed 10/4/17 | ETS |
| 933 | CDE 2nd review of Alternate Assessment TAM | 5 days | Thu 10/5/17 | Wed 10/11/17 | CDE |
| 934 | Apply updates and deliver final Alternate Assessment TAM to CDE for approval | 3 days | Thu 10/12/17 | Mon 10/16/17 | ETS |
| 935 | Post Alternate Assessment TAM to caaspp.org | 1 day | Tue 10/17/17 | Tue 10/17/17 | ETS |
| 936 | Print Alternate Assessment TAM | 20 days | Wed 10/18/17 | Tue 11/14/17 | ETS |
| 937 | Distribute Alternate Assessment TAM to LEAs | 5 days | Wed 11/15/17 | Tue 11/21/17 | ETS |
| 938 | LEA CAASPP Test Coordinators Manual (LEA TCM) | 47 days | Thu 10/26/17 | Fri 12/29/17 |  |
| 939 | Develop LEA TCM | 25 days | Thu 10/26/17 | Wed 11/29/17 | ETS |
| 940 | CDE reviews LEA TCM | 10 days | Thu 11/30/17 | Wed 12/13/17 | CDE |
| 941 | Apply CDE edits to LEA TCM | 3 days | Thu 12/14/17 | Mon 12/18/17 | ETS |
| 942 | CDE 2nd review of LEA TCM | 5 days | Tue 12/19/17 | Mon 12/25/17 | CDE |
| 943 | Apply updates and deliver final LEA TCM to CDE for approval | 3 days | Tue 12/26/17 | Thu 12/28/17 | ETS |
| 944 | Post LEA TCM to caaspp.org | 1 day | Fri 12/29/17 | Fri 12/29/17 | ETS |
| 945 | Test Site Coordinators Manual (SCM) | 47 days | Thu 10/26/17 | Fri 12/29/17 |  |
| 946 | Develop SCM | 25 days | Thu 10/26/17 | Wed 11/29/17 | ETS |
| 947 | CDE reviews SCM | 10 days | Thu 11/30/17 | Wed 12/13/17 | CDE |
| 948 | Apply CDE edits to SCM | 3 days | Thu 12/14/17 | Mon 12/18/17 | ETS |
| 949 | CDE 2nd review of SCM | 5 days | Tue 12/19/17 | Mon 12/25/17 | CDE |
| 950 | Apply updates and deliver final SCM to CDE for approval | 3 days | Tue 12/26/17 | Thu 12/28/17 | ETS |
| 951 | Post SCM to caaspp.org | 1 day | Fri 12/29/17 | Fri 12/29/17 | ETS |
| 952 | Test Examiners Manual (TEM) | 47 days | Thu 11/2/17 | Fri 1/5/18 |  |
| 953 | Develop TEM | 25 days | Thu 11/2/17 | Wed 12/6/17 | ETS |
| 954 | CDE reviews TEM | 10 days | Thu 12/7/17 | Wed 12/20/17 | CDE |
| 955 | Apply CDE edits to TEM | 3 days | Thu 12/21/17 | Mon 12/25/17 | ETS |
| 956 | CDE 2nd review of TEM | 5 days | Tue 12/26/17 | Mon 1/1/18 | CDE |
| 957 | Apply updates and deliver final TEM to CDE for approval | 3 days | Tue 1/2/18 | Thu 1/4/18 | ETS |
| 958 | Post TEM to caaspp.org | 1 day | Fri 1/5/18 | Fri 1/5/18 | ETS |
| 959 | Technology Services Coordinators Manual (TSCM) | 47 days | Thu 11/2/17 | Fri 1/5/18 |  |
| 960 | Develop TSCM | 25 days | Thu 11/2/17 | Wed 12/6/17 | ETS |
| 961 | CDE reviews TSCM | 10 days | Thu 12/7/17 | Wed 12/20/17 | CDE |
| 962 | Apply CDE edits to TSCM | 3 days | Thu 12/21/17 | Mon 12/25/17 | ETS |
| 963 | CDE 2nd review of TSCM | 5 days | Tue 12/26/17 | Mon 1/1/18 | CDE |
| 964 | Apply updates and deliver final TSCM to CDE for approval | 3 days | Tue 1/2/18 | Thu 1/4/18 | ETS |
| 965 | Post TSCM to caaspp.org | 1 day | Fri 1/5/18 | Fri 1/5/18 | ETS |
| 966 | CAASPP Test Operations Management System Manual (TOMS) | 47 days | Mon 8/14/17 | Tue 10/17/17 |  |
| 967 | Develop TOMS manual | 25 days | Mon 8/14/17 | Fri 9/15/17 | ETS |
| 968 | CDE reviews TOMS manual | 10 days | Mon 9/18/17 | Fri 9/29/17 | CDE |
| 969 | Apply CDE edits to TOMS manual | 3 days | Mon 10/2/17 | Wed 10/4/17 | ETS |
| 970 | CDE 2nd review of TOMS manual | 5 days | Thu 10/5/17 | Wed 10/11/17 | CDE |
| 971 | Apply updates and deliver final TOMS manual to CDE for approval | 3 days | Thu 10/12/17 | Mon 10/16/17 | ETS |
| 972 | Post TOMS manual to caaspp.org | 1 day | Tue 10/17/17 | Tue 10/17/17 | ETS |
| 973 | STS for Dual Immersion Students Manual | 47 days | Mon 9/11/17 | Tue 11/14/17 |  |
| 974 | Develop STS manual | 25 days | Mon 9/11/17 | Fri 10/13/17 | ETS |
| 975 | CDE reviews STS manual | 10 days | Mon 10/16/17 | Fri 10/27/17 | CDE |
| 976 | Apply CDE edits to STS manual | 3 days | Mon 10/30/17 | Wed 11/1/17 | ETS |
| 977 | CDE 2nd review of STS manual | 5 days | Thu 11/2/17 | Wed 11/8/17 | CDE |
| 978 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Thu 11/9/17 | Mon 11/13/17 | ETS |
| 979 | Post STS manual to caaspp.org | 1 day | Tue 11/14/17 | Tue 11/14/17 | ETS |
| 980 | Test Administrator Quick Start Guide | 47 days | Mon 9/25/17 | Tue 11/28/17 |  |
| 981 | Develop STS manual | 25 days | Mon 9/25/17 | Fri 10/27/17 | ETS |
| 982 | CDE reviews STS manual | 10 days | Mon 10/30/17 | Fri 11/10/17 | CDE |
| 983 | Apply CDE edits to STS manual | 3 days | Mon 11/13/17 | Wed 11/15/17 | ETS |
| 984 | CDE 2nd review of STS manual | 5 days | Thu 11/16/17 | Wed 11/22/17 | CDE |
| 985 | Apply updates and deliver final STS manual to CDE for approval | 3 days | Thu 11/23/17 | Mon 11/27/17 | ETS |
| 986 | Post STS manual to caaspp.org | 1 day | Tue 11/28/17 | Tue 11/28/17 | ETS |
| 987 | Online Reporting Guide | 52 days | Mon 12/18/17 | Tue 2/27/18 |  |
| 988 | Develop Online Reporting Guide manual | 30 days | Mon 12/18/17 | Fri 1/26/18 | ETS |
| 989 | CDE reviews Online Reporting Guide manual | 10 days | Mon 1/29/18 | Fri 2/9/18 | CDE |
| 990 | Apply CDE edits to Online Reporting Guide manual | 3 days | Mon 2/12/18 | Wed 2/14/18 | ETS |
| 991 | CDE 2nd review of Online Reporting Guide manual | 5 days | Thu 2/15/18 | Wed 2/21/18 | CDE |
| 992 | Apply updates and deliver final Online Reporting Guide manual to CDE for approval | 3 days | Thu 2/22/18 | Mon 2/26/18 | ETS |
| 993 | Post Online Reporting Guide to caaspp.org | 1 day | Tue 2/27/18 | Tue 2/27/18 | ETS |
| 994 | CAASPP Post-Test Guide | 76 days | Mon 1/15/18 | Mon 4/30/18 |  |
| 995 | Develop Post-Test Guide | 30 days | Mon 1/15/18 | Fri 2/23/18 | ETS |
| 996 | CDE reviews Post-Test Guide | 10 days | Mon 2/26/18 | Fri 3/9/18 | CDE |
| 997 | Apply CDE edits to Post-Test Guide | 3 days | Mon 3/12/18 | Wed 3/14/18 | ETS |
| 998 | CDE 2nd review of Post-Test Guide | 5 days | Thu 3/15/18 | Wed 3/21/18 | CDE |
| 999 | Apply updates and deliver final Post-Test Guide to CDE for approval | 3 days | Thu 3/22/18 | Mon 3/26/18 | ETS |
| 1000 | Post Post-Test Guide to caaspp.org | 1 day | Tue 3/27/18 | Tue 3/27/18 | ETS |
| 1001 | Print Post-Test Guide | 20 days | Tue 3/27/18 | Mon 4/23/18 | ETS |
| 1002 | Distribute Post-Test Guide to LEAs | 5 days | Tue 4/24/18 | Mon 4/30/18 | ETS |
| 1003 | Training Webcasts and Workshops | 197 days | Fri 8/18/17 | Mon 5/21/18 |  |
| 1004 | Training Webcasts | 192 days | Fri 8/18/17 | Mon 5/14/18 |  |
| 1005 | Present and archive Using the Digital Library webcast | 1 day | Fri 8/18/17 | Fri 8/18/17 | ETS |
| 1006 | Present and archive Using Interim Assessments webcast | 1 day | Thu 9/7/17 | Thu 9/7/17 | ETS |
| 1007 | Present and archive Preparing CALPADS Data for Testing webcast | 1 day | Thu 9/14/17 | Thu 9/14/17 | ETS |
| 1008 | Present and archive Test Operations Management System (TOMS) Training webcast | 1 day | Thu 9/21/17 | Thu 9/21/17 | ETS |
| 1009 | Present and archive Preparing Technology for Online Testing webcast | 1 day | Thu 10/12/17 | Thu 10/12/17 | ETS |
| 1010 | Present and archive Accessibility and Accommodations webcast | 1 day | Thu 10/19/17 | Thu 10/19/17 | ETS |
| 1011 | Present and archive Using the Online Practice Tests and Training Tests webcast | 1 day | Thu 11/16/17 | Thu 11/16/17 | ETS |
| 1012 | Present and archive Pre-Test webcast | 1 day | Tue 1/9/18 | Tue 1/9/18 | ETS,AIR |
| 1013 | Present and archive Alternate Assessment training webcast | 1 day | Wed 1/10/18 | Wed 1/10/18 | ETS |
| 1014 | Present and archive Test Security LEA Training webcast | 1 day | Tue 1/16/18 | Tue 1/16/18 | ETS |
| 1015 | Present and archive Post-Test webcast | 1 day | Mon 5/14/18 | Mon 5/14/18 | ETS |
| 1016 | Regional Training Workshops | 181 days | Mon 9/11/17 | Mon 5/21/18 |  |
| 1017 | Present regional Digital Library and Interim workshops | 5 days | Mon 9/11/17 | Fri 9/15/17 | ETS |
| 1018 | Present regional Pre-Test Workshops | 22 days | Mon 1/15/18 | Tue 2/13/18 | ETS,AIR |
| 1019 | Present regional Post-Test Workshops | 5 days | Tue 5/15/18 | Mon 5/21/18 | ETS |
| 1020 | Interim CR Scoring Training | 101 days | Wed 10/11/17 | Wed 2/28/18 |  |
| 1021 | Receive CR scoring methodology and procedures from Smarter Balanced | 1 day | Wed 10/11/17 | Wed 10/11/17 | Smarter Balanced |
| 1022 | Produce workshop slides and e-mail announcement | 20 days | Thu 1/11/18 | Wed 2/7/18 | ETS |
| 1023 | Deliver summative and interim CR scoring training workshops | 15 days | Thu 2/8/18 | Wed 2/28/18 | ETS |
| 1024 | Training & LEA Support Complete | 0 days | Tue 6/19/18 | Tue 6/19/18 |  |
| 1025 | Test Development | 392 days | Thu 6/29/17 | Fri 12/28/18 |  |
| 1026 | Begin Test Development | 0 days | Mon 7/3/17 | Mon 7/3/17 |  |
| 1027 | Primary Language Field Test | 138 days | Wed 1/24/18 | Fri 8/3/18 |  |
| 1028 | Administer Primary Language Census Field Test | 100 days | Wed 1/24/18 | Tue 6/12/18 | ETS |
| 1029 | Conduct range finding external committee meeting | 2 days | Wed 6/27/18 | Thu 6/28/18 | ETS,External Committee,CDE |
| 1030 | CDE approves training scoring sets | 10 days | Fri 6/29/18 | Thu 7/12/18 | CDE |
| 1031 | Perform analysis on field test data | 20 days | Fri 6/29/18 | Thu 7/26/18 | ETS |
| 1032 | Conduct data review external committee meeting | 1 day | Fri 7/27/18 | Fri 7/27/18 | External Committee,CDE,ETS |
| 1033 | CDE approval of data review results | 5 days | Mon 7/30/18 | Fri 8/3/18 | CDE |
| 1034 | NGSS Field Test (Including Alt NGSS) | 121 days | Mon 3/12/18 | Mon 8/27/18 |  |
| 1035 | Administer NGSS Census Field Test | 80 days | Mon 3/12/18 | Fri 6/29/18 | ETS |
| 1036 | Conduct range finding external committee meeting | 2 days | Thu 7/26/18 | Fri 7/27/18 | External Committee,CDE,ETS |
| 1037 | Perform analysis on field test data | 20 days | Mon 7/30/18 | Fri 8/24/18 | ETS |
| 1038 | Conduct data review external committee meeting | 1 day | Mon 8/27/18 | Mon 8/27/18 | External Committee,CDE,ETS |
| 1039 | Alternate Assessment ELA/Math Embedded Field Test Item Development | 40 days | Thu 6/29/17 | Wed 8/23/17 |  |
| 1040 | Develop Alternate Assessment ELA/Math Assessment items | 23 days | Thu 6/29/17 | Mon 7/31/17 | ETS |
| 1041 | CDE reviews new items | 10 days | Tue 8/1/17 | Mon 8/14/17 | CDE |
| 1042 | External committee item review meetings | 2 days | Tue 8/15/17 | Wed 8/16/17 | External Committee,CDE,ETS |
| 1043 | CDE approves new items | 5 days | Thu 8/17/17 | Wed 8/23/17 | CDE |
| 1044 | Primary Language Embedded Field Test Item Development | 117 days | Wed 1/24/18 | Thu 7/5/18 |  |
| 1045 | Develop Primary Language Assessment items | 80 days | Wed 1/24/18 | Tue 5/15/18 | ETS |
| 1046 | CDE reviews new Primary Language items | 10 days | Wed 5/16/18 | Tue 5/29/18 | CDE |
| 1047 | External committee item review meetings | 2 days | Wed 5/30/18 | Thu 5/31/18 | External Committee,CDE,ETS |
| 1048 | CDE approves new items | 5 days | Fri 6/1/18 | Thu 6/7/18 | CDE |
| 1049 | Finalize items | 20 days | Fri 6/8/18 | Thu 7/5/18 | ETS |
| 1050 | Primary Language Operational Forms for the 2018 administration | 47 days | Fri 6/8/18 | Mon 8/13/18 |  |
| 1051 | Develop operational forms | 30 days | Fri 6/8/18 | Thu 7/19/18 | ETS |
| 1052 | CDE reviews operational forms | 10 days | Fri 7/20/18 | Thu 8/2/18 | CDE |
| 1053 | External committee forms review meeting | 2 days | Fri 8/3/18 | Mon 8/6/18 | External Committee,CDE,ETS |
| 1054 | CDE approves operational forms | 5 days | Tue 8/7/18 | Mon 8/13/18 | CDE |
| 1055 | NGSS Science (Including Alt NGSS) Embedded Field Test Item Development | 320 days | Mon 10/9/17 | Fri 12/28/18 |  |
| 1056 | Develop NGSS Science items | 152 days | Mon 10/9/17 | Tue 5/8/18 | ETS |
| 1057 | External committee item review meetings | 3 days | Wed 5/9/18 | Fri 5/11/18 | External Committee,CDE,ETS |
| 1058 | Develop pilot test forms | 100 days | Mon 5/14/18 | Fri 9/28/18 | ETS |
| 1059 | Prepare for online test delivery | 65 days | Mon 10/1/18 | Fri 12/28/18 | ETS |
| 1060 | Test Development Complete | 0 days | Fri 12/28/18 | Fri 12/28/18 |  |
| 1061 | Operational Test Administration | 369 days | Mon 7/3/17 | Thu 11/29/18 |  |
| 1062 | Operational Test Administration Begins | 0 days | Mon 7/3/17 | Mon 7/3/17 |  |
| 1063 | CAASPP Assessments | 276 days | Mon 7/3/17 | Mon 7/23/18 |  |
| 1064 | Testing Systems | 156 days | Mon 7/3/17 | Mon 2/5/18 |  |
| 1065 | Minimum System Requirements Document | 20 days | Mon 7/3/17 | Fri 7/28/17 |  |
| 1066 | Develop Minimum System Requirements Document | 5 days | Mon 7/3/17 | Fri 7/7/17 | ETS |
| 1067 | CDE reviews and approves Minimum System Requirements Document | 15 days | Mon 7/10/17 | Fri 7/28/17 | CDE |
| 1068 | System Configurations | 20 days | Mon 7/3/17 | Fri 7/28/17 |  |
| 1069 | Develop list of system configurations | 5 days | Mon 7/3/17 | Fri 7/7/17 | ETS |
| 1070 | CDE reviews and approves system configurations | 15 days | Mon 7/10/17 | Fri 7/28/17 | CDE |
| 1071 | Item Transfer | 45 days | Mon 11/13/17 | Fri 1/12/18 |  |
| 1072 | Receive Interim items from Smarter Balanced | 1 day | Mon 11/13/17 | Mon 11/13/17 | Smarter Balanced |
| 1073 | Import Interim field test items from Smarter Balanced | 10 days | Tue 11/14/17 | Mon 11/27/17 | ETS |
| 1074 | Receive Summative pools from Smarter Balanced | 1 day | Fri 12/29/17 | Fri 12/29/17 | Smarter Balanced |
| 1075 | Import items from Smarter Balanced and embed new field test items into testing system | 10 days | Mon 1/1/18 | Fri 1/12/18 | ETS |
| 1076 | Test Operations Management System (TOMS) | 71 days | Mon 7/3/17 | Mon 10/9/17 |  |
| 1077 | CDE confirms CALPADS information and list of designated supports/accommodations | 1 day | Mon 7/3/17 | Mon 7/3/17 | CDE |
| 1078 | Confirm business requirements for pre-test delivery reporting and application enhancements | 1 day | Tue 7/4/17 | Tue 7/4/17 | ETS |
| 1079 | Update CALPADS import function | 20 days | Tue 7/4/17 | Mon 7/31/17 | ETS |
| 1080 | Configure TOMS enhancements for the 2018 CAASPP administration | 15 days | Mon 7/31/17 | Fri 8/18/17 | ETS |
| 1081 | Begin daily updates of district and school user contact information | 1 day | Mon 8/21/17 | Mon 8/21/17 | ETS |
| 1082 | Functional testing | 10 days | Mon 8/21/17 | Fri 9/1/17 | ETS |
| 1083 | Dev-2-Dev Testing | 5 days | Mon 9/4/17 | Fri 9/8/17 | ETS |
| 1084 | Integration testing | 10 days | Mon 9/11/17 | Fri 9/22/17 | ETS |
| 1085 | Load testing | 10 days | Mon 9/11/17 | Fri 9/22/17 | ETS |
| 1086 | CDE UAT of TOMS enhancements | 5 days | Mon 9/25/17 | Fri 9/29/17 | CDE |
| 1087 | Apply fixes to TOMS enhancements | 5 days | Mon 10/2/17 | Fri 10/6/17 | ETS |
| 1088 | Deploy enhancements to TOMS | 1 day | Mon 10/9/17 | Mon 10/9/17 | ETS |
| 1089 | CA ISAAP Tool | 49 days | Wed 7/5/17 | Mon 9/11/17 |  |
| 1090 | Gather business requirements for CA ISAAP tool enhancements | 20 days | Wed 7/5/17 | Tue 8/1/17 | ETS |
| 1091 | Configure CA ISAAP tool for the 2018 administration | 5 days | Mon 8/21/17 | Fri 8/25/17 | ETS |
| 1092 | CDE UAT of CA ISAAP Tool | 5 days | Mon 8/28/17 | Fri 9/1/17 | CDE |
| 1093 | Apply fixes to CA ISAPP | 5 days | Mon 9/4/17 | Fri 9/8/17 | ETS |
| 1094 | Deploy CA ISAAP Tool | 1 day | Mon 9/11/17 | Mon 9/11/17 | ETS |
| 1095 | Test Delivery System (TDS) | 121 days | Mon 8/21/17 | Mon 2/5/18 |  |
| 1096 | Update Secure Browsers | 25 days | Mon 9/25/17 | Fri 10/27/17 | AIR |
| 1097 | Gather business requirements for application enhancements | 10 days | Mon 8/21/17 | Fri 9/1/17 | ETS,AIR |
| 1098 | Configure TDS for the 2018 CAASPP administration | 40 days | Mon 9/4/17 | Fri 10/27/17 | AIR |
| 1099 | TDS Testing for Interim Assessments | 41 days | Mon 10/30/17 | Mon 12/25/17 |  |
| 1100 | Functional testing | 10 days | Mon 10/30/17 | Fri 11/10/17 | AIR,ETS |
| 1101 | Dev-2-Dev Testing | 5 days | Mon 11/13/17 | Fri 11/17/17 | ETS,AIR |
| 1102 | Integration testing | 5 days | Mon 11/20/17 | Fri 11/24/17 | ETS,AIR |
| 1103 | Load testing | 5 days | Mon 11/27/17 | Fri 12/1/17 | ETS,AIR |
| 1104 | CDE UAT | 10 days | Mon 11/20/17 | Fri 12/1/17 | CDE |
| 1105 | End-to-End (E2E) Testing | 15 days | Mon 12/4/17 | Fri 12/22/17 | ETS,AIR |
| 1106 | Deploy TDS for Interim Assessments including Teacher Hand Scoring | 1 day | Mon 12/25/17 | Mon 12/25/17 | AIR |
| 1107 | TDS Testing for Summative Assessments | 41 days | Mon 12/11/17 | Mon 2/5/18 |  |
| 1108 | Functional testing | 10 days | Mon 12/11/17 | Fri 12/22/17 | AIR,ETS |
| 1109 | Dev-2-Dev Testing | 5 days | Mon 12/25/17 | Fri 12/29/17 | ETS,AIR |
| 1110 | Integration testing | 5 days | Mon 1/15/18 | Fri 1/19/18 | ETS,AIR |
| 1111 | Load testing | 5 days | Mon 1/22/18 | Fri 1/26/18 | ETS,AIR |
| 1112 | CDE UAT | 10 days | Mon 1/1/18 | Fri 1/12/18 | CDE |
| 1113 | End-to-End (E2E) Testing | 15 days | Mon 1/15/18 | Fri 2/2/18 | ETS,AIR |
| 1114 | Deploy TDS for Summative Assessments including Online Reporting System and Participation Reports | 1 day | Mon 2/5/18 | Mon 2/5/18 | AIR |
| 1115 | Formative Digital Library | 116 days | Mon 9/11/17 | Mon 2/19/18 |  |
| 1116 | Provide access to Digital Library | 116 days | Mon 9/11/17 | Mon 2/19/18 | ETS |
| 1117 | Interim Assessment Registration, Test Content and Ancillaries | 176 days | Mon 7/3/17 | Mon 3/5/18 |  |
| 1118 | Current Interim Assessments available | 0 days | Mon 7/3/17 | Mon 7/3/17 | Smarter Balanced |
| 1119 | Update enrollment/test administration information | 50 days | Mon 9/25/17 | Fri 12/1/17 | ETS |
| 1120 | New enhanced test packages available from Smarter Balanced | 0 days | Mon 2/5/18 | Mon 2/5/18 | Smarter Balanced |
| 1121 | Process new test packages | 20 days | Mon 2/5/18 | Fri 3/2/18 | AIR |
| 1122 | Updated Interim Comprehensive Assessment (summative clone) (ICA) launched | 1 day | Mon 3/5/18 | Mon 3/5/18 | AIR |
| 1123 | Updated Interim Assessment Blocks (IAB) launched | 1 day | Mon 3/5/18 | Mon 3/5/18 | AIR |
| 1124 | Configure Smarter Balanced System User Guide for CA | 40 days | Mon 7/3/17 | Fri 8/25/17 | ETS,AIR |
| 1125 | Configure Smarter Balanced Scoring Guide for CA | 40 days | Mon 7/3/17 | Fri 8/25/17 | ETS,AIR |
| 1126 | Configure Smarter Balanced System Infrastructure Guide for CA | 40 days | Mon 7/3/17 | Fri 8/25/17 | ETS,AIR |
| 1127 | Configure Smarter Balanced System Training Workbook for CA | 40 days | Mon 7/3/17 | Fri 8/25/17 | ETS,AIR |
| 1128 | Interim Assessment Reporting | 101 days | Tue 2/6/18 | Tue 6/26/18 |  |
| 1129 | Deliver Interim Results to Smarter Balanced | 101 days | Tue 2/6/18 | Tue 6/26/18 | ETS,AIR |
| 1130 | Summative Computer Based Assessments | 176 days | Mon 11/13/17 | Mon 7/16/18 |  |
| 1131 | Summative content packages available for CAT | 0 days | Mon 11/13/17 | Mon 11/13/17 | Smarter Balanced |
| 1132 | Summative content packages available for PT | 0 days | Fri 12/1/17 | Fri 12/1/17 | Smarter Balanced |
| 1133 | Summative test packages available for CAT and PT | 0 days | Fri 1/5/18 | Fri 1/5/18 | Smarter Balanced |
| 1134 | Import and QC test packages | 20 days | Fri 1/5/18 | Thu 2/1/18 | ETS |
| 1135 | Update enrollment/test administration information | 20 days | Tue 1/16/18 | Mon 2/12/18 | ETS |
| 1136 | Administer summative assessments (Smarter Balanced ELA/Math, ELA/Math Alternate) | 90 days | Tue 3/13/18 | Mon 7/16/18 | ETS |
| 1137 | Summative Braille and Large Print Paper/Pencil Testing | 205 days | Tue 10/10/17 | Mon 7/23/18 |  |
| 1138 | Reprint CST/CMA/CAPA Science & STS paper test | 30 days | Tue 11/21/17 | Mon 1/1/18 | ETS |
| 1139 | Receive material orders | 39 days | Tue 10/10/17 | Fri 12/1/17 | ETS |
| 1140 | Receive paper-based tests from Smarter Balanced | 1 day | Tue 12/5/17 | Tue 12/5/17 | Smarter Balanced |
| 1141 | Add covers | 10 days | Wed 12/6/17 | Tue 12/19/17 | ETS |
| 1142 | Produce Braille and large print summative operational paper tests | 30 days | Wed 12/20/17 | Tue 1/30/18 | ETS |
| 1143 | Distribute Braille and large print paper tests as needed | 88 days | Wed 2/14/18 | Fri 6/15/18 | ETS |
| 1144 | Receive Braille and large print paper tests | 75 days | Tue 3/20/18 | Mon 7/2/18 | ETS |
| 1145 | Scan Braille and large print paper tests | 76 days | Tue 3/20/18 | Tue 7/3/18 | ETS |
| 1146 | Conduct resolutions on paper tests | 90 days | Tue 3/20/18 | Mon 7/23/18 | ETS |
| 1147 | Scoring | 121 days | Tue 3/27/18 | Tue 9/11/18 |  |
| 1148 | Summative Computer Based Assessments | 90 days | Tue 3/27/18 | Mon 7/30/18 |  |
| 1149 | Hand and AI scoring occurs | 90 days | Tue 3/27/18 | Mon 7/30/18 | ETS,MI |
| 1150 | Perform scoring QC | 90 days | Tue 3/27/18 | Mon 7/30/18 | ETS |
| 1151 | Final scoring occurs | 90 days | Tue 3/27/18 | Mon 7/30/18 | ETS |
| 1152 | Psychometric Analysis | 38 days | Tue 5/22/18 | Thu 7/12/18 |  |
| 1153 | Conduct Item Analysis of CAASPP Summative assessments | 16 days | Tue 5/22/18 | Tue 6/12/18 | ETS |
| 1154 | Item Analysis Files delivered to CDE | 1 day | Wed 6/13/18 | Wed 6/13/18 | ETS |
| 1155 | Facilitate Alternate Assessment Data Review meeting | 1 day | Thu 7/12/18 | Thu 7/12/18 | ETS |
| 1156 | Standard Setting for Primary Language | 5 days | Wed 9/5/18 | Tue 9/11/18 |  |
| 1157 | Conduct Primary Language Standard Setting | 5 days | Wed 9/5/18 | Tue 9/11/18 | ETS,CDE |
| 1158 | Reporting | 324 days | Mon 9/4/17 | Thu 11/29/18 |  |
| 1159 | Summative Assessment | 266 days | Mon 9/4/17 | Mon 9/10/18 |  |
| 1160 | Delivery of Data Files to CDE and Smarter Balanced | 117 days | Tue 3/27/18 | Wed 9/5/18 |  |
| 1161 | Prepare student data files | 90 days | Tue 3/27/18 | Mon 7/30/18 | ETS |
| 1162 | Post initial student data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Tue 7/31/18 | Tue 7/31/18 | ETS |
| 1163 | Post final data files to SFTP site for CDE and Smarter BalancedSmarter Balanced Data Warehouse | 1 day | Wed 9/5/18 | Wed 9/5/18 | ETS |
| 1164 | Online Reporting Systems | 226 days | Mon 9/4/17 | Mon 7/16/18 |  |
| 1165 | Online Reporting Systems Setup | 37 days | Mon 9/4/17 | Tue 10/24/17 |  |
| 1166 | Gather specifications for AIR online reporting systems | 5 days | Mon 9/4/17 | Fri 9/8/17 | ETS,AIR |
| 1167 | CDE reviews online reporting system specifications | 10 days | Mon 9/11/17 | Fri 9/22/17 | CDE |
| 1168 | Configure online reporting systems | 20 days | Mon 9/25/17 | Fri 10/20/17 | ETS,AIR |
| 1169 | Demonstrate online reporting systems to CDE | 1 day | Mon 10/23/17 | Mon 10/23/17 | ETS,AIR |
| 1170 | Deploy online reporting system | 1 day | Tue 10/24/17 | Tue 10/24/17 | ETS,AIR |
| 1171 | Student Level Reporting | 129 days | Wed 1/17/18 | Mon 7/16/18 |  |
| 1172 | Provide final individual scores within 4 weeks of student online test completion | 90 days | Tue 3/13/18 | Mon 7/16/18 | ETS,AIR |
| 1173 | Launch ISR availability within online reporting system | 1 day | Wed 1/17/18 | Wed 1/17/18 | ETS,AIR |
| 1174 | School Level Reporting | 1 day | Thu 4/12/18 | Thu 4/12/18 |  |
| 1175 | Launch school level reporting functionality | 1 day | Thu 4/12/18 | Thu 4/12/18 | ETS,AIR |
| 1176 | LEA Level Reporting | 1 day | Fri 4/27/18 | Fri 4/27/18 |  |
| 1177 | Launch LEA level reporting functionality | 1 day | Fri 4/27/18 | Fri 4/27/18 | ETS,AIR |
| 1178 | State Level Reporting | 188 days | Mon 10/23/17 | Wed 7/11/18 |  |
| 1179 | State Aggregate Reporting Website | 188 days | Mon 10/23/17 | Wed 7/11/18 |  |
| 1180 | Develop business requirements | 45 days | Mon 10/23/17 | Fri 12/22/17 | ETS |
| 1181 | CDE provides text for site | 1 day | Mon 3/19/18 | Mon 3/19/18 | CDE |
| 1182 | Construct web reporting site | 30 days | Tue 3/20/18 | Mon 4/30/18 | ETS |
| 1183 | CDE UAT of Web Reporting Site | 10 days | Tue 5/1/18 | Mon 5/14/18 | CDE |
| 1184 | CDE provides feedback on changes needed | 10 days | Tue 5/15/18 | Mon 5/28/18 | CDE |
| 1185 | Apply changes | 5 days | Tue 5/29/18 | Mon 6/4/18 | ETS |
| 1186 | CDE second UAT | 5 days | Tue 6/5/18 | Mon 6/11/18 | CDE |
| 1187 | Finalize site with CDE updates | 5 days | Tue 6/12/18 | Mon 6/18/18 | ETS |
| 1188 | Deploy State level reporting website | 1 day | Wed 7/11/18 | Wed 7/11/18 | ETS |
| 1189 | Individual Student Report | 201 days | Mon 10/23/17 | Mon 7/30/18 |  |
| 1190 | Develop individual student report | 40 days | Mon 10/23/17 | Fri 12/15/17 | ETS |
| 1191 | CDE reviews individual student report | 10 days | Mon 12/18/17 | Fri 12/29/17 | CDE |
| 1192 | Update individual student report | 3 days | Mon 1/1/18 | Wed 1/3/18 | ETS |
| 1193 | CDE 2nd review of individual student report | 5 days | Thu 1/4/18 | Wed 1/10/18 | CDE |
| 1194 | Apply updates & submit to CDE for approval | 3 days | Thu 1/11/18 | Mon 1/15/18 | ETS |
| 1195 | Provide electronic student roster reports to LEAs | 20 days | Tue 7/3/18 | Mon 7/30/18 | ETS |
| 1196 | Print and ship Individual Student Reports (ISR) to LEAs | 20 days | Tue 7/3/18 | Mon 7/30/18 | ETS |
| 1197 | Rescore Process | 120 days | Tue 3/27/18 | Mon 9/10/18 |  |
| 1198 | LEAs request rescores | 90 days | Tue 3/27/18 | Mon 7/30/18 | LEAs |
| 1199 | Provide rescore results | 90 days | Tue 5/8/18 | Mon 9/10/18 | ETS |
| 1200 | Invoicing for rescores occurs | 10 days | Tue 5/15/18 | Mon 5/28/18 | ETS |
| 1201 | Interpretive Guides | 31 days | Mon 3/12/18 | Mon 4/23/18 |  |
| 1202 | Produce interpretive guides | 30 days | Mon 3/12/18 | Fri 4/20/18 | ETS |
| 1203 | Post interpretive guides | 1 day | Mon 4/23/18 | Mon 4/23/18 | ETS |
| 1204 | Technical Report | 61 days | Thu 9/6/18 | Thu 11/29/18 |  |
| 1205 | Develop Technical Manual | 40 days | Thu 9/6/18 | Wed 10/31/18 | ETS |
| 1206 | CDE reviews Technical Report and returns edits to ETS | 10 days | Thu 11/1/18 | Wed 11/14/18 | CDE |
| 1207 | ETS applies edits and delivers final Technical Report to CDE | 3 days | Thu 11/15/18 | Mon 11/19/18 | ETS |
| 1208 | CDE 2nd review of Technical Report | 5 days | Tue 11/20/18 | Mon 11/26/18 | CDE |
| 1209 | Apply updates and deliver Technical Manual to CDE for approval | 3 days | Tue 11/27/18 | Thu 11/29/18 | ETS |
| 1210 | Operational Test Administration Complete | 0 days | Thu 11/29/18 | Thu 11/29/18 |  |
| 1211 | Transition contract to new testing vendor | 20 days | Mon 12/3/18 | Fri 12/28/18 | ETS |
| 1212 | Contract Complete | 0 days | Mon 12/31/18 | Mon 12/31/18 |  |

# Appendix B—Reporting Expectations for Special Studies and Research Projects

Special studies and research conducted by ETS must adhere to the American Educational Research Association (AERA) Guidelines for Reporting on Empirical Social Science Research (2006). The following requirements are adapted from the guidelines and represent the basic expectations of the department for reporting results of special studies and research projects contracted for by the CDE.

Overall, reports on special studies and research projects must be:

- Warranted; that is, adequate evidence should be provided to justify the results and conclusions.

- Transparent; that is, reporting should make explicit the logic of inquiry and activities that led from the development of the initial interest, topic, problem, or research question; through the definition, collection, and analysis of data or empirical evidence; to the articulated outcomes of the study.

All reports on empirical research submitted to the CDE should include:

- A problem formulation that provides a clear statement of the purpose and scope of the study. It should describe the question, problem, or issue the study addresses, situate it in context, and describe the approach taken to addressing it.

- A review of the relevant scholarship that bears directly on the topic of the report. It should include a clear statement of the criteria used to identify and select the relevant scholarship in which the study is grounded. The rationale for the conceptual, methodological, or theoretical orientation of the study should be described and explained with relevant citations to what others have written.

- A specific and unambiguous description of the design—the way the sources of evidence for data collection or data identification activities selected for and organized in the investigation. Significant developments or alterations in the research questions or design should be described and a rationale for the changes presented.

- A complete description of the data or empirical materials that were collected, the methods used to collect the data, and the source(s) of the data or materials collected. The means of selection of the sites, groups, participants, events, or other units of study should be described.

- A complete description of measurement instruments used or classification systems developed to analyze the data. The description must include evidence of the meaningfulness and appropriateness of the measure or classification system for capturing important characteristics of the groups or individuals being studied. With qualitative methods in particular, classification is integral to the data analysis process.

- The procedures used for analysis should be precisely and transparently described from the beginning of the study through presentation of the outcomes. Descriptive and inferential statistics should be provided for each of the statistical analyses essential to the interpretation of the results. Any considerations that arose in data collection or identified during data analysis and processing that might compromise the validity of the statistical analysis or inferences should be reported.

  - For qualitative studies the procedures used for analysis should be precisely and transparently described from the beginning of the study through presentation of the outcomes. Analytic techniques should be described in sufficient detail to permit understanding of how the data were analyzed and the processes and assumptions underlying specific techniques. Analysis and interpretation should include information about any intended or unintended circumstances that may have significant implications for interpretation of the outcomes, limit their applicability, or compromise their validity. If coding processes are used, the description should include, as relevant, information on the backgrounds and training of the coders; inter-coder reliability or outcomes of reviews by other analysts; and, where relevant, indications of the extent to which those studied (participants) agree with the classifications.

  - For quantitative studies reporting should clearly state what statistical analyses were conducted and the appropriateness of the statistical tests, linking them to the logic of design and any claims or interpretations based on them. For each of the statistical results that is critical to the logic of the design and analysis, there should be included an indication of the uncertainty of the results such as a standard error or a confidence interval. When hypothesis testing is used, the test statistic and its associated significance level should be presented along with a qualitative interpretation of the meaningfulness of the results in terms of the questions the study was intended to answer.

- A presentation of conclusions and recommendations that provide a statement of how claims and interpretations address the research problem, question, or issue underlying the research; (b) show how the conclusions connect to support, elaborate, or challenge conclusions in earlier scholarship; and (c) emphasize the theoretical, practical, or methodological implications of the study.

# Appendix C—Minimum System Requirements

The following table is included in this appendix for reference. ETS will work with the CDE, the IV&V consultant, the IPOC, and other stakeholders to determine the final minimum system requirements for each administration.

Table19:  Minimum System Requirements

| # | Type | Requirement |
| --- | --- | --- |
| ARC-01.01 | Architecture | The contractor must provide a data dictionary that utilizes the CDE preferred variation for each data element collected or stored. |
| ARC-01.02 | Architecture | The contractor must provide dataflow diagrams. |
| ARC-01.03 | Architecture | The contractor must provide an Entity Relationship Diagram (ERD) in the format determined by the CDE. |
| ARC-01.04 | Architecture | The contractor must provide a complete list of system configurations (that differ from the open-source system default settings) annually. |
| ARC-01.05 | Architecture | The Assessment Delivery System must be scalable to accommodate new and modified consortium and California specific assessments |
| INT-02.00 | Interface | The Assessment Delivery System must accept test packages (both Smarter and non-Smarter) in the Smarter Balanced test package format (see http://www.smarterapp.org) and accurately deliver tests and applicable tools, supports, and accommodations to students with authenticity (inclusive of the adaptive algorithm), collect responses, score responses, and deliver scores to the Data Warehouse. |
| INT-02.01 | Interface | The Assessment Delivery System must successfully and completely process a daily electronic student registration information file, containing up to 6.5 million records, by 6 a.m. PT of the same day of the file availability. The CDE will make the student registration information file available by 2 a.m. PT, Monday through Friday. All current student registration information must be available within the Assessment Delivery System immediately after processing of the student registration information file. |
| INT-02.02 | Interface | The Assessment Delivery System must successfully identify and process all student information changes (new, modified, deleted, etc.) contained in CALPADS electronic student registration information file. |
| INT-02.03 | Interface | The Assessment Delivery System must be able to complete the processing of electronic data student registration information files received from CALPADS without impacting any other nightly batch processing or maintenance windows. |
| INT-02.04 | Interface | The Assessment Delivery System must generate and deliver to the CDE a daily electronic student data files (final specifications will be determined during joint requirement sessions), for CALPADS in a location designated by the CDE. |
| INT-02.05 | Interface | The Assessment Delivery System must accept and process daily (Monday through Friday) Student Access Data Files from LEAs that specify accessibility tools, supports, and accommodations that the student must be provided during summative and/or interim testing, the specifications of which are to be derived during the joint requirement sessions. |
| INT-02.06 | Interface | The Assessment Delivery System must provide students with access to the accessibility tools, supports, and accommodations specified in the Student Access Data File within 24 hours of the contractor receiving the data file from the LEA. |
| INT-02.07 | Interface | The Assessment Delivery System must be able to accommodate annual changes to the Student Access Data File to coincide with the use of new tools, supports, and accommodations as they become available. |
| INT-02.08 | Interface | The contractor must provide a document describing the solution’s application programming interfaces and Web-services. |
| INT-02.09 | Interface | The Assessment Delivery System must be able to deliver assessments using the minimum technology standards (e.g., network connections, student devices, operating systems) established (and annually updated) by the Smarter Balanced Consortium in the Technology Strategy Framework and Testing Device Requirements. |
| INT-02.10 | Interface | The Assessment Delivery System must not require the use of any additional software beyond the Secure Browser (e.g., use HTML5 and Javascript as the means to render items and submit responses). |
| INT-02.11 | Interface | The Assessment Delivery System must support the use of all Smarter Balanced embedded accessibility supports (see Smarter Balanced Assessment Consortium: Usability, Accessibility, and Accommodations Guidelines for description of the Smarter Balanced supports). |
| INT-02.12 | Interface | The Assessment Delivery System must use either the Smarter Balanced Assessment Item Packaging Format as described in the Smarter Balanced Assessment Item Format Specification or, if available, another format consistent with the Smarter Balanced Assessment Item Packaging Format. |
| INT-02.13 | Interface | The Assessment Delivery System must support the scoring of selected response and constructed-response items using machine scoring, hand scoring, and artificial intelligence (artificial intelligence applicable only if the contractor is using artificial intelligence scoring). |
| INT-02.14 | Interface | The contractor must download the electronic data student registration information file, extracted from CALPADS by the CDE, once a day Monday through Friday, from a CDE designated location.” |
| INT-02.15 | Interface | The Assessment Delivery System must successfully and completely process a daily electronic school and associated district information file by 6 a.m. Pacific Standard Time (PST) of the same day of the file availability. The school and associated district information file will be extracted from CALPADS and made available by 2 a.m. PST the same day. |
| SEC-3.00 | Security | The contractor must provide security policy and governance, including: - Information security program policies - Information security governance - Use of human-resource policy and practice security controls related to employees and contractors with potential access to sensitive information - Physical security of facilities hosting sensitive information resources - Organization’s security audit policy and practice including internal audits, independent audits, the audit scope, the audit frequency, and the exposure/reporting of audit results - Contractor’s system administrator roles and access levels and related controls |
| SEC-03.01 | Security | The Assessment Delivery System must provide hosted and delivered system access control features consistent with RFS Tables 3.3.2 and 3.3.3 that describe required user roles and permissions, including: - System-level access controls - Feature/function access controls - Information/data access controls - System’s incorporation of role based, group-based, and specific user based access controls |
| SEC-03.02 | Security | The Assessment Delivery System must provide authentication of users using industry-standard user authentication methods. |
| SEC-03.03 | Security | The Assessment Delivery System must provide the ability to set and enforce password strength and reset policies. |
| SEC-03.04 | Security | The Assessment Delivery System must use encryption (in transit and at rest) using a FIPS 140-2 validated solution (128-bit AES encryption or better) to protect confidential information handled by the system, including student registration information, student identifiable results information, test items, and other information as identified by the CDE Information Security Officer (ISO). |
| SEC-03.05 | Security | The Assessment Delivery System must purge, dispose, and/or archive sensitive information securely. |
| SEC-03.06 | Security | The Assessment Delivery System must employ integrity, controls such as source authentication, checksums, and message authentication methods to ensure that the secure information, such as student information, test content, answers, and scores, are unaltered and reliable. |
| SEC-03.07 | Security | The Assessment Delivery System must provide availability controls, such as protections against denial of service attacks. |
| SEC-03.08 | Security | The Assessment Delivery System must provide logging and audit controls available in the system to identify all user and system access of all data and functions and make the information available to the CDE Information Security Officer (ISO) on demand. |
| SEC-03.09 | Security | The contractor must provide a security plan that follows the National Institute of Standards and Technology (NIST) Special Publication 800-15 rev 1 at http://csrc.nist.gov/publications/nistpubs/800-18-Rev1/sp800-18-Rev1-final.pdf. |
| SEC-03.10 | Security | The contractor shall provide storage administration that includes the strict control and accessibility of all storage media. |
| SEC-03.11 | Security | The contractor must ensure that all storage media is inventoried on an annual basis, or sooner as dictated by CDE, regulatory or other contractual agreements. |
| SEC-03.12 | Security | The contractor must ensure all portable storage devices, including backup tapes, are encrypted using a FIPS 140-2 validated solution. (SAM 5350.1) |
| SEC-03.13 | Security | The contractor must ensure all data files and databases containing personally identifiable information (PII) are encrypted using a FIPS 140-2 validated solution at least 128 bit AES encryption or better before being electronically transferred across an internal network. All data files and databases containing PII data are to be encrypted using a FIPS 140-2 validated solution at least 128 bit AES encryption or better before being electronically transferred across a public network. |
| SEC-03.14 | Security | The contractor must ensure all data files and databases that contain PII are backed up to physical media for transfer to secondary storage are encrypted using a FIPS 140-2 validated solution backed up using at least 128 bit AES encryption or better using the backup utility’s encryption capability. No unencrypted intermediate backup files are to be created. |
| SEC-03.15 | Security | The contractor must ensure physical media containing PII is maintained in a secure environment prior to its transfer offsite. |
| SEC-03.16 | Security | The contractor must ensure physical media containing PII is monitored during the internal shipping process and must never be left unattended before handoff to the shipper. |
| SEC-03.17 | Security | The contractor must ensure that physical media containing PII is shipped in locked containers with no special markings or other indications of the sensitive nature of the contents. |
| SEC-03.18 | Security | The contractor must ensure shipping procedures should include a positive acknowledgement of receipt of encrypted backup files at the destination. |
| SEC-03.19 | Security | If a Cloud Service Provider is used as part of the Assessment Delivery System, the cloud system must be listed as a FedRAMP Compliant Cloud System (see http://cloud.cio.gov/fedramp/cloud-systems). |
| SEC-03.20 | Security | The contractor must ensure data remains within the continental United States. |
| SEC-03.21 | Security | If a Cloud Service Provider is used as part of the Assessment Delivery System, the data maintained by the Cloud Service Provider shall be encrypted with a FIPS 140-2 validated solution and the Contractor shall ensure that CDE maintains possession of the encryption key. |
| SEC-03.22 | Security | The contractor must ensure that data will not be converted into a proprietary format which will render the data non-portable. |
| SEC-03.23 | Security | The contractor must deploy a secure browser (that supports Operating Systems as dictated by the Smarter Balanced) annually in order to create a secure interface for students to access only the CAASPP summative tests without any other online-enabled utility (i.e., students may only access the exam). (Refer to the Secure Browser Requirements and Specifications at http://www.smarterapp.org/specs/SecureBrowserSpecification.html.) |
| SDP-04.00 | System Development Process | The Assessment Delivery System must provide real time progress reporting to LEA CAASPP coordinators, site coordinators, and the CDE pertaining to aggregate test administration information by district, school, course/grade or content area consistent with the roles and permissions established during joint requirement sessions. The specifications of the progress reporting are to be finalized during joint requirement sessions but may include such information as number of tests scheduled (by date or session and test type), number of tests being administered, number of tests completed, and the number of scoreable tests completed. |
| SDP-04.01 | System Development Process | The contractor must develop System/Functional, Integration, and User Acceptance Test Plans that describe, at a minimum: - Roles and responsibilities - Scope - System test phases and schedule - System test approach, methodology, and tools - System test entry and exit criteria - System test pass/fail criteria - System test data and metrics - System test reporting - System test scenarios, cases and scripts - System test defect management processes and procedures |
| SDP-04.02 | System Development Process | The contractor must provide automated test environment(s) for each system test phase, including System/Functional, Integration, and User acceptance. |
| SDP-04.03 | System Development Process | The contractor must provide functional testing, including test environment(s), test data, and test to requirements/feature coverage. |
| SDP-04.04 | System Development Process | The Assessment Delivery System must have the ability to limit interim assessment usage (i.e., restrict interim usage) within 1 hour of receiving the direction from the CDE to do so. |
| SDP-04.05 | System Development Process | The Assessment Delivery System must create unique test session IDs that ensure secure test administration. |
| SDP-04.06 | System Development Process | The Assessment Delivery System must allow for functionality to process approved appeals (i.e., test reset, invalidation, reopen, and restore). |
| SDP-04.07 | System Development Process | The Assessment Delivery System must allow all students to review their answers for certain sections or sets of questions before moving on to the next section or completing the exam. |
| SDP-04.08 | System Development Process | The Assessment Delivery System must have controls to prevent a student from prematurely exiting an assessment or from being inadvertently exited from an assessment. |
| SDP-04.09 | System Development Process | The Assessment Delivery System must default to human voice when both human and machine voice options are available as a feature of accessibility supports, tools or accommodations. |
| SDP-04.10 | System Development Process | The Assessment Delivery System must save student responses to selected response items (both linked to common stimuli and not) upon selection by the student. |
| SDP-04.11 | System Development Process | The Assessment Delivery System must save student responses to constructed response items and technology-enhanced (e.g., drag/drop, graphing) items. |
| SDP-04.12 | System Development Process | The Assessment Delivery System must allow test administrators to start, stop, pause, and resume a test session. |
| SDP-04.13 | System Development Process | For the Smarter Balanced interim assessments only, the Assessment Delivery System must allow test administrators to specify a limited set (number) of questions for testing. |
| SDP-04.14 | System Development Process | The Assessment Delivery System must allow test administrators to monitor student progress during testing, which includes but is not limited to having the ability to determine which item a student is currently working on without showing the item or student response. |
| SDP-04.15 | System Development Process | The Assessment Delivery System must provide a user interface (accessible to user roles consistent those established during joint requirement sessions) to activate and deactivate accessibility tools, supports and accommodations. The activations/deactivations made via the user interface must be made prior to a student taking a test and must be immediately available to the student once they begin testing. |
| SDP-04.16 | System Development Process | The Assessment Delivery System must retain previously saved student responses when a test is paused or restarted. |
| SDP-04.17 | System Development Process | The Assessment Delivery System must save student responses and end a test session when there is no activity on the test for a specified period established during joint requirement sessions. |
| SDP-04.18 | System Development Process | For the Smarter Balanced interim assessment only, the Assessment Delivery System must allow for out-of-level testing (i.e., administration of tests that are not consistent with the student’s enrolled grade). |
| SDP-04.19 | System Development Process | For the Smarter Balanced interim assessment only, the Assessment Delivery System must allow an unlimited number of interim tests to be administered to any one student. |
| SIM-05.00 | System Implementation | The contractor must develop a System Implementation Plan that describes how the Assessment Technology Platform will be deployed, installed and transitioned into an operational system. The plan shall include, at a minimum: - An overview of the hosting system - System implementation readiness assessment methodology and schedule - Implementation schedule, including field tests and pilots - Description of the major tasks involved in the implementation - Overall resources needed to support the implementation effort, including hardware, software, facilities, materials and personnel - Security features associated with the system when it is implemented, including security during implementation - Description of performance monitoring tools and techniques - Any site-specific implementation requirements - Description of process for validating the implementation was successful - Description of system acceptance and sign-off process |
| UEP-06.00 | User Experience | The Assessment Delivery System must conform to a consistent look and feel for each class of user for all components of the system, including Smarter Balanced and non-Smarter Balanced components. |
| UEP-06.01 | User Experience | The Assessment Delivery System must display (on the workstation screen) the name of the student who is testing. |
| UEP-06.02 | User Experience | The Assessment Technology Platform must be presented as a cohesive, single system with a single sign-on and seamless navigation. The single sign-on may be achieved by using the Smarter Balanced single sign-on or, if available, the use of a California single sign-on that can integrate with the Smarter Balanced single sign-on (inclusive of the Digital Library). |
| UEP-06.03 | User Experience | The Assessment Delivery System must adhere to industry best practice user interface standards and use industry best practice user interface controls in accordance with the supported end-user devices (e.g., W3C, Microsoft). |
| UEP-06.04 | User Experience | The Assessment Delivery System must comply with all applicable accessibility standards set forth in California Government Code Section 11135 as well as policy set forth in the CDE Web Accessibility standards located at http://www.cde.ca.gov/re/di/ws/webaccessstds.asp. |
| UEP-06.05 | User Experience | The Assessment Delivery System must provide online, context-sensitive help for each class of user. The specific features requiring online help shall be identified during joint requirement sessions. |
| UEP-06.06 | User Experience | The user interfaces (both administrators and students) of the Assessment Delivery System must be identical except for required deviations due to differences between Smarter Balanced and non-Smarter Balanced tests (e.g., skip item functionality would only be available on non-Smarter Balanced tests). |
| TAC-07.00 | Technical Assistance Center | The contractor must provide Tier 1, 2 and 3 supports for technical issues as referenced in RFS Section 3.2.3. |
| TAC-07.01 | Technical Assistance Center | The contractor must provide an escalation to Tier 2 and 3 support for unresolved Tier 1 issues consistent with RFS Section 3.2.3. |
| TAC-07.02 | Technical Assistance Center | The contractor must provide a process for working with user-sponsored technical support organizations (i.e., LEA and CDE information technology groups). |
| TAC-07.03 | Technical Assistance Center | The contractor must provide system support ticket tracking, resolution, and reporting. |
| SRM-08.00 | System Delivery Release Management | The contractor must provide a System Delivery Release Management Plan that includes, at a minimum: - Scope - Roles and responsibilities - Release Management approach and methodology - Processes and procedures for solution maintenance and upgrade as it relates to participation in, and implementation of, subsequent versions of the open-source Smarter Balanced code base, as well as proprietary modifications and independently developed components (only applicable if the Assessment Delivery System uses the Smarter Balanced open-source code) - Process and procedures for communications and coordination with internal and external partners - Description of release artifacts, including release notes and reports - Inputs to Release Management - Description of release types, including maintenance and emergency releases - Processes and procedures for performing scheduled and unscheduled releases - System outage management - Processes and procedures for performing scheduled and unscheduled releases - Release testing procedures, including regression and integration testing with CALPADS and other external partners - Production readiness procedures - Production deployment procedures - Production validation procedures - Processes and procedures for system delivery acceptance - Release rollback/back-out procedures |
| SRM-08.01 | System Delivery Release Management | The contractor must provide a process for scheduled and unscheduled releases. |
| SRM-08.02 | System Delivery Release Management | The contractor must comply with the system delivery acceptance process as defined by the CDE for the initial, and each subsequent, system delivery release. |
| PER-09.00 | Performance | The Assessment Delivery System must support the concurrent use by up to 500,000 users inclusive of student test takers and test administrators between the hours of 6 a.m. and 8 p.m. PT Monday through Friday. |
| PER-09.01 | Performance | The Assessment Delivery System must provide an adequate number of concurrent Web sessions to support the number of concurrent users at any given time. |
| PER-09.02 | Performance | The Assessment Delivery System must deliver 100% of the test questions with no more than five seconds of latency while serving a simulated peak concurrent user load as tested from a series of test devices connected to a test lab at the CDE headquarters site. |
| PER-09.03 | Performance | The contractor must conduct performance/load/stress testing that address, at a minimum, the following objectives: - To verify the reliability of the application under stress. - To determine application’s behavior under extreme load conditions. - To discover application bugs that occurs only under high load conditions. These can include such things as synchronization issues, race conditions and memory leaks. - To determine the application's robustness in terms of extreme load and help application administrators to determine if the application will perform sufficiently if the current load goes well above the expected maximum. |
| PER-09.04 | Performance | The Assessment Delivery System must demonstrate performance and stress requirements compliance through rigorous performance testing. |
| PER-09.05 | Performance | The contractor must provide a performance, load, and stress testing environment that mirrors the production environment and is capable of simulating peak transaction and user loads as well as and data creation/storage/transfer capacities. |
| PER-09.06 | Performance | The contractor must work with the CDE during joint requirement development sessions to define performance thresholds that include, but are not limited to, network utilization, and component latency/processing time, screen refresh rates, test item delivery latency, and test answer submission latency. |
| PER-09.07 | Performance | The contractor must conduct performance/load/stress testing that identify, at a minimum: - The hardware and/or the system's configurations/communication bottlenecks and their causes. - Application’s response times. - Application’s throughput. - Maximum concurrent users that application can bear in a system. - Resource (e.g., CPU, RAM, network I/O, and disk I/O) utilizations that application consumes during the test. - Behavior of the system under various workload types including normal load and peak load. - At what parameter levels beyond the minimum the system performance degrades below acceptable performance thresholds. - Symptoms and causes of application failure under stress conditions. - Weak points in the application (e.g., an increase in the number of users, amount of data, or application activity might cause an increase in stress). |
| PER-09.08 | Performance | The contractor must instrument and monitor the production hosted and delivered system to ensure the production implementation remains compliant with performance requirements and service level agreements. |
| PER-09.09 | Performance | The contractor must develop a Performance/Load/Stress Test Plan that includes, at a minimum: - Scope - Roles and Responsibilities - Performance/Capability Goals - Dependencies and baseline assumptions - Test tools - Testing approach and methodology - Test schedules including length of tests and number of times each is executed - Testing processes, procedures, and activities - Testing scenarios - Test status reporting - Performance thresholds - Test metrics - Test entry/exit criteria - Test pass/fail criteria - Process for communicating the performance test results and the system performance acceptance process to the CDE |
| PER-09.10 | Performance | The contractor must provide a process for monitoring and reporting production system performance, the specifics of which will be determined through joint requirement sessions. |
| PER-09.11 | Performance | The contractor must provide production system health reporting capabilities that include, but are not limited to, the ability for the CDE to monitor in real time, or through reports, the number of test takers, number of in-progress tests (interim and summative counts), number of administrative users, and other technical system health and use parameters to be determined through joint requirement sessions. |
| PER-09.12 | Performance | The contractor must obtain a network peering agreement (or functionally similar agreement) with the K12HSN to enable efficient routing of messages. |
| DRC-10.00 | Disaster Recovery and Business Continuity | The Assessment Delivery System must maintain an availability rate of 99.9 percent annually from January 1 through August 30, exclusive of designated California school holidays, between the hours of 6 a.m. and 8 p.m. PT. Otherwise maintain an availability rate of 99 percent between the hours of 6 a.m. and 8 p.m. PT. |
| DRC-10.01 | Disaster Recovery and Business Continuity | The Assessment Delivery System must be at a Tier 3 data center. A Tier 3 data center is defined as a facility consisting of multiple active power and cooling distribution paths; however, only one path is active. Additionally, the facility has redundant components and is concurrently maintainable providing 99.982% availability. |
| DRC-10.02 | Disaster Recovery and Business Continuity | The Assessment Delivery System must provide sufficient information on student progress or state of the application with sufficient detail necessary for system recovery, including saving the state of partially completed answers to multi-part items. |
| DRC-10.03 | Disaster Recovery and Business Continuity | The Assessment Delivery System must have the ability to recover from end-user device failure while minimizing the loss of information, progress, and state. |
| DRC-10.04 | Disaster Recovery and Business Continuity | The Assessment Delivery System must have the ability to recover from network failure while minimizing the loss of information, progress, and state. |
| DRC-10.05 | Disaster Recovery and Business Continuity | The Assessment Delivery System must have the ability to recover from a Web server/application server/database server failure while minimizing the loss of information, progress, and state. |
| DRC-10.06 | Disaster Recovery and Business Continuity | The Assessment Delivery System must ensure the maintenance of test integrity during outage events that occur while test administration is in process. |
| DRC-10.07 | Disaster Recovery and Business Continuity | The Assessment Delivery System must have robust data backup and recovery process and architecture that adhere to industry best practices. |
| DRC-10.08 | Disaster Recovery and Business Continuity | The contractor must provide a Disaster Recovery and Business Continuity Plan that provides for the Assessment Delivery System to stay functional in a disastrous state. The plan must include, at a minimum: - Scope - Approach and methodology - Roles and responsibilities - Backup and restore strategies and policies for data, database, and code - Business continuity planning activities - Disaster recovery process, procedures and timeframes - Ongoing testing, updates, and maintenance of the plan |
| DRD-11.00 | Data Policy Retention and Destruction | The Assessment Delivery Component must securely store and transmit student- level data in accordance with the requirements of the SAM Section 5305.8 for highly sensitive data. Data must be accessed only by authorized personnel and securely destroyed after the termination of the contract. |
| DRD-11.01 | Data Policy Retention and Destruction | The contractor must adhere to the Department of Education Administrative Manual (DEAM), sections 10120, 10600, and 10601 with regards to the retention and destruction of data security, retention and destruction. |
| DRD-11.02 | Data Policy Retention and Destruction | The contractor must adhere to EC 60607 and to the Family Educational Rights and Privacy Act (FERPA) of 1974 , Section 1232g in Part 4 of Title 20 of the Code of Federal Regulations (20 C.F.R. § 1232g) with regard to the access and destruction of personally identifiable information and/or confidential data. |
| MAO-12.00 | Maintenance and Operation | The contractor must develop a maintenance and operation plan that describes, at a minimum: - Process for system maintenance and upgrades (e.g., implementation of subsequent versions of the open-source Smarter Balanced code base; implementation of proprietary modifications and independently developed components) - Process for scheduled and unscheduled releases - Process for release testing and coordination - Release notes, communications and coordination processes |

# Appendix D—Summary of Embedded Universal Tools, Designated Supports, and Accommodations Supported by the CAASPP 2015 Test Delivery System

The following table includes the full set of embedded universal tools, designated supports, and accommodations (see gray boxes) which the Assessment Delivery System (ADS) supports.

Dcosta, Amanda. A Practical Approach to Creating a Risk Management Plan. February 4, 2014.
http://www.brighthubpm.com/risk-management/2875-a-practical-approach-to-creating-a-risk-management-plan/

Although operational during the life of the contract, ETS assumes that the California Alternate Assessments for ELA and mathematics and the CAPA for Science will not require braille and large-print versions since the proposed assessment design is primarily an examiner-led test delivery. ETS also assumes that the NGSS (general and alternate) and the primary language assessments will not require braille and large print during this contract period.

Perie, M. (2014). University of Kansas. Report prepared March 27, 2014 for the Smarter Balanced Assessment Consortium. Unpublished manuscript.