| California Department of Education Executive Office SBE-003 (REV. 09/2011) dsib-adad-nov15item08 |  | ITEM #03 |  |  |
| --- | --- | --- | --- | --- |
|  | CALIFORNIA STATE BOARD OF EDUCATION NOVEMBER 2015 AGENDA |  |  |  |
| ### SUBJECT California Assessment of Student Performance and Progress: Update on Program Activities, including, but not limited to, Smarter Balanced Assessments (Summative, Interim, and Digital Library Resources), Technology, Summative Assessment in Primary Languages Other than English, California Alternate Assessment, California Next Generation Science Standards Assessments, and Outreach Activities. |  |  |  | Action |
|  |  |  |  | Information |
|  |  |  |  | Public Hearing |

SUMMARY OF THE ISSUE(S)

This item reflects the collaboration of the Assessment Development and Administration Division (ADAD), the Educational Data Management Division (EDMD), the Special Education Division (SED), and the Analysis, Measurement, and Accountability Reporting Division (AMARD) of the California Department of Education (CDE) with regard to the California Assessment of Student Performance and Progress (CAASPP) System.

Update on Smarter Balanced Summative Assessments

Using feedback from surveys and focus groups to guide changes in the assessment platform system, the CDE has rolled out new user roles and test delivery system enhancements. Several enhancements to the test administrator interface were implemented in October. For example, the updated test administrator interface was redesigned to assist test administrators with selecting the appropriate test. Additionally, the assessment names are more clearly identified to assist the test administrator in selecting the correct assessment for his/her testing session. The updated test administrator interface has been restructured to allow test administrators to use tablets that will closely mirror the test administrator interface on a desktop computer. This feature will give the test administrator greater mobility within the classroom or computer lab.

2015 Smarter Balanced Results

California’s new assessment system provides local educational agencies (LEAs) with models for high-quality instruction and a powerful signal about our state’s educational goals. In addition, Carolina Cardenas, Director of Academic Outreach and Early Assessment, California State University will be presenting an update on the Early Assessment Program (see Attachment 1).

As educators become more familiar with the specific skills students must master to perform well on assessments that require problem-solving, critical thinking and analytical writing, they will increasingly tailor classroom instruction to address these skills. In the process, they will naturally work in greater alignment with California’s goals of career and college readiness for all students.

LEAs are analyzing their results from the 2015 Smarter Balanced assessments to begin the inherently local process of analyzing student performance and designing strategies for improvement. Summative assessments, in and of themselves, cannot pinpoint what specific instructional changes are needed. However, they do provide a critical starting point for this ongoing process of local inquiry, analysis, and improvement.

Other components of the assessment system, particularly interim assessments and formative resources, have an important role to play in assisting LEAs as they focus on improving instruction. Along with providing resources for classroom use, these tools also foster educator participation in the scoring process, thus making them more familiar with constructed response items and scoring rubrics, and contributing to a better understanding of California’s goals for student learning.

In addition, the results have provided new information to digest about the tests themselves. Analyses of the data by the CDE, Educational Testing Service (ETS), University of California at Los Angeles – Center for Research on Evaluation, Standards, and Student Testing (UCLA CRESST), and the Independent Evaluator, Human Resources Research Organization (HumRRO) are ongoing and include analyses of the assessment performance. Ongoing research will confirm the validity, reliability, fairness and accuracy of the assessments as well as begin to gauge the impact of the assessments on teaching and learning.

Enhanced Assessment Instruments Grant Update

The CDE, in partnership with the UCLA CRESST, has been awarded an Enhanced Assessment Instruments Grant by the U.S. Department of Education. The grant will support the development of innovative indices of the Smarter Balanced high school assessments that can support improved career readiness inferences.

The goal of the study is to enhance the value of the current CDE high school assessments without adding testing time. Combining qualitative and quantitative approaches, the project will develop a means of reusing the current item pool, as well as undertake the development of new items of richer and technology-enhanced types. The CDE will have a framework for understanding the Smarter Balanced assessments in a new way that will inform reporting and interpretation statewide, as well as a new set of digital support resources and innovative item formats.

Central to the study design is a feature-based approach to test design, item analysis, scoring, and validation. Detailed qualitative feature analysis paired with rigorous psychometric analysis of existing state test item response data will allow the computation of scores that carry the intended career readiness interpretations. The project will also gather preliminary validity evidence in support of new and improved inferences by comparing assessment results across groups with a range of career experience, including grade eleven students, community college students, and individuals in the world of work.

Update on Smarter Balanced Interim Assessments

On August 10, 2015, the Smarter Balanced Interim Assessments were made available to LEAs for the 2015–16 school year. As of September 29, a total of 44,610 interim assessments had been started across 214 California LEAs.

In October 2015, eight regional trainings referred to as “Digital Library and Interim Assessment Clinics” were provided to LEA CAASPP coordinators by ETS as part of the CAASPP administration contract. The clinics focused on administration practices for the Smarter Balanced Interim Assessments, reviewed various resources that are available in the Digital Library, and provided coordinators with guidance on promoting the use of both components within their LEA.

Also in October 2015, ETS provided eight regional “Interim Assessment Hand Scoring Workshops” for teachers and other LEA staff members. The hand scoring workshops provided tools and hands-on experience scoring constructed response interim assessment items that require hand scoring. An update on the number of attendees will be provided during the State Board of Education (SBE) meeting.

Enhancements to the interim and summative assessment test delivery system were made as part of the October test delivery system update. Enhancements included interface changes to more prominently distinguish between interim and summative assessments.

Update on Smarter Balanced Digital Library of Formative Resources

As of October 8, 2015, over 248,000 California educators were registered users of the Smarter Balanced Digital Library. To support LEAs in encouraging teachers to use the Digital Library, the CDE developed a brief PowerPoint presentation for LEAs to introduce the Digital Library to teachers. This resource was made available on the CDE Digital Library Web page at http://www.cde.ca.gov/ta/tg/sa/diglib.asp in October.

Technology Update

The CDE continues to assist the K-12 High Speed Network (K12HSN) with the implementation of the Broadband Infrastructure Improvement Grant (BIIG) programs, which are designed to assist schools improve their connection to the Internet to administer computer-based assessments. In the first round of funding (BIIG 1.0) from the 2014–15 school year, there are 11 sites completed with data passing through the circuits as of October 8, 2015. Also in the final stages of connection through upgraded microwave systems are three (3) sites in the Death Valley Unified School District and three (3) sites in the Baker Valley Unified School District.

For additional information about the status of the remaining sites receiving upgraded connections from BIIG 1.0, please visit the K12HSN BIIG Circuit Installation Web page at https://sites.google.com/a/icoeapps.org/biig/. (Note: If the preceding link does not display properly, copy and paste the Web address to a Web browser directly.)

The application deadline for BIIG 2.0 concluded on September 30, 2015, and as of October 21, 2015, 182 applications were submitted. Of these applications, 95 were from district/consortia and 87 were from single site schools. The 182 applications represent a total of 1,079 school sites, which includes 80 charters, of which 598 sites qualified based on one of the three priorities. Of the 598 sites, 121 are Priority 1, which are sites with a current connection below 20 Kilobits per second (Kbps) per student that are unable to improve their Internet connection. An additional 251 sites are Priority 2, which represent schools with less than 100 Kbps per student that have limited options to improve their connections for computer-based assessments. The remaining 226 sites are Priority 3, which represent underconnected schools. Funding to Priority 3 schools will be considered if funds are available. These applications will be ranked by the lowest connection capacity.

In October 2015, the K12HSN hosted three Bidder’s Conferences across the state for service providers to learn about BIIG 2.0. The submission window for service providers to submit bids is from October 19 to December 1, 2015. Evaluations of the bids, which include a Technical Peer Review and Stakeholder Review, will occur in December 2015 and January 2016. The 2015–16 Budget Act (Assembly Bill 93) requires that high-cost bids (over $1,000 per-pupil costs per test-taking pupil) receive prior approval from the Department of Finance and that notification be provided no sooner than 30 days after notification is received in writing to the Joint Legislative Budget Committee. It is anticipated that awarded sites for BIIG 2.0 will begin implementation of services between April 2016 and June 2017.

California Alternate Assessment

The CDE continues to monitor the progress of the Arizona State Department of Education Request for Proposals issued on behalf of the Multi-State Alternate Assessment (MSAA) collaborative (the collaborative developed out of nine previous National Center and State Collaborative [NCSC] states). The CDE remains hopeful that we will be able to negotiate involvement with the MSAA and/or obtain NCSC test items for potential use in operational California Alternate Assessments (CAAs).

Additionally, the CDE continues to work with LEA stakeholders and ETS in the development of items that will be available for use in the 2016 operational assessment. In late September, content reviewers (LEA representatives) participated in a virtual data review meeting, whereby they viewed item statistics and discussed the performance of the 2015 field test item types and provided input for future item development.

ETS continues to develop items for the 2016 operational CAAs based on the SBE-adopted blueprints. These items are being designed on the basis of research and development activities completed by the NCSC as well as information ETS has gathered from the 2015 CAA field tests and meetings with California content reviewers (teachers).

California Next Generation Science Standards Assessments

In October, work continued on a “cross-walk” between the 1998 California science content standards and the California Next Generation Science Standards (CA NGSS) in kindergarten through grade twelve (K-12). Information from this crosswalk will be used to estimate the alignment of the currently administered science tests to the NGSS as well as determine if there are currently owned items in the California bank that may align with NGSS.

Additionally, work began on the development of “connectors” from the CA NGSS to “enduring understandings.” Connectors determine how the performance expectations are unpacked and scaffolded to the enduring understandings. Enduring understandings capture the essence of each CA NGSS performance expectation, and create a bridge to more discrete science learning goals. These “connectors” will assist teachers in providing the scaffolding necessary to provide differentiated instruction to students with disabilities and for ETS in the development of future assessments.

Both the work on the “cross-walk” and the “connectors” was done by California teachers and LEA content experts.

To provide guidance and expertise on CA NGSS related issues, ETS has retained national experts including James Pellegrino and Kathleen Scalise, who serve on the National Research Council (NRC), Committee on Developing Assessments of Science Proficiency in K-12. James Pellegrino served as co-chair and lead author of the Developing Assessments for the Next Generation Science Standards (2014) (http://www.nap.edu/catalog/18409/developing-assessments-for-the-next-generation-science-standards).

Development of the State Superintendent of Public Instruction (SSPI) Recommendations for the Expansion of the CAASPP System

The CDE and partners are scheduling meetings for the development of guiding principles that shall be presented at the January 2016 SBE meeting. These meetings and potential additional meetings, along with the guiding principles, will lead to the presentation of the SSPI recommendations for the expansion of the CAASPP System at the March 2016 SBE meeting.

Further information will be provided at the November SBE meeting around the development of a guiding principles document and the development of the SSPI recommendations on expanding the CAASPP System to include additional assessments.

Outreach and Professional Development Activities

In October and November 2015, the CDE, through a contract with the Sacramento County Office of Education (SCOE), is delivering the first of a two-part CAASPP Institute for LEA teams throughout the state. Institute trainers provided guidance and planning time for LEA teams to effectively implement all components of the CAASPP System to improve teaching and learning. The Institute used as a model the three components of the Smarter Balanced assessment system (i.e., summative, interim, and Digital Library). LEA teams included members with expertise in a variety of areas including school and district leadership, English language development, mathematics, English language arts, assessment, accountability, and special education.

The Institute was delivered in 14 locations throughout the state for school districts and schools, and two additional Institutes were delivered to county office of education (COE) staff in a “train the trainer” format. Interest in the Institute far exceeded capacity. Applications were received from over 600 LEA teams representing over 2,700 staff members. Applications were able to be accepted from approximately 350 LEA teams representing approximately 1,600 staff members. The second half of the Institute will be delivered in February and March 2016. After the Institute in-person trainings are completed, each part of the Institute will be video recorded in a studio environment and made available in modules on the CDE Web site.

RECOMMENDATION

This item is for information only. No specific action is recommended.

BRIEF HISTORY OF KEY ISSUES

California Assessment of Student Performance and Progress

Per California Education Code (EC) Section 60640, the CAASPP System succeeded the Standardized Testing and Reporting (STAR) Program on January 1, 2014.

SUMMARY OF PREVIOUS STATE BOARD OF EDUCATION DISCUSSION AND ACTION

In October 2015, the CDE provided the SBE with two Information Memoranda on the CAASPP post-test survey and focus group results and the CAASPP 2014–15 Summative Assessment reports. The two October 2015 SBE Memoranda can be found on the SBE October Information Memoranda Web page at http://www.cde.ca.gov/be/pn/im/infomemooct2015.asp.

In September 2015, the CDE provided a pre-release CAASPP briefing to the SBE including a preview of the new public reporting Web site to report the results for the English language arts/literacy and mathematics assessments. The CDE also announced the posting of the Parent Guide to the Smarter Balanced Summative Assessments for three grade spans (three–five, six–eight, and eleven). These guides are posted on the CDE CAASPP Web page under the Students and Parents tab at http://www.cde.ca.gov/ta/tg/ca/index.asp?tabsection=3.

In August 2015, the CDE provided the SBE with an Information Memorandum on the California Assessment of Student Performance and Progress: Summary Results from Teacher and Student Feedback Sessions. The August 2015 SBE Memorandum can be found on the SBE August Information Memoranda Web page at http://www.cde.ca.gov/be/pn/im/infomemoaug2015.asp.

In June 2015, the CDE provided the SBE with an Information Memorandum on the CAASPP pre-test survey results and an update on the stakeholder meeting for CA NGSS Assessments required by the Elementary and Secondary Education Act (http://www.cde.ca.gov/be/pn/im/infomemojun2015.asp).

In May 2015, the SBE approved ETS as the new CAASPP contractor (http://www.cde.ca.gov/be/ag/ag/yr15/documents/may15item01.doc).

In April 2015, the CDE provided the SBE with an Information Memorandum on the process used to recruit, train, and monitor raters for the hand scoring of the Smarter Balanced Summative Assessment items (http://www.cde.ca.gov/be/pn/im/infomemoapr2015.asp).

In March 2015, the SBE approved the CAASPP Individual Student Report (ISR) with technical edits (http://www.cde.ca.gov/be/ag/ag/yr15/agenda201503.asp).

In January 2015, the CDE provided the SBE with an update on the Broadband Infrastructure Improvement Grant (BIIG), the progress of the Smarter Balanced Interim Assessments, the Digital Library, the California Alternate Assessments, and the plan for reporting the 2014–15 CAASPP results

(http://www.cde.ca.gov/be/ag/ag/yr15/agenda201501.asp).

In November 2014, the CDE provided the SBE with an update on CAASPP activities, including Smarter Balanced, achievement level setting, and technology (http://www.cde.ca.gov/be/ag/ag/yr14/documents/nov14item02a2.pdf).

In November 2014, the SBE approved the SSPI’s recommendations for the full implementation of a technology-enabled assessment system and the administration of the Smarter Balanced Summative Assessments in 2014–15 (http://www.cde.ca.gov/be/ag/ag/yr14/documents/nov14item03.doc).

FISCAL ANALYSIS (AS APPROPRIATE)

The 2015 Budget Act provides $50 million for the K–12 High Speed Network (K12HSN) for the BIIG program grants for LEAs and $10 million for the K12HSN professional development and technical assistance activities.

The 2015 Budget Act provides $94 million in funding for CAASPP contract activities in 2015–16. This funding is being utilized for the following CAASPP contracts:

- Contract activities provided by ETS ($83.6 million: $7.6 million in Contract 5417; $76 million in Contract CN150012) were approved by the SBE for test administration and development activities, including the development of CA NGSS and primary language assessments per SBE input

- A contract with the University of California, Los Angeles ($8 million) was approved by the SBE for Smarter Balanced consortium-managed services, including access to the Smarter Balanced Summative Assessments, Interim Assessments, and Digital Library tools

- A contract with the HumRRO ($774,117) for a multi-year independent evaluation of the CAASPP System per requirements in California EC Section 60649

- A contract with SCOE ($1.5 million in one-time funding) for CAASPP support activities, including regional CAASPP Institutes and Senior Assessment Fellows services per authority in the 2015 Budget Act (6100-113-0001, Provision 13)

Funding for 2016–17 and beyond will be contingent upon an annual appropriation being made available from the Legislature in future fiscal years.

ATTACHMENT(S)

Attachment 1:	Early Assessment Program: Transition to New Assessments PowerPoint presentation (PDF, 22 Pages).

Attachment 2:	California Assessment of Student Performance and Progress Outreach and Professional Development Activities (10 Pages)

California Assessment of Student Performance and Progress Outreach and Professional Development Activities

The California Department of Education (CDE), in coordination with its assessment contractor and CDE Senior Assessment Fellows, have provided a variety of outreach activities to prepare local educational agencies (LEAs) for the administration of California Assessment of Student Performance and Progress (CAASPP) System of assessments. Outreach efforts have included Webcasts, in-person test administration workshops, focus group meetings, and presentations for numerous LEAs throughout the state. The following table lists presentations during September and October 2015. In addition, the CDE continues to release information regarding the CAASPP System of assessments, including weekly updates, on its Web site and through e-mail Listservs.

| Webcasts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Event Location | Assessment | Number of Attendees | Description |
| 9/10/15 | Webcast -- Smarter Balanced Digital Library | Digital Library | 526 | Webcast to communicate the following information about the Digital Library to educators: - How to access the Digital Library - Resources that are available in the Digital Library - How Digital Library resources are designed to support teaching and learning How to train fellow educators to fully utilize the formative assessment tools |
| 09/18/15 | Webcast -- Assessment and Accountability Information Meeting | Sacramento | 398 | Update of California assessment and accountability systems |

| In-Person Regional Trainings |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Event Name | Event Location | Number of Attendees | Description |
| 10/19/15 | Digital Library and Interim Assessment Clinics | Various | TBD | Eight Digital Library and Interim Assessment Clinics occurred in eight regions beginning on October 19 through October 29 |
| 10/19/15 | Interim Assessment Hand Scoring Workshops | Various | TBD | Eight Interim Assessment Hand Scoring Workshops occurred in eight regions beginning on October 19 through October 29, 2015 |
| 10/21/15 | CAASPP Institutes | Various | TBD | Fourteen CAASPP Institutes provided professional development for teams from LEAs and schools on how to best implement all components of the CAASPP System, beginning in October and ending in March 2016 |

| Presentations by CDE Staff |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Event Name | Event Location | Number of Attendees | Description |
| 09/10/15 | Special Education Local Plan Directors | Conference Call | 6 | Update on Assessment Development and Administration Division assessment activities |
| 09/17/15 | Special Education Administrators of County Offices | Sacramento | 40 | Update on California Alternate Assessment activities and the CAASPP System |
| 09/18/15 | Assessment and Accountability Information Meeting | Sacramento | 466 | Update on California assessment and accountability systems |
| 09/21/15 | Power of Democracy Steering | Sacramento | 25 | Update on California Alternate Assessment activities and the CAASPP System |
| 09/24/15 | Instructional Quality Commission | Sacramento | 30 | Update on California Alternate Assessment activities and the CAASPP System |
| 09/25/15 | Central Region Assessment Network | Sacramento | 40 | Update on new student score reports for 2016 and changes to public Web pages for 2016 to show student progress |
| 09/28/15 | Assessment and Accountability Information Meeting | Ontario | 640 | Update on California assessment and accountability systems |
| 09/21/15 | Power of Democracy Steering | Sacramento | 25 | Update on California assessment and accountability systems |
| 10/01/15 | California Collaborative on Educational Excellence | Sacramento | 20 | Update on Smarter Balanced assessment results |
| 10/15/15 | Community College Common Assessment Steering Committee | Sacramento | TBD | Update on the reporting of CAASPP scores and the resources provided to stakeholders |
| 10/23/15 | Capitol Region Assessment Network | Sacramento | TBD | Update on California assessment and accountability systems |
| 10/28/15 | Advisory Committee on Special Education | Sacramento | TBD | Update on California assessment and accountability systems |

| CAASPP Presentations by Senior Assessment Fellows |  |  |  |  |
| --- | --- | --- | --- | --- |
| Dates | Event Location | Number of Attendees | Target Audience | Topic |
| 9/1/15 | Celerity Charter Schools | 25 | Charter school administrators and teachers | Using interim assessments strategically with a focus on scoring |
| 9/1/15 | Siskiyou COE | 25 | Principals and superintendents | Introduction to interims; and hands-on training to access tests and scoring materials |
| 9/3/15 | Inglewood Unified School District (USD) | 25 | Site administrators, site coordinators | Using interim assessments strategically |
| 9/3/15 | Chico Unified | 50 | Superintendents, Assistant Superintendents, Principals, and Assistant Principals | Reporting results from summative assessment |
| 9/4/15 | Butte COE | 40 | Superintendents, assistant superintendents, principals, assistant principals. | The purpose of the training was to help the school district superintendents and principals consider the use of the summative results as an entry point to consider instruction, communication with parents, and implementation of the interims |
| 9/8/15 | Torrance USD | 50 | LEA administrators, coaches, and principals | Using interim assessments strategically |
| 9/8/15 | Lassen COE | 18 | District superintendents and principals | Interpreting student results from summative assessments and accessing, implementing, and using results from interim assessments |
| 9/9/15 | Madera COE | 10 | Collaborative members. These are the county office staff charged with supporting district implementation of the Smarter Balanced and other assessments. | The purpose of the training was to help the Regional Capacity Building Collaborative (RCBC) members consider the use of the summative assessment results as an entry point for teachers to consider instruction and communication with parents |
| 9/9/15 | Oceanside USD | 45 | LEA administrators and coaches/leads | Smarter Balanced update |
| 9/9/15 | RSDSS at Alameda COE | 42 | Teachers, administrators, coaches | Summative Assessment |
| 9/10/15 | Marin COE | 25 | District superintendents | Smarter Balanced assessment system; using results to improve instruction; implementation and use of interim assessments and Digital Library​ |
| 9/10/15 | Orange COE | 45 | District Standards and Assessment Administrators | CAASPP update as well as interim assessment and Digital Library information, to inform district assessment planning |
| 9/10/15 | San Diego COE | 50 | District and charter school assessment leaders | General CAASPP updates with a focus on reporting and using summative results |
| 9/11/15 | Mountain View (LA County) | 35 | San Gabriel Valley instructional leaders | Smarter Balanced update |
| 9/11/15 | San Mateo COE | 30 | COE curriculum and instruction leaders | Summative assessments and interim assessments |
| 9/11/15 | Santa Barbara COE | 40 | COE curriculum council consisting of LEAs in Santa Barbara COE | Update on assessment and accountability, accessibility supports for interim assessments, and using the summative score reports |
| 9/11/15 | Making Waves Charter School | 40 | Teachers | Reviewed summative scores and implications |
| 9/16/15 | Red Bluff HS | 25 | Principals, teachers, instructional coaches | Smarter Balanced Assessment System components, use of the summative assessment results; and support for teacher professional learning |
| 9/16/15 | Downey USD | 80 | Teachers-on-Special-Assignment (TOSAs), principals, and assistant principals | Formative assessments, Digital Library, and interim assessments |
| 9/16/15 | LA USD Ed Center West | 125 | Principals | Reporting results from summative assessments and interim assessments |
| 9/16/15 | Los Angeles COE | 80 | District assessment and accountability network leads | Smarter Balanced update |
| 9/22/15 | Huntington Beach City Schools | 34 | LEA administrators and principals | CAASPP update, best practices, interim assessments, and Digital Library |
| 9/23/15 | Riverside COE | 70 | LEA administrators and coaches/leads | Using interim assessments strategically, with a focus on scoring |
| 9/23/15 | Sonoma COE | 30 | District administrators | Interim assessments |
| 9/24/15 | Mendocino COE | 30 | District administrators and teachers | Interim assessments |
| 9/24/15 | Lakeside Union School District | 20 | Principals and District Administrators | Interim assessments |
| 9/25/15 | Sacramento COE | 30 | District CAASPP coordinators, curriculum and assessment directors | How to use Smarter Balanced summative assessment results as an entry point to reflection on California standards implementation |
| 9/25/15 | Orange County Department of Education | 85 | LEA testing coordinators and other LEA administrators | Using interim assessments strategically with a focus on scoring requirements/time |
| 9/28/15 | Stanislaus COE | 50 | District administrators | Interim assessments, formative assessments, and Digital Library |
| 9/29/15 | Colusa COE | 10 | District superintendents | Help superintendents understand the components of the Smarter Balanced system and what supports are available to help them implement those components |
| 9/30/15 | Los Angeles COE | 30 | LEA administrators | Reporting results from summative assessments |
| 9/30/15 | San Joaquin COE | 75 | TBD | Reporting results from summative assessments and interim assessments |
| 10/2/15 | Trinity COE | 25 | TBD | Reporting results from summative assessments and interim assessments |
| 10/5/15 | Imperial COE | 80 | District curriculum, instruction and assessment leaders | Reporting results from summative assessments and interim assessments |
| 10/6/15 | Butte COE | TBD | District principals, curriculum directors | Implementation of Digital Library |
| 10/6/15 | Plumas COE/ Plumas USD | TBD | COE/District admin, site admins, instructional coaches | Overview of all components of the Smarter Balanced system; focus on using summative results and interim assessments; awareness of the Digital Library |
| 10/6/15 | Riverside COE | 30 | Charter school representatives | Smarter Balanced update |
| 10/7/15 | John Burroughs Middle School, LAUSD | 15 | Site administrators, leads, and teachers | Interim Assessments |
| 10/7/15 | Monterey COE | TBD | Teachers, Principals, Coordinators | Hand-scoring in math in the morning and again in the afternoon for English language arts |
| 10/8/15 | Tehama COE | TBD | Superintendents, Assistant Superintendents | Discussion with Superintendents to identify needs with respect to Smarter Balanced implementation |
| 10/9/15 | San Gabriel USD | 50 | TOSAs, staff who piloted the interim assessments, teacher leads, and administrators | Interim assessments |
| 10/12/15 | Fresno USD | TBD | District CAASPP coordinators and assessment coordinators | Implementation of interim assessments |
| 10/13/15 | Porterville USD | TBD | All site principals and instructional coaches | Interim assessment implementation |
| 10/16/15 | Shasta COE | TBD | Shasta County Curriculum Coordinators | Smarter Balanced update, CAASPP update and planning |
| 10/16/15 | Orange County Department of Education | TBD | District parent/community liaisons | Understanding the individual student score report |
| 10/20/15 | Dry Creek Elementary School District (ESD) | TBD | TBD | Use of summative assessment results and implementation of the interim assessments |
| 10/28/15 | Bayshore ESD | TBD | Teachers | Administration of the interim assessments |
| 10/30/15 | San Luis Obispo COE | TBD | Curriculum, instruction, and administration directors from districts across San Luis Obispo county | Formative assessments, Digital Library, and interim assessments |
| 11/5/15 | San Diego | TBD | LEA teams including administrator, assessment specialist, curriculum specialists, teachers, EL specialist, special education specialist | Summative Assessment |
| 11/5/15 | San Diego COE | TBD | Region 9 Curriculum & Assessment Leaders | Interim Assessment |
| 11/6/15 | Plumas COE | TBD | Teachers | Interim Assessment |
| 11/6/15 | San Diego | TBD | LEA teams including administrator, assessment specialist, curriculum specialists, teachers, EL specialist, special education specialist | Summative Assessment |
| 11/12/15 | San Gabriel USD Office | TBD | TOSAs, staff that piloted the interim assessments, teacher leads, and administrators | Interim Assessment |
| 11/12/15 | Humboldt COE | TBD | District Superintendents/Principals, Curriculum Coordinators, COE coordinators | Interim assessment implementation |

* Estimated number