## Activities
California Department of Education, Special Education Division February 2017
| Subject | Activity | Implementation Steps | Person/ Division Responsible | Proposed Completion Dates | Revised Completion Dates | Completed?
1 | Section 1. Infrastructure Development
2 | LCFF and LCAP Support
3 |  | CDE - Assemble and deploy a cross-divisional LCAP Support Team to coordinate department wide resources and technical assistance | Identify team members from relevant divisions, including Title I - III, Special Education, Student Support, Assessment, etc. | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | November 2015 |  | Completed
4 |  |  | Orient members to LCAP requirements, purpose of the team, logistics of team activities. | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | November 2015 |  | Completed
5 |  |  | Schedule and conduct team meetings every two weeks. | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | November 2015 (ongoing) |  | Completed
6 |  | CDE - Develop LCAP Resources | Create plan to develop an array of technical resources to support LEAs in LCAP development and implementation | LCAP Support Team members | July 2016 (ongoing) |  | Completed
7 |  |  | Develop a communication process to ensure LEA access technical expertise from CDE staff and contractor resources | LCAP Support Team members | July 2016 | TBD
8 |  |  | Take inventory of existing Web resources - e.g., Quality Schooling Framework, California State Standards (Common Core) | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | July 2016 (Ongoing) |  | Completed
9 |  |  | Identify any deficiencies in resources related to the eight/ten LCAP priority areas. | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | July 2016 |  | Completed
10 |  |  | Locate additional resources and evaluate for inclusion with existing Web resources that provide support to LEAs in LCAP development and implementation of LCAP resource array | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | July 2016 (ongoing) |  | Completed
11 |  | CDE - Distribute LCAP resources | Connect LEAs to the LCAP resource array | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | July 2016 (ongoing) | TBD
12 |  |  | Implement communication process for LEAs to access technical expertise from CDE staff and contractor resources | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | July 2016 | TBD
13 |  |  | Explore the implementation of a LCAP conference to connect LEAs with exemplary practices. | Chief Deputy and Local Accountability Systems and Support Office (LASSO) | November 2015 | TBD
14 |  | CDE/SBE - Develop LCAP Evaluation Rubrics | Contract for rubric development | SBE, WestEd | July 2013 - FY 2015/1016 |  | Completed
15 |  |  | Conduct stakeholder input meetings | SBE, WestEd | Summer - Fall 2013 |  | Completed
16 |  |  | Prepare draft evaluation rubrics for SBE consideration | SBE, WestEd | Summer/Fall - 2015 |  | Completed
17 |  |  | Conduct additional stakeholder input sessions (user acceptance testing pilot) | SBE, WestEd, LEAs | October 2015 - March 2016 | October 2014 - October 2016 | Completed
18 |  |  | Prepare evaluation rubric for SBE final approval | SBE, WestEd | Fall 2016 |  | Completed
19 |  | SBE, CDE, COEs and CCEE - disseminate evaluation rubrics | TBD | SBE, CDE, CCEE, COEs | Fall 2016 | Fall/Winter 2016 | Completed
20 |  | LEAs and COEs - apply evaluation rubrics | Use rubrics annually to evaluate and revise LCAPs as appropriate | LEAs, COEs | Fall/Spring 2016 | TBD
21 |  | CCEE - convene quarterly and develop system of LCAP technical assistance | TBD | CCEE, SBE | Spring/Summer 2016 (ongoing) |  | Completed
22 |  | SED - Participate on LCAP Support Team | Identify SED administrator to participate in Support Team activities and to make SED unit staff and contractors available to contribute to the activities of the team. | SED Director, SED Leadership Team | November 2015 |  | Completed
23 |  |  | Participate in team meetings scheduled every other month to represent SED and SWDs in LCAP support activities | SED Representative to LCAP Support Team | November 2015 (ongoing) |  | Completed
24 |  |  | Assist the LCAP Support Team in identifying and developing resources that assist LEAs in LCAP development and implementation | SED Representative to LCAP Support Team | November 2015 (ongoing) |  | Completed
25 |  | SED - Provide resources for including SWDs in LCAPs in coordination with CCEE | Attend bimonthly meetings | SED Representative to LCAP Support Team | November 2015 (ongoing) |  | Completed
26 |  |  | Provide information and presentations related to the SSIP and resources available to support SWDs in LCAPS as requested by team | SED Representative to LCAP Support Team | November 2015 (ongoing) |  | Completed
27 |  |  | Receive and follow up on referrals from LCAP Support Team for assistance to LEAs related to SWDs | SED Director, SED Representative to LCAP Support Team | November 2015 (ongoing as needed) | TBD
28 |  | SED - Provide information and support to California County Superintendents Educational Services Association (CCSESA) | Provide information and presentations related to the SSIP and resources available to support SWDs in LCAPS | SED Director | November 2015 (ongoing as needed) | TBD
29 |  |  | Receive and followup on referrals for assistance to LEAs related to SWDs | SED Director | November 2015 (ongoing as needed) | TBD
30 |  | SED - Work with SELPA to increase SPED participation in LEA LCAP planning | Participate in monthly SELPA meetings to share information about LCAP support team activities and to receive information on local concerns. | SED Director, SED Representative to LCAP Support Team | Spring 2013 (ongoing) |  | Completed
31 |  |  | Solicit input on products and activities that would encourage SELPAs to become more visible and participatory in LEA LCAP evaluation and revision | SED Director | Spring 2013 (ongoing) | Spring 2017
32 |  |  | Support SELPA Directors to assist LEA special education personnel to participate in the development, evaluation and revision of the LCAP. | SED Director | Spring 2013 (ongoing) | Spring 2017
33 | 2A. Developing Support for Implementing EBPs
34 | Refine system for selecting LEAs for SSIP Assistance
35 |  | Develop the selection measures to be used to identify LEAs for higher levels of assistance and potential intervention - criteria to include the LEA's recent compliance history, progress toward performance indicator targets, and changes in SIMR results |  |  | Fall/Winter 2015 | Spring 2017
36 |  |  | Identify the data or other criteria the CDE will use to select LEAs for assistance, which may include the LEA's recent compliance history/determinations, progress toward performance indicator targets, and changes in SIMR results | AES Adminstrator | Fall/Winter 2015 | Spring 2017
37 |  |  | For each data element or other criterion to be used in the LEA selection process, develop performance targets against which each LEA will be measured to enable the CDE to determine those LEAs that are making appropriate progress, and those LEAs that require additional assistance or intervention | AES Adminstrator | Fall/Winter 2015 | Summer 2017
38 |  |  | Obtain stakeholder (i.e., LCAP Support Team, SELPA) input on the calculation process for identifying LEAs for assistance or intervention and refine the process based on input obtained | AES Adminstrator | Fall/Winter 2015, ngoing | Fall/Winter 2016, Ongoing | Completed
39 | Support CDE's LCAP Assistance to LEAs | Develop systems for receiving and acting on referrals for assistance from the LCFF/LCAP technical assistance system. | Participate in ongoing LCAP Support Team Activities | PPS Unit Administrator | Winter/Spring 2015 | Completed/Ongoing | Completed
40 |  |  | Provide special education expertise and resources for inclusion in the LCAP technical assistance structure being developed to support LEAs in implementing effective LCAPs | PPS Unit Administrator | Winter/Spring 2015 | Completed/Ongoing | Completed
41 |  |  | Establish the means by which the CCEE, a COE, or a single school district may submit a request to the SED to provide expertise or assistance to support improved LCAP development and/or implementation | SED Director, Associate Director | Winter/Spring 2015 | TBD
42 |  |  | Build SED capacity to respond to requests for assistance from LEAs or COEs seeking to improve their LCAP development and/or implementation processes | PPS Unit Administrator | Fall/Winter 2015 | Fall 2017
43 | Communicate SIMR and related data to LEAs | Develop process for SED to annually provide data to each LEA to highlight the performance of students with IEPs who are members of the LCAP target groups. | Identify key LEA data elements that provide LEAs information on school climate, student behavior, instructional efficacy, etc. | SED Director, AES Administrator | Fall/Winter 2015 | Spring 2017
44 |  |  | Develop process for compiling data for each LEA on the selected data elements | SED Director, AES Administrator | Winter 2015 | Spring 2017
45 |  |  | Compile results for each LEA to include in an annual update on the status of the LEA to assist in identifying areas for LEA improvement | SED Director, AES Administrator | Winter 2015 1st implementation Winter 2016?? | Spring 2017
46 |  |  | Identify information to be included in the annual update to each LEA, including current data on key elements, noted concerns identified by the data, potential areas on which to focus LEA self-evaluation, the LEA's monitoring status, etc. | SED Director | Winter 2015 | Spring 2017
47 |  |  | Develop template for the annual update to LEAs that will allow for inclusion of information specific to each LEA | SED Director, AES Administrator | Winter 2015/2016 | Spring 2017
48 | Develop system for reporting progress to the CDE/SED | Develop template for each LEA required to implement a Tier 1, 2, or 3 plan to report (twice annually) on its status | Consult with SSIP Work Group to identify information to require LEAs to include in the report, including key findings on current improvement activities, areas needing further improvement, progress on implementing the local improvement plan, etc. | SED Director | Fall/Winter 2015 | Summer 2017
49 |  |  | Develop a self-assessment process to be used by LEAs identified for assistance or intervention to assist them in identifying areas for improvement, citing root causes, and selecting effective improvement activities - the results of which are to be included in the LEA reporting process | SED Director | Fall/Winter 2015 | Spring 2017
50 |  |  | Determine the most effective mode and layout for LEAs to report information the CDE needs to evaluate LEA improvement efforts, progress on implementing the local improvement plan, etc. | SED Director | Fall/Winter 2015 | Summer 2017
51 |  |  | Develop means for receiving reported information, reviewing it, and providing feedback to districts on reporting elements as necessary | SED Director, AES Administrator | Fall/Winter 2015 | Summer 2017
52 | Develop and refine systems for housing and communicating resources to LEAs | Develop repository for EBPs and resources to support LEA improvement | Identify target areas in which CDE will provide resources on EBPs to support improvement, including improved attendance and truancy reduction, improved behavior mangagement practices to reduce suspensions and expulsions, improved teaching and learning in the California State Standards (Common Core), etc. | SED Director, PPS Administrator | Spring 2016 | Spring 2017
53 |  |  | Develop dedicated Web page on the CDE Web site as a repository of EBP resources, links to EBP resources at other Web sites, and contact information for CDE Contractors who provide EBP-based support services | SED Director, PPS Administrator | Spring/Summer 2016 | Spring 2017
54 | Re-align technical assistance contracts to support SSIP and other APR indicators | Review and revise network of contractors and their scopes of work (SOWs) to provide array of needed LEA resources | Identify target areas (e.g., improved attendance, improved student behavior, improved instruction in the California State Standards) in which LEAs will benefit from direct support from SED contractors in implementing EBPs that support improved student performance among SWDs and student subgroups targeted by the LCFF | SED Director, PPS Administrator | Spring/Summer 2016 | Spring 2017
55 |  |  | Survey current SED contractor SOWs and evaluate the extent to which they currently provide EBP-based resources and support on the target topics | SED Director, PPS Administrator | Spring/Summer 2016 | Spring 2017
56 |  |  | Identify areas in which more contractor resources are needed, as well as areas in which contractor activities are redundant or not connected to the target topics - Include the following activities in contrator SOWs: Tier I (available to all LEAs): advice lines, links to resources, referrals to experts and materials, self-assessment tools based on EBPs, Webinars, communities of practice; Tier II (for selected LEAs): specialty communities of practice, guided self-assessment and improvement plan development, expert support for implementation; Tier III (for selected LEAs): Appropriate expertise assigned by the SED based on LEA needs, direct support in identifying areas for improvement and selection of effective improvement activities, and expert assistance in revising and refining the local SWD Improvement Plan | SED Director, PPS Administrator | Spring/Summer 2016 | Spring 2017
57 |  |  | Revise SED contractor SOWs as needed to ensure that as a whole they provide sufficient EBP-based resources and services to address LEA needs on the target topics, and that they are coordinated to limit redundancy in resources and services provided | PPS Administrator | Summer/Fall 2016 | Spring 2017
58 |  | Develop consistent approaches to provision of technical assistance | Plan and conduct in person and/or electronic contractor meetings |  | Fall/Winter2016 | Spring/Summer 2017
59 |  |  | Arrange training and facilitation to ensure consistent approaches to incorporating implementation science into advice lines, self assessment tools and technical assistance events |  | Winter/Spring 2017 | Fall 2017
60 |  |  | Establish quarterly reporting mechanisms regarding regarding inquiries, service requests, and issue resolution |  | Winter/Spring 2017 | Spring 2017
61 |  | Develop contractor capacity to receive and respond to LEA information requests | Identify the responsibilities and specific tasks involved to ensure that all SED contractors identified as part the SSIP EBP resource array are prepared to receive and respond to LEA requests for assistance from LEAs | PPS Administrator | Winter/Spring 2017 | Fall/Winter 2017
62 |  |  | Revise SED contractor SOWs as needed to clarify their responsibilities to receive and respond to all LEA requests for assistance related to the target topics | PPS Administrator | Winter/Spring 2017 | Fall/Winter 2017
63 |  | Develop clear process for LEAs to access contractor resources | Work with SED contractors to identify the most effective means for receiving LEA requests for information and assistance on target topics each contractor addresses | PPS Administrator | Summer/Fall 2016 | Fall/Winter 2017
64 |  |  | Develop any procedures necessary to support SED contractors in preparing to receive and respond to LEA requests for information and assistance on target topics | PPS Administrator | Summer/Fall 2016 | Fall/Winter 2017
65 |  |  | Ensure that all SED contracts include the requirement for contractors to receive and respond to LEA requests for information and assistance in their contract SOWs | PPS Administrator | Summer/Fall 2016 | Fall/Winter 2017
66 | Refine SED/LEA Communication Processes | Develop and update an annual notice for SELPAs and LEAs to identify the availability of resources to support LEAs | Develop an annual notice on available EBP-based resources and services to support improvement on the target topics to all LEAs and other appropriate organizations via the SED's e-mail listservs | SED Director | Spring/Summer 2016 | Spring 2017
67 |  |  | Develop and distribute periodic notices on available EBP-based resources via the SED's e-mail listservs as new resources become available, or semi-annually, whichever is more frequent | SED Director | Starting Spring/Summer 2016 | Summer 2017
68 |  |  | Inform SELPA directors of their responsibilities to assist LEAs in meeting performance targets and understanding potential consequences for not doing so, identifying instances of noncompliance and instituting procedures to correct them and avoid future occurrences, conducting self-assessment activities, and developing and refining local improvement plans | SED Director | Spring 2016 | Summer 2017
69 |  | Develop or refine existing materials to support implementation of Tier 1, 2, and 3 technical assistance evaluations and plans | Prepare notices for LEAs regarding their identification as needing support for implementing EBPs at the Tier 1, 2, or 3 level | SED Director, Associate Director, AES Administrator | Fall 2016 | Summer 2017
70 |  |  | Refine existing review instructions for LEAs as appropriate to support evaluation and planning activities in the LEA | Quality Assurance Administrator, FMTA Administrators, PPS Administrator | Winter 2016 | Summer 2017
71 |  |  | Refine existing review instructions for staff as appropriate to support evaluation and planning activities in the LEA | Quality Assurance Administrator, FMTA Administrators, PPS Administrator | Winter 2016 | Summer 2017
72 |  |  | Develop or adapt existing compliance review materials for use in Tier 1, 2, or 3 evaluations | Quality Assurance Administrator, FMTA Administrators, PPS Administrator | Winter 2016 | Summer 2017
73 |  |  | Develop or refine LEA reporting and improvement plan forms/formats for use in Tier 1, 2, or 3 activities | Quality Assurance Administrator, FMTA Administrators, PPS Administrator | Winter/Spring 2017 | Summer 2017
74 |  |  | Adapt existing correspondence templates and notices to provide feedback to LEAs | Quality Assurance Administrator, FMTA Administrators, PPS Administrator | Winter/Spring 2017 | Summer 2017
75 |  |  | Revise notice regarding annual compliance determinations to support activities under the SSIP | SED Director, Associate Director, AES Administrator | Winter 2016 (Jan-March) | Winter 2017
76 | 2B. Implementing the System of Support for LEAs
77 | Annually Publish SIMR Results | Collect and Unduplicate CASEMIS data | Review and update CASEMIS software | AES Administrator | June 2016 (Ongoing) |  | Completed
78 |  |  | Update CASEMIS Technical Assistance Guide | AES Administrator | Fall 2015 (ongoing) |  | Completed
79 |  |  | Conduct statewide trainings (5) | AES Administrator | Fall/Winter 2015 (ongoing) |  | Completed
80 |  |  | Validate SELPA data submissions | AES Administrator | Spring/Summer 2016 (ongoing) |  | Completed
81 |  |  | Track and report on CASEMIS submissions | AES Administrator | Summer 2016 (ongoing) |  | Completed
82 |  |  | Secure late and incomplete data | AES Administrator | Summer 2016 (ongoing) |  | Completed
83 |  |  | Prepare Unduplication data sets | AES Administrator | Summer 2016 (ongoing) |  | Completed
84 |  |  | Send duplicated data notices to SELPAs | AES Administrator | Summer/Fall 2016 (ongoing) |  | Completed
85 |  |  | Receive and analyze SELPA responses | AES Administrator | Summer/Fall 2016 (ongoing) |  | Completed
86 |  |  | Finalize unduplicated data sets | AES Administrator | Summer/Fall 2016 (ongoing) |  | Completed
87 |  | Identify students with IEPs who are in the target groups for LCFF | Secure data identifying target group students including English Learners, Foster Youth and students eligible for free and reduced price meals (FRPM). | AES Administrator | Spring 2016 (ongoing) |  | Completed
88 |  |  | Prepare a data set of students with IEPs who are also target group students | AES Administrator | Spring 2016 (ongoing) |  | Completed
89 |  | Calculate assessment results by LEA for students with IEPs who are in the target groups for LCFF | Secure student level assessment results | AES Administrator | Summer 2016 (ongoing) |  | Completed
90 |  |  | Match results for students with IEPs who are also target group students | AES Administrator | Summer/Fall 2016 (ongoing) |  | Completed
91 |  |  | Identify proficiency levels for ELA and Math for each student | AES Administrator | Summer/Fall 2016 (ongoing) |  | Completed
92 |  | Calculate additional metrics (school climate, student behavior, instructional efficacy, etc.) for students with IEPs as adopted from SSIP stakeholder recommendations | Secure data regarding additional metrics for suspension and expulsion, truancy and other LCAP metrics identified by SSIP stakeholders | AES Administrator | December 2016 | Winter 2017
93 |  |  | Aggregate by LEA | AES Administrator | December 2016 | Winter 2017
94 |  |  | Format for inclusion in annual APR and for individual reports to LEAs who are identified to develop Tier 1, 2, and 3 plans | AES Administrator | December 2016 | Winter 2017
95 |  |  | Aggregate assessment results by LEA | AES Administrator | December 2016 (Ongoing) |  | Completed
96 |  | Prepare and publish APR results for the SIMR (Indicator 17) | Compare aggregated LEA data to state targets | AES Administrator | December 2016 |  | Completed
97 |  |  | Prepare a preview of the data for SELPA review | AES Administrator | December 2016 | Winter 2017
98 |  |  | Receive and respond to questions and comments | AES Administrator | December 2016 | Winter 2017
99 |  |  | Send results to each LEA | AES Administrator | December 2016 | Winter 2017
100 |  |  | Post results on the CDE web site | AES Administrator | December 2016 | Winter 2017
101 | LEA Notification | Identify technical assistance selection score for each LEA | Compare current year performance with prior year performance to identify technical assistance selection score for each LEA: 4= met target and increased percent proficient over prior year 3= met target and decreased percent proficient over prior year 2 = did not meet target and increased percent proficient over prior year 1 = did not meet target and decreased percent proficient over prior year | AES Administrator | Spring/Summer 2016 | Summer 2017
102 |  | Identify level of assistance that LEAs may require | Assign a compliance determination of "needs assistance" to districts with a technical assistance selection score of "1" | AES Administrator | Spring/Summer 2016 | Summer 2017
103 |  |  | Review prior year(s) compliance determination to identify needs for technical assistance - Tier 1/No plan required - all LEAs who earn a selection score of 2,3,or 4 Tier 1/ Plan required - all LEAs with a first year of selection score of 1 Tier 2 - all LEAs with two consecutive years of selection score of 1 (compliance determination of needs assistance for two years) Tier 3 - all districes who have previously implemented a Tier 2 plan and continue to receive a selection score of 1 (compliance determination of needs assistance for more than 2 years) | SED Director, Associate Director, AES Administrator | Spring/Summer 2016 | Summer 2017
104 |  | Prepare notices for LEAs | Prepare notices for all LEAs Tier 1/No plan required - Identify availability of technical assistance resources available through the CDE website and from CDE/SED contractors Tier 1/ Plan required - Identify requirement to submit an improvment plan to the SED/CDE and provide instructions for preparing and submitting plan (aligned to existing Performance Indicator Review process) Tier 2 - Indentify requirement to secure technical assistance and identify special grant conditions per 34 CFR 300.600 for LEAs with 2 consecutive years of needs assistance compliance determination. Provide instructions for conducting an assessment of compliance issues and evidence based practices related to the SIMR. Provide instructions for submitting a plan and for submission of ongoing evaluation data. Identify resources available through the CDE website. Identify resources availble from SED/CDE contractors Tier 3 - Indentify requirement to secure technical assistance and identify special grant conditions per 34 CFR 300.600 for LEAs with 2 or more consecutive years of needs assistance compliance determination. Provide instructions for participating in a CDE-led assessment of compliance issues and evidence based practices related to the SIMR. Provide instructions for implementing the resultant corrective action and improvement plans and for submission of ongoing evaluation data. Identify resources available through the CDE website. Identify resources availble from SED/CDE contractors. | Associate Director, Quality Assurance Admin II | Summer/Fall 2016 | Summer/Fall 2017
105 | Provide Tier 1 resources to all LEAs | Verify availability of evidence based practices on CDE and CDE/SED contractor websites | Conduct audit to verify links and to evaluate the continued availability of linked resources | PPS Administrator | Spring - Fall 2016 |  | Completed
106 |  |  | Repair any broken links | PPS Administrator | Spring - Fall 2016 | Fall 2017
107 |  |  | Remove outdated resources | PPS Administrator | Spring - Fall 2016 | Fall 2017
108 |  | Verify continued availability of CDE/SED contractor resources | Conduct annual validation of staffing | PPS Administrator | Spring - Fall 2016 | Fall 2017
109 |  |  | Conduct annual validation of expert consultants and exemplary programs | PPS Administrator | Spring - Fall 2016 | Fall 2017
110 |  |  | Conduct annual validation of help desk protocols | PPS Administrator | Spring - Fall 2016 | Fall 2017
111 |  |  | Verify self assessment tools | PPS Administrator | Spring - Fall 2016 | Fall 2017
112 |  |  | Verify Communities of Practice | PPS Administrator | Spring - Fall 2016 | Fall 2017
113 |  |  | Verify annual webinar schedule | PPS Administrator | Spring - Fall 2016 | Fall 2017
114 |  |  | Update descriptive materials regarding CDE and CDE/SED resources | PPS Administrator | Spring - Fall 2016 | Fall 2017
115 |  | Prepare and send resources to all Tier 1,2, and 3 LEAs |  |  | Winter 2016 | Fall 2017
116 | Provide specialized supports to Tier 1/ Plan required LEAs | Update CDE resources | Review Tier 1/ Plan required Program Improvement Plan (PIR) review materials related to the SIMR (Indicator 17) | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2017
117 |  |  | Conduct training with Focused Monitoring and Technical Assistance (FMTA) Unit staff and CDE/SED contractors regarding data calculation, selection, procedures and evaluation criteria for Tier 1 plans. | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2017
118 |  |  | Update materials posted on the CDE/SED website | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2017
119 |  |  | Verify TA contacts in SED for data and for plan submission/evaluation | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2017
120 |  |  | Prepare site and format for documenting questions from LEAs and answers provided | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2017
122 |  | Review the Tier 1/ Performance Indicator Review (PIR) process with SELPAs and LEAs | Meet with Monitoring workgroup to review requirements and to plan dissemination | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2018
123 |  |  | Conduct training at SELPA meeting | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2018
124 |  |  | Conduct statewide webinar | Associate Director, Quality Assurance Admin II | Fall 2016 - Winter 2017 | Spring 2018
125 |  | Disseminate notices to Tier 1/ Plan required LEAs | Provide letters and lists to Focused Monitoring and Technical Assistance unit managers and staff | Associate Director, Quality Assurance Admin II | Winter 2017 | Fall 2018
126 |  |  | Provide copies of letters and lists to CDE/SED contractors | Associate Director, PPS Unit Administrator | Winter 2017 | Fall 2018
127 |  |  | Answer questions and provide technical assistance regarding plan requirements | FMTA Units | Winter - Spring 2017 | Fall 2018
128 |  |  | Document questions and record responses | FMTA Units | Winter - Spring 2017 | Fall - Winter 2018
129 |  |  | Provide clarification by phone and in writing as appropriate | FMTA Units | Winter - Spring 2017 | Fall - Winter 2018
130 |  |  | Refer to CDE/SED contractors as appropriate | FMTA Units | Winter - Spring 2017 | Fall - Winter 2018
131 |  | Receive, review and approve plan submissions | Track plan submissions - contact LEAs in advance of due dates to verify progress | FMTA Units | Winter - Spring 2017 | Spring 2018
132 |  |  | Record submissions | FMTA Units | Summer 2017 | Spring 2018
133 |  |  | Conduct evaluation using CDE/SED protocol | FMTA Units | Summer - Fall 2017 | Spring 2018
134 |  |  | Document needs for technical assistance from CDE/SED staff and contractors that are embedded in the plan. | FMTA Units | Summer - Fall 2017 | Summer 2018
135 |  |  | Provide evaluation feedback to LEA - secure additional information as required to meeting plan requirements | FMTA Units | Summer - Fall 2017 | Summer - Fall 2018
136 |  |  | Review plan and evaluation with unit manager | FMTA Units | Summer - Fall 2017 | Summer - Fall 2018
137 |  |  | Prepare successful submission letter that confirms plans for provision of assistance by CDE/SED staff and consultants. | FMTA Units | Fall - Winter 2017 | Fall 2018
138 |  | Provide technical assistance as planned in successful submission letter | Verify continued need and content in advance of the planned date. | FMTA Units | Fall - Winter 2017 | Fall 2018
139 |  |  | Provide assistance; gather evaluations as appropriate for group events | FMTA Units | Fall - Winter 2017 | Fall - Winter 2018
140 |  |  | Conduct follow-up calls to solicit evaluation information. | FMTA Units | Winter - Spring 2017 | Winter 2018
141 | Provide Tier 2 supports to LEAs | Update Tier 2 resources | Verify capability in CDE/SED contractors | FMTA Units | Summer - Fall 2018 | Winter 2018
142 |  |  | Verify availability and schedule of Community of Practice | FMTA Units | Summer - Fall 2018 | Winter 2018
143 |  |  | Verify expert consultants are available to facilitate Tier 2 evaluation and planning processes | FMTA Units | Summer - Fall 2018 | Winter 2018
144 |  | Review the Tier 2 process | Meet with Monitoring workgroup to review processes and requirements; responsibilities for technical assistance and special conditions | Associate Director, Quality Assurance Admin II | Fall - winter 2018 | Spring 2018
145 |  |  | Conduct training at SELPA meeting | Associate Director, Quality Assurance Admin II | Fall - winter 2018 | Spring 2019
146 |  |  | Conduct statewide webinar for Tier 2 LEAs | Associate Director, Quality Assurance Admin II | Fall - winter 2018 | Spring 2019
147 |  | Disseminate notices to Tier 2 LEAs | Provide letters and lists to Focused Monitoring and Technical Assistance unit managers and staff | Associate Director, Quality Assurance Admin II | Winter 2018 | Fall 2019
148 |  |  | Provide copies of letters and lists to CDE/SED contractors | Associate Director, Quality Assurance Admin II | Winter 2018 | Fall 2019
149 |  |  | Answer questions and provide technical assistance regarding Tier 2 plan requirements | FMTA Units | Winter 2018 | Fall 2019
150 |  |  | Document questions and record responses | FMTA Units | Winter 2018 | Fall - Winter 2019
151 |  |  | Provide clarification by phone and in writing as appropriate | FMTA Units | Winter 2018 | Fall - Winter 2019
152 |  |  | Coordinate responses with CDE/SED contractors whenever possible. | FMTA Units | Winter 2018 | Fall - Winter 2019
153 |  | Link LEAs to CDE/SED contractors for assistance in conducting Tier 2 evaluation | Identify contact person in the LEA | FMTA Units | Winter 2018 | Winter 2019
154 |  |  | Make a joint call to the LEA contact with the appropriate CDE/SED contractor to identify the support resources available, the pool of expert facilitators, and the Community of Practice that includes other districts engaged in the same planning process | FMTA Units | Winter 2018 | Winter 2019
155 |  | Receive, review and approve plans to conduct Tier 2 evaluation and improvement planning. | Track plan submissions - contact LEAs in advance of due dates to verify progress | FMTA Units | Winter - Spring 2019 | Winter - Spring 2020
156 |  |  | Record submissions | FMTA Units | Winter - Spring 2019 | Winter - Spring 2020
157 |  |  | Conduct plan evaluation using CDE/SED protocol ensuring that the plan includes: External facilitator contracted to facilitate the evaluation and plan development Names and roles of participating staff, parents and experts representing general education, special education, English learners, foster youth and FRPM Methods and items for evaluating related compliance items Methods and data that will be used to assess root cause issues. Tools that will be used to evaluate implementation of evidence based practices. Major activities and timelines. | FMTA Units | Winter - Spring 2019 | Spring 2020
158 |  |  | Provide evaluation feedback to LEA - secure additional information as required to meeting planning requirements | FMTA Units | Winter - Spring 2019 | Spring 2020
159 |  |  | Review plan with unit manager | FMTA Units | Winter - Spring 2019 | Sprng 2020
160 |  |  | Prepare successful submission letter that confirms that the plan meets CDE/SED requirements for a Tier 2 evaluation. | FMTA Units | Spring - Summer 2019 | Spring 2020
161 |  | Provide technical assistance as needed to assist LEA to complete Tier 2 evaluation | Contact LEA and contracted facilitator at key phases in their Tier 2 evaluation to assess their progress, ascertain any changes to their plan, and to offer assistance. | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
162 |  |  | Note any changes to the evaluation plan | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
163 |  |  | Arrange or provide assistance as agreed | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
164 |  | Receive, review and approve initial LEA report of Tier 2 evaluation and improvement planning | Review Tier 2 evaluation using CDE/SED protocol ensuring that the LEA implemented the evaluation plan as approved or modified (in agreement with CDE/SED). Validate that LEA: Contracted for an External facilitator to facilitate the evaluation and plan development Included staff, parents and experts representing general education, special education, English learners, foster youth and FRPM Evaluated compliance items using the methods in the plan Assessed root cause issues using the data and methods in the plan Evaluated implementation of evidence based practices. | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
165 |  |  | Review the results of the evaluation to identify corrective actions that are required due to findings of noncompliance | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
166 |  |  | Review the improvement plan to determine its relationship to the root cause issues identified and the extent to which it relies on the components of implementation science. | FMTA Units | Summer - Fall 2019 | Summer - Fall 2020
167 |  |  | Review the improvement plan to verify the collection, use and reporting of evaluation information to the CDE using CDE issued self evaluation report formats. | FMTA Units | Fall - Winter 2019 | Summer - Fall 2020
168 |  |  | Provide feedback to LEA regarding the need for more information - secure additional information as needed to meet compliance or improvement plan requirements | FMTA Units | Fall - Winter 2019 | Fall - Wnter 2020
169 |  |  | Review plan with unit manager | FMTA Units | Fall - Winter 2019 | Fall -Winter 2020
170 |  |  | Prepare successful submission letter that confirms that the plan meets CDE/SED requirements for a Tier 2 evaluation. | FMTA Units | Winter - Spring 2019 | Fall - Winter 2020
171 |  | Receive, review and approve periodic LEA self-evaluation reports | Contact LEA and contracted facilitator at key phases in their Tier 2 implementation to assess their progress, ascertain any changes to their plan, and to offer assistance. | FMTA Units | Winter - Spring 2019 | Spring 2021
172 |  |  | Contact LEA to remind them of deadlines for self evaluation reports. | FMTA Units | Winter - Spring 2019 | Spring 2021
173 |  |  | Review self evaluation reports for clarity and completeness | FMTA Units | Summer 2019 | Summer 2021
174 |  | Follow up on correction of noncompliance | Review LEA evidence that they have corrected noncompliance for identified students | FMTA Units | Summer 2019 | Summer 2021
175 |  |  | Conduct a subsequent review of student records to ensure noncompliance is corrected in a new sample of students at the 100% level per OSEP requirements | FMTA Units | Summer 2019 | Summer 2021
176 | Provide Tier 3 supports to LEAs | Update Tier 3 resources | Identify CDE/SED staff available to lead a Tier 3 review | FMTA Units | Fall - Winter 2019 | Fall 2021
177 |  |  | Verify capability in CDE/SED contractors | FMTA Units | Fall - Winter 2019 | Fall 2021
178 |  |  | Verify availability and schedule of Community of Practice | FMTA Units | Fall - Winter 2019 | Fall 2021
179 |  |  | Verify expert consultants are available to participate in Tier 3 evaluation and planning processes | FMTA Units | Fall - Winter 2019 | Fall 2021
180 |  | Review the Tier 3 process | Meet with Monitoring workgroup to review processes and requirements; responsibilities for technical assistance and special conditions | Associate Director, Quality Assurance Admin II | Fall - Winter 2019 | Winter 2021
181 |  |  | Conduct training at SELPA meeting | Associate Director, Quality Assurance Admin II | Fall - Winter 2019 | Winter 2021
182 |  |  | Conduct statewide webinar for Tier 3 LEAs | Associate Director, Quality Assurance Admin II | Fall - Winter 2019 | Winter 2021
183 |  | Disseminate notices to Tier 3 LEAs | Provide letters and lists to Focused Monitoring and Technical Assistance unit managers and staff | Associate Director, Quality Assurance Admin II | Fall - Winter 2019 | Winter 2021
184 |  |  | Provide copies of letters and lists to CDE/SED contractors | Associate Director, Quality Assurance Admin II | Fall - Winter 2019 | Winter 2021
185 |  | Contact LEA to arrange Tier 3 review | Review the identification process and the data that was used to identify the LEA | FMTA Units | Winter - Spring 2020 | Winter 2021
186 |  |  | Identify the role of the CDE/SED and the requirements for district participation | FMTA Units | Winter - Spring 2020 | Winter 2021
187 |  |  | Identify a schedule that includes an initial review of compliance and evidence based practices and a schedule of improvement planning meetings to be held once the initial Tier 3 evaluation is completed. | FMTA Units | Winter - Spring 2020 | Winter 2021
188 |  |  | Answer questions and provide technical assistance regarding Tier 3 plan requirements | FMTA Units | Winter - Spring 2020 | Winter - Spring 2022
189 |  |  | Document questions and record responses | FMTA Units | Winter - Spring 2020 | Winter - Spring 2022
190 |  |  | Provide clarification by phone and in writing as appropriate | FMTA Units | Winter - Spring 2020 | Winter - Spring 2022
191 |  |  | Coordinate responses with CDE/SED contractors whenever possible. | FMTA Units | Winter - Spring 2020 | Winter - Spring 2022
192 |  |  | Record submissions | FMTA Units | Winter - Spring 2020 | Winter - Spring 2022
193 |  | Assemble collaborative team to conduct Tier 3 review | Assemble outside staff and experts to assist in the review, including staff of the CDE/SED, SELPA/LEA staff, content experts | FMTA Units | Spring - Summer 2020 | Spring 2022
194 |  |  | Identify other participants from within the district including parents, staff and experts representing general education, special education, English learners, foster youth and FRPM | FMTA Units | Spring - Summer 2020 | Spring 2022
195 |  |  | Orient staff to the purpose of the review, the processes that will be used and the roles of each of the participants. | LEAs, FMTA Units | Spring - Summer 2020 | Spring 2022
196 |  | Conduct meetings with the LEA to develop means for conducting the Tier 3 evaluation. | Identify each of the following: External facilitator contracted to facilitate the evaluation and plan development Names and roles of participating staff, parents and experts representing general education, special education, English learners, foster youth and FRPM Methods and items for evaluating related compliance items Methods and data that will be used to assess root cause issues. Tools that will be used to evaluate implementation of evidence based practices. Major activities and timelines. | LEAs, FMTA Units | Spring - Summer 2020 | Spring 2022
197 |  | Conduct Tier 3 review and prepare and review compliance and improvement plans | Review the results of the evaluation to identify corrective actions that are required due to findings of noncompliance | LEAs, FMTA Units | Summer - Fall 2020 | Spring - Summer 2022
198 |  |  | Identify root cause issues and identify major activities to address them | LEAs, FMTA Units | Summer - Fall 2020 | Spring - Summer 2022
199 |  |  | Prepare an improvement plan based on implementation science that identifies: Evidence based practices that will be implemented to address the root causes Sites that will be selected for implementation and key groups that will be convened to implement, review and adjust plans at the school and district level Specific training and other preparation that will take place to prepare for implementation Other, ongoing supports (e.g., coaching) that will be provided to ensure the fidelity of implementing the practices selected Data that will be collected and used to evaluate the results being achieved and the needs to adjust the implementation process Methods that will be used to prepare and submit evaluation data to the CDE on a twice a year basis. | LEAs, FMTA Units | Summer - Fall 2020 | Summer 2022
200 |  | Prepare a summary report and plan for review by the district board and submission to the CDE | Submit LEA board-approved plan to the CDE | LEAs, FMTA Units | Fall - Winter 2020 | Fall 2022
201 |  |  | Prepare successful submission letter that confirms that the plan meets CDE/SED requirements for a Tier 3 evaluation. | FMTA Units | Fall - Winter 2020 | Fall 2022
202 |  | Receive, review and approve periodic self evaluation reports | Contact LEA and contracted facilitator at key phases in their Tier 3 implementation to assess their progress, ascertain any changes to their plan, and to offer assistance. | FMTA Units | Fall - Winter 2020 | Fall - Winter 2022
203 |  |  | Contact LEA to remind them of deadlines for self evaluation reports. | FMTA Units | Fall - Winter 2020 | Winter 2022
204 |  |  | Review self evaluation reports for clarity and completeness. | FMTA Units | Fall - Winter 2020 | Spring 2023
205 | 3. Evaluation
206 | Develop Evaluation Contract | Select an external evaluation contractor | Develop a scope of work that identifies the purposes of the evaluation, the key evaluation questions, data collection methods and instrumentation, specifications for data analysis, reports and timelines. | PPS Administrator, AES Administrator | Winter 2015 | Spring 2017
207 |  |  | Identify potential contractors | PPS Administrator, AES Administrator | Winter 2015 | Spring 2017
208 |  |  | Secure and evaluate bids | PPS Administrator, AES Administrator | Winter 2015 | Spring 2017
209 |  |  | Select contractor | PPS Administrator, AES Administrator | Spring 2016 | Spring 2017
210 |  | Meet with contractor to review and refine evaluation questions | Discuss and evaluate the following evaluation questions. Did the CDE and its contractors complete planned activities in a timely manner? To what extent did LEAs consume technical assistance and supports? To what extent did the LEA consumers find the technical assistance resources valuable? To what extent did SSIP implementation (e.g., increased incorporation of SWDs in LCAPs, provision of data that highlighted performance of SWDs in the target population, consumption of Tier 1, 2 or 3 resources) have positive impacts on SIMR improvement ? Did the CDE collect and evaluate information related to relevant sections of the SSIP Theory of Action? Did the CDE collaborate with stakeholders to implement a continuous improvement process for the SSIP? | PPS Administrator, AES Administrator | Spring 2016 | Spring 2017
211 |  | Meet with contractor to review and refine methods for data collection and instrumentation | Clarify the methods that will be used to collect data and the specific instruments and data recording systems that will be used for the evaluation | PPS Administrator, AES Administrator | Spring 2016 | Spring 2017
212 |  | Meet with contractor to review and refine data analysis | Methods for collecting and analyzing information about completing SSIP activities Methods for measuring and analyzing use of SSIP data and technical assistance resources Methods for measuring the analyzing the LEAs evaluation of effectiveness of SSIP resources and supports Methods for measuring and analyzing impact SSIP activities on the SIMR for individual LEAs and for the state as a whole | PPS Administrator, AES Administrator | Spring 2016 | Spring 2017
213 |  | Meet with the contractor to clarify responsibilities and timelines for preparing quarterly and annual reports | Prepare quarterly reports related to SSIP accomplishments, resource use by LEAs, and LEA evaluation of SSIP resources | PPS Administrator, AES Administrator | Spring 2016 | Spring 2017
214 |  |  | Prepare biannual reports analyzing the impact of SSIP activities and progress on the SIMR for use in meetings with CDE and stakeholder groups. | PPS Administrator, AES Administrator | Spring 2016 | Summer 2017
215 |  |  | Prepare an annual report and recommendations for the CDE to consider for proposing modifications to the SIMRs and SSIP activities to the Superintendent, the SBE and the OSEP. | PPS Administrator, AES Administrator | Spring 2016 | Summer 2017
216 |  | Meet with the contractor to review responsibilities for working with the CDE and its SSIP contractors to develop data collection instruments and to collect data | Plan for quarterly meetings to develop and refine instruments and data collection and to collectively analyze the results of data collection activities. | PPS Administrator, AES Administrator | Spring 2016 | Summer 2017
217 |  | Meet with contractor to review responsibilities for preparing reports for use by the SSIP stakeholder group, meeting with stakeholders and capturing stakeholder recommendations. | Meet with the CDE to plan biannual meetings, prepare data summaries, present information, and record meeting proceedings. | PPS Administrator, AES Administrator | Spring 2016 | Summer 2017
218 | Develop Evaluation Instruments Evaluation of CA's SSIP Implementation | Develop implementation timeline to measure SED's progress | Identify specific steps required to effectively implement California's SSIP including dates by which they are to be accomplished (refer to all activities in this table). | SED Director | Fall - Winter 2015 | Winter 2016 (Revisions) | Completed
219 |  |  | Establish specific dates for completion of each step in California's implementation of its SSIP, and include them in a comprehensive timeline of California SSIP implementation | SED Director | November 2015 - February 2016 | Winter 2016 (Revisions) | Completed
220 | Evaluation of SSIP impact on school practices | Develop reporting information from SED contractors concerning the level of consumption of contractor products among LEAs | Initiate quarterly evaluation meetings with contractors. Identify information to be reported by all SED contractors regarding LEA consumption of contractor resources | SED Director, PPS Administrator | Quarterly starting Spring 2016 | Quarterly starting Spring 2017
221 |  |  | Develop a process for all SED contractors to report information regarding LEA consumption of contractor resources | SED Director, AES Administrator | Spring - Fall 2016 | Summer 2017
222 |  |  | Develop means for receiving and compiling information provided by contractors regarding LEA consumption of contractor resources | SED Director, AES Administrator | Spring - Fall 2016 | Summer 2017
223 |  | Develop survey information from all resource consumers | Consult with the SSIP Work Group to identify the type of information needed from consumers of contractor resources to determine the efficacy and relative effectiveness of those resources to support LEAs in meeting local improvement goals and improving results on California's SIMR | SED Director | Spring - Fall 2016 (Ongoing) |  | Completed
224 |  |  | Develop a survey instrument to be used by all SED contractors with consumers of contractor resources that will provide the information needed to determine the efficacy and relative effectiveness of contractor resources in providing support to LEAs in their improvement. Explore using an automatic e-mail to LEA participants requesting that they complete an online survey | SED Director, AES Administrator | Spring - Fall 2016 | Fall 2017
225 | Evaluation of SSIP impact on student performance | Calculate SIMRs for each LEA and the state as a whole | Assign staff of the SED's Assessment, Evaluation, and Support Unit (AES) to process annual statewide assessment results as needed to calculate California's SIMR annually | SED Director, AES Administrator | Fall 2016 (Ongoing) |  | Completed
226 |  |  | Annually calculate California's SIMR, and provide California's SIMR results from prior years (as available) and calculate year-to-year changes and longitudinal trends in SIMR results | SED Director, AES Administrator | October - November 2016 (Ongoing) |  | Completed
227 |  | Collect and analyze data | Review the California SSIP implementation timeline at least monthly to monitor the state's progress in implementation to ensure that all milestones in the timeline are met | PPS Administrator, Evaluation Contractor | Beginning March 2016 (Ongoing) |  | Completed
228 |  |  | Contact key staff and stakeholders to obtain information about activities completed, barriers encountered, outcomes achieved, and next steps planned. Compare to planned activities. | PPS Administrator, Evaluation Contractor | Beginning March 2016, ongoing | Beginning Spring 2018, ongoing
229 |  |  | Secure usage information from contractors including metadata related to online hits to website materials. | PPS Administrator, Evaluation Contractor | Beginning March 2016, ongoing | Beginning Spring 2018, ongoing
230 |  |  | Secure survey information. Prepare summary statistics about usage and survey information | PPS Administrator, Evaluation Contractor | Beginning March 2016, ongoing | Beginning Spring 2018, ongoing
231 |  |  | Secure appropriate CASEMIS, CALPADS and Assessment data to prepare SIMR and other information. Conduct analysis of services consumed and their relationship to changes in the SIMR | AES Administrator, Evaluation Contractor | Beginning March 2016, ongoing |  | Completed
232 |  |  | Prepare quarterly reports related to SSIP accomplishments, resource use by LEAs, and LEA evaluation of SSIP resources | AES Administrator, Evaluation Contractor | Beginning March 2016 (Ongoing) |  | Completed
233 |  |  | Prepare biannual reports analyzing the impact of SSIP activities and progress on the SIMR for use in meetings with CDE and stakeholder groups. | AES Administrator, Evaluation Contractor | Beginning March 2016 (Ongoing) |  | Completed
234 |  |  | Prepare an annual report and recommendations for the CDE to consider for proposing modifications to the SIMRs and SSIP activities to the Superintendent, the SBE and the OSEP. | AES Administrator, Evaluation Contractor | Beginning March 2016 (Ongoing) |  | Completed
235 | Expand Stakeholder group and work with stakeholder group to refine SSIP activities | Continue SSIP Stakeholder Group activities to refine SSIP process, resource array, and improve SIMR outcomes | Review SSIP Stakeholder membership and consider expanding to include additional members and specialty subgroups (e.g., support for English Learners with IEPs, general education/special education collaboration, implementation science). | SED Director, PPS Administrator, Evaluation Contractor | March to May 2016 | Spring 2017
236 |  |  | Schedule and conduct biannual SSIP Stakeholder group meetings to discuss evaluation findings, review the adequacy of the current EBP-resource array, assess student performance on the SIMR, and recommend activities needed to refine the State's support to LEAs on SSIP implementation. | SED Director, PPS Administrator, Evaluation Contractor | June and December of 2016 | Winter 2016-17 | Completed
237 |  |  | Work with SED contractors to develop additional resources, services, or activities identified by the SSIP Work Group as needed by LEAs to support improved SWD academic performance | SED Director, PPS Administrator, Evaluation Contractor | June 2016, ongoing |  | Completed

## SSIP Acronym Glossary List
California Department of Education Special Education Division January 2016
SSIP Acronym Glossary List
Legend | Acronym | Term
| ADAD | Assessment Development and Administration Division
| Admin. | Administrator
| AES | Assessment Evaluation and Support Unit
| AMARD | Analysis Measurement and Accountability Reporting Division
| CASEMIS | California Special Education Management Information System
| CCEE | California Collaborative on Educational Excellence
| CCSESA | California County Superintendents Educational Services Association
| CDE | California Department of Education
| CFR | Code of Federal Regulations
| COE | County Office(s) of Education
| EBP | Evidence Based Practice
| EL | English Learner
| ELA | English Language Arts
| FMTA | Focused Monitoring and Technical Assistance Unit
| FRPM | Free and Reduced Priced Meals
| FY | Foster Youth
| LASSO | Local Accountability System and Support Office
| LCAP | Local Control Accountability Plan
| LCFF | Local Control Funding Formula
| LEA | Local Educational Agency
| PPS | Policy Programs and Services Unit
| SBE | State Board of Education
| SED | Special Education Division
| SELPA | Special Education Local Plan Area
| SIMR | State Identified Measurable Result
| SOW | Scope(s) of Work
| Sped | Special Education
| SSIP | State Systemic Improvement Plan
| SSPI | State Superintendent of Public Schools
| SWD | Student(s) With Disability(ies)
| TA | Technical Assistance
| TAG | Technical Assistance Guide
| TSD | Technology Services Division
| WestEd | Contractor/consultant to the SBE developing the LCAP evaluation rubrics