## Slide 1: Item #16 Promise Academy – Material Revision State Board of Education September 7, 2018

## Slide 2: Background
Promise Academy (PA) was approved by the State Board of Education on January 19, 2018
  Grades transitional kindergarten (TK) through eight for a five year term - July 1, 2018, through June 30, 2023
  Three conditions as part of the approval
  Two conditions have been met
  One condition regarding the facility lease agreement has not been met
    “By June 15, 2018, the Promise Academy Board will provide the California Department of Education (CDE) with a fully executed facility lease agreement”

## Slide 3: Background (2)
School must open by September 30, 2018, to retain SBE authorization or be approved for a material revision
May 29, 2018, CDE received the request for material revision to delay the opening by one year due to inability to secure a facility

## Slide 4: CDE Recommendation (1)
The CDE recommendation is that the SBE hold a public hearing to approve the request from Promise Academy for a material revision under the oversight of the SBE:
Change from opening 2018–19 to
2019–2020 for a five-year year term of July 1, 2018, through June 30, 2023

## Slide 5: CDE Recommendation (2)
Recommendation based on:
  Sound Educational Program
  Demonstrably likely to successfully implement the program
  Reasonably comprehensive description of most charter elements

## Slide 6: Advisory Commission on Charter Schools
August 14, 2018, meeting
Advisory Commission on Charter Schools (ACCS) moved staff’s recommendation to approve the request for material revision.
The motion passed unanimously.

## Slide 7: CDE Review
Review of the conditions of the original SBE approval
By June 15, 2018, provide a revised budget with a positive three-year ending fund balance.
  This condition has been met.
By June 15, 2018, provide a revised charter petition containing the necessary changes needed to reflect the SBE as the authorizing entity.
  This condition has been met.
By June 15, 2018, the PPS Board will provide the CDE with a fully executed facility lease agreement.
  This condition has not been met.

## Slide 8: CDE Review (2)
Sound educational program:
Review of the educational program in the new charter petition
  Petition does provide a reasonably comprehensive description of most charter elements
    Charter School Petition Review Form - Attachment 1
  If approved by the SBE, the following charter elements need to be clarified by the petitioner: description of educational program, measurable pupil outcomes, governance structure and suspension and expulsion procedures.

## Slide 9: CDE Review (3)
Ability to Implement:
Review of multi-year financial plan based on 2018–19 being a planning year and opening 2019–2020
  Multi-year financial plan is not fiscally viable without Silicon Schools Fund grants
  Commitment letters received for $300,000 FY 2108–19 and $200,000 FY 2019–2020
  Positive ending fund balances and adequate reserves for fiscal years 2019–2020 through 2021–22, provided funds are secured

## Slide 10: Summary
CDE staff is recommending approval of the material revision
Sound educational program, fiscally viable provided funds are secured
Clarification of Charter Elements in petition