Attachment 4

Item 3.A.3.

November 21–22, 2013

ELA/ELD SMC

Updated Timeline for 2014 Revision of the

English Language Arts/English Language Development Framework for California Public Schools: Kindergarten Through Grade Twelve*

| Event | Schedule |
| --- | --- |
| Focus Group recruitment letter and application distributed to LEAs, English language arts/English language development and stakeholder organizations, and institutes of higher education | February 2012 |
| Recruitment of Focus Group members, pursuant 5 CCR, §9511(c) and Ed Code Section 44013(a) | February to April 2012 |
| State Board of Education (SBE) action to appoint Instructional Quality Commission (IQC) members | March 7, 2012 |
| IQC meets and establishes English Language Arts Subject Matter Committee (ELA SMC); reviews pending SBE action on the timeline and the Curriculum Framework and Evaluation Criteria Committee (CFCC) application | May 4, 2012 |
| SBE action on the timeline and the CFCC application form | May 9–10, 2012 |
| Superintendent appoints Focus Group members | May 2012 |
| CFCC recruitment letter and application distributed to LEAs, English language arts/English language development and stakeholder organizations, and institutes of higher education | Mid-May 2012 |
| Recruitment of CFCC members (at least 90 days pursuant to 5 CCR, §9513) | May to August 2012 |
| Focus Group meetings in four locations, pursuant to 5 CCR, §9511(c) - Orange County Department of Education, May 22 - California Department of Education, Sacramento, May 31 - Monterey County Office of Education, June 4 - Contra Costa County Office of Education, June 5 | Late May and early June 2012 |
| ELA SMC reviews CFCC members, guidance for development of the framework, and Focus Group Report in preparation for full IQC review | September 24–25, 2012 |
| IQC recommends CFCC members and guidance for development of the framework to the SBE, reviews Focus Group Report | September 24–25, 2012 |
| SBE appoints CFCC members, receives Focus Group Report, and approves guidance for revision of the framework | November 7–8, 2012 |
| CFCC meets, six 2-day meetings in Sacramento, to develop draft English Language Arts/English Language Development Framework (ELA/ELD Framework) CFCC meetings are tentatively scheduled for the following dates: February 28–March 1, 2013 March 27–28, 2013 May 30–31, 2013 June 27–28, 2013 July 25–26, 2013 September 26–27, 2013 | February to September 2013 |
| SBE action to adopt and include the college and career readiness standards and the recommended technical modifications to the Common Core State Standards adopted by California in 2010. | March 2013 |
| ELA SMC reviews draft ELA/ELD Framework in preparation for full IQC review | November 21–22, 2013 |
| IQC approves draft ELA/ELD Framework for initial 60-day public review period | November 21–22, 2013 |
| 60-day public review period prior to IQC recommendation to SBE, pursuant to 5 CCR, §9515(a)(3) | Mid-December 2013 to mid-February 2014 |
| ELA SMC reviews public review results and staff recommendations for edits to draft ELA/ELD Framework | March 7, 2014 |
| IQC analyzes public review results and revises draft ELA/ELD Framework, approves draft for second 60-day public review period | March 28, 2014 |
| Staff incorporates IQC changes to draft ELA/ELD Framework per IQC action | April 2014 |
| Required 60-day public review and comment on IQC’s recommended ELA/ELD Framework, pursuant to 5 CCR, Section §9515(c) | May to June 2014 |
| SBE action on IQC’s recommended ELA/ELD Framework, includes public hearing | July 10–11, 2014* |
| LEA implementation of ELA/ELD Framework | 2014–2015 |
| Smarter Balanced Assessments | 2014–2015 |
| Instructional Materials Adoption | November 2015 |

* The Schedule of Significant Events (Timeline) has been updated to reflect SB 300.

© California Department of Education

Posted November 2013