Item 3.A.2.

Education Technology Committee

November 17–18, 2016

Schedule of Significant Events for the

2018 Computer Science Standards for California Public Schools:

Kindergarten Through Grade Twelve

| Event | Schedule |
| --- | --- |
| Governor Brown signed Assembly Bill 1539 into law | September 30, 2014 |
| Focus Group recruitment letter and application distributed to Local Educational Agencies (LEAs), scientists and stakeholder organizations, and institutes of higher education | September 2016 |
| Recruitment of Focus Group members | September–October 2016 |
| Superintendent appoints Focus Group members | October 2016 |
| Focus Group Meeting Locations, - California Department of Education, Wednesday, November 9, 2016 4-6pm Video Conference Included (Humboldt, San Joaquin, Monterey County Offices of Education) - San Francisco County Office of Education, Wednesday, November 16, 2016, 4-6pm - San Diego County Office of Education Wednesday November 30, 2016, 4-6 p.m. Video Conference Included (Riverside County Office of Education and Orange County Department of Education) | November 2016 |
| Instructional Quality Commission (IQC) Approves Schedule of Significant Events, Standards Advisory Committee (SAC) Application | November 17-18, 2016 |
| SBE action on a timeline and SAC application form | January 11-12, 2017 |
| SAC recruitment letter and application published/released online for LEAs, computer science stakeholder organizations, and institutes of higher education | January 2017 |
| Recruitment of SAC members | January–March 2017 |
| IQC reviews Focus Group Report and recommends SAC members and guidance for creation of computer science standards to the SBE | May 18-19, 2017 |
| SBE appoints SAC members, receives Focus Group Report, and approves guidance for the Computer Science Standards | July 12-13, 2017 |
| SAC Meetings The SAC meetings are schedule for the following dates: - August 29-30, 2017 - September 25-26, 2017 - October 23-24, 2017 - November 14-15, 2017 | August–November 2017 |
| IQC Education Technology Subject Matter Committee (SMC) reviews draft Computer Science Standards in preparation for full IQC review | January 2018 |
| IQC/SSPI approves draft Computer Science Standards for 60-day public review period | January 2018 |
| 60-day public review period prior to IQC recommendation to SBE | February-March 2018 |
| Computer Science SMC analyzes public review results and staff recommendations for edits to draft Computer Science Standards | May 2018 |
| IQC/SSPI recommends draft Computer Science Standards to the SBE. | July 2018 [additional meeting TBD] |
| SBE action on IQC’s recommended Computer Science Standards includes public hearing. | September 2018 |

© California Department of Education, 2016