| California Department of Education SBE-002 (REV 05/17/04) | info-cib-cfir-oct04item03 |
| --- | --- |
| State of California | Department of Education |
| Information memorandum |

| Date: | October 5, 2004 |
| --- | --- |

| TO: | Members, STATE BOARD of EDucation |
| --- | --- |

| FROM: | Sue Stickel, Deputy Superintendent Curriculum and Instruction Branch |
| --- | --- |

| SUBJECT: | Senate Bill (SB) 1058 Follow-Up Adoptions for Instructional Materials |
| --- | --- |

SB 1058 (Torlakson) was chaptered on October 11, 2003, and went into effect January 1, 2004. This bill added Education Code Section 60227 that allows the California Department of Education (CDE) to conduct follow-up adoptions for K-8 instructional materials and assess publisher fees to defray the cost of those adoptions. Due to budget constraints, follow-up adoptions were not conducted in 2002-03 or 2003-04. The proposed regulations to implement SB 1058 were adopted by the State Board of Education (SBE) in May 2004. It is anticipated that regulations will become operative by November of this year. Education Code Section 60227 (enacted by SB 1058) does the following: Defines “follow-up adoption” as any adoption other than the primary adoption that occurs within a six- or eight-year cycle. Requires the notification of interested parties of an upcoming follow-up adoption via mail and by posting on the CDE Web site. Requires the publication of a Schedule of Significant Events. Requires publishers to provide a Letter of Intent to Participate in the Follow-Up Adoption. Requires the CDE to assess a fee for participation in the follow-up adoption. Follow-up adoptions are conducted using the same evaluation criteria as were used in the primary adoptions for the same subjects. Any program adopted in a follow-up adoption is added to existing adoption list for the affected subject and remains adopted only for the remainder of the list’s life. The CDE plans to move forward quickly with follow-up adoptions under SB 1058. Three subjects are planned for follow-up adoptions in 2005. Shown in parentheses is the year in which the primary adoption occurred for each subject and the date on which the existing adoption list expires. Mathematics, Grades 6-8 (primary adoption in 2001; list expires June 30, 2007.) Reading/Language Arts/English Language Development (primary adoption in 2002; list expires June 30, 2008.) Foreign Language (primary adoption in 2003; list expires June 30, 2012.) The following list summarizes key preliminary activities undertaken to date related to these 2005 follow-up adoptions: Conduct Publishers’ survey (August 10-September 22, 2004). Curriculum Commission reviews procedures and takes action on the draft Schedule of Significant Events (September 29-October 1, 2004). Provide information to the State Board (SBE) in October 2004 regarding procedures and draft Schedule of Significant Events. In November 2004, provide the SBE further information on publishers’ interest in the follow-up adoptions and request that the SBE approve the draft Schedule of Significant Events. In accordance with the requirements of Education Code Section 60227, the CDE has mailed information on the proposed 2005 Follow-Up Adoptions to interested parties and posted the information on the CDE Web site. A draft Schedule of Significant Events was included in the mailing and posting. At the November SBE meeting, information from the publishers’ survey will be provided to the Board. The SBE will be asked to take action on the Draft Schedule of Significant Events. A copy of the Draft Schedule of Significant Events for the 2005 Follow-Up Adoptions is attached. Attachment 1: Draft Schedule of Significant Events (2 Pages)

Draft Schedule of Significant Events

2005 Follow-Up Adoptions Timeline

Mathematics, Grades 6-8 (2001)

K-8 Reading/Language Arts/English Language Development (2002)

Foreign Language (2003) Primary Adoptions

| DATES | EVENTS |
| --- | --- |
| November 9-10, 2004 | State Board of Education (SBE) action on Schedule of Significant Events. |
| November-December 2004 | Notification of Invitation to Submit (ITS) meeting mailed and posted on California Department of Education (CDE) Web site. |
| December 2-3, 2004 | Instructional Materials Advisory Panel (IMAP)/Content Review Panel (CRP) members reviewed by Curriculum Commission.1 |
| December 2004- January 2005 | CDE calculates fees and invoices publishers. |
| January 12-13, 2005 | Curriculum Commission Chair presents IMAP/CRP recommended members to SBE. |
| January 31, 2005 | Deadline for receipt of publishers’ fees by CDE. |
| January 31, 2005 | Deadline for publishers to RSVP for ITS meeting. |
| February 8, 2005 | ITS Meeting/Publishers’ Review. |
| February 8, 2005 | CDE distributes Standards Maps and/or Language Learning Continuums on diskette to publishers. |
| March 9, 2005 | Deadline for receipt by CDE of submission diskette, technology requirements and contact, Program Descriptions, and Publisher’s Checklist. |
| March 9, 2005 | Deadline for publishers to request written permission from CDE to sample in other than final format. |
| March 17-18, 2005 | Training of IMAP/CRPs and publishers’ presentations. |
| March 23, 2005 | Distribution of requests for price quotations by CDE. |
| March 28, 2005 | Deadline for receipt of instructional materials samples and Standards Maps to designated sites and persons as directed by CDE. |
| April-May 2005 | Legal and Social Compliance Review (Contracted). |
| March-April 2005 | Materials on display at Learning Resource Display Centers (LRDCs) throughout the state. Forms for public comment are available at the centers. |
| April 27, 2005 | Price quotes due to CDE by close of business. |
| June 1, 2005 | Last day for publishers to withdraw from adoption. |
| June 13-14, 2005 | Deliberations. |
| July 15, 2005 | Curriculum Commission Meeting: Public hearing conducted by Subject Matter Committee and full Commission; Commission takes action. |
| August 2005 | Required 30-day public display of recommended resources for adoption. |
| September 7-8, 2005 | Curriculum Commission presents recommendations to SBE; SBE conducts public hearing (Info/Action). |
| October-November 2005 | Finalize SBE report for CDE Web site. |
| October 2005 | Materials added to online price lists. |
| October 2005 | Post-adoption briefing for all approved publishers. |
| November 14, 2005 | Deadline for receipt of final printed resources reflecting legal compliance and minor edits and corrections (60 days after SBE action). |
| November 14, 2005 | Deadline for publishers to send materials to the Clearinghouse for Specialized Media and Technology for transcription. |
| December 2005- January 2006 | Distribution of Price Lists and Order Forms to School Districts by CDE. |

* Note: In several instances, more than one item may be due on the same day.