| California Department of Education Executive Office SBE-002 (REV. 06/2008) | memo-sssb-sfpd-aug09item02 |
| --- | --- |
| State of California | Department of Education |
| memorandum |  |

| Date: | August 20, 2009 |
| --- | --- |

| TO: | Members, STATE BOARD of EDucation |
| --- | --- |

| FROM: | Dr. William Ellerbee, Jr., Deputy Superintendent Special Services and Support Branch |
| --- | --- |

| SUBJECT: | Development of a Specific School Building Plan to Provide Adequate Pupil Capacity Regarding the Elimination of the Multitrack Year-Round Education Concept 6 Calendar by Los Angeles Unified School District Pursuant to California Education Code Section 37687, Chapter 901, Statutes of 2004 (Assembly Bill 1550). |
| --- | --- |

Concept 6 is a multitrack year-round calendar that divides a school’s student population into three tracks of which two tracks attend the school at one time. The Concept 6 calendar provides districts the maximum number of students that can attend any school but limits the number of instructional days to 163 instead of the required 180 (Education Code (EC) Section 37670). The lost days of instruction are made up by adding additional minutes to each school day.

EC Section 37687, which was pursuant to the Eliezer Williams, et al. vs. State of California, et al. settlement, prohibits the use of Concept 6 calendars after July 1, 2012. Any district that is operating a school on a Concept 6 multitrack year-round calendar after July 1, 2009, is required to submit evidence in writing each July 1 to the State Superintendent of Public Instruction (SSPI), who shall report to the State Board of Education (SBE), on the specific school building plan to provide adequate pupil capacity to eliminate the Concept 6 program by the earliest practicable date and no later than July 1, 2012.

The SBE approved the Los Angeles Unified School District (LAUSD) comprehensive action plan on July 6, 2005. On June 30, 2009, the district reported to the SSPI on the specific school building plan as required by EC Section 37687. LAUSD is the only district with remaining Concept 6 schools.

As of July 1, 2009, the district has developed a specific school building plan to eliminate the Concept 6 program and provide adequate pupil capacity. During the 2009-10 school year there will be 28 existing schools scheduled on a Concept 6 calendar (Attachment 1). The district has identified preferred sites to build new schools and has approved buildings needed to satisfy the pupil capacity projected on the comprehensive action plan (Attachment 2). Additionally, the district has identified and obtained the funding necessary to complete the particular projects identified.

Attachment 1: List of 2009-10 Concept 6 Schools in the Los Angeles Unified School District

(1 page)

Attachment 2: Los Angeles Unified School District Specific School Building Plan (1 page)

| Location Code | School Name | 2009-10 Calendar | 2010-11 Calendar | 2011-12 Calendar | 2012-13 Calendar |
| --- | --- | --- | --- | --- | --- |
| 4685 | Auroa Elementary School | X | X |  |  |
| 8536 | Bell Senior High | X | X | X |  |
| 8057 | Berendo Middle School | X |  |  |  |
| 2589 | Bryson Elementary School | X |  |  |  |
| 8094 | Carver Middle School | X | X |  |  |
| 8112 | Drew Middle School | X | X |  |  |
| 8113 | Edison Middle School | X | X |  |  |
| 3548 | Elizabeth Learning Center | X | X |  |  |
| 8132 | Foshay Learning Center | X | X |  |  |
| 8650 | Fremont Senior High | X | X | X |  |
| 8151 | Gage Middle School | X | X | X |  |
| 8679 | Garfield Senior High | X | X |  |  |
| 2385 | Gratts Elementary School | X |  |  |  |
| 4295 | Gridley Elementary School | X |  |  |  |
| 2375 | Hughes Elementary School | X |  |  |  |
| 8700 | Huntington Park Senior High | X | X | X |  |
| 7439 | Kindergarten Learning Academy | X |  |  |  |
| 8200 | Los Angeles Academy Middle School | X | X |  |  |
| 8736 | Los Angeles Senior High | X | X |  |  |
| 8743 | Manual Arts Senior High | X | X | X |  |
| 8750 | Marshall Senior High | X | X | X |  |
| 8268 | Nimitz Middle School | X | X |  |  |
| 4980 | Pio Pico Elementary School | X | X |  |  |
| 8636 | Polytechnic Senior High | X |  |  |  |
| 6466 | San Gabriel Elementary School | X |  |  |  |
| 8716 | Santee Education Complex | X | X | X |  |
| 7438 | Van Nuys Elementary School | X |  |  |  |
| 8462 | Virgil Middle School | X |  |  |  |
| Total Number of Schools on Concept 6 |  | 28 | 18 | 7 | 0 |

List of 2009-10 Concept 6 Schools in the Los Angeles Unified School District

	Concept 6

	Not Concept 6

Los Angeles Unified School District Specific School Building Plan

| Project Name | Board Approval Date of Preferred Site | California Environmental Quality Act/Project Approval | School Occupancy | Schools Relieved | 2009-10 Calendar | 2010-11 Calendar | 2011-12 Calendar | 2012-13 Calendar |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bell ES #3 Addition | 09/26/00 | 04/09/02 | 07/06/04 | Gage MS, Nimitz MS, Elizabeth LC |  |  |  |  |
| Bryson ES Addition | 01/03/00 | 09/25/97 | 01/06/06 | Bryson ES | X |  |  |  |
| Central LA Area New HS #1 | 09/25/01 | 09/25/01 | 09/03/08 | Marshall HS |  |  |  |  |
| Central LA Area New HS #2 | 05/28/02 | 05/28/02 | 09/04/07 | Los Angeles HS, Manual Arts HS |  |  |  |  |
| Central LA Area New MS #1 | 03/15/01 | 08/27/02 | 09/04/07 | Virgil MS, Berendo MS |  |  |  |  |
| Central LA Area New MS #3 | 07/16/02 | 06/22/04 | 09/08/09 | Berendo MS, Virgil MS |  |  |  |  |
| Central LA Area New MS #4 | 04/23/01 | 04/23/02 | 09/05/06 | Carver MS, Los Angeles Academy MS |  |  |  |  |
| Central LA New Learning Center #1 MS/HS | 12/10/02 | 10/12/04 | 09/07/10 | Berendo MS, Virgil MS, Los Angeles HS |  |  |  |  |
| Central Region Belmont Span 6-12 Reconfiguration | 01/20/03 | N/A | 09/08/09 | Virgil MS |  |  |  |  |
| Central Region ES #13 | 11/09/04 | 01/24/06 | 09/07/10 | Pio Pico ES |  |  |  |  |
| Central Region ES #16 | 07/22/04 | 11/22/05 | 09/07/10 | Aurora ES |  |  |  |  |
| Central Region HS #13 | 12/14/04 | 01/24/06 | 09/06/11 | Marshall HS |  |  |  |  |
| Central Region HS #16 | 03/07/06 | 09/25/07 | 09/06/11 | Santee Education Complex |  |  |  |  |
| Central Region MS #7 | 09/21/04 | 01/24/06 | 09/06/11 | Carver MS, Los Angeles Academy MS |  |  |  |  |
| Columbus Avenue School | 01/01/97 | 02/04/00 | 04/15/02 | Van Nuys ES |  |  |  |  |
| East LA HS #2 | 06/22/04 | 10/11/05 | 09/24/10 | Garfield HS |  |  |  |  |
| East Valley Area New HS #2 | 09/25/01 | 09/25/01 | 10/03/06 | Polytechnic HS |  |  |  |  |
| Gratts New PC | 03/11/03 | 02/08/05 | 09/07/10 | Gratts ES |  |  |  |  |
| Jefferson New Continuation HS #1 | 04/11/00 | 04/09/02 | 07/05/05 | Manual Arts HS |  |  |  |  |
| Los Angeles New Continuation HS #1 | 05/28/02 | 05/28/02 | 09/04/07 | Los Angeles HS |  |  |  |  |
| San Gabriel ES Addition | 01/01/00 | 01/22/01 | 10/01/03 | San Gabriel ES | X |  |  |  |
| SE Area New Learning Center | 05/06/01 | 03/31/02 | 09/05/06 | Huntington Park HS, Bell HS, Gage MS, Nimitz MS |  |  |  |  |
| South LA Area New HS #1 | 04/11/00 | 04/09/02 | 07/05/05 | Manual Arts HS | X | X | X |  |
| South LA Area New Hs #3 | 11/28/06 | 02/26/08 | 09/04/12 | Manual Arts HS |  |  |  |  |
| South Region ES #12 | 09/22/08 | 11/25/08 | 09/04/12 | Drew MS, Edison MS |  |  |  |  |
| South Region ES #2 | 11/02/04 | 03/07/06 | 09/07/10 | Drew MS, Edison MS |  |  |  |  |
| South Region ES #3 | 01/11/05 | 05/23/06 | 09/07/10 | Hughes ES, Elizabeth LC |  |  |  |  |
| South Region ES #4 | 11/02/04 | 03/28/06 | 09/07/10 | Bryson ES, San Gabriel ES |  |  |  |  |
| South Region ES #7 | 03/28/06 | 04/24/07 | 09/07/10 | Drew MS, Edison MS |  |  |  |  |
| South Region HS #12 | 02/14/06 | 02/26/08 | 09/04/12 | Fremont HS |  |  |  |  |
| South Region HS #2 | 07/22/04 | 05/23/06 | 09/06/11 | Fremont HS |  |  |  |  |
| South Region HS #7 | 11/25/08 | 12/31/08 | 09/04/12 | Huntington Park HS |  |  |  |  |
| South Region HS #8 | 05/28/09 | 12/31/09 | 09/02/14 | Bell HS |  |  |  |  |
| South Region HS #9 | 06/21/05 | 06/30/09 | 09/04/12 | Huntington Park HS, Bell HS |  |  |  |  |
| South Region MS #2 | 07/22/04 | 03/07/06 | 09/07/10 | Gage MS, Nimitz MS, Elizabeth LC |  |  |  |  |
| South Region MS #3 | 04/22/08 | 12/09/08 | 09/04/12 | Gage MS |  |  |  |  |
| South Region MS #6 | 07/22/04 | 01/24/06 | 09/07/10 | Foshay LC |  |  |  |  |
| Southeast Area New HS #2 | 10/25/00 | 02/26/02 | 09/06/05 | Huntington Park HS, Bell HS |  |  |  |  |
| Valley Region Byrd HS Reconfiguration | 01/10/06 | 08/28/07 | 10/31/09 | Polytechnic HS |  |  |  |  |
| Valley Region ES #8 | 12/14/04 | 05/09/06 | 09/07/10 | Gridley ES |  |  |  |  |
| Valley Region ES #9 | 01/11/05 | 04/25/06 | 09/07/10 | Kindergarten Lrn Acad, Van Nuys ES |  |  |  |  |
| Valley Region Hesby Span K-8 Reopening | 01/20/04 | 10/12/04 | 09/06/06 | Van Nuys ES |  |  |  |  |
| Valley Region Polytechnic Addition | 10/28/03 | 10/28/03 | 07/07/04 | Polytechnic HS | X |  |  |  |

   Concept 6

   Not Concept 6

    Un-shaded schools are not yet opened

The school occupancy date represents the date the addition or new school was opened and does not necessarily coincide with the date that the Concept 6 schools were or will be relieved.

Schools that are slated to be opened after June 30, 2012, are adding additional capacity to the district and were projects in the original comprehensive action plan. Due to demographic and other factors, these schools are not necessary to relieve Concept 6.