California Department of Education

Program Improvement Corrective Action with Intensive Technical Assistance (DAIT)

Part I (A): Implementation of Corrective Action 6

County: Monterey		Local Educational Agency: Greenfield Union Elementary School District

| Corrective Action 6 | Status Report on Actions Taken to Implement |
| --- | --- |
| Local Educational Agency (LEA) implementation of State Board of Education-adopted/standards aligned core and intervention materials ensuring full implementation in every classroom. - Reading/English Language Arts - R/ELA Intervention - Mathematics - Mathematics Intervention | ● Reading/English Language Arts Gr. K-5 Houghton Mifflin (2002) core program fully implemented Gr. 6-8 Holt/Reinhart/Winston (2002) core program fully implemented ● R/ELA Intervention Gr. 4-8 Inside Language Intervention (2009) purchased and implemented August 2009 ● Mathematics Gr. K-5 Houghton Mifflin Math (2009) core materials purchased and fully implemented Gr. 6-8 McDougal Littell (2009) core materials purchased and fully implemented ● Math Intervention Gr. K-5 Curriculum-embedded intervention components are used during math intervention instructional time Gr. 6-8 Intervention math shadow classes have been implemented to support the core program |
| LEA has implemented professional development in the adopted materials for teachers and administrators. - English Language Arts - R/ELA Intervention - Mathematics - Mathematics Intervention | ● AB466 ELA and Math Gr. K-8 teachers, training began in 2003 and has been ongoing as SB472 for new hires ● AB430 ELA and Math Administrators’ training began in 2003 and has been ongoing as SB35 for new administrators ● SB472 ELA Intervention Gr. 4-8 Inside Language teachers, began in August 2009 and concluded in October 2009. Participants: 22 teachers & all 4 principals Training provided by DAIT team members. |
| LEA implementation of nine Essential Programs Components (EPCs) for instructional success in underperforming schools including interventions and supports for English learners (ELs), students with disabilities (SWDs), and other high priority students. | EPC 1: Instructional Program: Substantially Implemented New math and ELA intervention adoptions in place, new ELA adoption process underway EPC 2: Instructional Time: Substantially Implemented Instructional day includes state-recommended minutes in ELA and math and intervention time for ELA and math for all students: ELs, SWDs, and other high priority students EPC 3: Lesson Pacing Guides: Substantially Implemented Pacing guides for grades K-8 have been developed in ELA and math and are in daily use. LEA working on developing pacing guides for the newly adopted grades 4-8 Intensive Intervention program for ELA (Inside Language). Daily implementation of pacing guides is monitored by principal walkthroughs and teacher submitted lesson plans. Pacing guides need to be reevaluated at end of year and adjusted to align with benchmark tests and state tests. EPC 4: School Administrator Instructional Leadership Training: Substantially Implemented All administrators completed 40 hours of training and structured practicum in ELA and math (AB 430). Administrators also attended training in: Gradual Release of Responsibility, Professional Learning Communities, RTI2, Anita Archer classroom management, cognitive coaching, and principals receive weekly coaching with DAIT personnel. Principals need more training in data analysis, use of formative and summative assessments, and use of research-based practices to plan and deliver instruction to meet varying student needs. District leadership would benefit from continuous improvement methodology and application. EPC 5: Credential Teachers and Professional Development Opportunity: Fully Implemented ●AB466 ELA and Math Gr. K-8 teachers, training began in 2003 and has been ongoing as SB472 for new hires ● AB430 ELA and Math Administrators’ training began in 2003 and has been ongoing as SB35 for new administrators ● SB472 ELA Intervention Gr. 4-8 Inside Language teachers, began in August 2009 and concluded in October 2009. Participants: 22 teachers & all 4 principals Training provided by DAIT team members. At this time all teachers are appropriately credentialed for their assignments. Three (3) teachers are not Highly Qualified as per NCLB requirements. EPC 6: Ongoing Instructional Assistance and Support for Teachers: Partially Implemented Coaches have been trained in Direct Instruction and are receiving more training and modeling in the Gradual Release model. There are 4 academic coaches and an ELA intervention specialist who provide coaching for teachers and who assist teachers with planning, collaboration, data analysis, intervention placement and monitoring, and instructional strategies for all students. Coaches need to implement the DI model with demonstration lessons and coaching daily for full compliance. EPC 7: Student Achievement Monitoring System: Partially Implemented Reading First (Houghton Mifflin Theme tests) administered in grades K-3, HM summative assessments in grades K-5 in ELA. Grades K-5 math benchmarks administered and entered into data system; grades 6-8 benchmarks administered but not in data system. In addition, weekly standards-based mini quizzes are administered grades K-5 in math and reading/language arts and in grades 6-8 in ELA, math, science and social studies. These data assist teachers to identify more immediate student needs and are used to plan instruction during collaboration time. DataWise is the electronic data management system and not all teachers and administrators have the needed skills to extract benchmark data. Training is underway. District-wide data analysis protocols need to be developed. EPC 8: Monthly Collaboration by Grade Level: Substantially Implemented Every Thursday is teacher collaboration time for approximately 90 minutes. Teachers meet at site by grade level to create weekly standards-based quiz and to analyze prior week’s results to use in planning ELA and math instruction. Teacher collaboration protocols are used at each site. Lesson plans are submitted weekly. Formal district walk-through process has been implemented and all sites are visited once a month. Walk-throughs started with administrators and coaches and are now include teachers. Principals monitor standards and lessons during informal classroom walk-throughs. EPC 9: Fiscal support: Substantially Implemented District and school’s general and categorical funds are used to support implementation of all EPCs and are aligned with the LEA and SPSA. School plans need to be realigned to LEA plan and reprioritized due to current budget constraints. LEA plan with budgets need to be updated. Principals need training on understanding budget reports for human and material resource planning. |
| LEA demonstrates improvement across four measures: percentage of Adequate Yearly Progress (AYP) targets met, percentage of Title I schools in the LEA that are not in Program Improvement (PI), relative growth in the Academic Performance Index (API) over time, and relative API performance. | ● AYP 2009 targets (criteria) met: 11 of 21 LEA 14 of 17 Cesar Chavez Elem. 8 of 17 Greenfield Elem. 14 of 17 Oak Ave. Elem. --- exited SAIT (HPSGP) 8 of 17 Vista Verde MS ● Program Improvement status --- LEA in PI Year 3 LEA has 3 elementary and 1 middle school --- all in PI Year 5+ ● API for LEA 2008 2009 604 612 All 598 607 Hispanic 600 608 Socioeconomically Disadvantaged 582 596 English Learners 401 384 Special Education ● Title III Met AMAOs in 2009 AMAO 1 was 50.2% - missed target by 1.4% AMAO 2 met target for first time in 6 years AMAO 3 did not meet ELA or math AYP targets |

California Department of Education

Program Improvement Corrective Action with Intensive Technical Assistance (DAIT)

Part I (B): District Assistance and Intervention Team Recommendations

County: Monterey		Local Educational Agency: Greenfield Union Elementary School District

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Governance - Update the LEA plan to include the 2009-10 allocations and align the four schools Single Site and Alternative Governance plans required by site Program Improvement status. - Provide mentoring and twice monthly progress monitoring with Superintendent. - Ensure hiring of all district office administrators is in agreement with DAIT recommendations. Superintendent will design and implement an effective interview, reference check and final decision process. - District superintendent will meet with DAIT human resources (HR) regarding collective bargaining issues. District and county HR representatives will meet on a regular basis and attend Personnel Directors meetings. Classified union contract negotiated for 2009-2012; certificated union contract still being negotiated for 2008-09. - Superintendent will define and communicate nonnegotiable policies regarding curriculum, assessment, instruction, collaborative planning and professional development. | 1. SPSA aligned to LEA plan; budget updates given to principals 3/10, SPSAs not updated. 2. Superintendent mentoring 3. Special Ed. Consultant; C&I Director; principal have been hired 4. Superintendent consults with LEA attorney regarding collective bargaining issues; HR monthly meetings held at MCOE 5.Non-negotiables: standards -based instruction; pacing guides;collaborative data analysis & lesson planning; benchmarks; walk-throughs. | 1.DAIT, Spdt., C&I Director, principals 2. DAIT, Spdt. 3 DAIT, Spdt. HR Supvsr. 4. DAIT, Spdt., Asst. Spdt., HR Supvsr., LEA attorney 5. DAIT, Spdt., C&I Dir., principals, coaches | Jan. 2010 Bi-weekly Aug. 2009 ongoing ongoing | X X X X | X X X |  |  | 1. SPSAs being realigned & reprioritized based on state & federal funding. Lea will be updated in June 2. Monitoring by DAIT; no formal mentoring for the Supt. 3. Positions filled 4. DAIT Human Resources has not been adequate support; Supt. has relied on external network of supt. 5. Non-negotiables communicated to all district personnel by DAIT & Spdt. |

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| - Create and monitor six-week continuous improvement plans focused on high priority actions and results. | 6. Action plans for principals C&I Director are monitored by DAIT Lead. | DAIT, Spdt., C&I Director | on-going | X | X |  |  | Action plans revised as tasks are completed |
| Alignment of Curriculum, Instruction, and Assessments to State Standards - Maintain the district Curriculum Council comprised of teacher representatives from all school sites and grade level spans initially facilitated by DAIT team member and District’s C&I Director: - Review currently adopted instructional materials, assessments and accountability requirements. - Make recommendations for improvement in curriculum, instruction and assessment using formative assessment data. - Ensure site and district administrators and grade level/subject area collaborative planning teams use grade level, classroom and individual student results for planning and improving instruction. - Ensure collaborative teams meet weekly to conduct instructional planning. - Instructional coaches at each school site engage in daily demonstration lessons, observation, feedback and support for collaborative instructional planning. | 1. Curriculum Council has been assembled and has representatives from each school site. The first meeting took place on 10/5/09. Meetings are set to take place the last Monday of each month. 1a. Assessments and accountability requirements are being addressed. Task force for new language arts has reconvened with the goal of having a recommendation for new adoption by April. 1b. Benchmark assessments and pacing guides need to be reviewed for alignment, gaps, rigor by the coaches. 2-3. Site and District Administrators assure that collaborative planning occurs a minimum of 3 times per month focused on standards mastery and DI 4. Instructional Coaches have been trained in the Direct Instruction model and are beginning demonstration lessons. | DAIT, Spdt., C&I Director, principals, coaches, Curr. Council mbrs | on-going | X | X |  |  | ●Curriculum Council monthly meetings scheduled for the last Monday of each month. ●Assessment Task Force gr. K-5 reviewed pacing guides, focus standards, and textbook alignment ●Grade level site teachers collaborating on focus-standard mini quiz and mastery of standard |

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Fiscal Operations - Continue monitoring and controlling expenditures. - Continue to fiscally support the district’s ongoing initiative to support teachers becoming highly qualified. - Continue to prioritize and seek funding for ongoing site maintenance needs. - As soon as district allocations are received, complete work on aligning LEA plan goals and actions with appropriate funding sources. - Role and services of any external consultant involved in any academic program/ services must be in agreement with DAIT Team. Use of district DAIT funding must receive approval from DAIT Team. | 1. Superintendent, CBO and Departments/Sites monitor and control expenditures bi-weekly. 2. Human Resources has worked with teachers to provide needed support to meet HQT requirements, EL authorization and credentialing requirements as per CMIS report 3. Resolution brought to Board to start work on 8 million bond for repairs and maintenance needs prioritized by MOT. 4. Updates of LEA plans have been through the PI addendums. The plan will be revised to be more inclusive in the summer of 2010. 5. Followed as specified | Spdt., CBO, C&I Director, principals Spdt., CBO, HR Spvsr. Spdt., CBO, Maintenance & Operations Spvsr. DAIT, Spdt., C&I Director, principals DAIT, Spdt. | on-going on-going on-going July 2010 Nov. 2009 | X X X X | X X X |  |  | Note: CBO presented 2nd Interim Budget to Board on Mar.11, 2009 – LEA with positive certification 2. 4 teachers have been non- re-elected pending completion of certificates. 3. Grant writer securec for library grant and outside company is working on bond passage for facility improvements. 4. LEA revision planned for July 2010 5. Spdt. is requesting SBE / CDE approval to contract with other DAIT provider(s) as deemed necessary |
| Parent and Community Involvement Begin parent education in standards-based classroom instruction and expectations. | Parent education not formally offered by the district, some sites are doing informal meetings and trainings. | Spdt, C&I Director, principals | Jan. 2010 |  | X |  |  |  |
| Human Resources - Continue to coordinate all new teacher support efforts in the district (BTSA and intern) programs. - Continue to support veteran teachers in acquiring the professional development they need to serve English learners. 3. Actively address the relationship between the district and the collective bargaining units for a more positive, collegial environment for all. | 1. BTSA is underway with 22 participants 2. All professional development applicable to new and veteran teachers: direct Instruction model has been the focus of staff development and needs are addressed through the DI model. 3. CSEA classified union ratified 3 year contract 3b. GTA teacher union in process of negotiating the 08-09 to be followed by 09-10 contract. 3c. GTA grievance level IV regarding teaching assignments and credentialing resolution is pending has been settled. A second one is pending. | MCOE, C&I Director DAIT, C&I Director Spdt., CBO, HR Spvrs, union leadership teams, LEA attorney | Sept. 2009 on-going on-going | X X X | X X X |  |  | BTSA underway and actively supporting new teachers Coaching and training for all teachers GTA teacher union contract for 2008-09 currently being negotiated |

| High-Priority DAIT Recommendations by Category | Actions to Implement Recommendations | Person Responsible | Due Date | Completion Status |  |  |  | Comments on District Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  |
| Data Systems and Achievement Monitoring - Implement the formative assessment benchmark system with on-going monitoring to insure progressively higher goals are achieved with all subgroups. - Ensure effective testing protocols and tools are used by each school/teacher. | 1. Benchmark #1 in LA and Math across all grade levels have been completed 2. Training for Data reports has been given to principals and coaches; training for teachers to begin in March. Dir. Of C&I will review external benchmark protocols for consideration of a district adoption. | DAIT, C&I Director, coaches DAIT | on-going on-going | X X | X X |  |  | LEA implementing benchmarks; need to develop and train staff in analysis protocols |
| Professional Development - Train all teachers in the D. Fischer Gradual Release Model during two buy-back days. - Train and coach principals in walk-through and support on supervision and Explicit Direct Instruction Model. - Improve at least 2 areas of Explicit Direct Instruction per semester, focusing on reading comprehension. - Provide training in data analysis of state and district formative assessments to all administrators, coaches and teachers. 5. Train all district and site administrators in systems analysis and alignment and continuous improvement planning and monitoring. | 1. Implemented on 8/17/09, 8/18/09 2.Coaches have received training and continue to receive ongoing support form MCOE DAIT team. Principals will be trained with a monthly DI focus. DO walk-throughs occur weekly with every school visited once a month and sites are conducting informal walk-throughs with teachers. 3. December is focused on content standard and learning objective. January-February was focused on the explain model demonstrate stage of D.I March will be think alouds and sentence frames. The rest of the year will be devoted to developing guided practice and checking for understanding. 4.Training provided in state and district formative assessments 5.Initial introduction is continuous improvement was given to all site and district administrators. Six week continuous improvement action plans are used for monitoring of progress of EPCs and help target specific areas of need at each site. | 1. DAIT, C&I Director, coaches 2. DAIT, C&I Director, coaches - DAIT, C&I Director, coaches - DAIT, C&I Director, coaches 5. DAIT | Aug. 17 & 18 on-going on-going on-going Fall 2009 | X X X X X | X X X |  |  | 1. Buy-Back Day Jan. 11 used for PD with DI and GRR model 2. District-wide walk-throughs conducted weekly with each site visited once a month. Teachers are now joining coaches and amin on the walk-throughs 3. DI and GRR to continue the rest of the school year 4. DAIT provided training at sites 5. DAIT providing training at sites through on-going principal coaching. |

|  | 2007 AYP |  | 2009 AYP |  | Difference in % Proficient |  | District Assessments Used | Frequency of Use | How Programs are Measured | Latest Data Summary | Use of Data by Principals and Teachers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| English/lLang. Arts (ELA) | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math | % Proficient ELA | % Proficient Math |  |  |  |  |  |
| Mathematics |  |  |  |  |  |  |  |  |  |  |  |
| LEA-wide | 17.9 | 20.6 | 22.5 | 26.5 | 4.6 | 5.9 | ▪Standards-based mini quiz ▪Benchmarks ▪Intensive Intervention Program ▪Gr. K-3 Reading Lions | ▪Weekly ▪Quarterly ▪Weekly ▪ 6-8 weeks |  |  | Thursdays early release days for collaboration |
| Hispanic or Latino | 16.7 | 20.1 | 21.6 | 26.0 | 4.9 | 5.9 |  |  |  |  |  |
| Socio-economically Disadvantaged | 16.1 | 20.0 | 21.9 | 25.5 | 5.8 | 5.5 |  |  |  |  |  |
| English Learners | 14.0 | 18.1 | 19.4 | 25.0 | 5.4 | 6.9 |  |  |  |  |  |
| Students with Disabilities | 8.0 | 10.4 | 13.0 | 13.0 | 5.0 | 2.6 |  |  |  |  |  |
| Statewide Targets | 24.4 | 26.5 | 46.0 | 47.5 | 21.6 | 21.0 |  |  |  |  |  |

| Inside Language Intensive Intervention Program grades 4-8 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2,701 = Total # students grades K-8 |  |  |  |  |  |  |  |  |
| 1,778 = Total # English Learners grades K-8 |  |  |  |  |  |  |  |  |
| 1,326 = Total # students grades 4th-8th |  |  |  |  |  |  |  |  |
| Grade | # Stds | # Stds w/ IEPs | % Stds w/ IEPs | # Stds w/ IEPs enrolled in “Inside” | % Stds w/ IEPs enrolled in “Inside” | # ELs | # ELs enrolled in “Inside” | % ELs enrolled in “Inside” |
| 4th | 271 | 18 | 7% | 12 | 67% | 177 | 79 | 45% |
| 5th | 283 | 21 | 7% | 13 | 62% | 171 | 63 | 37% |
| 6th | 261 | 32 | 12% | 16 | 50% | 131 | 39 | 30% |
| 7th | 250 | 43 | 17% | 17 | 40% | 123 | 42 | 34% |
| 8th | 261 | 34 | 13% | 20 | 59% | 114 | 36 | 32% |
| TOTAL | 1,326 | 148 | 11% | 78 | 53% | 716 | 259 | 36% |

| Grade: 1 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 303 | 90.8% | 274 | 59.1% |
| Cesar Chavez | 97 | 90.7% | 103 | 48.5% |
| Greenfield Elementary | 93 | 86.0% | 59 | 61.0% |
| Oak Avenue | 113 | 94.7% | 112 | 67.9% |

| Grade: 2 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 303 | 19.5% | 327 | 10.1% |
| Cesar Chavez | 109 | 19.3% | 109 | 14.7% |
| Greenfield Elementary | 85 | 15.3% | 110 | 9.1% |
| Oak Avenue | 109 | 22.9% | 108 | 6.5% |

| Grade: 3 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 304 | 24.7% | 274 | 4.0% |
| Cesar Chavez | 105 | 29.5% | 99 | 8.1% |
| Greenfield Elementary | 104 | 21.2% | 84 | 0% |
| Oak Avenue | 95 | 23.2% | 91 | 3.3% |

| Grade: 4 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 164 | 15.2% | 180 | 18.3% |
| Cesar Chavez | 63 | 17.5% | 66 | 24.2% |
| Greenfield Elementary | 41 | 17.1% | 54 | 5.6% |
| Oak Avenue | 60 | 11.7% | 60 | 23.3% |

| Grade: 5 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 177 | 11.3% | 201 | 27.9% |
| Cesar Chavez | 54 | 7.4% | 57 | 22.8% |
| Greenfield Elementary | 49 | 2.0% | 68 | 13.2% |
| Oak Avenue | 74 | 20.3% | 76 | 44.7% |

| Grade: 6 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| Vista Verde M.S. | 170 | 8.2% | 146 | 42.5% |

| Grade: 7 ELA Benchmarks | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| Vista Verde M.S. | 58 | 8.6% | 142 | 12.0% |

| Grade: 8 ELA Benchmark | Number of Students Tested Benchmark 1 | Percentage of Students At or Above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage of Students At or Above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| Vista Verde M. S. | 177 | 21.5% | 118 | 11.0% |

| Grade: Kinder Math | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 337 | 67.4% | 353 | 77.9% |
| CCES | 106 | 50% | 111 | 56.8% |
| GES | 119 | 58.8% | 125 | 82.4% |
| OAS | 112 | 92.9% | 117 | 93.2% |

| Grade: 1 Math | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 324 | 73.8% | 325 | 64.3% |
| CCES | 98 | 71.4% | 96 | 50% |
| GES | 112 | 69.6% | 113 | 71.7% |
| OAS | 114 | 79.8% | 116 | 69% |

| Grade: 2 Math | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD District | 340 | 27.9% | 310 | 55.5% |
| CCES | 109 | 29.4% | 101 | 51.5% |
| GES | 119 | 17.6% | 106 | 52.8% |
| OAS | 112 | 37.5% | 103 | 62.1% |

| Grade: 3 Math | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD | 298 | 45.0% | 304 | 27.6% |
| CCES | 104 | 37.5% | 105 | 26.7% |
| GES | 103 | 49.5% | 104 | 21.2% |
| Oak Avenue | 91 | 48.4% | 95 | 35.8% |

| Grade: 4 Math | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD | 254 | 42.9% | 252 | 46% |
| CCES | 86 | 45.6% | 84 | 53.6% |
| GES | 90 | 23.1% | 81 | 25.9% |
| Oak Avenue | 78 | 58.1% | 87 | 57.5% |

| Grade: 5 Math Benchmark 1 | Number of Students Tested Benchmark 1 | Percentage at or above Proficient Benchmark 1 | Number of Students Tested Benchmark 2 | Percentage at or above Proficient Benchmark 2 |
| --- | --- | --- | --- | --- |
| GUSD | 254 | 42.9% | 264 | 10.6% |
| CCES | 90 | 45.6% | 79 | 2.5% |
| GES | 78 | 23.1% | 89 | 3.4% |
| Oak Avenue | 86 | 51.8% | 96 | 24% |

| Grade: 6 Math Benchmark 2 | Number of Students Tested | Percentage of Students At or Above Proficient |
| --- | --- | --- |
| Vista Verde M.S. | 220 | 9.1% |

| Grade: 7 Math Benchmark 2 | Number of Students Tested | Percentage of Students At or Above Proficient |
| --- | --- | --- |
| Vista Verde M.S. | 219 | 17.4% |

| Grade: 8 Algebra Benchmark 2 | Number of Students Tested | Percentage of Students At or Above Proficient |
| --- | --- | --- |
| Vista Verde M.S. | 142 | 23.2% |