| California Department of Education Executive Office SBE-002 (REV. 01/2011) | memo-tlsb-cfird-aug17item01 |
| --- | --- |
| memorandum |

| Date: | August 18, 2017 |
| --- | --- |

| TO: | MEMBERS, State Board of Education |
| --- | --- |

| FROM: | TOM TORLAKSON, State Superintendent of Public Instruction |
| --- | --- |

| SUBJECT: | Revision to 2018 Science Adoption Schedule of Significant Events |
| --- | --- |

Summary of Key Issues

The State Board of Education (SBE) approved the 2018 Science Instructional Materials Adoption Schedule of Significant Events (Timeline) on March 9, 2017. In consultation with SBE staff, the California Department of Education (CDE) has made the following minor adjustments.

Subsequent to the approval of the Timeline, the September 2017 Instructional Quality Commission meeting dates were changed from September 21–22, 2017, to 
September 27–28, 2017. The revised Timeline reflects this change.

Additionally, the Publishers Invitation to Submit (ITS) meeting was scheduled to precede the January SBE meeting but has been rescheduled from January 17, 2018 to January 30, 2018, so as to follow the SBE meeting. This change will allow the CDE to distribute at the ITS meeting documents approved by the SBE at its January 2018 meeting. Consequently, the due dates for the Intent to Submit Form, Submission Form, and publisher fees have all been extended accordingly.

The CDE anticipates these minor Timeline changes will not affect the final action dates and will have no negative impacts, but may instead benefit the participating publishers.

Attachment(s)

Attachment 1: Revised 2018 Science Instructional Materials Adoption Draft Schedule of Significant Events (2 pages)

Revised 2018 Science Instructional Materials Adoption

Draft Schedule of Significant Events

Approved by the SBE on March 9, 2017

| Event | Schedule |
| --- | --- |
| State Board of Education (SBE) Adoption of Framework/Evaluation Criteria | November 3, 2016 |
| Instructional Quality Commission (IQC) approves Schedule of Significant Events (Timeline) and online reviewer application | January 19–20, 2017 |
| SBE approves Timeline and online reviewer application (per California Code of Regulations, Title 5 [5 CCR] §9513) | March 8–9, 2017 |
| Recruitment of reviewers (at least 90 days per 5 CCR §9513) | April 21–July 21, 2017 |
| IQC recommends reviewers to SBE | September 27–28, 2017 |
| Small publisher fee reduction requests due | November 2, 2017 |
| SBE appoints reviewers | November 8–9, 2017 |
| IQC approves training materials (5 CCR §9512[h]) | November 16–17, 2017 |
| SBE approves training materials (5 CCR §9512[h]) and small publisher fee reduction requests (5 CCR §9517.3) | January 18–19, 2018 |
| Invitation to Submit Meeting | January 30, 2018 |
| Intent to Submit forms due from publishers (5 CCR §9517.3) | February 1, 2018 February 12, 2018 |
| Submission List information for programs due (5 CCR §9517.3) | March 8, 2018 |
| Deadline for payment of publisher participation fees (5 CCR §9517.3) | March 27, 2018 |
| Reviewer Training | April 16–20, 2018 |
| Instructional Materials Samples Due | April 27, 2018 |
| Independent Review | April–July 2018 |
| Reviewer Deliberations | July 16–20, 2018 |
| IQC holds public meeting to receive comment (5 CCR §9524[a]) | August 2018 |
| IQC makes recommendation | September 2018 |
| SBE holds public hearing to receive comment (Education Code 60203 and 5 CCR §9524[b]) | November 2018 |
| SBE takes action on recommendation | November 2018 |

# Footnotes

All IQC dates beyond 2018 and SBE dates beyond November 2017 are estimates; those meetings have not yet been scheduled.