## Slide 1: An Update on the California State Plan for Career Technical Education Item 02
August 6, 2021

## Slide 2: Overview
Project Context and Overview
Discussion on Study Sessions
Discussion on Focus Groups
Discussion on Timeline

## Slide 3: Project Context and Overview

## Slide 4: State Plan Framework
With Equity and Access at the Foundation
State Plan Framework | Supply that meets the Demand | Effective Delivery and Support | Data that informs the investments | Systems alignment
Career Pathways | Yes | Yes | Yes | Yes
CTE Teacher Prep and Pipeline | Yes | Yes | Yes | Yes
Dual Enrollment | Yes | Yes | Yes | Yes
Regional Partnership Development | Yes | Yes | Yes | Yes
Workbased Learning | Yes | Yes | Yes | Yes

## Slide 5: Discussion on Study Sessions

## Slide 6: Discussion on Study Sessions (continued)
Session 1: A Bold Vision for CTE in CA (Sep)
  What Has Changed?
  Where Do We Want to Go?
  Role of State Systems and Leaders in Driving Innovation in High-Quality CTE
  Building and Sustaining Pathways Partnerships

## Slide 7: Discussion on Study Sessions (continued1)
Session 2: Innovative High-Quality CTE (Nov)
  Deep Dive: Areas of Innovation and Focus for the State Plan for CTE
  Opportunities for Advancing the Areas of Focus for California’s State Plan for CTE
  Summary of Discussion and Next Steps

## Slide 8: Discussion on Focus Groups

## Slide 9: Discussion on Focus Groups
Leverage Feedback from Previously Conducted Perkins Stakeholders Meetings
15 Focus Group Meetings
Areas of Focus
Cross-Section of Stakeholders

## Slide 10: Discussion on Timeline

## Slide 11: Phased Approach
PHASE | OUTLINE OF ACTIVITIES | TIMELINE
1 | Engaging Stakeholders and Understanding the Context | Jul 2021– Nov 2021
2 | Drafting the State Plan for CTE | Nov 2021–May 2022
3 | Supporting Regional Implementation of the State Plan | Jun 2022–May 2023
4 | Measuring Outcomes | Apr 2023–Jul 2023

## Slide 12: Phase 1
Engaging Stakeholders and Understanding the Context (Jul – Nov 2021)
Background Research - review of materials including plans, notes, reports, etc. (Jul/Aug 2021)
Planning for two study sessions for the CWPJAC in Sep and Nov. (Aug 2021)
Plan and conduct up to 15 virtual focus groups with regional stakeholders. (Aug - Nov 2021)

## Slide 13: Phase 2
Drafting the State Plan for CTE (Nov 2021 – May 2022)
Synthesize Research, input from the CWPJAC study sessions, virtual focus groups. (Nov 2021)
Draft State Plan using an iterative process. (Dec 2021 - Mar 2022)
Draft State Plan for CWPJAC approval. (Mar 2022)
Design a communications and dissemination strategy for the state plan. (Apr 2022)

## Slide 14: Phase 2 (continued)
Drafting the State Plan for CTE (Dec 2021 – May 2022)
Manage public comments process. (Apr/May 2022)
Finalize State Plan for CWPJAC approval. (May 2022)

## Slide 15: Phase 3
Supporting Regional Implementation of the State Plan (Jun 2022 – May 2023)
Conduct Town Halls in regions across the state (Jun - Aug 2022)
Development of State and Regional Implementation Plans (Sep 2022 - Apr 2023)
Statewide virtual implementation meetings (May 2023)

## Slide 16: Phase 4
Measuring Outcomes (Apr - Jul 2023)
Development of Outcomes Dashboard
Key metrics and benchmarks aligned to the priorities in the State Plan for CTE

## Slide 17: Questions and Discussion