## Slide 1: An Update on the California State Plan for Career Technical Education Item 04
Posted by the California Department of Education May 2021

## Slide 2: Overview
Brief History
Recap of Approach to Strategic Plan/Call to Action
Update to Plan Development and Phases
Revised Timeline
Discussion on Focus Groups

## Slide 3: November 2019–July 2020
Established the California State Team (CAST) for developing the California State Plan of Career Technical Education (CTE)
The CAST recommended a Strategic Plan/Call to Action that is a high-level, forward-looking document with clear goals and outcomes

## Slide 4: Goals for the Strategic Plan/Call to Action for CTE
  Preserve intentionality of California’s student-centered approach.
  Provide cohesion and direction for visionary and innovative approaches to the current state, regional, and local level CTE work.
  Ensure relevance for stakeholders, particularly for students and employers who are the CTE system’s ultimate benefactors.

## Slide 5: Sources of Inspiration
Student-Centered K–14 + Pathways (Guiding Policy Principles)
Larger context of State education and workforce development priorities and initiatives (Future of Work)
The Federal Strengthening Career and Technical Education for the 21st Century Act (Perkins V) State Plan for California

## Slide 6: Ongoing Considerations of CTE in California
Student-centered CTE program across local educational agencies and community colleges within California.
Employer engagement related to inter-segmental and inter-sectoral career pathways and worked based learning to improve student outcomes.
Cross system partnership and continuous improvement strategies.

## Slide 7: Ongoing Considerations of CTE in California (cont.)
Teacher and faculty preparation, qualifications (industry experience), and professional development
Barriers and strategies to increase dual/concurrent enrollment opportunities for all students
Increasing student employment readiness and outcomes

## Slide 8: Emerging Trends Impacting CTE
Online education
Competency-based education
Credential transparency
Skilled-based hiring by business

## Slide 9: Proposed Strategic Framework
Organize into four key areas*:
  Workforce supply that meets demand
  Instructional delivery and support services
  Data that informs the investments
  Cross systems alignment
  *Equity and access are foundational threads
  that are woven throughout the above four areas.

## Slide 10: Proposed Strategic Focus Areas
Jan 2021
Career Pathways
Dual Enrollment/Teacher Pathways
Adult Education
Regional Partnership Development
May 2021
Career Pathways
Teacher Pathways
Dual Enrollment
Regional Partnership Development
Workbased Learning

## Slide 11: State Plan Framework
With Equity and Access at the Foundation
State Plan Framework | Supply that meets the Demand | Effective Delivery and Support | Data that informs the investments | Cross Systems alignment
Career Pathways | Yes | Yes | Yes | Yes
Teacher Prep | Yes | Yes | Yes | Yes
Dual Enrollment | Yes | Yes | Yes | Yes
Regional Partnership Development | Yes | Yes | Yes | Yes
Workbased Learning | Yes | Yes | Yes | Yes

## Slide 12: Proposed Phased Approach
PHASE | OUTLINE OF ACTIVITIES | TIMELINE
1 | Engaging Stakeholders and Understanding the Context | Jul – Nov 2021
2 | Drafting the State Plan for CTE | Nov 2021 – May 2022
3 | Supporting Regional Implementation of the State Plan | Jun 2022 – May 2023
4 | Measuring Outcomes | Apr – Jul 2023

## Slide 13: Phase 1
Engaging Stakeholders and Understanding the Context (Jul – Nov 2021)
Background Research - review of materials including plans, notes, reports, etc. (Jul/Aug 2021)
Planning for two study sessions for the CWPJAC in Sep and Nov (Aug 2021)
Plan and conduct up to 15 virtual focus groups with regional stakeholders (Aug - Nov 2021)

## Slide 14: Phase 2
Drafting the State Plan for CTE (Nov 2021 – May 2022)
Synthesize Research, input from the CWPJAC study sessions, virtual focus groups. (Nov 2021)
Draft State Plan using an iterative process. (Dec 2021 - Mar 2022)
Draft State Plan for approval. (Mar 2022)
Design a communications and dissemination strategy for the state plan. (Apr 2022)

## Slide 15: Phase 2 (continued)
Drafting the State Plan for CTE (Nov 2021 – May 2022)
Manage public comments process. (Apr/May 2022)
Finalize State Plan for approval. (May 2022)

## Slide 16: Phase 3
Supporting Regional Implementation of the State Plan (Jun 2022 – May 2023)
Conduct Town Halls in regions across the state (Jun - Aug 2022)
Development of State and Regional Implementation Plans (Sep 2022 - Apr 2023)
Statewide virtual implementation meetings (May 2023)

## Slide 17: Phase 4
Measuring Outcomes (Apr - Jul 2023)
Development of Outcomes Dashboard
Key metrics and benchmarks aligned to the priorities in the State Plan for CTE

## Slide 18: Discussion on Focus Groups
Stakeholder Composition
Incorporation of Perkins V plan comments
Other Considerations

## Slide 19: Member Comments
  Members,
  Please use the “Raise Hand” feature in Zoom which can be found in the “Participant” tab. Staff will call your name so you can make your comment.
  Please remember to lower your hand and place yourself on mute after you have completed your comment.
Notes: Ask for Member Comments

## Slide 20: Public Comment
  Zoom
Register at: https://us02web.zoom.us/webinar/register/WN_NHMP3Wl9QQaHNikgfj2FsA [Link Removed - Link no longer valid]
When logging into Zoom please use your first and last name to provide public comment.
  Email
  Path2Work@cde.ca.gov and include the following:
  1) your name; 2) your affiliation, if any; 3) the agenda item number (i.e., Item 01); and 4) your public comment.
  Phone
  712-432-0075, Participant Access Code: 651905#
  Press *6 during the public comment period to be added to the queue.
Notes: Ask for Public Comment