# Working Timeline of Activities for the Development of the California State Plan for Career Technical Education

Posted by California Department of Education

June 28, 2019

## 2019

July 12	CWPJAC Meeting

Early Aug. 	Virtual Stakeholder meeting (20 people to prep. for August meeting)

Aug. 13	Stakeholder Meeting #1 – 10:00 a.m. to 3:00 p.m. @ SCOE Conference Center (Per SCOE: We need to be out by 3:30 p.m.)

Sept. 13	CWPJAC Meeting

Sept.		Stakeholder Meeting #2 – 10:00 a.m. to 3:00 p.m. @ TBD

Oct. 2-4	Advance CTE – Perkins Implementation Meeting, Washington DC

5 Team Members: Pradeep Kotamraju, Michelle McIntosh, SBE, CCCCO, and CCCCO

Oct. 15	CCCAOE (California Community College Association for Occupational Education) Conference, Rancho Mirage, CA – Public Feedback

Oct. 25	Complete Draft Plan A for January State Board of Education (SBE) Meeting

Nov. 08	CWPJAC Meeting

Incorporate CWPJAC edits for public feedback survey

Nov. 15	Open Public Feedback Survey

Nov. 15	Public Meeting #1 in Sacramento

*Move to Nov. 22 (Any day besides the 1, 15, or 19

Nov. 18	Board of Governors (BOG) Meeting, Informational Item

Nov. 20-22	CAROCP (Association of Career and College Readiness Organizations) CTE Conference, Rancho Mirage, CA – Public Feedback

Dec. 03	Public Meeting #2 - Los Angeles – CCCCO looking for a location in LA

Linking with the national Association for Career Technical Education Conference (ACTE) in Anaheim beginning on December 4, 2019.

Dec. 		December SBE, Informational Item

Dec. 11-13	JSPAC (Joint Special Populations Advisory Committee) Conference – Public Feedback

Dec. 20	Close Public Feedback Survey

2020

Jan. 08	SBE Meeting, Draft Plan A is presented

Jan. 		CWPJAC Meeting

Jan. 13	BOG Meeting, Draft Plan A approved with any recommendations

March 11-12	SBE Meeting, State Plan approved

March 13	To Governor for approval (30 days)

March 16	BOG Meeting, Final Plan (informational item)

April 12	Governor Approval Complete

Spring		Submit Plan to the U.S. Dept. of Education (Sometime in April or May)