# CALIFORNIA STATE PLAN FOR CAREER TECHNICAL EDUCATION Working Timeline

Posted by California Department of Education
November 2019

This document is a working timeline for the submission of the federal Strengthening Career Technical Education for the 21st Century Act (Perkins V) State Plan including an extended timeline to complete the full California State Plan for Career Technical Education (CTE).

## 2019

### Completed:

May 29	California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting

July 12	CWPJAC Meeting

Aug. 7 	Virtual Stakeholder Meeting

Aug. 13	Stakeholder Meeting #1

Sept. 13	CWPJAC Meeting

Sept. 17	Stakeholder Meeting #2

Oct. 2-4	Advance CTE – Perkins Implementation Meeting, Washington DC

Oct. 11	CWPJAC Meeting

Oct. 16	California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback

Oct 17	K–12 Teacher Feedback Virtual Meeting

Nov. 08	CWPJAC Meeting – Present the full Draft responses to the Perkins V State Plan and timeline for the California State Plan for CTE

Nov. 20-22	Association of Career and College Readiness Organizations (CAROCP) CTE Conference, Rancho Mirage, CA

### In Progress:

Nov. 25	CWPJAC Meeting – Second review of the California Perkins V State Plan

Nov. 26-27	Incorporate CWPJAC edits for posting/public comment

Dec. 02	Public Meeting #1 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference [ACTE] in Anaheim on December 4-7, 2019).

- 10:00 A.M.–12:00 P.M.

- 1:00–3:00 P.M.

Dec. 2	Open the California Perkins V State Plan Public Feedback Survey

Dec. 2	SBE Staff to share the Federal Perkins V State Plan with the Governor

Dec.	Public Meeting #2 in Sacramento, date is to be determined (TBD)

Dec. 11-13	Joint Special Populations Advisory Committee (JSPAC) Conference – Opportunity for Receiving Public Feedback

## 2020

Jan. 3	Close the California Perkins V State Plan Public Feedback Survey 
(32 days)

Jan 4-10	Analyze California Perkins V State Plan Public Feedback Survey results

Jan 6-17	Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into the Final California Perkins V State Plan

Jan. 8	SBE Meeting, the Draft California Perkins V State Plan is presented

*The version presented to the CWPJAC on November 25, 2019

Jan. 13	BOG Meeting, the Draft California Perkins V State Plan is presented

*The version presented to the CWPJAC on November 25, 2019

Jan. 17	March SBE Item due to the EAB

- Need a delayed submission date (February 7, 2020) for posting the final California Perkins V State Plan to allow a week to incorporate the edits from the January 31, 2019 CWPJAC meeting

Jan. 21	CWPJAC Agenda Posting Date for the January 31, 2020 meeting

Jan. 31	CWPJAC Meeting – Review the final California Perkins V State Plan

Feb. 1-5	Incorporate CWPJAC feedback on the California Perkins V State Plan to present to the SBE in March

Feb. 6	Final California Perkins V State Plan complete for SBE approval/March meeting

March 3	CWPJAC Agenda Posting Date for the March 13, 2020 meeting

March 11-12	SBE Meeting – the Final California Perkins V State Plan approved

March 13	CWPJAC Meeting – Review Chapter Three of the complete California State Plan for CTE

March 13	The Final California Perkins V State Plan is sent to the Governor for approval

March 16	BOG Meeting, the Final California Perkins V State Plan is presented (informational item)

April 12	Governor Approval of the California Perkins V State Plan Complete 
(30 days)

April 15	Submit the California Perkins V State Plan to the United States Department of Education

### Extension of Timeline to complete California State Plan for CTE

April 28	CWPJAC Agenda Posting Date for the May 8, 2020 meeting

May 8	CWPJAC Meeting – Present Chapter Four and Five of the California State Plan for CTE

June 30	CWPJAC Agenda posting date for the July 1, 2020 meeting

July 1	Receive the United States Department of Education’s response to California’s submitted California Perkins V State Plan

July 10	CWPJAC Meeting – Present final draft of the California State Plan for CTE

Aug.-Sept.	Public Feedback on draft of the California State Plan for CTE

TBD	CWPJAC Agenda Posting Date (Sept.)

September	CWPJAC Meeting –

TBD	CWPJAC Agenda Posting Date (Nov.)

November	CWPJAC Meeting – Approval of final draft of the California State Plan for CTE