# Working Timeline for the Submission of the

# California State Plan for Career Technical Education

Posted by California Department of Education

October 2019

## 2019

### Completed:

May 29	California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting

July 12	CWPJAC Meeting

Aug. 7 	Virtual Stakeholder meeting

Aug. 13	Stakeholder Meeting #1

Sept. 13	CWPJAC Meeting

Sept. 17	Stakeholder Meeting #2

Oct. 2-4	Advance CTE – Perkins Implementation Meeting

### In Progress:

Oct. 11	CWPJAC Meeting

Oct.	Stakeholder Meeting #3 (focused on accountability) – Date and location to be determined

Oct. 16	California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback

Oct 17	K–12 Teacher Feedback Virtual Meeting

Oct. 25	Draft Strengthening Career and Technical Education for the 21st Century Act (Perkins V) Application Complete

Nov. 08	CWPJAC Meeting – Present full Draft Perkins V Application

Nov. 12	Incorporate CWPJAC comments for Perkins V Application which will be used at the January SBE Meeting, the January Board of Governors (BOG) Meeting, and for the Public Feedback Survey

Nov. 13	SBE Staff to share Perkins V Application with the Governor

Nov. 13	Public Meeting #1 in Sacramento (California Department of Public Health Auditorium)

Nov. 15	Open Perkins V Application Public Feedback Survey

Nov. 18	BOG Meeting, Informational Item

Nov. 20-22	Association of Career and College Readiness Organizations (CAROCP) Career Technical Education (CTE) Conference, Rancho Mirage, CA – Public Feedback

Dec. 02	Public Meeting #2 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference (ACTE) in Anaheim on December 4-7, 2019).

- 10:00 A.M.–12:00 P.M.

- 1:00–3:00 P.M.

Dec. 	Informational Memo to SBE

Dec. 11-13	Joint Special Populations Advisory Committee (JSPAC) Conference – Public Feedback

Dec. 20	Close Public Perkins V Application Feedback Survey

Dec. 31	Analyze Public Perkins V Application Feedback Survey results

## 2020

Jan. 08	SBE Meeting, Draft Perkins V Application is presented

Jan. 13	BOG Meeting, Draft Perkins V Application is presented

Jan. 20	Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into a Final Perkins V Application

Jan. 31	CWPJAC Meeting – Review final Perkins V Application and Chapters One and Two of the California State Plan for CTE

Feb. 1	Incorporate CWPJAC feedback on the Perkins V Application to present to the SBE in March

March 11-12	SBE Meeting, Final Perkins V Application approved

March 13	CWPJAC Meeting – Review Chapter Three of the California State Plan for CTE

March 13	Perkins V Application to the Governor for approval (30 days)

March 16	BOG Meeting, Final Perkins V Application (informational item)

April 12	Governor Approval of the Perkins V Application Complete

April 15	Submit Perkins V Application to the U.S. Department of Education

### Extension of Timeline to complete California State Plan for CTE

May 8	CWPJAC Meeting – Present Chapter Four and Five of the California State Plan for CTE

July 1	Receive the U.S. Department of Education’s response to California’s submitted Perkins V Application

July 10	CWPJAC Meeting – Present final draft of the California State Plan for CTE

Aug.-Sept.	Public Feedback on draft of the California State Plan for CTE

September	CWPJAC Meeting –

November	CWPJAC Meeting – Approval of final draft of the California State Plan for CTE