# Working Timeline for the Submission of the

# California State Plan for Career Technical Education

Posted by California Department of Education

October 2019

## 2019

### Completed:

*May 29 California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting*

*July 12 CWPJAC Meeting*

*Aug. 7 Virtual Stakeholder meeting*

*Aug. 13 Stakeholder Meeting #1*

*Sept. 13 CWPJAC Meeting*

*Sept. 17 Stakeholder Meeting #2*

*Oct. 2-4 Advance CTE – Perkins Implementation Meeting*

### In Progress:

Oct. 11 CWPJAC Meeting

Oct. Stakeholder Meeting #3 (focused on accountability) – Date and location to be determined

Oct. 16 California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback

Oct 17 K­–12 Teacher Feedback Virtual Meeting

Oct. 25 Draft *Strengthening Career and Technical Education for the 21st Century Act* (Perkins V) Application Complete

Nov. 08 CWPJAC Meeting – Present full Draft Perkins V Application

Nov. 12 Incorporate CWPJAC comments for Perkins V Application which will be used at the January SBE Meeting, the January Board of Governors (BOG) Meeting, and for the Public Feedback Survey

Nov. 13 SBE Staff to share Perkins V Application with the Governor

Nov. 13 Public Meeting #1 in Sacramento (California Department of Public Health Auditorium)

Nov. 15 Open Perkins V Application Public Feedback Survey

Nov. 18 BOG Meeting, Informational Item

Nov. 20-22 Association of Career and College Readiness Organizations (CAROCP) Career Technical Education (CTE) Conference, Rancho Mirage, CA – Public Feedback

Dec. 02 Public Meeting #2 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference (ACTE) in Anaheim on December 4-7, 2019).

* 10:00 A.M.–12:00 P.M.
* 1:00–3:00 P.M.

Dec. Informational Memo to SBE

Dec. 11-13 Joint Special Populations Advisory Committee (JSPAC) Conference – Public Feedback

Dec. 20 Close Public Perkins V Application Feedback Survey

Dec. 31 Analyze Public Perkins V Application Feedback Survey results

## 2020

Jan. 08 SBE Meeting, Draft Perkins V Application is presented

Jan. 13 BOG Meeting, Draft Perkins V Application is presented

Jan. 20 Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into a Final Perkins V Application

Jan. 31 CWPJAC Meeting – Review final Perkins V Application and Chapters One and Two of the California State Plan for CTE

Feb. 1 Incorporate CWPJAC feedback on the Perkins V Application to present to the SBE in March

March 11-12 SBE Meeting, Final Perkins V Application approved

March 13 CWPJAC Meeting – Review Chapter Three of the California State Plan for CTE

March 13 Perkins V Application to the Governor for approval (30 days)

March 16 BOG Meeting, Final Perkins V Application (informational item)

April 12 Governor Approval of the Perkins V Application Complete

April 15 Submit Perkins V Application to the U.S. Department of Education

### Extension of Timeline to complete California State Plan for CTE

May 8 CWPJAC Meeting – Present Chapter Four and Five of the California State Plan for CTE

July 1 Receive the U.S. Department of Education’s response to California’s submitted Perkins V Application

July 10 CWPJAC Meeting – Present final draft of the California State Plan for CTE

Aug.-Sept. Public Feedback on draft of the California State Plan for CTE

September CWPJAC Meeting –

November CWPJAC Meeting – Approval of final draft of the California State Plan for CTE