# Working Timeline for the Submission of the California State Plan for Career Technical Education

Posted by California Department of Education

September 5, 2019

**2019**

Sept. 13 California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting – Present two-thirds of the State Plan

Sept. 17 Stakeholder Meeting #2 – 10:00 a.m. to 5:00 p.m. at the California Community Colleges chancellor’s Office (CCCCO)

Oct. 2-4 Advance CTE – Perkins Implementation Meeting, Washington DC

5 Team Members attending: Patricia de Cos, State Board of Education (SBE); Pradeep Kotamraju, CDE; Sheneui Weber, CCCCO; Michelle McIntosh, CDE; and Jeff Mrizek, CCCCO

Oct. Stakeholder Meeting #3 (Accountability) – 10:00 a.m. to 3:00 p.m., Location to be determined

Oct. 11 CWPJAC Meeting – Present Draft State Plan

Oct. 15 California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback

Oct. 25 Draft State Plan Complete

Nov. 08 CWPJAC Meeting – Present full Draft State Plan

Nov. 12 Incorporate CWPJAC comments for Draft Plan A which will be used at the January SBE Meeting, the January Board of Governors (BOG) Meeting, and the Public Feedback Survey

Nov. 13 SBE Staff to share Draft Plan A with the Governor

Nov. 13 Public Meeting #1 in Sacramento (California Department of Public Health Auditorium)

Nov. 15 Open Public Feedback Survey

Nov. 18 BOG Meeting, Informational Item

Nov. 20-22 Association of Career and College Readiness Organizations (CAROCP) Career Technical Education (CTE) Conference, Rancho Mirage, CA – Public Feedback

Dec. 03 Public Meeting #2 - Los Angeles – CCCCO looking for a location in Los Angeles to link with the national Association for Career Technical Education Conference (ACTE) in Anaheim beginning on December 4, 2019.

Dec. Informational Memo to SBE

Dec. 11-13 Joint Special Populations Advisory Committee (JSPAC) Conference – Public Feedback

Dec. 20 Close Public Feedback Survey

Dec. 31 Analyze Public Feedback Survey results

**2020**

Jan. 08 SBE Meeting, Draft Plan A is presented

Jan. 13 BOG Meeting, Draft Plan A is presented

Jan. 20 Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into a Final Draft Plan

Jan. 31 CWPJAC Meeting

Feb. 1 Incorporate CWPJAC feedback to present to the SBE in March

March 11-12 SBE Meeting, Final Draft Plan approved

March 13 To Governor for approval (30 days)

March 16 BOG Meeting, Final Plan (informational item)

April 12 Governor Approval Complete

April 15 Submit Plan to the U.S. Dept. of Education