# California Department of Education
California Assessment System
Request for Submissions CN260003

Contract Term: March 1, 2027 – December 31, 2032

RFS Release Date: December 18, 2025

Intent to Submit

Due Date: January 9, 2026, 1 p.m. Pacific Time

Submission

Due Date: February 12, 2026, 1 p.m. Pacific Time

California Department of Education

Assessment Development and Administration Division

1430 N Street, Suite 4409

Sacramento, CA 95814

Email: CASRFS@cde.ca.gov

This page intentionally left blank to facilitate double-sided printing

## TABLE OF CONTENTS

California Department of Education California Assessment System Request for Submissions CN260003	1

TABLE OF CONTENTS	3

TABLES	3

ATTACHMENTS	4

1. PURPOSE AND BACKGROUND	5

2. GENERAL SUBMISSION INFORMATION	16

3. SUBMISSION SPECIFICATIONS	23

4. EVALUATION PROCESS	39

5. AWARD AND PROTEST	41

6. STANDARD CONDITIONS OF SERVICE	42

7. SCOPE OF WORK	43

8. BUDGET DETAIL AND PAYMENT PROVISIONS	141

9. GENERAL TERMS AND CONDITIONS	149

10. SPECIAL TERMS AND CONDITIONS	150

11. ADDITIONAL PROVISIONS	159

APPENDIX A—Minimum System Requirements	167

APPENDIX B—CERS Minimum System Requirements	183

APPENDIX C—CAASPP and ELPAC Item Counts	187

APPENDIX D—Scoring Guide	199

## TABLES

Table 1. California Assessment System—First Year of Operational Testing by Assessment and Type	8

Table 2. California Assessment System Testing Windows	9

Table 3. Consortium Services Provided by UCSC/Smarter Balanced	11

Table 4. Schedule of Events	18

Table 5. Estimated Test Takers by Assessment for Each Year of Contract	44

Table 6. Provider of Help Desk Support, by Component and Tier	59

Table 7. Training Planning Tool—Sample Entries	65

Table 8. Annual CAASPP Item Rested, Refreshed, and Released Rates	86

Table 9. Annual ELPAC Item Rested, Refreshed, and Released Rates	87

Table 10. Required Test Types by Assessment	89

Table 11. Number of Special Form Paper-Pencil Tests Ordered by Grade and Test Form Type for 2023–24 Smarter Balanced Summative Assessments for ELA and Mathematics	90

Table 12. Number of Special Form Paper-Pencil Tests Ordered by Grade and Test Form Type for 2023–24 California Science Test	91

Table 13. Number of Special Form Paper-Pencil Tests Ordered by Grade/Grade Span and Test Form Type for 2023–24 Summative ELPAC	91

Table 14. Number of Special Form Paper-Pencil Tests Ordered by Grade/Grade Span and Test Form Type of 2023–24 Initial ELPAC	91

Table 15. California Assessment System Manuals	104

Table 16. Estimated Constructed-Response Item Counts for Smarter Balanced Summative ELA Assessments	120

Table 17. Estimated Constructed-Response Item Counts for Smarter Balanced Summative Mathematics Assessments	121

Table 18. Smarter Balanced Item Types for ELA Constructed-Response and Performance Task Items	121

Table 19. Estimated Constructed-Response Item Counts for CAST	122

Table 20. Estimated Machine-Scored and Hand-Scored Item Counts for a CAST Form	123

Table 21. Machine Scored and Hand-Scored Item Counts for the CSA	123

Table 22. Estimated Constructed-Response Item Counts for Summative ELPAC Writing Domain	124

Table 23. Number of Constructed-Response Items Administered in the 2024–25 Summative ELPAC Speaking Domain	124

Table 24. Estimated Constructed-Response Item Counts for Initial ELPAC Writing Domain	125

Table 25. Number of Constructed-Response Items Administered in the 2024–25 Initial ELPAC Speaking Domain	125

Table 26. Estimated Rubric-Scored Item Counts for the Alternate ELPAC	126

Table 27. Estimated Rubric-Scored Item Counts for the CAA for ELA	126

Table 28. Minimum Exact Agreement Rates for the California Assessment System	126

Table 29. California Assessment System Completion Criteria by Component Task	145

## ATTACHMENTS

Attachments are incorporated herein and attached as separate document(s):

- Intent to Submit

- Attachment Checklist

- Bidder Certification Sheet

- Federal Certifications

- Iran Contracting Act Certification

- California Civil Rights Laws Certification

- Bidder References

- Conflict of Interest and Confidentiality Statement

- California Department of Education Computer Security Policy

- Cost Submission

# California Assessment System Request for Submissions

## 1. PURPOSE AND BACKGROUND

### 1.1 Purpose

The California Department of Education (CDE), Assessment Development and Administration Division (ADAD) is seeking submissions for the implementation of the California Assessment of Student Performance and Progress (CAASPP) and the English Language Proficiency Assessments for California (ELPAC), collectively known as the California Assessment System. The purpose of this Request for Submissions (RFS) is to identify and select an assessment contractor with the capacity and expertise to successfully implement the California Assessment System. The organizations submitting submissions are referred to as “submitters” and/or “bidders” interchangeably throughout this document and its attachments. This RFS is requesting a formal written submission, including a scope of work with a transition plan, and a cost submission with a proposed budget. The process is competitive and open, using standardized scoring criteria.

Pursuant to Education Code (EC) Section 60643, the CDE will evaluate the submissions received in response to this RFS as set forth in RFS Section 4, Evaluation Process. The CDE will present the evaluation results and make a recommendation to the California State Board of Education (SBE) for the selection of the California Assessment System contractor(s) at the May 2026 SBE meeting.

Once the SBE approves the successful bidder, the scope of work and budget will be finalized through negotiations between the successful bidder, CDE, SBE, and California Department of Finance (DOF). The negotiated contract is anticipated to go to the SBE for approval at the September 2026 meeting. Award of a contract as a result of the RFS shall be contingent on SBE, CDE, and DOF approvals. In addition, award is contingent upon the availability of funding provided to and by the CDE, including appropriation in the annual Budget Act. Funding is described in RFS Section 2.4 Contract Funding and Time Period. It is anticipated that the contract will begin on March 1, 2027, and continue through December 31, 2032.

The CDE cannot guarantee that any future business will result from the information provided, nor shall it pay for the information provided or the resources used to participate in this procurement process. Costs for developing a response to this RFS are the sole responsibility of the bidder and shall not be charged to the State of California.

In accordance with efforts by the State of California to reduce paper waste, information available on the internet will be referenced in this document and will not be appended.

Acronyms are introduced once in the RFS and then used in subsequent sections without spelling out the terms again.

### 1.2 Background

The CDE is using a competitive-bid RFS procurement process for selecting the next assessment contractor(s) with the capacity and expertise to develop, administer, score, analyze, and report assessments as well as implement technology solutions for the CAASPP, as defined in EC sections 60605 through 60648.5, and the ELPAC, as defined in EC Section 313 and 60810.

EC Section 60643 states:

(a) Notwithstanding any other law, the contractor or contractors of the achievement tests provided for in Section 60640 shall comply with all of the conditions and requirements of the contract to the satisfaction of the Superintendent and the state board.

(b)(1) The department shall develop, and the Superintendent and the state board shall approve, a contract or contracts to be entered into with a contractor in connection with the tests provided for in Sections 60640 and 60810. The department may develop the contract through negotiations. In approving a contract amendment to the contract authorized pursuant to this section, the department, in consultation with the state board, may make material amendments to the contract that do not increase the contract cost. Contract amendments that increase contract costs may only be made with the approval of the department, the state board, and the Department of Finance.

(2) For purposes of the contracts authorized pursuant to this subdivision, the department is exempt from the requirements of Part 2 (commencing with Section 10100) of Division 2 of the Public Contract Code and from the requirements of Article 6 (commencing with Section 999) of Chapter 6 of Division 4 of the Military and Veterans Code. The department shall use a competitive and open process utilizing standardized scoring criteria through which to select a potential administration contractor or contractors for recommendation to the state board for consideration. The state board shall consider each of the following criteria:

- The ability of the contractor to produce valid and reliable scores.

- The ability of the contractor to report accurate results in a timely fashion.

- Exclusive of the consortium assessments, the ability of the contractor to ensure technical adequacy of the tests, inclusive of the alignment between the California Assessment of Student Performance and Progress tests and the state-adopted content standards.

- The cost of the assessment system.

- The ability and proposed procedures to ensure the security and integrity of the assessment system.

- The experience of the contractor in successfully conducting statewide testing programs in other states.

EC Section 60643(7) requires that the contract(s) approved by the State Superintendent of Public Instruction (SSPI) and the SBE include the following separate/distinct component tasks:

- Development of new tests or test items.

- Test materials production or publication.

- Delivery or electronic distribution of test materials to local educational agencies.

- Test processing, scoring, and analyses.

- Reporting of test results to the local educational agencies, including, but not necessarily limited to, all reports specified in this section.

- Reporting of valid and reliable test results to the department, including, but not necessarily limited to, the following electronic files:

  - Scores aggregated statewide, and by county, school district, school, and grade.

  - Disaggregated scores based on English proficiency status, gender, ethnicity, socioeconomic disadvantage, foster care status, and special education designation.

- All other analyses or reports required by the SSPI to meet the requirements of state and federal law and set forth in the Agreement.

- Technology services to support the activities listed in subparagraphs (A) to (G), inclusive.

- Perform regular performance checks and load simulations to ensure the integrity and robustness of the technology system used to support the activities listed in subparagraphs (A) to (G), inclusive.

In addition, submissions need to integrate the SBE’s goals and priorities as approved on September 10, 2025, and provided below:

- Implement the California Assessment System during the 2027–32 school years with the development and administration of high-quality assessments that are authentic, culturally responsive, inclusive, and provide actionable results that inform teaching and learning

- Provide a robust assessment system that is:

  - Comprehensive and coherent

  - Flexible and accessible to support the needs of educators, students, and families while providing data that supports valid inferences

  - Innovative to increase value and efficiency

  - Designed with technology solutions that meet industry best practices and standards

- Support California in complying with applicable state and federal laws.

Table 1 provides all the current California Assessment System summative and interim assessments with the first year of operational testing, a description of the assessment, and test type that need to be implemented during this contract. The types are computer adaptive test (CAT), computer-based test (CBT), performance task (PT), and paper pencil test (PPT).

Table 1. California Assessment System—First Year of Operational Testing by Assessment and Type

| First Year of Operational Status | Assessment | Type |
| --- | --- | --- |
| 2014–15 | Smarter Balanced Summative Assessments for English language arts (ELA) and mathematics for grades 3–8 and grade 11 | CAT/PT |
| 2015–16 | California Alternate Assessments (CAAs) for ELA and mathematics for grades 3–8 and grade 11 | CAT |
| 2015–16 | Smarter Balanced Interim Assessments for ELA and mathematics for grades 3–8 and grade 11 (Available to all K–12 students and educators) (Optional) | CBT/PT |
| 2018–19 | California Science Test (CAST) for grades five and eight and once while in high school | CBT |
| 2018–19 | California Spanish Assessment (CSA) for grades 3–8 and grade 11 high school (Optional) | CBT |
| 2019–20 | CAA for Science for grades five and eight and once while in high school, per individualized education program (IEP) team decision | CBT |
| 2019–20 | Summative ELPAC for eligible students in kindergarten through grade twelve | CBT |
| 2020–21 | Initial ELPAC for eligible students in kindergarten through grade twelve | CBT |
| 2021–22 | Summative Alternate ELPAC for eligible students in kindergarten through grade twelve, per IEP team decision | CBT |
| 2022–23 | Initial Alternate ELPAC for eligible students in kindergarten through grade twelve | CBT |
| 2022–23 | CAST Interim Assessments for grades five and eight and once while in high school (Optional) | CBT |
| 2022–23 | ELPAC Interim Assessments for grades 3–8 and grade 11 (Available to all Kindergarten through grade twelve (K–12) students and educators) (Optional) | CBT |
| 2024–25 | Revised CSA for grades 3–8 and grade 11 high school (Optional) | CBT |

The successful bidder is responsible for the integration, hosting, delivery, operations, and administration of all the existing assessments and those yet to be developed as a single integrated system.

Table 2 provides the required testing windows for the assessments described in Table 1 that must be available for administration.

Table 2. California Assessment System Testing Windows

| Assessment | Testing Window |
| --- | --- |
| - Smarter Balanced Summative Assessments for ELA and mathematics - CAAs for ELA and mathematics - CSA - CAST | The available testing window shall begin on the day in which 66 percent of the school's or track's annual instructional days have been completed, but no earlier than the second Tuesday in January of each year, and testing may continue up to and including the last day of instruction for the regular school's or track's annual calendar, but in no case later than June 30 or the weekday preceding the 30th if the 30th is not a weekday. |
| - CAA for Science | First Tuesday in September through June 30, annually |
| - Initial ELPAC | July 1 through June 30, annually |
| - Summative ELPAC | February 1 through May 31, annually |
| - Initial Alternate ELPAC - Summative Alternate ELPAC | July 1 through June 30, annually (Initial) February 1 through May 31, annually (Summative) |
| - Smarter Balanced Interim Assessments for ELA and mathematics - CAST Interim Assessments - ELPAC Interim Assessments | Year-round assessments with a window that opens in early August and closes in late July to prepare for rollover activities (e.g., the addition of new assessments). |

Currently, the full implementation of the California Assessment System consists of the following contracts:

- California Assessment System

Current contractor(s): ETS as prime contractor with the following subcontractors: Cambium Assessment, Measurement Inc., WestEd, Sacramento County Office of Education, Red Dog Records, MetaMetrics, University of California Santa Cruz (UCSC)/Smarter Balanced

- Consortium Services and California Educator Reporting System (CERS)

Current contractor: UCSC/Smarter Balanced

- Assessment Validity and Outreach

Current contractor: Sacramento County Office of Education

The successful bidder will not be required to conduct test development activities for the

Smarter Balanced assessments. The successful bidder will be required to provide peer review materials for non-consortium required evidence.

In addition, the successful bidder will be required to support the field testing of new items within the testing sessions during the operational assessment. The successful bidder should anticipate including 3–5 additional items in the computer-based tests, including the CAT component, and one PT to support ongoing field test activity. This design should be applied to both content areas. The contractor will not be responsible for scoring the field test items or field test PTs. The successful bidder should anticipate ingesting 2,000 to 10,000 field test items and tasks (across ELA and mathematics) each year to be allocated to students per the Consortium’s established embedded field test processes.

The Smarter Balanced Summative Assessments for ELA and mathematics for grade 11 are used for the Early Assessment Program (EAP) as allowed per EC Section 99300. The successful bidder will be required to coordinate with the California State University (CSU) EAP contractor. More information about the EAP can be found on the CDE’s EAP web page at https://www.cde.ca.gov/ci/gs/hs/eapindex.asp.

Per EC Section 60605.7, California joined the Smarter Balanced Assessment Consortium (Smarter Balanced) in June 2011 as a governing state for the development of ELA and mathematics assessments. As stipulated in EC Section 60640(b)(1), the Smarter Balanced assessments measure the Common Core State Standards (CCSS) for ELA and mathematics adopted by the SBE. The three components of the Smarter Balanced Assessment System—summative assessments, interim assessments, and Tools for Teachers, consisting of formative assessment resources—are designed to support teaching and learning throughout the school year.

Table 3 summarizes the services that are provided to the CDE within the consortium services contract with UCSC/Smarter Balanced.

Table 3. Consortium Services Provided by UCSC/Smarter Balanced

| Assessment | Service |
| --- | --- |
| Summative and Interim Assessments for ELA and Mathematics | - Develop, calibrate, and evaluate quality of items; include applicable accessibility resources based on Consortium guidelines and budget - Ensure integrity of the measurement scale and Consortium-adopted blueprints for summative and interim assessments - Provide necessary Peer Review assurances for federal accountability for Consortium-wide elements - Maintain and deploy an implementation readiness package for service providers - Support members in their review of implementation evidence from the implementation readiness package of successful bidders for test administration - Provide member and service provider procedure guidelines that support implementation and provide a description of required and suggested actions - Produce materials and processes to maintain consistency across States (e.g., training, administration manuals, accommodations procedures, etc.) - Produce standardized reports for assessment results for ELA and mathematics assessments - Supply student results for ELA and mathematics assessments to the State and via access to the reporting system (if requested) - Conduct research studies in support of the Smarter Balanced validity, framework and use of effective accessibility resources (designated supports and accommodations for students) - Deliver paper and pencil forms as budgeted by membership on an annual basis. Paper and pencil tests are required for students who still have it designated in their IEP. The Smarter Balanced Consortium provides the paper and pencil test packages and answer document templates for the contractor to mass produce. The successful bidders come up with their process of printing, scoring, and reporting. Currently, the answer documents for the Smarter Balanced are non-scannable. Test examiners enter the student responses into the paper pencil test data entry interface. Then, they are electronically scored by the system. For other paper tests, refer to RFS Section 7.4.10 - Make paper braille forms available through the American Printing House - Hand-score and validate rubrics, create anchor-sets, training sets and scoring materials as appropriate for field test items - Make items and tests available to members’ test administration contractors in standardized formats |
| Tools for Teachers (Formative Assessment Resources) | - Develop and maintain Tools for Teachers application - Host Tools for Teachers application - Procure and facilitate the development and review of formative assessment materials - Conduct regular reviews and evaluations of user needs |

The CAASPP includes the following assessments:

- Smarter Balanced Assessment System—summative assessments, interim assessments, and Tools for Teachers—for ELA and mathematics

- CAAs for ELA, mathematics, and science—for students with the most significant cognitive disabilities, as designated in their IEP

- CAST and CAST Interim Assessments

- CSA for Spanish reading/language arts

The ELPAC includes the following assessments:

- Initial ELPAC—used to determine a student’s initial classification as an English learner (EL) or as initial fluent English proficient (IFEP)

- Initial Alternate ELPAC—for students with the most significant cognitive disabilities, as designated in their IEP—used to determine a student’s initial classification as an EL or IFEP

- Summative ELPAC—used to measure progress toward English language proficiency for students identified as ELs and support decisions for students to be redesignated fluent English proficient (RFEP)

- Summative Alternate ELPAC—for students with the most significant cognitive disabilities, as designated in their IEP—used to measure progress toward English language proficiency for students identified as ELs and support decisions for students to be RFEP

- ELPAC Interim Assessments

The CAASPP and most ELPAC assessments are computer-based tests that measure what students know and can do. Within the ELPAC, the kindergarten through grade two (K–2) Writing domain will continue to be a paper–pencil administration. The CAASPP and ELPAC assessments produce scores that can be aggregated and disaggregated for the purpose of informing parents/guardians, local educational agencies (LEAs) staff, the public, and the state officials about students’ achievement in their learning of the California academic content standards and English language development and proficiency. The assessments (1) provide individual student results to students, parents/guardians, and teachers; (2) produce school-, LEA-, county- and state-level results that allow for the monitoring of progress; and (3) produce results to meet the requirements of the Every Student Succeeds Act (ESSA), enacted on December 10, 2015, which reauthorized the Elementary and Secondary Education Act of 1965. Since 2019, the delivery of Student Score Reports has transitioned to an electronic process, reducing the need for the processing of paper reports and in postage.

Under the federal requirements of ESSA, LEAs must assess students as follows:

- For reading/language arts and mathematics, administer annual summative assessments in each of grades three through eight and once in high school

- For science, administer annual summative assessments in grades five and eight and once in high school (i.e., grade ten, eleven, or twelve)

- For English language proficiency, administer an initial assessment for identification purposes and then annually for identified ELs in kindergarten through grade twelve, inclusive

CAASPP tests are used to meet federal requirements through the administration of the following:

- The Smarter Balanced Summative Assessments and the CAAs for ELA and mathematics in grades three through eight and grade eleven

- The CAST and CAA for Science in grades five and eight and one time in high school (once in grade ten, eleven, or twelve) (All grade twelve students who have not yet taken a science assessment in high school are required to take either the CAST or the CAA for Science, if identified in their IEP.)

ELPAC tests are used to meet the federal requirements through administration of the following:

- The Initial and Initial Alternate ELPAC for identification purposes in kindergarten through grade twelve, inclusive

- The Summative and Summative Alternate ELPAC for identified ELs in kindergarten through grade twelve, inclusive

The CAASPP and ELPAC contracts were competitively procured, separately, in 2014‒15. At that time, the CAASPP contract encompassed the technology infrastructure. In 2018, the ELPAC was brought onto the same technology infrastructure as CAASPP and included the development and administration of both the CAASPP and the ELPAC as the California Assessment System. The current contract will expire on December 31, 2027. The current scope of work is available on the SBE Agenda for November 2021, item 04 at https://www.cde.ca.gov/be/ag/ag/main202111.asp. For a copy of the current executed contract, refer to RFS Section 2.7 for directions.

The current California Assessment System contract is a cost reimbursement, service-based contract that includes sufficient hardware, software, materials, technical support, and specialized resources to support the capacity and growth of assessment operations throughout the term of the contract. The system operates year-round, with minimal downtimes (e.g., weekend maintenance, overnight updates).

In 2024–25, more than 20 million interim and summative assessments were administered. On May 8, 2019, the system infrastructure supported 683,673 concurrent users—the highest number of concurrent users to date.

The following websites provide information and resources about each assessment:

- CDE website at https://www.cde.ca.gov/

  - California Content Standards: https://www.cde.ca.gov/be/st/ss/

  - CAASPP web pages containing links to each assessment and program resources, including blueprints:

    - Smarter Balanced Assessment System: https://www.cde.ca.gov/ta/tg/sa/index.asp

    - CAST: https://www.cde.ca.gov/ta/tg/ca/caasppscience.asp

    - CAAs for ELA and Mathematics: https://www.cde.ca.gov/ta/tg/ca/altassessment.asp

    - CAA for Science: https://www.cde.ca.gov/ta/tg/ca/caascience.asp

    - CSA: https://www.cde.ca.gov/ta/tg/ca/csa.asp

  - ELPAC web page at https://www.cde.ca.gov/ta/tg/ep/

- CAASPP & ELPAC website for testing coordinators and educators to access testing systems, training materials, and resources is at https://www.caaspp-elpac.org/

- California Legislative Information website with the complete text of EC sections is at https://leginfo.legislature.ca.gov/

- Refer to the California Code of Regulations, Title 5 (5 CCR) sections 850–864 for CAASPP and 5 CCR Section 11518 for ELPAC for the text of the regulations that have been formally adopted, approved, and filed with the Secretary of State and posted at https://govt.westlaw.com/calregs/.

## 2. GENERAL SUBMISSION INFORMATION

### 2.1 Bidder Eligibility

Sole proprietorships, partnerships, public or private agencies, unincorporated organizations such as non-profits, or associations may respond to this RFS. The bidder must be legally constituted and qualified to do business within the State. If required by law, any business entity required to be registered with the California Secretary of State must submit a current Certificate of Good Standing issued by the California Secretary of State. The required document(s) may be obtained through the Certification Unit by phone at 916-657-5448 or through the California Secretary of State, Business Entities Records Request web page https://www.sos.ca.gov/business-programs/business-entities/information-requests/.

Note: Allow sufficient time to obtain the certificate from the California Secretary of State.

If the bidder’s legal status does not require a filing or registration with the California Secretary of State, a separate paragraph in the submission must clearly state the bidder’s legal status and evidence that it is legally constituted and qualified to do business with the State. With the exception of organizations whose legal status precludes incorporation (i.e., public agencies, sole proprietorships, partnerships) bidders that are not fully incorporated by the deadline for submission will be disqualified.

The bidder responding to this RFS must serve as the Prime Contractor and will be the responsible entity in ensuring that all tasks and activities are competently and successfully completed. In the event the bidder is subcontracting more than 25 percent to any one subcontractor, then that subcontractor must also meet the minimum qualifications listed in Section 2.2 below. (Refer to RFS Section 2.9 for the definition of “Prime Contractor”.)

#### 2.1.1 Targets of Economic Sanctions; Executive Order N-6-22 – Russia Sanctions

On March 4, 2022, Governor Gavin Newsom issued Executive Order N-6-22 (the EO) regarding Economic Sanctions against Russia and Russian entities and individuals. “Economic Sanctions” refers to sanctions imposed by the U.S. government in response to Russia’s actions in Ukraine, as well as any sanctions imposed under state law. By submitting a bid or proposal, Contractor represents that it is not a target of Economic Sanctions. Should the State determine Contractor is a target of Economic Sanctions or is conducting prohibited transactions with sanctioned individuals or entities, that shall be grounds for rejection of the Contractor’s bid/proposal any time prior to contract execution, or, if determined after contract execution, shall be grounds for termination by the State.

### 2.2 Minimum Qualifications for Bidders

The bidder responding to this RFS must serve as the Prime Contractor and therefore must meet the Minimum Qualifications for Bidders as stated in this section. The Prime Contractor must have the experience and qualifications to provide oversight to all proposed subcontractors and review and approve work products created by all proposed subcontractors.

Bidders must have a minimum of three years (within the last five years) of full-time experience in both computer- and paper-based large-scale assessments in all the following:

- Administering, scoring, and reporting large-scale assessments (including, but not limited to, experience with data management systems; online and remote testing; and human scoring and Artificial Intelligence (AI) scoring of constructed responses).

- Designing and developing high-quality academic and English language proficiency assessments that are accessible for all students.

- Maintaining security for all test materials, items, and data.

- Designing and implementing technology solutions for assessment delivery systems.

- Creating and providing training for students and professional learning opportunities for educators to understand and use assessment systems.

Refer to RFS Section 3.1 for additional information pertaining to personnel requirements.

### 2.3 Schedule of Events

The RFS activities and deadlines are displayed in Table 4, Schedule of Events, below. The schedule shown is tentative and subject to change.

Table 4. Schedule of Events

| Activity | Action Date |
| --- | --- |
| Request for Submissions Posted by the CDE | December 18, 2025 |
| Informational Webinar by the CDE Refer to RFS Section 2.5 for webinar registration instructions. | January 6, 2026 1–2 p.m. PST |
| Intent to Submit Form and Questions Due from Bidders | January 9, 2026 Must be received by 1 p.m. PST |
| Questions and Answers Posted on CDE Website | January 23, 2026 |
| Submissions Due from Bidders | February 12, 2026 Must be received by 1 p.m. PST |
| Review of Submissions | February 13‒March 30, 2026 |
| CDE Recommendation to SBE of the Successful Bidder to Enter into Contract Negotiations | April 28, 2026 (Tentative posting date for SBE May 2026 agenda item) |
| SBE Designation of Contractor | May 12–13, 2026 (Tentative dates for SBE May 2026 meeting) |
| Contract Negotiations Begin | June 3, 2026 (Tentative) |
| CDE Recommendation to SBE to Approve Negotiated Contract Documents | August 25, 2026 (Tentative posting date for SBE September 2026 agenda item) |
| SBE Approval of Negotiated Contract Documents | September 9–10, 2026 (Tentative dates for SBE September 2026 meeting) |
| Anticipated Contract Start Date | March 1, 2027 |

### 2.4 Contract Funding and Time Period

#### 2.4.1 Funding

Contract funding is contingent upon the availability of funds, including appropriation in the annual Budget Act. The final budget for the contract is to be negotiated and approved by the CDE, SBE, and DOF. In fiscal year (FY) 2024‒25, it cost $90,251,556.00 to implement the California Assessment System contract with ETS.

The resulting contract will be a cost reimbursement contract based on actual, documented expenses. The SBE, the CDE, and the DOF will negotiate the final contract costs with the bidder designated by the SBE. Approval of a final contract shall be contingent upon funding and program authorization provided to and by the CDE.

If insufficient funds are appropriated in the annual Budget Act for any portion of the work in this contract, or if any other funds upon which this contract is contingent are reduced or no longer available, the CDE may cancel the contract, or portion thereof, with no liability of any kind accruing to or against the CDE, its employees, agents, contractors or representatives. The bidder shall not be obligated to perform any work, or the contract may be amended by the CDE and the successful bidder to reflect a reduction of work and the reduced appropriation subject to appropriate government agency approval.

#### 2.4.2 Time Period

It is anticipated that the contract will begin on March 1, 2027, or upon CDE, SBE, and DOF approval (whichever is later) and will continue through December 31, 2032. The contract period covers seven FYs, for a total of 70 months:

- 2026–2027: March 1, 2027 – June 30, 2027 (4 months)

- 2027–2028: July 1, 2027 – June 30, 2028 (12 months)

- 2028–2029: July 1, 2028 – June 30, 2029 (12 months)

- 2029–2030: July 1, 2029 – June 30, 2030 (12 months)

- 2030–2031: July 1, 2030 – June 30, 2031 (12 months)

- 2031–2032: July 1, 2031 – June 30, 2032 (12 months)

- 2032–2033: July 1, 2032 – December 31, 2032 (6 months)

### 2.5 Informational Webinar

An informational webinar will be held. The date and time are indicated in Table 4. Schedule of Events in RFS Section 2.3. Attendance at the informational webinar is not mandatory, but all interested parties are encouraged to attend. Prime Contractors should bring their intended subcontractors to the webinar to better understand the RFS requirements.

To request registration information for the webinar, send an email to the CDE at CASRFS@cde.ca.gov with the subject line “RFS Webinar Attendance‒Organization Name.” Provide the names and emails of those who intend to attend the webinar. Follow-up emails will be sent with webinar registration information.

If there is a need for sign language interpretation or other accommodation due to a disability, send an email to the CDE at CASRFS@cde.ca.gov no later than the date and time specified in RFS Section 2.3 Schedule of Events. The CDE will make reasonable efforts to provide the accessibility resources needed.

### 2.6 Intent to Submit

Bidders are required to complete and submit RFS Attachment 1 Intent to Submit, as described in the directions on the form. The Intent to Submit form must be signed by the bidder’s authorized signatory and include the title of the person signing the Intent to Submit form and show the date of signing. The completed form must be emailed to the CDE at CASRFS@cde.ca.gov. A submission will not be accepted unless the completed RFS Attachment 1, Intent to Submit, is received by the CDE by the date and time specified in RFS Section 2.3 Schedule of Events.

It is the bidders’ responsibility to ensure that the Intent to Submit form reaches the CDE Assessment Development and Administration Division no later than the date and time specified in RFS Section 2.3 Schedule of Events. Proposals for which the Intent to Submit has not been received by the date and time specified shall not be accepted.

### 2.7 Questions and Clarifications

Bidders may submit questions, requests for clarification, concerns, and/or comments (hereinafter referred to collectively as “questions”) regarding this RFS. All questions must be submitted in writing. The bidder must include its name, email address, and telephone number with its submission of questions. The bidder should specify the relevant section, task/subtask, and page number of the RFS for each question submitted. Questions must be received by the date and time specified in RFS Section 2.3 Schedule of Events. The CDE will make every effort to email its responses to the questions to all who submitted an Intent to Submit form by the date and time specified in RFS Section 2.3 Schedule of Events. At its discretion, the CDE may respond to questions that are submitted late or not in proper form. The CDE reserves the right to rephrase or not answer any question submitted.

Written questions regarding the RFS will be included in the response to questions posted on the CDE website, which will occur by the date and time specified in RFS Section 2.3 Schedule of Events.

All questions must be submitted by email to the CDE at CASRFS@cde.ca.gov with the subject line “RFS Questions‒Organization Name.” It is the bidder’s responsibility to ensure that questions are received by the time and date specified in RFS Section 2.3, Schedule of Events.

To request a copy of the current executed California Assessment System contract, send an email to CASRFS@cde.ca.gov with the subject line “California Assessment System Contract Request.”

### 2.8 Cost of Preparing a Submission

The costs of preparing and delivering the submission are the sole responsibility of the bidder. The State will not provide reimbursement for any costs incurred or related to the bidder’s involvement or participation in the RFS process.

### 2.9 Definitions

- “Assessment” shall mean any systematic method of obtaining information from tests and other sources, used to draw inferences about characteristics of people, objects, or programs, as defined in Standards for Educational and Psychological Testing (2014).

- “Bidder” shall mean each and every business entity, sole proprietorship, partnership, public or private corporation, agency, organization, or association that submits a response to the RFS.

- “CDE Business Hours” shall be Monday through Friday from 8 a.m. to 5 p.m. PST/PDT.

- “Contract” shall mean the requirements set forth in this RFS and subsequent scope of work and budget submitted by the bidder and approved by the CDE, SBE, and DOF.

- “Contractor” shall mean the successful bidder selected by the CDE as the business entity to administer its submission and subsequent contract to support the accomplishment of any tasks described in this RFS.

- “Cost reimbursement contract” provides for payment of allowable incurred costs related to services performed, to the extent prescribed in the contract. These contracts establish an estimate of total cost for the purpose of obligating funds and establishing a ceiling that the successful bidder may not exceed for each line item without formal approval by the CDE, the SBE and the DOF per EC Section 60643(b).

- “Department of General Services” (DGS) is the California state agency that provides oversight of the state contracting process. This contract is authorized under EC Section 60643, and is exempt from the requirements of Part 2 (commencing with Section 10100) of Division 2 of the Public Contract Code and from the requirements of Article 6 (commencing with Section 999) of Chapter 6 of Division 4 of the Military and Veterans Code.

- “Fiscal year” means the state fiscal year July 1 through and including the following June 30.

- “Key Personnel” are defined as those people in conjunction with the Project Manager who will exercise a major management and/or administrative role on behalf of the bidder (directing, overseeing and/or coordinating the work of assigned staff, subcontractors and/or independent consultants performing task and activities) or who will have significant responsibility for completing or assisting with the completion of tasks described in this RFS. Key Personnel include the Project Manager and Fiscal Manager. Key personnel do not include clerical staff.

- “Local educational agency (LEA)” means a county office of education, school district, state special school, or charter school.

- “Original Signature” shall mean a manual handwritten signature or mark in wet ink.

- “Prime Contractor” shall be defined as the entity who submits a response to this RFS and is the responsible entity in ensuring that all tasks and activities are competently and successfully completed. The Prime Contractor must have the experience and qualifications to provide oversight to all proposed subcontractors and review and approve work products created by all proposed subcontractors.

- “Specifications” shall mean the minimum specifications required by the CDE for a task, subtask, or activity. Specifications provided in this RFS represent a comprehensive outline of the detail required in the bidder’s submission for successful accomplishment of a task, subtask, or activity.

- “Subcontract” shall mean any and all agreement(s) between a bidder and another entity (including, but not limited to, an individual or business) for the accomplishment of any task, subtask or activity, in whole or in part, described in this RFS and in the subsequent contract, or to provide goods or services in support of the work described in this RFS and in the subsequent contract.

- “Subcontractor” shall mean each and every entity (including, but not limited to, an individual or business) with whom a bidder enters into any agreement for the accomplishment of any task, subtask, or activity, in whole or in part, described in this RFS, or to provide goods or services in support of the work described in this RFS. All persons who are not employees of the bidder are to be considered subcontractors.

- “Successful bidder” shall mean the business entity selected by the CDE as the business entity to administer its submission and subsequent contract to support the accomplishment of any task(s) described in this RFS.

- “Universally Designed Assessment” is an assessment that is designed from the beginning to be accessible and valid with respect to the widest possible range of students, including students with disabilities and students with limited English proficiency.

- “Working day” shall mean days Monday through Friday, inclusive, but exclusive of the CDE-observed holidays.

## 3. SUBMISSION SPECIFICATIONS

### 3.1 Submission Requirements

Each submission must contain all of the required items listed in RFS Section 3 (All items in RFS Sections 3.1 through 3.7). One (1) original hardcopy (marked as “Original Copy”), ten (10) copies (hardcopy), and one (1) electronic copy of the submission on a portable USB drive must be submitted along with all required attachments or forms. Also refer to RFS Section 3.2, Required Attachments/Forms, for attachments and forms that must accompany the submission, and refer to RFS Section 3.5, Submission to CDE, for submittal details.

#### 3.1.1 Table of Contents

The submission must include a table of contents that identifies, by page number, all the section and subsection headings, including the submission of documents in the same order presented in this RFS.

#### 3.1.2 Scope of Work

The submission must include a section that addresses all parts of RFS Section 7 Scope of Work of the RFS. All tasks and subtasks in RFS Section 7 must be addressed. Any deviation from the tasks and subtasks described in Section 7 Scope of Work will not be considered and will cause a submission to be rejected.

This submission must address six main tasks:

- Task 1 – Comprehensive Plan and Schedule of Deliverables

- Task 2 – Program Support Services

- Task 3 – Technology Services

- Task 4 – Assessment Development and Accessibility

- Task 5 – Test Administration and Security

- Task 6 – Scoring and Reporting

#### 3.1.3 Organization Structure and Personnel Resources

The content of this section must describe how the bidder proposes to organize its resources necessary to complete the tasks and deliverables contained in RFS Section 7 Scope of Work. The content must demonstrate the bidder’s ability to provide the services set forth in this RFS. This section of the submission must address the following:

- Services and Activities

Provide a description of the nature of the bidder’s services and activities. Indicate when the bidder, if a business, was established; its brief history; and location. List the location(s) of the office(s) from which the primary work of this project will be conducted. The bidder must provide for an office in the city of Sacramento, California. Include a description of the facility and the staff to be located in Sacramento.

- Project Manager

Identify by name, the Project Manager to be employed by the Prime Contractor, and describe how the proposed Project Manager meets the minimum qualifications stated below. The submission must describe how the bidder’s Project Manager will effectively coordinate, manage, and monitor the efforts of the assigned staff, including subcontractors and/or consultants, to ensure that all tasks/subtasks, activities, and functions are completed effectively and in a timely manner.

The Project Manager is the bidder’s primary person assigned to oversee the project. The Project Manager must be an employee of the Prime Contractor and will act as the liaison between the CDE and all other project staff. The Project Manager is responsible for ensuring completion of all project deliverables, tasks, and subtasks.

The Project Manager must have, at a minimum, a master’s degree in one of the following: Education, Public Policy and Administration, Business Administration, Sociology, Psychology, Mathematics, or Statistics. Additionally, the Project Manager must have three years of recent experience (within the last five years) in successfully managing large-scale assessment programs and projects comparable to the size and scope of the services described in this RFS. Certification as a Project Management Professional (PMP) is required.

The Project Manager must be located in Sacramento, California and accessible to the CDE Contract Monitor at all times during normal CDE business hours (refer to RFS Section 2.9 for the definition of “CDE business hours”). In addition to other specified responsibilities, the Project Manager will be responsible for all matters related to the bidder’s project staff/personnel including, but not limited to:

  - Supervising, reviewing, monitoring, training, and directing all project staff/personnel.

  - Overseeing personnel assigned to complete the required work as specified.

  - Maintaining project files.

  - Implementing and maintaining quality control procedures to manage conflicts, ensure product accuracy, identify critical reviews and milestones.

  - Submitting monthly progress reports and invoices in a timely matter.

  - Acting as primary contact for all contractual matters covered by the scope of work.

- Fiscal Manager

Identify by name the Fiscal Manager to be employed by the Prime Contractor and describe how the proposed Fiscal Manager meets the minimum qualifications stated herein. The submission must describe the fiscal accounting processes and budgetary controls that will be employed to ensure the responsible use and management of contract funds and accurate invoicing.

The Fiscal Manager is the bidder’s fiscal person responsible for the fiscal oversight and management, invoicing, and accounting for this entire project. The Fiscal Manager must be an employee of the Prime Contractor.

The Fiscal Manager must possess, at a minimum, a bachelor's degree in accounting or related field, and have at least three years of recent experience (within the last five years) providing fiscal oversight and management of large complex contracts comparable to the size and scope of the services described in this RFS.

- Technology Manager

Identify by name the Technology Manager to be employed and describe how the proposed Technology Manager meets the minimum qualifications stated below. The submission must describe in detail the Technology Manager’s experience with developing and/or implementing database-driven systems with web interfaces and batch processes used for state-level, large-scale assessments; developing and/or implementing adaptive test delivery systems; and developing and/or implementing systems with the highest level of security (comparable to that required by financial institutions and the U.S. Government to prevent security breaches).

This person is the bidder’s technology expert and is responsible for the oversight of the development, maintenance, and performance of the California Assessment Technology Platform. The minimum qualifications of the Technology Manager include at least three years of recent experience (within the last five years) providing technology oversight and management over the development and/or implementation of a large-scale, computer-based assessment system delivered via the web. The Technology Manager must possess, at a minimum, a bachelor's degree; a degree in an information-technology field (e.g., computer science and engineering) is desired.

- Key Personnel

Identify by name and position title all key personnel who will exercise a major management, oversight and/or administrative role (including, but not limited to, attorneys, consultants, and advisors who will exercise a major management, oversight and/or administrative role) on behalf of the bidder or who will have significant responsibility for completing or assisting with the completion of tasks described in RFS Section 7. This includes the Project Manager, Fiscal Manager, and Technology Manager positions.

Key personnel are defined as those people who, in conjunction with the Project Manager, will exercise a major management and/or administrative role on behalf of the bidder (directing, overseeing and/or coordinating the work of assigned staff, subcontractors and/or independent consultants performing task and activities) or who will have significant responsibility for completing or assisting with the completion of tasks described in this RFS. Key personnel do not include clerical staff.

  - Key Personnel Qualifications

Describe in detail how the proposed Key Personnel identified above meet the minimum qualifications stated below. The submission must describe the expertise and professional qualifications of all Key Personnel.

The submission must describe the expertise and professional qualifications of all Key Personnel. Key Personnel identified must possess the following qualifications:

    - At minimum, a bachelor's degree in education, education research, or a related area.

    - A minimum of three years of experience and demonstrated work history conducting the tasks as described in this RFS.

Assigned Key Personnel must be capable of assisting the Project Manager in all aspects of project work.

The bidder shall identify all key personnel proposed for each task by name, job position title, and the specific responsibilities assigned to each individual.

- Changes to Key Personnel Requirements

The submission must acknowledge and ensure that the successful bidder cannot change or substitute the assigned Project Manager, Fiscal Manager, Technology Manager, Key Personnel (including, subcontractors or independent consultants, if identified as Key Personnel) without the CDE Contract Monitor’s prior written approval. The replacement or substitute Project Manager, Fiscal Manager, Technology Manager, and Key Personnel shall meet or exceed the qualifications and experience level of the previously assigned Project Manager, Fiscal Manager, Technology Manager, and Key Personnel. The submission must specify that the bidder will comply with the Changes to Key Personnel Requirements.

- Current Résumés

Provide résumés for all Key Personnel (Project Manager, Fiscal Manager, Technology Manager, Key Personnel, subcontractors or independent consultants) identified who will exercise a major management and/or administrative role on behalf of the bidder (directing, overseeing and/or coordinating the work of assigned staff, subcontractors and/or independent consultants performing task and activities) or who will have significant responsibility for completing or assisting with the completion of tasks.

Résumés must be provided for the following, including but not limited to, the Project Manager, the Fiscal Manager, the Technology Manager, any subcontractors or independent consultants, managers, supervisors, and all other Key Personnel identified by the bidder.

To the extent possible, résumés must include dates but should not include personal information such as social security number, home address, home telephone number, marital status, sex, birth date, etc.

- Subcontractors

Provide the full legal names of all proposed subcontractors (refer to RFS Section 2.9 for the definition of “subcontractor”) that will be used to perform services. For each subcontractor, include:

  - A clear description of the functions, activities, and responsibilities that will be performed by each subcontractor and/or independent consultants.

  - A brief explanation as to why the subcontractor or independent consultant was selected including expertise, knowledge, specialty, past experience, etc.

  - A résumé for each subcontractor’s Key Personnel and independent consultants. To the extent possible, résumés must include dates but should not include personal information such as social security number, home address, home telephone number, marital status, sex, birthdate, etc. All subcontractors must conform to all requirements of this RFS. (Refer to RFS Section 2.9 for the definition of “subcontractor.”)

  - A commitment letter, signed by an official representative of each subcontractor or independent consultant, acknowledging their intended participation/availability and confirmation that they have been made aware of the terms and conditions of the proposed contract. A commitment letter is required for all subcontractors. No cost should be included in the commitment letter (refer to RFS Section 3.2.7).

At a minimum, the following subcontractors are required:

- MetaMetrics as the sole source for the Lexile® Framework for Reading and the Quantile® Framework for Mathematics.

- UCSC/Smarter Balanced as co-owner with the CDE of CERS.

- Staff Labor Hours by FY

For each individual and job position title, include the specific tasks each individual/job position will perform and the specific number of labor hours the individual/job position title will devote to each task contained in RFS Section 7 Scope of Work (refer to Attachment 10A Staffing Labor Hours). A Staffing Labor Hours (RFS Attachment 10A) must be completed for each FY, or part thereof. The labor hours specified in Staffing Labor Hours (RFS Attachment 10A) must correlate with the labor hours contained in Cost Submission Task Detail (RFS Attachment 10C).

- Subcontractor Labor Hours by FY

If Subcontractors are being used, Staffing Labor Hours (RFS Attachment 10A) must be clearly identified, completed, and submitted for each subcontractor. A Staffing Labor Hours (RFS Attachment 10A) must be completed for each FY, or part thereof. The labor hours specified in Staffing Labor Hours (RFS Attachment 10A) must correlate with the labor hours contained in Cost Submission Task Detail (Attachment 10C).

In the event that a specific subcontractor does not perform a task by hours (for example a printer) but rather they charge by the job, then the potential contractor may list ”0” hours and make a notation on Staffing Labor Hours (RFS Attachment 10A) to that effect. For example:

“Printer company name*: Task 2, 0 hours

*Printer will not charge hourly, but by print job.”

- Organization Chart

Include an organization chart showing the hierarchy of Key Personnel working on this project. The organization chart must show the relationship between the bidders’ Project Manager, Fiscal Manager, Technology Manager, and all Key Personnel of the bidder’s organization and all other parties (subcontractors and/or independent consultants) that will have primary responsibility for managing, directing, overseeing and/or conducting the work of the project.

Additionally, the organization chart must include for the prime contractor, the job position title and name of Key Personnel, subcontractors and/or independent consultants identified above, as well as, the job position title and name of each supervisor who has approval authority over Key Personnel, subcontractors and/or independent consultants and the relationship of the individuals to the bidder, i.e., bidder, bidder’s employee, subcontractor, or subcontractor’s employee. In addition, the subcontractor must identify the supervisor who has approval authority over their Key Personnel.

#### 3.1.4 Capacity and Experience

The submission must describe and demonstrate in detail the bidder’s capacity and ability to perform and administer all tasks related to this project. If the bidder will be subcontracting a portion of the work, the submission must describe and demonstrate in detail the subcontractor’s capacity and ability to perform the portion of the work in which the subcontractor will be involved.

As outlined in RFS Section 2.2, the successful bidder must have the capacity and experience to conduct the work outlined in RFS Section 7. The submission must describe the bidder’s capacity and experience with respect to conducting the following types of activities. Additionally, bidders must have a minimum of three years, within the last five years, of full-time experience in both computer- and paper-based large-scale assessments in all the following:

- Administering, scoring, and reporting large-scale assessments (including, but not limited to, experience with data management systems; online and remote testing; and human scoring and AI scoring of constructed responses).

- Designing and developing high-quality academic and English language proficiency assessments that are accessible for all students.

- Maintaining security for all test materials, items, and data.

- Designing and implementing technology solutions for assessment delivery systems.

- Creating and providing training for students and professional learning opportunities for educators to understand and use assessment systems.

#### 3.1.5 Facilities and Resources

The submission must describe in detail the prime bidder’s company/business and its ownership structure. The submission must describe in detail the prime bidder’s and the subcontractor’s (if any) facilities, equipment, and technical capacity, including a detailed description of all software and hardware that will be used in performance of the work outlined in RFS Section 7. The submission must state the location(s) of the office(s) from which the primary work on this contract is to be performed. The bidder must provide for an office in the city of Sacramento, California. Include a description of the facility and the staff to be located in Sacramento.

### 3.2 Required Attachments/Forms

The bidder’s submission must be submitted as specified in RFS Section 3.5 Submission to the CDE and must include the following correctly completed attachments. Failure to complete the attachments correctly or missing attachments may cause the submission to be deemed non-responsive and therefore rejected.

#### 3.2.1 Attachment Checklist (RFS Attachment 2)

The Attachment Checklist (RFS Attachment 2) must be completed and submitted with the original submission, along with originals of all correctly completed required attachments/forms. A copy of the Attachment Checklist (RFS Attachment 2) and required attachments/forms must be included with each copy of the submission.

#### 3.2.2 Bidder Certification Sheet (RFS Attachment 3)

The Bidder Certification Sheet (RFS Attachment 3) must be completed and signed by an individual who is authorized to bind the bidder contractually. The Bidder Certification Sheet must be completed with an original signature and submitted with the original submission and a copy of the form included with each copy of the submission.

Only an individual who is authorized to contractually bind the Bidder shall sign the Bidder Certification Sheet (RFS Attachment 3). The individual signing the Bidder Certification Sheet must indicate their name and position title. The mailing address, telephone number, and email address of the authorized representative who signed the Bidder Certification Sheet must be included.

#### 3.2.3 Federal Certifications (RFS Attachment 4)

Federal Certifications (RFS Attachment 4) must be completed, signed and dated with an original signature on the form and included in the original submission and a copy of the form included with each copy of the submission.

#### 3.2.4 Iran Contracting Act Certification (RFS Attachment 5)

Iran Contracting Act Certification (RFS Attachment 5) must be completed, signed and dated with an original signature on the form included in the original submission and a copy of the form included with each copy of the submission.

#### 3.2.5 California Civil Rights Laws Certification (RFS Attachment 6)

California Civil Rights Laws Certification (RFS Attachment 6) must be completed, signed and dated with an original signature on the form included in the original submission and a copy of the form included with each copy of the submission.

#### 3.2.6 Bidder References (RFS Attachment 7)

Bidders must provide three (3) references using the Bidder Reference Form included in this RFS (RFS Attachment 7). References may be contacted by CDE to verify the information provided on the form. References that contain false or misleading statements shall be rejected. Failure to complete and include the form with the submission will cause your submission to be rejected and deemed non-responsive.

#### 3.2.7 Subcontractor Commitment Letter(s)

A subcontractor commitment letter, signed by an official representative of each subcontractor or independent consultant (refer to RFS Section 2.9 for the definition of “subcontractor”), acknowledging their intended participation/availability and confirmation that they have been made aware of the terms and conditions of the proposed contract, is required for each subcontractor who will provide services in the bidder’s submission. A commitment letter is required for all subcontractors and/or independent consultants, which are also required to be named in response to RFS Section 3.1.3. No cost should be included in the commitment letter. Each letter must be completed, signed and dated with an original signature included in the original submission and a copy of the letter included with each copy of the submission.

#### 3.2.8 Contractor Certification Clauses CCC 04/2017

Contractor Certification Clauses CCC 04/2017 must be completed, signed, and dated with an original signature on the form and included in the original submission and a copy of the form included with each copy of the submission. The CCC 04/2017 can be found at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language.

#### 3.2.9 Payee Data Record (STD. 204)

The Payee Data Record (STD. 204) must be fully completed, signed and dated with an original signature on the form included with the original submission and a copy of the form included with each copy of the submission. The Payee Data Record STD. 204 can be found at https://www.documents.dgs.ca.gov/dgs/fmc/pdf/std204.pdf.

The Payee Data Record Supplement (STD. 205) may be completed, signed and dated with an original signature and included with the original submission and a copy of the form included with each copy of the submission if the bidding firm must identify a remittance address if different from the mailing address identified on the STD. 204. The Payee Data Record Supplemental STD. 205 can be found at https://www.documents.dgs.ca.gov/dgs/fmc/pdf/std205.pdf.

#### 3.2.10 Certificate of Good Standing

Include with the bidder’s submission, a copy of the bidding firm’s most current Certificate of Good Standing issued by the California Secretary of State, or a separate paragraph that clearly states the bidder’s legal status and evidence that it is legally constituted and qualified to do business with the State (refer to RFS Section 2.1).

#### 3.2.11 Conditional Attachments

The following two (2) attachments are required by the successful bidder of this RFS, upon award of the contract, and do not need to be included with the bidder’s submission. However, bidders are required to certify on the Bidder Certification Sheet (RFS Attachment 3) that Attachment 8 and Attachment 9 will be completed and signed in accordance with the instructions indicated below:

- Conflict of Interest and Confidentiality Statement (RFS Attachment 8)

The Conflict of Interest and Confidentiality Statement (RFS Attachment 8) must be completed, signed and dated by the successful bidder, and all subcontractors, as a condition of receipt of the contract. By signing the Bidder Certification Sheet (RFS Attachment 3), the bidder agrees to comply with this requirement.

- California Department of Education Computer Security Policy (RFS Attachment 9)

The California Department of Education Computer Security Policy (RFS Attachment 9) must be completed, signed and dated by the bidder, subcontractors and each of their employees engaging in services to the CDE related to this RFS and the resulting contract and kept on file by the bidder and made available to the CDE upon request, as a condition of receipt of the contract. By signing the Bidder Certification Sheet (RFS Attachment 3) the bidder agrees to comply with this requirement.

#### 3.2.12 Staffing Labor Hours (RFS Attachment 10A)

The Staffing Labor Hours must be completed for each FY, or part thereof as instructed in RFS Section 3.1. If subcontractors are being used, a separate Staffing Labor Hours must be submitted for each subcontractor as instructed in RFS Section 3.1.

#### 3.2.13 Cost Submission (RFS, Attachments 10B and 10C)

Cost information must be included in the submission as instructed in RFS Section 3.3.

#### 3.2.14 Generative Artificial Intelligence (GenAI) Disclosure Notification

The State seeks to realize the potential benefits of GenAI, through the development and deployment of GenAI tools, while balancing the risks of these new technologies.

Bidder must notify the State in writing if it: (1) intends to provide GenAI as a deliverable to the State; or (2), intends to utilize GenAI, including GenAI from third parties, to complete all or a portion of any deliverable that materially impacts: (i) functionality of a State system, (ii) risk to the State, or (iii) Contract performance. For avoidance of doubt, the term “materially impacts” shall have the meaning set forth in State Administrative Manual (SAM) § 4986.2 Definitions for GenAI.

Failure to report GenAI to the State may result in disqualification. The State reserves the right to seek any and all relief to which it may be entitled to as a result of such non-disclosure.

Upon notification by a bidder of GenAI as required, the State reserves the right to incorporate GenAI Special Provisions into the final contract or reject bids/offers that present an unacceptable level of risk to the State.

California Government Code (GC) Section 11549.64 defines “Generative Artificial Intelligence (GenAI)” as an AI system that can generate derived synthetic content, including text, images, video, and audio that emulates the structure and characteristics of the system’s training data.”

### 3.3 Cost Submission Requirements

#### 3.3.1 Cost Submission Specifications

The following FYs must be addressed in the cost submission. It is anticipated that the contract will begin on March 1, 2027, or upon CDE, SBE, and DOF approval (whichever is later) and will continue through December 31, 2032. The contract period covers seven FYs, for a total of 70 months:

- 2026–2027: March 1, 2027 – June 30, 2027 (4 months)

- 2027–2028: July 1, 2027 – June 30, 2028 (12 months)

- 2028–2029: July 1, 2028 – June 30, 2029 (12 months)

- 2029–2030: July 1, 2029 – June 30, 2030 (12 months)

- 2030–2031: July 1, 2030 – June 30, 2031 (12 months)

- 2031–2032: July 1, 2031 – June 30, 2032 (12 months)

- 2032–2033: July 1, 2032 – December 31, 2032 (6 months)

The Cost Submission Task Detail (RFS Attachment 10C) must correspond with the hours in Staffing Labor Hours (RFS Attachment 10A). The Cost Submission Task Detail (RFS Attachment 10C) must correlate with the tasks set forth in Section 7 of this RFS.

The total submission bid amount must be for all tasks specified in the scope of work (Refer to RFS Section 7), including work done by subcontractors, and all related labor costs, travel, overhead or indirect costs, etc. for each of the seven FYs covered by this contract. Except as noted, the potential contractor is responsible for all logistics and costs incurred by the potential contractor or other program participants, including, but not limited to, travel costs (e.g., meals and lodging), and meeting costs (e.g., meeting materials, interpreters, video hook-up fees, facilities rental, etc.). The potential contractor is not responsible for costs of outside observers or CDE staff. Refer to Cost Submission Task Detail (RFS Attachment 10C).

No costs, direct or indirect, shall be omitted from the Cost Submission. Computations must accurately compute and calculate to the exact cent (expressed in dollars to two decimal places).

The costs/rates must be reasonable. Any proposed costs submitted by the bidder that are not included in the total amount for the overall contract as stated on the Cost Submission Summary by FY (RFS Attachment 10B), are not binding on the CDE, or the State, and the bidder will be legally bound to fully perform all work for the total amount stated and absorb such amounts not included. Every component of the cost is subject to reasonableness of cost justification to the CDE, the SBE, and the DOF.

The bidder must provide a cost submission conforming to the format of the model displayed in RFS Attachments 10A, 10B, and 10C:

- RFS Attachment 10A: Staffing Labor Hours by Task and by FY

The bidder must provide staffing labor hours by task and FY conforming to the format of the model displayed in Attachment 10A for each separate test administration. Columns and rows may be added as needed. The bidder is to provide the name, title, hours per each task in the scope of work, total hours, and full-time-equivalency (FTE) percentage for each person identified, including subcontractors, in RFS Section 3.1. The bidder must clearly identify any hours that the contractor will provide as in-kind costs.

- RFS Attachment 10B: Cost Submission Summary by FY

The bidder must provide a cost submission summary conforming to the format of the model displayed in Attachment 10B. The bidder must provide the total of all costs identified in Attachment 10C for all tasks in RFS Section 7. The bidder is to provide all costs by the FY in which the costs will be incurred.

- RFS Attachment 10C: Cost Submission Task Detail

The bidder must provide a cost submission detail conforming to the format of the model displayed in Attachment 10C. Columns and rows may be added as needed. The bidder must provide cost details by each task and subtask as specified in RFS Section by FY. The bidder is to provide all costs by the FY in which the costs will be incurred.

At a minimum, the details must include:

- Detailed labor/staff costs, including hourly or billing rates and number of hours per position (identifying the position) detailed in the staff organizational plan (all management titles and hours used must agree with the titles and hours in RFS Section 3.1 and Attachment 10A)

- Detailed operating expenses (e.g., facility, equipment, etc.)

- Identify, if applicable, which details within a task are being provided by a subcontractor

- Travel costs must not exceed those established for CDE’s nonrepresented employees, computed in accordance with and allowable pursuant to applicable California Department of Human Resources regulations available at https://www.calhr.ca.gov/about-calhr/divisions-programs/personnel-management/rules-regulations/ 
https://www.calhr.ca.gov/about-calhr/divisions-programs/benefits/travel-reimbursements/.

### 3.4 Errors in a Bidder’s Submission

An error in the submission may cause rejection of that bid; however, the CDE may, at its sole discretion, retain the submission and require certain corrections. In determining if a correction will be made, the CDE will consider the conformance of the bid to the format and content required by the RFS, and any unusual complexity of the format and content required by the RFS.

If the bidder’s intent is clearly established based on review of the submission, the CDE may, at its sole discretion, require a bidder to correct an error based on that established intent. The CDE may, at its sole discretion, require a bidder to correct obvious clerical errors. The CDE may, at its sole discretion, require a bidder to correct errors of omission, and in the following three situations, the CDE will take the indicated actions if the bidder’s intent is not clearly established by the complete bid submittal:

- If a deliverable, task, subtask, or staff is described in the narrative and omitted from the cost submission, it will be interpreted to mean that the deliverable, task, subtask, or staff will be provided by the bidder at no cost.

- If a deliverable, task, or subtask is not mentioned at all in the bidder’s submission, the bid will be interpreted to mean that the bidder does not intend to perform that deliverable, task, or subtask.

- If a deliverable, task, or subtask is omitted, and the omission is not discovered until after contract award, the bidder shall be required to perform that deliverable, task, or subtask at no cost.

### 3.5 Submission to CDE

- The submission packages must provide clear and concise descriptions of the bidder’s ability to satisfy the requirements of this RFS. The submission packages must include all requirements specified in this RFS. Significant omissions, inaccuracies, or misstatements may be sufficient cause for rejection of a submission and disqualification.

If the CDE determines that a required submission element(s) was not included in the bid submission but exercises its right to consider the submission, the recommendation to the state board will identify the required element(s) that the CDE determined were not included in the submission.

- The submission must include a table of contents that identifies, by page number, all the section and subsection headings, including the submission of documents in the same order presented in this RFS.

- The submission packages must conform with all requirements specified in RFS Section 3.

- The CDE does not accept alternate agreement language from a bidder. A submission with such language will be considered a counter submission and will be rejected.

- The State General Terms and Conditions (GTC) are not negotiable and will be incorporated into the final contract. The GTC 02/2025 may be found at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language.

- The submission packages must be received by the CDE no later than February 12, 2026, by 1:00 p.m., PST. The submission package(s) must be plainly marked “CONFIDENTIAL,” with the RFS number and title, your firm name, and address, as shown in the following example:

Business Name

12345 Any Street

Any City, CA 55555

California Assessment System

Request for Submissions – CN260003 - CONFIDENTIAL

If the submission is made under a fictitious name or business title, the actual legal business name of the bidder also must be provided.

- Submissions may be mailed or delivered. It is solely the responsibility of the bidder to ensure that the package is received by the CDE by the date and time specified in this RFS.

The submission package(s), if mailed or sent through third-party delivery services, must be addressed according to the following:

Attention: Chad Portney – RFS CN260003 - CONFIDENTIAL

California Department of Education

Assessment Development and Administration Division

1430 N Street, Suite 4409

Sacramento, CA 95814-5901

- Each submission will be reviewed to determine whether it meets the requirements.

- The CDE may modify the RFS up to the specified time and date stated for submissions by issuance of an addendum to all parties who the CDE has received a submission package or all parties who submitted an Intent to Submit form.

- The CDE reserves the right to reject all submissions for reasonable cause. The CDE, at its sole discretion, reserves the right to waive immaterial defect(s) or clerical error(s), request bidders to correct immaterial defect(s) or clerical error(s), or request clarification at any time during the RFS process. The CDE is not required to award a contract.

- Bidders are cautioned not to rely on the CDE during the evaluation of the submissions to discover and report to bidders of any immaterial defects and/or clerical errors made to the documents submitted. Before submitting documents, bidders should carefully proofread them for immaterial defect(s) or clerical error(s) and adherence to the RFS requirements.

### 3.6 Submission Conditions

- The CDE may reject any or all submissions at its reasonable discretion. Examples include, but are not limited to, a proposal that is not responsive, does not meet the technical standards, is not from a responsible bidder, is from a bidder suspected of past or present collusion, is conditional or incomplete, contains unauthorized options or alternatives, is one of multiple alternative submissions from the same bidder, is suspected to be the product of collusion or otherwise is suspect or contains irregularities of any kind. Alternatively, the CDE may waive any immaterial defects in a submission or may require bidders to correct an immaterial defect or request clarification at any time during the RFS process. The CDE’s waiver of an immaterial defect shall in no way modify the RFS document or excuse the bidder from full compliance with all requirements if the bidder is awarded the contract.

- Costs for developing submissions and in anticipation of award of the contract are the sole responsibility of the bidder and shall not be charged to the State under any circumstance.

- A bidder may withdraw its submission only by submitting a written withdrawal request to the CDE that is signed by the bidder’s authorized representative prior to the bid submission deadline. Submissions may not be withdrawn or modified after the bid submission deadline.

- A bidder may modify a submission after submittal only by withdrawing its original submission and resubmitting a new submission prior to the bid submission deadline. submission modifications offered in any other manner, oral or written, will not be considered.

- The CDE may modify the RFS by issuance of an addendum to all parties who received a proposal package. All addenda will be posted on the Cal eProcure website, https://caleprocure.ca.gov/pages/Events-BS3/event-search.aspx, as well as the CDE Funding web page, https://www.cde.ca.gov/fg/fo/af. The CDE also reserves the right to cancel the RFS in its entirety at its discretion. The CDE is not required to award a contract.

- Each bidder is solely and entirely responsible for all aspects of its submission. Before submitting documents, bidders should carefully examine any RFS specifications or RFS requirements and fully proof the documents. In the event a submission contains errors, inaccurate assumptions, inconsistencies or other defects, the CDE shall interpret the submission in the manner it determines is the most favorable to the State.

- More than one submission or a submission that includes various options or alternatives from an individual, firm, partnership, corporation or association under the same or different names, may be rejected. Reasonable grounds for believing that any bidder has submitted more than one submission for the work contemplated herein will cause the rejection of all proposals submitted by that bidder. If there is reason for believing that collusion exists among the bidders, none of the participants in such collusion will be considered in this procurement or future procurements.

### 3.7 Disposition of Submissions

Upon submission, all documents submitted in response to this RFS will become the property of the CDE. Documents submitted to the CDE may be subject to public disclosure pursuant to a request made under the California Public Records Act (GC Section 7920.000 et seq.). The State cannot prevent the disclosure of public documents. We recommend that bidders register the copyright for any proprietary material submitted. The bidder agrees to defend, indemnify and hold harmless the State, CDE, SBE, its officers and employees, in any action in which disclosure of the submission in response to this RFS is requested.

## 4. EVALUATION PROCESS

- Each submission shall be evaluated to determine responsiveness to the general requirements and components, as well as format and content requirements, as described in this RFS. Each bidder’s submission will be evaluated per the process described in RFS Appendix D – Scoring Guide.

- Formal Requirements

- At the time of the submission opening, each submission will be checked for the presence or absence of required information in accordance with the submission requirements of this RFS. Submissions that do not provide the requested information may be rejected as non-responsive at the discretion of the CDE.

- Submissions that contain false or misleading statements, or which provide references that do not support an attribute or condition claimed by the proposer, shall be rejected at the discretion of the CDE.

- The CDE will evaluate each submission to determine its responsiveness to the CDE’s needs as described in RFS Appendix D.

- Evaluation Phases

- Phase I: Requirements Checklist

In Phase I, the CDE will use the Requirements Checklist in Appendix D to verify that each of the requirements is included in the bidder’s submission. Submissions will be rated on a yes/no basis. Receipt of a “no” on any of the requirements on the checklist may result in elimination of the submission from further consideration and review at the discretion of the CDE.

Within Phase I, the CDE reserves the right to require a bidder to remedy any obvious clerical or incidental errors in a submission. Bidders will be required to initial corrections made. Submissions that fail to provide any of the required documentation will not advance to Phase II. One completed Requirements Checklist for each bidder will be saved as documentation of Phase I of the evaluation process.

- Phase II: Submission and Cost Evaluation

Phase II consists of the following sequence: 1) submission evaluation; 2) cost evaluation review; and 3) ranking of bidders using the submission evaluation and cost evaluation scores. The bidder with the highest overall score, in accordance with RFS Appendix D, Scoring Guide, will be recommended by the CDE to the SBE at a publicly noticed meeting, to participate in Phase III.

- Phase III: Recommendation and Contract Negotiations

The CDE will request approval from the SBE to begin contract negotiations with the successful bidder who passed the submission evaluations with the highest overall score. It is anticipated that this request will occur at the May 2026 SBE meeting.

Once the CDE receives approval from the SBE, staff from the CDE, the SBE, and DOF will commence contract negotiations. It is anticipated that contract negotiations will begin on June 3, 2026 (tentative) in Sacramento, California. The CDE reserves the right to conduct contract negotiations via teleconference or video conference. If, after such negotiations, the bidder fails to accept the state’s best and final offer, negotiations may be conducted with the bidder with the next highest score.

It is anticipated that the CDE will bring a recommendation to the SBE for approval of negotiated contract documents at the September 2026 SBE meeting.

## 5. AWARD AND PROTEST

- Award of a contract as a result of the RFS shall be contingent on SBE, CDE, and DOF approvals. In addition, award is contingent upon the availability of funding provided to and by the CDE, including appropriation in the annual Budget Act.

- EC Section 60647 states an action to challenge a provision of EC sections 60640–60648.5 or a determination made by the SBE under this article, shall be filed and adjudicated pursuant to sections 860 to 870, inclusive, of the California Code of Civil Procedure. No exercise of discretion by the SBE in its administration of EC sections 60640–60648.5 or exercise of its discretion pursuant to EC Section 60605 shall be overturned absent a finding that the SBE acted in an arbitrary and capricious manner.

## 6. STANDARD CONDITIONS OF SERVICE

- All submissions and related documents submitted in response to this RFS shall become the property of the State.

- RFS Sections 8 through 11 and the successful bidder’s submission will be incorporated into the final negotiated contract.

- Service shall be available no sooner than the express date set by the CDE and the successful bidder, after all approvals have been obtained and the contract is fully executed.

- All performance under the contract shall be completed on or before the termination date of the contract.

- No oral understanding or agreement shall be binding on either party.

## 7. SCOPE OF WORK

The Contractor must plan and budget for the costs of all tasks/subtasks and activities.

The successful bidder must comply with all relevant laws and regulations in the performance of work in furtherance of the contract established pursuant to this procurement.

The term of the contract is from March 1, 2027, through December 31, 2032, which spans seven FYs, for a total of 70 months:

- 2026–2027: March 1, 2027 – June 30, 2027 (4 months)

- 2027–2028: July 1, 2027 – June 30, 2028 (12 months)

- 2028–2029: July 1, 2028 – June 30, 2029 (12 months)

- 2029–2030: July 1, 2029 – June 30, 2030 (12 months)

- 2030–2031: July 1, 2030 – June 30, 2031 (12 months)

- 2031–2032: July 1, 2031 – June 30, 2032 (12 months)

- 2032–2033: July 1, 2032 – December 31, 2032 (6 months)

Submissions must describe in detail the performance of all tasks described herein. Any deviation from the tasks described in RFS Section 7 will not be considered and will cause a submission to be rejected. This RFS seeks submissions addressing six main tasks:

- Task 1 – Comprehensive Plan and Schedule of Deliverables

- Task 2 – Program Support Services

- Task 3 – Technology Services

- Task 4 – Assessment Development and Accessibility

- Task 5 – Test Administration and Security

- Task 6 – Scoring and Reporting

For the purposes of this RFS, bidders are to propose FY costs to administer (and develop as applicable) the assessments identified in RFS Table 1 to the estimated test takers by assessment identified in RFS Table 5 for each year of the contract (i.e., 2027–28, 2028–29, 2029–30, 2030–31, and 2031–32). (The costs associated with the CDE’s UCSC contract for Smarter Balanced summative assessments, interim assessments, and formative assessment resources for ELA and mathematics in Tools for Teachers are not included in this RFS.)

Table 5. Estimated Test Takers by Assessment for Each Year of Contract

| Assessment | Subject | Grade | Estimated Test Takers |
| --- | --- | --- | --- |
| Smarter Balanced Interim | ELA and Mathematics | K–12 | 5,800,000 |
| Smarter Balanced Summative | ELA and Mathematics | 3–8, 11 | 2,950,000 |
| CAST | Science | 5, 8, and high school | 1,300,000 |
| CAA for ELA and Mathematics | ELA and Mathematics | 3–8, 11 | 37,600 |
| CAA for Science | Science | 5, 8, and high school | 15,300 |
| CSA | Reading/ Language Arts | 3–8 and high school | 52,000 |
| Summative ELPAC | English Language Proficiency | K–12 | 951,000 |
| Initial ELPAC | English Language Proficiency | K–12 | 151,000 |
| Summative Alternate ELPAC | English Language Proficiency | K–12 | 16,300 |
| Initial Alternate ELPAC | English Language Proficiency | K–12 | 600 |

### 7.1 TASK 1 – COMPREHENSIVE PLAN AND SCHEDULE OF DELIVERABLES

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 1 and must describe in detail the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge and staffing level of the subjects and skills necessary to successfully complete the project as stated in Task 1.

The successful bidder shall coordinate communications with the CDE during the entire contract period. The successful bidder shall provide timely and accurate communication and coordination with CDE staff and other policy, administrative, and advisory groups; attend and provide minutes for required meetings; adhere to the Approval and Certification Process (refer to RFS Section 7.1.6.A) for project deliverables. The submission must include the following information to address Task 1 activities which include the following subtasks. The Task 1 activities include, but are not limited to, the following subtasks.

#### 7.1.1 Schedule of Deliverables, Narrative Schedule and Timeline

The submission must include a comprehensive process to develop a project management plan (PMP) by a certified project manager (PMP® or equivalent certification) to address all activities described in RFS Section 7. The process must include a schedule that provides the CDE with at least 20 working days for the review of the initial PMP. The PMP must clearly identify all activities and deliverables, including, for example, the development and adaptation of technology delivery services, the non-Smarter Balanced item bank system, test items, test forms, training materials, administration materials, reports, and logistics, as set forth in RFS Section 7.

This section of the submission must include a detailed narrative schedule and timeline that outlines, for all FYs and parts thereof, both by task/subtask and chronology for each activity to be performed for the entire contract term. The schedule and timeline must list all tasks, subtasks, activities, and deliverables to be performed in each FY, or part thereof, as set forth in RFS Section 7. The chronological schedule and timeline must include proposed task/subtask initiation dates, completion dates, effort required, dependencies between deliverables and activities, and person(s) assigned, for each FY covered under the proposed contract, or part thereof. The schedule and timeline will also serve as a monitoring document to ensure timely completion of tasks as proposed by the successful bidder. The submission’s comprehensive plan and schedule must conform to the CDE approval and certification process and must be updated and maintained throughout the term of the contract. (Refer to RFS Section 7.1.6.)

The schedule must be based on a fixed-duration task model, and all tasks must be configured to auto schedule (as opposed to manual schedule). All contract deliverables and associated tasks must be captured as a discrete work package within a major project phase. In addition, the PMP must identify all work and resources associated with the TDS as described in RFS Section 7.3.2 that are consistent with the California Project Management Framework available through the California Department of Technology at https://www.capmf.cdt.ca.gov/.

The PMP must be created and delivered within 30 working days of the contract start date for CDE review and approval. The process must include the development of a PMP that addresses the methodologies for project management and must include the following subplans:

- Scope management plan

- Organizational chart and governance model

- Change control management plan

- Communications management plan

- Risk management and escalation plan

- Quality management plan

- Requirements management plan (inclusive of the requirements traceability matrix)

- Schedule management plan

- Resource management plan

These subplans may be consolidated into a single or a few deliverables to minimize duplicative information.

##### 7.1.1.A Secure Web-Based Collaboration System

The submission must describe the bidder’s approach to collaborative project management. The submission must propose a secure, web-based collaborative software product (i.e., social intranet software with built-in collaboration tools) that will be used to plan, coordinate, control, and monitor activities and deliverables for the project. The proposed solution must enable the project team to collaborate across team, department, and corporate boundaries. It must provide a secure, web-based system that can allow remote workers to meet, collaborate, and complete specific tasks within a virtual workspace. All project team members should have appropriate access to the project information and tools, such as tasks, messages, documents, requirements and so forth. This information must be updated in real time when changes occur. The proposed solution must provide for the sharing of documents, a document repository, and a shared overall project meeting calendar that displays every meeting.

#### 7.1.2 Meetings

The submission must describe a plan for conducting meetings between the bidder and CDE staff that provide for effective and efficient project oversight. The successful bidder and any proposed subcontractors must plan and budget for the cost of sending staff to all required meetings. The successful bidder must propose the method in which the meetings within this section will be held (i.e., in-person or virtual), and if in-person is selected, the meetings will be held in Sacramento, California.

The CDE reserves the right to require any successful bidder or subcontractor staff involved with the contract to attend the meetings in person or virtually, whichever the CDE deems warranted. Additional meetings will be scheduled as needed. The successful bidder and any subcontractors must plan and budget for the cost of sending staff to management meetings.

In accordance with any recommendation(s) or order(s) contained in a Governor’s executive order, an advisory or order of the California Department of Public Health, or an advisory or order of a county health department with authority over the area in which this contract is to be performed or an advisory or order of a law enforcement authority, the in-person meetings may be cancelled or changed to a virtual meeting at the discretion of the CDE. Therefore, any announcement for the event must state that the event may be in-person, virtual, or both. The CDE cannot reimburse the Contractor for any cancellation fees, deposit or pre-payments under any circumstances, even if the CDE decides to cancel the event. This applies to all in-person meetings mentioned in this RFS.

##### 7.1.2.A Orientation Meeting

The submission must include a detailed plan for conducting an orientation meeting that will occur within the first two weeks of the commencement of this contract. The submission must ensure that all key personnel of the prime contractor and any subcontractor(s) including the management team (Project Manager, Fiscal Manager, Technology Manager, and any other key personnel identified in RFS Section 3.1.3), task leaders, and significant subcontractors will meet with CDE staff for up to two full days for an orientation meeting. The successful bidder must develop and document the meeting agenda in coordination with the CDE.

The submission must acknowledge and ensure that during the orientation meeting, the bidder will review each task and subtask(s), the detailed narrative schedule and timeline (refer to RFS Section 7.1.1), and staffing regarding the proposed method(s) for implementation of the contract as contained in the submission. The successful bidder must develop the meeting agenda in coordination with the CDE. The orientation meeting must address all tasks, including timelines, questions, and concerns about the implementation of the contract.

##### 7.1.2.B Semi-Annual Planning Meeting

The submission must include a detailed plan to coordinate two semi-annual planning meetings with CDE that is to occur annually to confirm the procedures and timeline for implementing subsequent year activities. The submission must ensure that all key personnel of the bidder and any subcontractor(s) including the management team (Project Manager, Fiscal Manager, Technology Manager, and any other key personnel identified in RFS Section 3.1.3), task leaders, and significant subcontractors will meet with CDE staff for up to two full days. The successful bidder must develop and document the meeting agenda in coordination with the CDE.

The submission must acknowledge and ensure that the semi-annual planning meetings will address all tasks, timelines, questions, and concerns related to the project. The submission must acknowledge and ensure that during the meeting, the successful bidder will provide a review of all tasks, timelines, task implementation, deliverables, and status as contained in the submission. The successful bidder must develop the meeting agenda in coordination with the CDE. The agenda must include the status of all pending activities along with the deadline and person(s) assigned to each activity.

##### 7.1.2.C Weekly Management Meetings

The submission must include a plan to hold weekly management meetings between the CDE and the bidder’s Project Manager to review and discuss task implementation and status. The submission must acknowledge and ensure that the bidder’s key personnel, including staff and any proposed subcontractors, will be present and must attend, at the request of the CDE, the meetings as appropriate to the task. The weekly management meetings will be held virtually or in person at the CDE headquarters in Sacramento, California or other agreed upon location at the CDE’s request. The successful bidder must develop the meeting agenda in coordination with the CDE. The agenda must include, but is not limited to, the status of all pending activities along with deadline, status, issue(s), and person(s) assigned to each activity.

##### 7.1.2.D Weekly Project Meetings

The submission must provide a plan for weekly project meetings between the bidder and CDE staff to review, discuss, and improve task implementation and status. The successful bidder must develop the meeting agenda in coordination with the CDE. The meeting agenda must clearly indicate any topics that require specific staff input. The agenda must be submitted to the CDE at least three working days prior to each meeting. The successful bidder will ensure that the appropriate contract monitors, project managers, and subcontractors are invited to each weekly meeting as needed according to agenda topics. The list of participants must be provided to the CDE at least three working days prior to each meeting. The successful bidder’s project manager or their representative must attend each meeting. Subcontractors must be included as appropriate to the task and may be included with the agreement of the CDE.

##### 7.1.2.E Change Control Meetings

The submission must provide a plan for biweekly change control meetings in-person, via telephone, or video conference. As a component of the change control management plan (refer to RFS Section 7.1.1), the successful bidder must conduct biweekly change control meetings between the successful bidder and CDE staff to provide opportunities to review and discuss project changes. The successful bidder must develop the meeting agenda in coordination with the CDE. The agenda and accompanying documents must be submitted to the CDE at least three working days prior to each meeting. The successful bidder’s project manager or their representative must attend each change control meeting. Subcontractors must be included as appropriate to the task and may be included in-person, via telephone, or videoconference.

##### 7.1.2.F State Board of Education Meetings

The submission must provide a plan for attendance (by the bidder) at SBE meetings. The bidder must plan and budget to attend in-person SBE meetings held in Sacramento, California. The successful bidder must also be prepared to make presentations to the SBE and have appropriate staff available for questions as required by the CDE. These presentations must be approved by the CDE prior to the in-person presentations (refer to RFS Section 7.1.6). The successful bidder is not responsible for costs associated with SBE meetings, other than those associated with their staff attendance at the SBE meetings.

##### 7.1.2.G Technical Advisory Group Meetings

The submission must provide a plan for attendance by the bidder (and subcontractor[s], if applicable) for meetings with the CDE’s testing technical advisory group (TAG) as required by the CDE. These meetings will provide opportunities to review, discuss, and improve task implementation.

The CAASPP TAG and the ELPAC TAG, which are panels of outside experts and LEA representatives, are recruited to provide advice on evaluation plans and the interpretation of evaluation results. These panels of nationally recognized experts in technical and policy areas meet up to two times each year; once virtually and once in person in the Sacramento area. The successful bidder must coordinate with the CDE in the development of the TAG meeting agenda(s) pertaining to the CAASPP and ELPAC and present to the TAG on topics of interest, as needed.

#### 7.1.3 Coordination and Continuous Improvement

The submission must describe a process for coordinating with a variety of entities identified by the CDE and for monitoring continuous improvement.

##### 7.1.3.A Coordination with the Smarter Balanced Assessment Consortium and CDE Entities and Staff

The submission must describe a plan to coordinate and collaborate, effectively and efficiently, with the Smarter Balanced Assessment Consortium to administer the Smarter Balanced assessment system. Administration must be conducted in a manner pursuant to the Memorandum of Understanding (MOU) approved by the SBE in January 2022 (or any subsequently approved agreement) and included in the contract amendment with the University of California, Santa Cruz (UCSC). The contract amendment is located in Revised Attachments 2, 2a, and 2b of Revised Item 03 on the CDE SBE Agenda for January 2022 web page at https://www.cde.ca.gov/be/ag/ag/yr22/agenda202201.asp.

The successful bidder must also plan to coordinate with the CDE Contract Monitor; staff from other CDE divisions, including but not limited to the Educational Data Management Division (EDMD) for California Longitudinal Pupil Achievement Data System (CALPADS) integration; Analysis, Measurement, and Accountability Reporting Division (AMARD), Technology Services Division (TSD); the California K–12 High Speed Network (K12HSN); the California State University (CSU) Early Assessment Program (EAP) contractor; and other necessary entities to plan and implement all tasks and activities that are to be conducted over the period of the contract.

##### 7.1.3.B Development of Plan for Continuous Improvement

The submission must provide a plan for the continuous improvement of the California Assessment System. The submission must include details and activities to be undertaken as part of the plan to monitor continuous improvement. The successful contractor will be required to submit an annual continuous improvement plan to the CDE as a deliverable under the contract.

#### 7.1.4 Records and Minutes

The submission must describe procedures for maintaining records and minutes in an online shared drive for all meetings, including, but not limited to, weekly and semi-annual meetings, item reviews, standard settings, and other management meetings. The successful bidder will conduct the meeting, record minutes, and maintain lists of participants, including their institutional affiliation and contact information. The minutes must describe the status of current activities, the deadline for completion, and the person(s) assigned to each activity. The successful bidder must also review contact information for each meeting and update contact information if changes have occurred. The successful bidder must, within five working days after the meeting, submit the meeting minutes to the CDE through the Approval and Certification Process (RFS Section 7.1.6.A) for review and approval.

#### 7.1.5 Web, Document, and Accessibility Standards

The submission must acknowledge and ensure that the successful bidder will adhere to the CDE Web, Document, and Accessibility Standards which can be found at https://www.cde.ca.gov/re/di/ws/webstandards.asp. These standards are based upon industry best practices, mandates (such as GC Section 7405, federal sections 504 and 508 of the Rehabilitation Act of 1973, and Title II of the Americans with Disabilities Act [ADA]), and styles and practices specific to the CDE. There is an expectation that CDE staff, its contractors, and anyone else doing work on behalf of the CDE will comply with them. The platforms and file formats used for project deliverables must be compatible with CDE systems and software.

The submission must describe in detail that the successful bidder has the resources, staff, knowledge, skills, and abilities to deliver Section 508 accessible products. If needed during the contract period, the successful bidder may request to meet with the CDE Web Application Review Team (WebART) to answer questions about proposed accessibility strategies and request WebART to review a small sample of a deliverable to help guide the process.

The submission must acknowledge and ensure that the CDE and all authorized state control agencies must have access to all internal and external reports, documents, data, and working papers used by the successful bidder and potential subcontractors in the performance and administration of this contract. The submission must acknowledge and ensure that the successful bidder shall allow the CDE to monitor all aspects of the successful bidder's performance.

#### 7.1.6 CDE Notification and Approval Requirements

The CDE must approve all materials and deliverables developed in conjunction with this contract. The bidder must commit to not disseminating any written information, materials, or deliverables to LEAs, the public, or any other third party without the CDE’s prior written approval.

The submission must include a procedure by which deliverables and review items are submitted to the CDE. The successful bidder must designate a single point of contact for submitting deliverables and review items to the CDE and notifying the CDE of the submissions. There must be a single point of contact for all contract deliverables, regardless of which assessment they are related to. The procedure must provide for the tracking of all deliverables and review items through a gatekeeper process as described in the Approval and Certification Process.

##### 7.1.6.A Approval and Certification Process

The successful bidder will be responsible for creating and maintaining an approval and certification process that allows sufficient time, as defined below, for the CDE to review materials and deliverables and, if necessary, for the successful bidder to make modifications as required by the CDE and for the CDE to review and approve the revised submission. Unless otherwise specified in this RFS or agreed to in writing by the CDE, the successful bidder must (1) allow at least ten working days for the CDE to initially review and provide feedback on the submission; (2) make edits to the initial draft within three working days from receipt of feedback from the CDE; (3) allow the CDE at least five working days to review and edit the revised draft; and (4) make edits to the revised draft and provide the CDE with a final document reflecting all edits within three working days from receipt of the CDE feedback.

The successful bidder will be responsible for ensuring that all materials and deliverables submitted to the CDE have been reviewed and approved by the successful bidder’s project manager before submission to the CDE. The gatekeeper process is outlined below:

- The successful bidder submits the fully-vetted initial version of the deliverable to the CDE.

- The CDE reviews the initial version and provides comments to successful bidder within 10 working days of the submission.

- The successful bidder prepares and submits the revised version of the deliverable to the CDE within three working days after receipt of the CDE’s written comments to the initial version.

- The CDE reviews within five working days the revised version and provides one of

the following decisions:

- Approve

- Approve with edits

- Return with edits

- Disapprove

- For Archive

- For Reference

- The successful bidder will take one of the following actions depending on the CDE review decision in step 4:

- Deliverables that receive an “approve” decision will be finalized by the successful bidder. The finalized deliverable will be submitted to the CDE for archive purposes within five working days of the date of CDE’s notice of approval.

- Deliverables that receive an “approve with edits” decision will be revised and finalized by the successful bidder while incorporating the additional CDE edits. The finalized deliverable will be submitted to the CDE for archive purposes within five working days of the date of the CDE’s notice of approval.

- Deliverables that receive a “disapprove” decision will be returned to the successful bidder. The program managers overseeing the deliverable must discuss with the appropriate program office how the deliverable did not meet expectations and revisions that need to be made to submit to the CDE for review within five working days as an initial version.

Deliverables that receive a “return with edits” decision will be revised by the successful bidder and submitted to the CDE for another review. The iterative revision and review process will continue until the CDE has approved the deliverable.

The submission must acknowledge and ensure that the successful bidder shall be responsible for a variety of activities related to reports, invoices, and data file requirements and will adhere to the relative timelines.

#### 7.1.7 Monthly Written Progress Reports

The submission must include a detailed process for providing monthly written progress reports to the CDE. The submission must ensure that, at a minimum, each monthly progress report must include:

- Task number and title;

- Description of tasks;

- A report of activities completed and deliverables produced during the prior month;

- An update of current or ongoing activities and the progress noted for each;

- Unanticipated outcomes or problems (as applicable);

- Root cause analysis of the problems (as applicable, refer to RFS Section 7.1.7.A);

- Tasks planned for completion the following month; and

- A detailed list of activities.

The submission must ensure that the monthly progress report for the month prior will be submitted to the CDE for review and approval within five working days after the last day of each month. The CDE will not approve invoices for payments on this contract without an approved monthly progress report. The submission must indicate that the bidder understands that the progress reports must reflect all tasks specified in the corresponding monthly invoice.

The submission must specify that the monthly progress reports will note progress on all tasks and activities and will be used as a basis for tracking progress and making improvements. The monthly progress reports must reflect all tasks specified in the corresponding monthly invoice, and each monthly progress report must be used to determine approval for payment of the corresponding monthly invoice. Additionally, the original CDE-approved monthly progress report must be signed by the successful bidder's Project Manager and submitted to the CDE with the monthly invoice.

##### 7.1.7.A Root Cause Analysis

The submission must acknowledge and ensure that if a problem occurs, the successful bidder must notify the CDE Contract Monitor within one working day and submit a Root Cause Analysis Report as part of the monthly progress report within 30 calendar days after the incident.

The submission must acknowledge and ensure that, at a minimum, the Root Cause Analysis Report must address the following:

1.	Identify the problem;

2.	Evaluate the significance and impact of the problem;

3.	Identify the root cause of the problem and the responsible party;

4.	Recommend actions to prevent recurrence of this or similar problems;

5.	Assign responsibility for developing and implementing corrective action;

6.	Implement new process or quality controls as necessary;

7.	Determine what to do with failed items/deliverables; and

8.	Record permanent changes in process documentation.

#### 7.1.8 Transition of Contracts Plan

The submission must develop and provide a transition plan. The plan must describe in detail the procedures for the effective and smooth transition between the current California Assessment System contractor, ETS, and the successful bidder, as well as the procedures that will ensure an effective and smooth transition at the end of the contract with any future contractor(s).

The current California Assessment System contract ends on December 31, 2027, and this contract is anticipated to start on March 1, 2027. The overlap of contracts is essential to provide the current contractor time to complete tasks and provide the successful bidder with time to prepare and administer the assessments. The successful bidder and subcontractors must cooperate fully with the CDE and the current contractor and any future contractor to allow for a smooth transition between administrations. At the beginning of the contract, the successful bidder will receive from the current contractor, including, but not limited to, all reports and electronic data files, applications and supporting documentation, and other materials developed for the California Assessment System, including test blueprints and item specifications for any assessments under development. At the end of the contract, the successful bidder must deliver to the future contractor all required materials, including, but not limited to, reports and electronic data files, applications and supporting documentation, and other materials developed for the California Assessment System, including test blueprints and item specifications for any assessments under development, on a schedule to be determined by the CDE. The successful bidder must also provide staff as needed to work with the next contractor and establish regular meetings during any overlap of contracts.

The submission must provide detailed processes for system maintenance, operations, and transition that include the required components described below:

- How the successful bidder will maintain and operate the system during the contractual period when the system is partially and fully in production.

- How ownership and responsibility of the system will be formally transferred to the successor contractor at the end of the contract engagement.

- The knowledge-transfer activities that the successful bidder will create to assist state technical staff in understanding, operating, and maintaining the new system.

- The knowledge-transfer activities that the successful bidder will create to assist help desk staff as necessary for providing support to system users.

- How equipment, configurations, software, and data stores will be transitioned into the successor contractor’s production environment.

- Processes for documenting and approving contingency plans for all significant risks.

- Coordination activities with the hosting provider that provides a clear definition of data center responsibilities and tasks.

- How computer-based and paper-pencil tests will be developed and made available in the system by July 1, 2032.

- The successful bidder will need to continue to support the CAASPP and ELPAC until the contract ends.

- The process for an orderly closeout of the contract, to include, at a minimum, the following areas:

  - Archiving of project materials

  - Business processes and system migration

  - Event debriefings

  - Preparation of a final report, to include lessons learned and an analysis of project objectives achieved

  - Transfer of application operations and maintenance to the successor contractor

  - Transfer of all tools and licenses and related data needed to maintain the system

  - Delivery of current system and supporting documentation, including, but not limited to, all deliverables specified in the contract

  - Transfer of supporting project data to the State, including change requests, help desk requests, issues, and risks

  - Support of the migration of business and technical processes and procedures to the State or its designee through knowledge transfer as approved by the CDE Contract Monitor

The successful bidder and any subcontractors must plan and budget for all costs for staff to attend all required transition meetings.

### 7.2 TASK 2 – PROGRAM SUPPORT SERVICES

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 2 and must provide a description of the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge of the subjects and skills necessary to successfully complete the project as stated in Task 2.

The successful bidder must adhere to the Approval and Certification Process as stated in RFS Section 7.1.6.A for generating and delivering required reports/deliverables.

#### 7.2.1 Coordinators

The submission must provide a detailed process for the management and maintenance of superintendent and LEA coordinator designation form(s). The plan must describe and demonstrate in detail how the bidder will carry out the following:

- Request that the superintendent of each LEA designate an LEA CAASPP Coordinator, on or before July 1, and LEA ELPAC Coordinator, on or before April 1, as required by the testing regulations (5 CCR Section 857: LEA CAASPP Coordinator; and 5 CCR Section 11518.40: LEA ELPAC Coordinator) and submit the designation forms electronically. Either the superintendent or the designated LEA CAASPP or LEA ELPAC Coordinator may authorize one or more other employees of the LEA to perform the duties of the LEA CAASPP or LEA ELPAC Coordinator.

- Collect and input updates/changes to the LEA CAASPP and LEA ELPAC coordinator designation information throughout the year.

- Follow up via email and telephone as necessary with LEAs that have not returned their designation forms and security agreements and provide the CDE with an updated list of outstanding forms on a regular basis until all forms are completed from all LEAs.

- Automatically designate an LEA superintendent or charter school administrator as the LEA coordinator if one is not selected by an LEA by the deadline.

- Provide LEAs and site coordinators with the Test Security Agreement Form for LEA and test site coordinators.

- Provide the LEA coordinator with a username and temporary password to access an administration management system (refer to RFS Section 7.2.2.) upon receipt of the Test Security Agreement Form and LEA Coordinator Designation Form.

- Require that the LEA coordinators sign a Test Security Affidavit and Test Security Agreement and obtain a signed Test Security Agreement and signed Test Security Affidavit from each test site ELPAC coordinator.

- Require that all the LEA coordinators obtain signed Test Security Affidavits from all test examiners, proctors, and scribes as well as from any other LEA and school staff who will have access to the test materials, either on paper or electronically.

- Require that the signed agreements and affidavits be kept on file at the LEA office or electronically in an administration management system.

- Provide LEAs with a report of all security forms and affidavits that were submitted.

For more information regarding the role of the CAASPP or ELPAC coordinator and CAASPP or ELPAC test security agreement documents, refer to 5 CCR sections 850–864 for CAASPP and 5 CCR Section 11518.50 for ELPAC. Regulations that have been formally adopted, approved, and filed with the Secretary of State are posted at https://govt.westlaw.com/calregs/.

#### 7.2.2 Administration Management System

The submission must describe a detailed process to create and maintain a secure web-based administration management system that restricts access to certain tasks on the basis of designated roles. The submission must describe and demonstrate in detail how the management system will restrict access and, if applicable, how the management system will integrate with the TDS outlined in RFS Section 7.3. The successful bidder will provide support to LEAs to carry out the following:

- Establish LEA testing windows for each LEA as determined by state regulations and set their planned testing dates (not applicable to ELPAC or CAA for Science).

- Submit orders for special testing materials including, but not limited to, braille and large-print tests for registered students.

- Manage and track LEA requests for rescores and appeals, as allowable by state regulations, using a system for LEAs to report any test security incidents. Refer to RFS Section 7.6.9 for more information about rescores and to RFS Section 7.5.3.B for more information about appeals.

- Allow secure access to the LEA results reporting website. (Refer to RFS Section 7.6.3.)

- Allow secure access to secure materials for test administration, such as the Directions for Administration, scoring guides, and audio for testing.

- Create a dashboard that illustrates an overview of test administration metrics, as dependent on user role (site coordinator, LEA coordinator, state user, technical assistance center [TAC] staff).

#### 7.2.3 Technical Assistance Center

The submission must describe procedures for the operation of a tiered customer TAC dedicated solely to the California Assessment System. The submission must describe and demonstrate in detail how technical assistance will be provided to more than 2,000 LEAs. The TAC staff must respond to questions regarding the administration of CAASPP and ELPAC. The submission must describe a comprehensive TAC and address how it will fulfill the minimum system requirements outlined in RFS Appendix A as well as the following:

- Provide dedicated staff to support each assessment region (i.e., dedicated only to CAASPP and ELPAC) to respond to questions and concerns between 7 a.m. and 5 p.m. Pacific standard time (PST), Monday through Friday, except on designated California school holidays as specified in EC Section 37220(a).

- Provide web chat, toll-free telephone, maintenance, continuous updates, and monitoring to virtual assistance. All messages left during regular working hours and before 3 p.m. PST must be returned the same working day. After-hour messages received after 3 p.m. PST the prior day must be responded to by 9 a.m. PST the next working day.

- Provide a dedicated email address and a dedicated representative for each assessment region to respond to all emails received prior to 3 p.m. PST with a substantive response (i.e., not just an acknowledgement) within two hours of receipt during normal business hours. After-hour email messages and those received after 3 p.m. PST the prior day must be responded to by 9 a.m. PST the next working day. Provide sufficient staff to meet the requirements above.

- Respond to inquiries from subcontractors, other contractors, and CDE staff within two business hours. In addition, respond to CDE questions outside of TAC normal working hours on request.

- Provide a single point of contact to coordinate with the CDE and the Smarter Balanced contractor on critical Smarter Balanced issues (e.g., Tier 3 Support issues).

- Provide a process to ensure that staff respond to routine questions with CDE-approved answers (using the CDE approval process outlined in RFS Section 7.1.6).

- Describe the contact management system that will be used to log communications by date, name, contact information as well as summarize comments, complaints, questions and actions taken relating to LEAs.

- Describe the technology (e.g., database, phone system) that will be used by TAC staff to effectively track and respond to LEA requests.

RFS Table 6 shows the different tiers of support that the various entities will provide for each component of the CAASPP System and ELPAC System. Bidders using proprietary systems/components will need to provide all tiers of help desk service for that system/component. For example, the bidder will need to provide Tier 1 and 2 supports for Tools for Teachers but Smarter Balanced will supply Tier 3 support for that component.

Table 6. Provider of Help Desk Support, by Component and Tier

| Component | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Test Delivery System | Bidder | Bidder | Bidder |
| Summative test—paper (special test versions, braille and large print) administration | Bidder | Not applicable | Not applicable |
| Data warehouse and reporting | Bidder | Bidder | Smarter Balanced for Smarter Balanced data warehouse and reporting and bidder for non-Smarter Balanced warehouse and reporting |
| Tools for Teachers | Bidder | Bidder | Smarter Balanced |
| Single sign-on | Bidder | Bidder | Bidder |

The submission must describe, in detail, an approach to customer support and help desk service that provides for a unified, single point of contact for school, LEA, and state staff to obtain information regarding a variety of CAASPP- and ELPAC-related inquiries including, but not limited to, ordering of materials, material deliveries and retrieval, technical guidance for computer-based test administration, score report deliveries, and implementation of procedures in the event of security breaches. The submission must describe and demonstrate tiered support, defined as follows:

- A help desk solution that includes Tier 1, Tier 2, and Tier 3 services; however, Smarter Balanced will provide Tier 3 support for some components (refer to RFS Table 6). The submission must describe the training and technical expertise requirements of the staff that provide each of the support tiers.

- Tier 1 support must offer the first line of customer support, addressing basic customer issues (e.g., general inquiries, nontechnical questions, password recovery, website navigation assistance, basic procedural “how-to” questions). In general, Tier 1 support will provide information that can be found in manuals, with questions needing answers not found in manuals (generally more technical in nature) going to Tier 2. That is, issues not resolved by Tier 1 support must automatically be sent to Tier 2, which is to offer more in-depth technical support than Tier 1.

- Tier 2 support staff are technicians who can assist with common mid-level technical questions, such as local system setup, local network issues, or compliance with data and interoperability standards as well as the application of technical solutions to issues that have established resolution methods.

- Tier 3 support requires the greatest level of technical expertise to address the most complex technical problems. Tier 3 issues are handled by systems engineers and other technical experts and may require multiple interactions with the customer before the issue is resolved. These issues are bugs in the system that prevent a student from completing a valid test or otherwise prevent a user from accessing the system (e.g., producing student score). These are not enhancement requests or changes that consist of style or preference.

The submission must describe in detail how staff will provide Tier 1, Tier 2, and Tier 3 support and are knowledgeable about and trained on the California Assessment System. At a minimum, the submission must acknowledge that staff are regularly trained to perform and support LEAs with topics including, but not limited to: installing secure browsers; provisioning educator user accounts, including logins and passwords; implementing technology and procedures for computer-adaptive test administration; administering computer-based tests, materials, and processes. In addition, the submission must describe in detail the bidder’s ability to assist LEA coordinators and technology coordinators with issues related but not limited to: operating systems, software installation, and network configuration. The submission must also describe in detail how the bidder will ensure that staff are providing LEAs with excellent customer service and technical knowledge.

The submission must describe procedures to develop and maintain a weekly log (or daily, during peak usage, as requested by the CDE) of customer concerns for the CDE’s use in preparing reports and performing analytics.

The log must include a compilation of details such as volume of phone calls, emails, and chats by day or by week, the nature of services (e.g., tiered support, escalation from tiers, category/nature of call), date of contact, name and location of the person who initiated contact, and nature and date of resolution provided. The content and format of the reports must be approved by the CDE in accordance with RFS Section 7.1.5.

#### 7.2.4 Student Accessibility Tool

The submission must describe and demonstrate in detail a process for the annual customization of a web-based student accessibility tool specific to California (inclusive of all assessments in the CAASPP System and ELPAC System) and consistent with the Smarter Balanced Individual Student Assessment Accessibility Profile (ISAAP). The CDE owns the current student accessibility tool. The new contractor will need to update the web-based student accessibility tool. The student accessibility tool for California must be user-friendly to assist teachers, IEP teams, or other designated staff in identifying appropriate and available accessibility resources inclusive of universal tools, designated supports, and accommodations. The student accessibility tool for California must provide an innovative solution for the efficient importing of student test settings into the TDS either directly, or indirectly via the registration system.

The student accessibility tool for California must be consistent with:

- The Smarter Balanced Usability, Accessibility, and Accommodations Guidelines (UAAG) at https://portal.smarterbalanced.org/library/en/usability-accessibility-and-accommodations-guidelines.pdf,

- The current California Assessment Accessibility Resources Matrix at https://www.caaspp-elpac.org/s/docs/CA-Accessibility-Matrix-25-26.docx, and

- The Accessibility Guide at https://ca-toms-help.ets.org/accessibility-guide.

The tool must be able to provide an output consistent with the Student Access Data File described in the minimum system requirements in RFS Appendix A. (The Smarter Balanced ISAAP tool can be found on the Smarter Balanced web page at https://isaap.smarterbalanced.org/). The submission must describe how the student accessibility tool for California will be updated for Smarter Balanced and non-Smarter Balanced assessments, on an annual basis, to reflect the most current applicable accessibility resources across the California Assessment System.

#### 7.2.5 Internet Resource Sites

The submission must describe in detail the development of procedures for hosting and maintaining a website for LEA coordinators and the public. (Note: The current contractor will provide the successful bidder with the https://www.caaspp-elpac.org website during the contract transition period. The website must conform to the CDE design standards and comply with federal Section 508 accessibility, style, content, and application standards as specified in the CDE’s Web, Document, and Accessibility Standards located at https://www.cde.ca.gov/re/di/ws/webstandards.asp. The procedures must allow a period for the CDE and the CDE Web Application Review Team (WebART) to review and approve the website annually and must detail how concerns documented by WebART will be addressed.

The websites will be a portal to assessment technical and administrative resources and materials for use by LEAs and the public. New documents or information proposed for posting must adhere to the requirements in RFS Section 7.1.5 and must first be approved by the CDE in accordance with RFS Section 7.1.6.A. All documents on the website must remain available, either as current resources or archived documents, until the CDE approves their removal.

The submission must describe the development and maintenance of a website that provides the public with access to the following:

- Nonsecure versions of manuals, forms, brochures, and other reference documents and web pages that provide information regarding the administration of the assessments in the California Assessment System

- All announcements and news updates, webcasts and in-person workshops, and any other related information regarding the California Assessment System

- Training materials for test administrators to prepare for computer-based test administrations by demonstrating the testing format and the procedures for preparing for, and administering, computer-based tests

- All testing applications (e.g., secure browser) related to CAASPP and ELPAC assessments

- Regularly updated frequently asked questions (FAQs)

- Links to practice and training tests and related materials and resources

- A link to the assessment management system

- Emergency notifications (e.g., TDS is offline or other system issues) and a list of known issues and the resolution status/date of each

- Links to parent/guardian resources necessary for test administration

- Links to educator resources and online tools in support of the California Assessment System (e.g., Smarter Content Explorer, Interim Assessment Item Portal, Smarter Annotated Response Tool, Tools for Teachers, Interim Assessment Lookup Tool, Test Results for California Assessments)

The submission must detail a process to conduct focus groups to obtain feedback regarding the website and must include feedback from LEAs, the public, and other stakeholders. The feedback must be delivered to the CDE in the form of an annual report, which must include descriptions of the ways in which the information derived from the focus groups will be used to make improvements to the CAASPP and ELPAC websites.

#### 7.2.6 Trainings

The submission must describe a detailed process for developing and delivering training workshops, presentations, and videos as well as ensuring CDE approval as required in RFS Section 7.1.6. The trainings must account for all California Assessment System and program needs.

In accordance with any recommendation(s) or order(s) contained in a Governor’s executive order, an advisory or order of the California Department of Public Health, or an advisory or order of a county health department with authority over the area in which this contract is to be performed or an advisory or order of a law enforcement authority, the in-person meetings or trainings may be cancelled or changed to a virtual meeting at the discretion of the CDE. Therefore, any announcement for the event must state that the event may be in-person, virtual, or both. The CDE cannot reimburse the Contractor for any cancellation fees, deposit or pre-payments under any circumstances, even if the CDE decides to cancel the event. This applies to all in-person meetings mentioned in this RFS.

##### 7.2.6.A Workshops and Presentations

The submission must provide a training plan that includes workshops and presentations, at a minimum. The plan must provide a detailed outline of no fewer than 50 interactive workshops and no fewer than 50 informational presentations to be offered in a manner that allows for the participation of LEA staff across California over the span of the contract.

The requirements for the methodology, materials, and planning process detailed in the outline are as follows:

- Methodology. In addition to identifying the workshop or presentation title, type, purpose, audience, location(s), room layout and capacity, duration, and so forth, the outline must describe the methodology to be used (refer to RFS Table 7). This description may include the specific media to be used for each workshop or presentation and can include, but not be limited to, in-person, videoconferencing, web-based streaming of videos, or other conferencing techniques. The outline must include a proposed timeline for these deliverables and identify the staff, and any subcontractors, required to produce media and conduct the workshops and presentations.

- Materials. The outline must include descriptions of any materials to be used in the presentation for each of the workshops and presentations. These materials must be made available to LEA participants at no cost for professional learning and, when necessary, training LEA staff locally. Materials may include, but are not limited to, PowerPoint presentations, electronic documents, printed materials, and recordings of web-based trainings. Presentations developed specifically for, or that may be interpreted as valid to include in, the training of trainers of LEA staff must include presentation talking points at the time of posting.

- Planning process. The planning process for each workshop and presentation must include an intake meeting and sufficient planning meetings to create an outline for the presentation and content for the PowerPoint slide deck. The process must include a detailed plan to provide access to workshops and presentations for various stakeholders and LEA participants throughout the state.

Workshop and presentation presenters, and all associated materials, must adhere to the requirements in RFS Section 7.1.5 and must be approved by the CDE in accordance with RFS Section 7.1.6.A. Materials for the workshops and presentations must be posted on the CAASPP and ELPAC website maintained by the successful bidder so participants can download them before the presentation of the workshop. All online workshops, presentations, and materials must be archived and posted for later viewing.

##### 7.2.6.B Additional Trainings

The submission must describe and demonstrate the development and delivery of additional trainings each year on topics based on LEA need or updates to be determined in consultation with and approved by the CDE. Topics for the trainings may include, but are not limited to, use of the administration management systems; use of the TDS; testing of students with disabilities (including the use of accessibility tools for California and online braille administration); administration of interim assessments; use of a teacher hand scoring system; use of CERS; or preparing LEA CAASPP and ELPAC coordinators to plan for administration and interpret and use test results.

Participants must be provided with a method of electronically submitting questions to the presenters during the training. Presenters, and all associated materials, must adhere to the requirements in RFS Section 7.1.5 and must be approved by the CDE in accordance with RFS Section 7.1.6.A. Materials for trainings must be posted on the CAASPP or ELPAC website before the training for use and download. All trainings and materials must be archived and posted for later viewing.

The successful bidder must assume responsibility for all costs associated with these trainings and for making all arrangements, including locations and equipment. Costs include, but are not limited to, training materials, conference rooms, videoconferencing facilities, and equipment detailed in RFS Table 7. The successful bidder will not be responsible for travel, lodging, per diem, and substitute costs for attendees or for costs associated with attendees who are outside observers or CDE staff.

##### 7.2.6.C Videos

The submission must describe, in detail, a plan for reviewing, and maintaining or updating existing videos and the development, production, and distribution of new videos according to program needs.

Priority of new videos will include the following:

- Accessibility resource videos when accessibility resources are added or updated to show how each resource works in the TDS. Administration and scoring training videos for the Initial and Summative ELPAC and the Initial and Summative Alternate ELPAC. The updates must reflect changes in test content and administration for the Initial ELPAC, Summative ELPAC, and Alternate ELPAC. The training videos must be of a length that ensures the standardization of the administration of the ELPAC and Alternate ELPAC; they must include, but not be limited to, audio and video samples of student responses that align with test content.

Videos must be developed using a professional video producer(s), technical staff, and equipment (e.g., cameraperson, sound specialist, teleprompter, etc.) as well as a professional presenter(s). The video producer(s) must have at least thirty-six months of experience producing similar types of training videos.

The videos will be produced in English and another language (e.g., Spanish) as determined by the CDE, if necessary. Videos must meet all accessibility requirements in RFS Section 7.1.5, including closed captioning in both versions, with accompanying scripts in English and Spanish (PDF versions tagged in English and Spanish for accessibility). The submission must ensure that the bidder will make these videos available through both streaming and download. The videos must be posted on a nonsecure web page of the CAASPP & ELPAC website so LEA staff and the general public can access them.

The submission must ensure that all videos and accompanying scripts will be annually updated as needed to reflect changes in test administration, including any necessary recording of accompanying student responses. The successful bidder must obtain any and all permissions required for recording purposes.

Table 7. Training Planning Tool—Sample Entries

| Training Title | Science Academy | Security Webinar |
| --- | --- | --- |
| Type | In-person | Webinar |
| Purpose | Professional development (PD) | Training |
| Audience | Teachers | Coordinators |
| Location(s) | 1. Sacramento area 2. Fresno area 3. Anaheim area | On-line |
| Room Layout | 8-person round tables with podium | Zoom meeting with breakout rooms |
| Number of Days Per Location | 2 days | 1.5 hours |
| Total Number of Training Days | 6 | 1 |
| Number of Attendees Per Location | 250 | 2,000 |
| Total Training Capacity | 750 | 2,000 |

#### 7.2.7 Local Assessments: Interim Assessments and Formative Assessment Tools

In California, interim assessments and formative assessment tools must be accessible to all LEAs. The submission must describe and demonstrate program services to support LEAs with the administration of all CAASPP and ELPAC interim assessments and the use of formative assessment tools, including the Tools for Teachers website. EC Section 60642.6 requires the CDE to acquire, and offer at no cost to LEAs, interim assessments and formative assessment tools, as provided through its membership in the Smarter Balanced Assessment Consortium. In addition, the CDE provides interim assessments for CAST and ELPAC (developed by the current California Assessment System contractor) as well as formative assessment resources in Tools for Teachers for CAST and ELPAC (developed through the current Assessment Validity and Outreach contract).

##### 7.2.7.A Interim Assessments

The submission must describe and demonstrate in detail a process to provide outreach to LEAs and schools on the use of the Smarter Balanced, CAST, and ELPAC interim assessments. The interim assessments must be available year-round through the end of the contract.

The submission must outline a plan to collaborate with the CDE and Smarter Balanced Assessment Consortium in the development or customization of already existing materials including, but not necessarily limited to the following:

- A system user’s guide that fully details the functionality of the online assessment system for a user in an LEA

- Scoring guides that fully detail how to score items; for example, performance task and constructed-response items

- A system infrastructure guide that details the minimum and recommended technical specifications and configurations needed to successfully access the California Assessment Delivery System

- A system training workbook (i.e., a collection of quick reference guides) that provides step-by-step details for completing the most commonly performed tasks in each component of the California Assessment Delivery System, including the administration, test delivery, scoring, and reporting of results

- Tutorial videos that provide step-by-step details for completing commonly performed tasks in each component of the California Assessment Delivery System, including test settings, test administration, the Security and Test Administration Incident Reporting System, and other processes important to test coordinators and administrators.

##### 7.2.7.B Formative Assessment Resources—Tools for Teachers

The submission must describe and demonstrate in detail procedures to support the use of formative assessment tools and resources in the Smarter Balanced Tools for Teachers website at https://smartertoolsforteachers.org/, including procedures for establishing accounts individually and by group and using the website to support the planning and implementation of classroom instruction. All K–12 educators and administrators employed by an LEA may have access to the Tools for Teachers website. The procedures must describe outreach to LEAs and schools on the use of Tools for Teachers.

The submission must describe and demonstrate in detail how the bidder will support the development and incorporation into Tools for Teachers of instructional and professional learning resources for all assessments within the California Assessment System. Currently, Tools for Teachers has instructional resources developed for ELA, mathematics, and science. Additionally, there are professional learning resources that support various topics, including ELPAC.

##### 7.2.7.C Item Bank of Released Science Test Questions

The submission must describe and demonstrate in detail how the bidder will develop and maintain a site that shares released CAST test questions with educators. The site must include a system for searching and filtering items by grade level or grade band, standard or performance expectation, domain, claim, target, or dimension, and item type. The submission must ensure that educators will be able to choose individual items to create classroom assessments. The site must include keys, rubrics, and exemplars but would not be required to score assessments.

#### 7.2.8 Data-Driven Improvement

The submission must plan to have a process to collect data and information from various activities (e.g., website use, testing procedures, in-person and virtual workshops) that occur throughout this contract and must analyze and use that information to improve the California Assessment System and provide increased customer service to LEAs, schools, and other stakeholders. The submission must ensure that the bidder will submit this analysis to the CDE on an annual basis. The submission must describe how the bidder will solicit and incorporate feedback from the CDE when developing content designed to elicit feedback from stakeholders and LEA staff participating in CDE events. The submission must include how the feedback and related data will be used to improve outreach and support. The submission must detail the following:

- How information on the registration and attendance at various workshops, webcasts, and other trainings will be used to provide targeted assistance to LEAs and how the data will be used to effectively address patterns such as low participation.

- How information collected in various ways (e.g., focus groups, TAC inquiries, surveys, and webcast questions) from LEAs and other stakeholders will be used to improve the support provided to LEAs and the CDE (e.g., produce documents on FAQs or make website improvements to reduce TAC inquiries).

- How the bidder will use information to provide targeted technical assistance to LEAs, including how LEAs will be provided with support specific to their unique situation (e.g., LEA with low bandwidth, LEA with large paper-pencil orders, infrequent use of the interim assessments).

- How the bidder will analyze information to identify patterns of need and provide targeted outreach and assistance in anticipation of issues or concerns from LEAs, schools, or the CDE.

### 7.3 TASK 3 – TECHNOLOGY SERVICES

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 3 and must provide a description of the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge of the subjects and skills necessary to successfully complete the project as stated in Task 3.

The successful bidder must adhere to the Approval and Certification Process as stated in RFS Section 7.1.6.A for generating and delivering required reports/deliverables.

The submission must describe and demonstrate an assessment delivery system that is designed with a highly scalable architecture to support the delivery of computer-based CAASPP and ELPAC summative assessments to approximately 10,000 schools and more than 4.2 million students in more than 2,000 LEAs statewide that will use a wide variety of online testing devices (e.g., desktop computers, laptop computers, tablets). In addition, more than 14 million administrations of the interim assessments are anticipated each school year.

#### 7.3.1 California Assessment System Long-Term Technology Plan

In 2016, the Smarter Balanced Technical Hosting Solution project, which implemented an assessment infrastructure for the CAASPP assessments, was completed. Subsequently, EC Section 60602.6 was revised to require that all “California computer-based assessments utilize the infrastructure and hosting platform outlined in the Smarter Balanced Technical Hosting Solution, as approved by the Department of Technology for the statewide pupil assessment system.” In November 2018, the ELPAC assessments were moved onto the same platform. The infrastructure continues to be expanded and improved to support additional assessments and has become the California Assessment System.

The comprehensive assessment technology infrastructure is the unique network of software and programs that manage assessment production, registration, delivery, data storage and reporting, and educator resources. The California Assessment Delivery System contains a series of integrated modules that appear to users as a single, integrated system. Once logged in, users can navigate between the various components of the system securely without having to use additional logon credentials.

The system has five major components: access management, test administration, test delivery, scoring, and reporting. Although originally designed for the Smarter Balanced ELA and mathematics assessments, California has expanded the use of the infrastructure to support the development and implementation of non-Smarter Balanced tests and continues to refresh tests with new items on an annual basis.

As the CDE has expanded its assessments and assessment resources, there has been greater and more frequent use of operational and reporting systems by California educators. Rather than using assessment systems seasonally, simply for test registration and ordering, the assessment system provides valuable reporting and resources that educators can use more frequently to inform classroom instruction. The need for technology solutions to evolve along with the expansion of the assessments is significant and will require innovative solutions to meet California’s needs.

The continuous improvement of California’s infrastructure to support assessments beyond those produced by Smarter Balanced provides opportunities to enhance the technology platform, where all CAASPP and ELPAC assessments will be managed, administered, scored, and reported. This system will allow for the stability of the infrastructure even when California changes assessment contractors.

#### 7.3.2 California Assessment Delivery System

The submission must describe a technology hosting solution that supports the implementation of the California Assessment System components (described below) to support the delivery of the Smarter Balanced assessments (both interim and summative) and all other CAASPP and ELPAC computer-based tests.

The submission must describe in detail how the successful bidder will support these assessments using secure technology solutions and tools to address the following functions:

- Item authoring. A tool for the creation of new assessment items and the management of the workflow involved in reviewing the items, specifying and creating accessibility resources, and approving them for use.

- Item bank and test packager. A storage service that maintains the collection of assessment items for CAASPP and ELPAC, including metadata that indicates the academic standards with which the items are aligned, item difficulty calibration data, item use and exposure data, and so forth. This component includes test authoring and a test packager that collects a test definition and a set of assessment items in a test version/package for use within an assessment delivery system.

- Test administration system (TAS). An automated system that handles the operations needed to administer assessments in California. Functions within this system will include:

  - Management of the registration of students for tests

  - Creation and management of testing windows for California LEAs

  - Integrated data sharing with existing system components

- Test Delivery System (TDS). A technology platform that delivers computer-based test items to student test-takers (accessed by a secure browser) and stores student responses for scoring. (Note that students may utilize the assistance of their test examiner to interface with the TDS.) It is preferable that the item bank and test packager be closely integrated with the TDS.

- Secure browser. The TDS must be accessible to students through the California-designated secure browser. This is a special web browser that provides a secure testing environment that limits student access to authorized applications for the duration of the test and facilitates the use of accessibility resources.

- Scoring system. An automated solution that allows for the machine scoring of computer-based items, constructed-response items, and AI scoring. Other additional uses of technology to support the validity and reliability of the assessments should be described.

- Public reporting system. An automated solution that provides the capabilities of public reporting and parent/guardian reporting.

- CERS. A data warehouse and reporting system that acts as a comprehensive storehouse of all California student test results and includes a system to generate reports on or extracts of that data. CERS is the California-specific instance of the Smarter Balanced Assessment Consortium’s Smarter Reporting System and is the one-stop-shop for housing and accessing California’s historical and future test results for CAASPP and ELPAC summative and interim assessments. CERS is a restricted-access website for California educators and LEA and school administrators to find test results for individual students and student groups.

- An automated access management system that includes an access management function, security features, system monitoring and alerting, and management statistics.

##### 7.3.2.A System Requirements

The submission must include a detailed description of the California Assessment Delivery System inclusive of Smarter Balanced (summative and interim) and non-Smarter Balanced components and how they integrate to provide the services required. The description must include information on whether each of the technology components is currently in use and whether the component will require additional functionality before it can meet all California requirements. If the component will require additional functionality to meet all California requirements, the submission must describe in detail the additional functionality that is needed.

The submission must acknowledge and ensure adherence to the minimum system requirements in RFS Appendix A and Appendix B and include a schedule and method for conducting joint requirement sessions. The sessions must be conducted in person in Sacramento, California, unless otherwise approved by the CDE. The submission must include a schedule and plan for working jointly with the CDE and other stakeholders (i.e., joint requirement sessions) to finalize and document detailed business, functional, and technical requirements, as necessary, that support the California Assessment System within 15 working days of the contract start date. The submission must indicate how periodic modifications to the minimum system requirements to incorporate system enhancements and fixes will be accomplished and documented. (Note: All modifications to the minimum system requirements require the prior approval of the CDE.) All system requirements must be stored in an industry-standard requirements tool, to be approved by the CDE, and CDE staff must be given access to the tool for the purpose of reviewing and managing all requirements related to the California Assessment System.

The following have been identified as the components within the overall infrastructure of the California Assessment System:

- A secure access management system

- A secure test administration system

- A secure TDS serving an automated test item bank

- A secure scoring system

- A reporting system to support public reporting and parent/guardian reporting

- Integration with CERS

The submission must include a detailed description of the technology solutions proposed for these components and how they integrate to provide the services required. The submission must indicate if any adaptations must be made to the proposed system for it to fully meet California’s minimum requirements.

The submission must include a description of the solution that integrates fully with the existing CERS already in place. The CDE will provide the bidder with the opportunity to test integration with this existing system during the transition period.

The submission must include detailed information about each of the components proposed and how they meet the minimum system requirements in RFS Appendix A and Appendix B.

###### 7.3.2.A.1 Item Authoring Tool

The submission must describe in detail how the bidder will provide an automated tool for the development of new test items. Test items must be in a format that is compatible with CAASPP and ELPAC item specifications.

###### 7.3.2.A.2 Item Bank

The submission must describe in detail how the bidder will provide an automated storage solution for retaining the test items and allowing CDE-authorized staff access to them.

###### 7.3.2.A.3 Access Management System

The submission must describe in detail how the bidder will provide a solution for the California access management system. This system must have the ability to be accessed by statewide users through the use of a secure logon process. A copy of the current user identification information and associated roles and permissions will be provided to the successful bidder. User roles and associated permissions will be transmitted electronically from the access management system component to all other components of the California Assessment System. The submission must acknowledge adherence to the access management system minimum system requirements are included in RFS Appendix A.

###### 7.3.2.A.4 Test Administration System

The submission must describe in detail how the bidder will provide a test administration system that supports the following automated functions:

- User management

- Registration of students

- Student-level data files

- Demographic snapshot

- Ordering paper tests

- Packaging and logistics

The submission must acknowledge adherence to the detailed minimum system requirements for each of these system functions are included in RFS Appendix A.

###### 7.3.2.A.5 Test Delivery System

The submission must describe in detail how the bidder will provide an automated TDS. The TDS will deliver test items to students from the test bank. These items must render properly on the screen and be accessible by students using the CDE secure browser(s). The successful bidder must annually review the TDS, provide results of the review to the CDE, and prioritize enhancements based on evidence gathered to improve the system.

In addition, the submission must indicate how the proposed TDS will meet the minimum system requirements in RFS Appendix A for the following:

- Electronic student response files

- User experience

- Release management

- System Implementation

###### 7.3.2.A.6 Scoring

The submission must describe in detail how the bidder will provide an automated scoring solution. Results must be captured by the TDS, and then be scored by this system component. After the scores are calculated, there must be an integrated approach to sharing this data with the existing CERS. The bidder must propose a scoring solution that addresses the following:

- Interim assessment scoring

- Summative assessment scoring

- Hand scoring

- Automated scoring

###### 7.3.2.A.7 Public Reporting

The submission must describe in detail how the bidder will provide a reporting solution that allows for the presentation of data for use by the public. Reports must be compatible in format and be available for access through the existing system.

###### 7.3.2.A.8 Parent/Guardian Reporting

The submission must describe in detail how the bidder will provide a reporting solution that allows for the provision of student performance information to parents/guardians. Reports must be compatible in format and be available for access through a cloud-based solution or through integration with student information system vendors.

###### 7.3.2.A.9 Integration with CALPADS and CERS

The submission must describe in detail how the bidder will provide a solution that allows for transfer of data to and from CALPADS. The solution must also allow for transfer of data to CERS. Reports must be compatible in format and be available for access through the existing systems. Specifications for interfacing with CALPADS and CERS are included in RFS Appendix A and Appendix B.

California is a member of the Smarter Balanced Assessment Consortium, and Smarter Balanced developed CERS as the California instance of the Smarter Reporting System. The submission must acknowledge the requirement to work with the Smarter Balanced Assessment Consortium for the reporting of all CAASPP and ELPAC summative and interim assessment results that are housed in CERS as well as for the ongoing maintenance and development of CERS.

The submission must acknowledge that the successful bidder will work with Smarter Balanced to develop and implement a plan for the ongoing evaluation and maintenance of CERS and prioritize enhancements based on evidence gathered to improve the system. In addition, the submission must acknowledge that CERS will continue to meet the minimum system requirements in RFS Appendix B.

##### 7.3.2.B System Architecture

The submission must describe, in detail, a physical and logical architecture that supports the components of the California Assessment Delivery System that can accommodate the maximum number of expected concurrent users for both interim and summative assessments and is compliant with the minimum system requirements in RFS Appendix A. The submission must include both system physical and logical architecture diagrams that include an overview of system architecture—data center locations, high-level network topology—and major hardware and software components and their physical and logical connections. The submission also must include all required integrations with external hardware and software systems (e.g., CERS, CALPADS, LEA systems/networks).

The submission must describe a detailed process for modifying the system architecture documentation (inclusive of the list of system configurations) as changes to the architecture, system requirements, or configurations are made to ensure that these documents are kept current at all times.

In addition, the submission must include a description of how the bidder will develop and maintain an asset inventory of all system components containing information, including but not limited to, the asset name, a unique asset ID number, asset type (screen, report, process, etc.), creation date, version number, most recent date updated, frequency of review/update, and associated/dependent inventory items. The system asset listing must be kept current at all times.

###### 7.3.2.B.1 Interface Requirements

The submission must describe and demonstrate an integrated California Assessment System compliant with the minimum system requirements in RFS Appendix A. The submission must address the various components within the architecture and describe how the system components are coupled to provide enhanced functions that allow for seamless user experiences. In addition, the submission must include the capability of implementing the components for the delivery of non-Smarter Balanced computer-based tests that are integrated with the Smarter Balanced system components, as appropriate.

- Interface with CALPADS for daily downloads of statewide student and organizational entities (e.g., LEAs and schools) data

- Interface with CALPADS for the automated updating of English Language Acquisition Status (ELAS) status

7.3.2.B.1.a California Educator Reporting System

The submission must demonstrate, in detail, how the California Assessment Delivery System will support the reporting of results for all CAASPP and ELPAC summative and interim assessments in CERS. The submission must describe how the California Assessment Delivery System will interface with Smarter Balanced for the exchange of student assessment information.

7.3.2.B.1.b CALPADS

The CDE will provide a daily electronic file to the successful bidder from CALPADS containing information for all enrolled students. The submission must describe a detailed process for identifying new and changed data to be added to or updated on a daily basis as described in the minimum system requirements in RFS Appendix A.

The submission must include a detailed process of how the California Assessment System will accept a list of schools and associated LEAs provided by the CDE, determine the differential, and process the new, updated, or deleted schools and LEAs in the test registration component on a daily basis.

The submission must also describe bidder’s reporting solution that allows for the transfer of data to CALPADS. The process must ensure that the California Assessment System will produce and provide to the CDE, on a daily basis, electronic student data files containing test results and other information for consumption by and incorporation into CALPADS.

7.3.2.B.1.c LEA System Compatibility

The submission must describe the procedure of how the California Assessment System will accept and process an import file for student embedded and non-embedded designated supports and accommodations (Student Access Data File). The submission must also provide a web-based user interface to update designated supports and accommodations for individual students separately for both the summative and interim assessments. Specifically, the procedure must describe how the LEA will use the same process, file layout, and data definitions for identifying the Smarter Balanced test designated supports and accommodations as well as non-Smarter Balanced test designated supports and accommodations. The test registration component must allow LEA-level users to access, select, and export student data for all schools in their LEA.

###### 7.3.2.B.2 Data Security

The submission must include a detailed data security plan consistent with the minimum system requirements found in RFS Appendix A to ensure data security within the hosting environment that follows the National Institute of Standards and Technology Special Publication 800-18 rev 1, available at https://csrc.nist.gov/pubs/sp/800/18/r1/final.

In addition, the data security plan must provide a detailed description of how the system will meet each of the security requirements specified in RFS Appendix A as well as any additional data security measures to be used. The submission must describe the procedure to be in place on how to report security incidents in the event of a data security breach, with steps to take to help mitigate damage.

The submission must describe the capacity of the proposed access management system component to provide for numerous and complex user roles and permissions. The submission must propose user roles and permissions and provide a plan and schedule for those roles and permissions to be finalized in joint requirement sessions within 15 working days of the contract start date.

###### 7.3.2.B.3 System Development Process

The submission must describe and demonstrate the system development method, consistent with the minimum system requirements found in RFS Appendix A, to be utilized in the development and delivery of computer-based assessments, including the following:

- Design process

- Development and testing process, including User Acceptance Testing (UAT)

- Validation process—independent validation and verification

- Implementation process—field tests, pilots

The system must provide real-time progress reporting of aggregate test administration information to appropriate stakeholders at various levels according to permissions. The specifications of the progress reporting are to be finalized during joint requirement sessions but may include such information as the number of tests scheduled (by date or session and test type), number of tests being administered, number of tests completed, and number of scoreable tests completed.

The submission must describe in detail how the bidder will develop system/functional, integration, and UAT plans that describe, at a minimum, the roles and responsibilities, scope, phases, schedule, reporting, pass-fail criteria, data and metrics, test cases, approach, and defect management process. The submission must also acknowledge and ensure that the bidder will provide automated test environment(s) for each system test phase as well as test data. The bidder must provide functional testing, including test environment(s), test data, and test requirements/feature coverage.

The submission must describe in detail how the bidder will conduct UAT for all LEA-facing online systems maintained through this contract. In addition, the submission must describe in detail how the bidder will coordinate and support CDE staff in all CDE UAT activities by providing a UAT environment that directly imitates the production environment, provides appropriate test data, stores test scripts, relates testing to requirements, and allows for the capture and tracking of UAT issues using Jira, the CDE’s chosen UAT management tool.

The submission must ensure that the UAT conducted by the bidder must precede the UAT conducted by CDE.

The submission must ensure that the system will have the capability to:

- Allow for the administration of assessments both in person and remotely.

- Allow all students to review their answers for certain sections or sets of questions before moving on to the next section or completing the exam.

- Create unique test session IDs that ensure a secure test administration.

- Allow for functionality to process approved appeals (i.e., test reset, invalidation, reopen, and restore).

- Have controls to prevent a student from prematurely exiting an assessment or from being inadvertently exited from an assessment.

- Default to human voice when both human and machine voice options are available as a feature of accessibility supports, tools, or accommodations.

- Save student responses to selected response items (both linked to common stimuli and not) upon selection by the student.

- Save student responses to constructed-response items and technology-enhanced items (e.g., drag & drop, graphing).

- Have the ability to limit interim assessment use (i.e., restrict interim assessment use) within one hour of having received direction from the CDE to do so.

- Allow test administrators to start, stop, pause, and resume a test session.

- Allow test administrators to monitor student progress during testing (in-person or remote administration). The monitoring capability must include, but not be limited to, test administrators’ ability to determine which item a student is currently working on without showing the item or student response.

- Provide a user interface (accessible to user roles consistent with those established during joint requirement sessions) to activate and deactivate accessibility tools, designated supports, and accommodations. The activations and deactivations via the user interface must be made prior to a student taking a test and must be immediately available to the student once they begin testing.

- Retain previously saved student responses when a test is paused or restarted.

- Save student responses and end the test session when no activity has occurred on the test for a specified period established during joint requirement sessions.

For the interim assessments only, the submission must ensure that the Assessment Delivery System will have the capability to:

- Allow for out-of-level testing (i.e., administration of tests that are not consistent with the student’s enrolled grade).

- Allow an unlimited number of interim assessment blocks (IABs), focused IABs, CAST interim assessments, and ELPAC interim assessments to be administered to any one student.

- Allow no more than three administrations of any ICA per student per school year.

- Allow test administrators to specify a limited set (number) of questions for testing.

- Provide item-level results for display in CERS for all applicable item types. Item-level results include, but are not limited to, key and distractor analysis, student responses to items, and writing extended response scores.

###### 7.3.2.B.4 System Implementation

The submission must describe and demonstrate a process for system implementation. In addition, the process must describe, in detail, how the bidder will develop a system implementation plan that includes the required components described in the minimum system requirements found in RFS Appendices A and B.

The submission must describe in detail how the bidder will develop a System Implementation Plan that describes how the California Assessment System will be implemented, installed, and transitioned to an operational system. The plan must include, at a minimum, an overview of the hosting system, an implementation schedule, a description of the major tasks, security features, performance monitoring tools and techniques, a list of resources required, a description of the process for validating the success of the implementation, and the acceptance process. This plan must specifically include activities that are expected from the CDE as well as those of the outgoing (i.e., current) contractor.

###### 7.3.2.B.5 User Experience

The submission must describe and demonstrate how the integrated California Assessment System will conform to the interface and user-experience minimum system requirements in RFS Appendix A. The submission must address the various components of the California Assessment System architecture and describe how the system components are coupled to give enhanced functionality that provides for a seamless user experience. In addition, the description must include the capability of implementing the components for the delivery of non-Smarter Balanced computer-based tests that are integrated with the Smarter Balanced system components, as appropriate.

The submission must ensure that the California Assessment System technology platform will be presented as a cohesive, single system with a single sign-on and seamless navigation. The single sign-on must directly integrate with the Smarter Balanced single sign-on (inclusive of Tools for Teachers and CERS).

The submission must ensure that system will adhere to industry best practice user interface standards and use industry best practice user interface controls in accordance with the supported end-user devices (e.g., W3C, Microsoft). The submission must ensure that the California Assessment System will also comply with all applicable accessibility standards set forth in California GC Section 11135 as well as policy set forth in the CDE Web Accessibility Standards, located at https://www.cde.ca.gov/re/di/ws/accessibility2017.asp.

The submission must ensure that the system will provide online, context-sensitive help for each class of user. Help components must include context-sensitive help for key terms, page-level help for each screen, and access to an online manual from within the application. Each specific help component must be considered a system asset and be tracked according to a unique asset number and description and is subject to all version control requirements described for system assets.

The submission must ensure that the user interfaces (both administrator and student) of the system will be identical except for required deviations due to differences between Smarter Balanced and non-Smarter Balanced tests (e.g., skip-item functionality would be available only on non-Smarter Balanced tests) and must conform to a consistent look and feel for each class of user for all components of the system, including Smarter Balanced and non-Smarter Balanced components.

###### 7.3.2.B.6 System Release Management

The submission must describe and demonstrate the process for delivery release management consistent with the minimum system requirements found in RFS Appendix A. The process should include an annual release schedule. In addition, the process must include a detailed description of how the bidder will develop a system release management plan inclusive of all the components outlined in the minimum system requirements.

The submission must ensure that the bidder’s system release management plan will include, at a minimum, the scope, roles and responsibilities, release management approach and method, inputs, system outage management, and descriptions of release types and artifacts. The plan must also include the processes and procedures for communications with internal and external partners; for performing scheduled and unscheduled releases; for system delivery acceptance; for production readiness, deployment, and validation; for release testing; and for solution maintenance and upgrade.

###### 7.3.2.B.7 Performance

The submission must describe and demonstrate a detailed, comprehensive performance testing procedure to support the performance expectations consistent with the minimum system requirements found in RFS Appendix A. The procedure must describe a detailed process to conduct performance testing annually, consistent with the minimum system requirements in RFS Appendix A and a detailed process to develop a detailed system functional test plan and system performance test for CDE approval. The procedure must address the requirement to work with the CDE to provide any performance testing procedures as well as the results of performance tests. The procedure must address how the bidder will work collaboratively with the CDE Contract Monitor to resolve any issues with regard to system performance and performance testing.

The submission must describe and demonstrate a process for the bidder to conduct, in coordination with LEA staff, system benchmark testing at a mutually agreed-upon number of schools. The submission must ensure that these benchmark tests will determine the level of compatibility of the testing site with the California Assessment System and must occur at various times throughout a normal school day to gain a realistic sense of system performance under a variety of conditions. The submission must ensure that the factors to be examined during TDS benchmark testing must include, at a minimum, bandwidth speeds (download and upload); latency between test items; browser used; screen resolution; testing device performance, including response metrics, such as average response time and peak response time; error rate; and volume metrics, such as concurrent users, requests per second, and throughout. The process must describe and demonstrate a plan to provide a system benchmark testing report that includes recommendations describing the work that is necessary to bring the system into compliance with the requirements. The submission must ensure that the benchmark tests will be scheduled and coordinated with CDE staff, including the CDE Contract Monitor.

The submission must include a list of the performance testing metrics that will be measured, which eventually will be filled with values.

###### 7.3.2.B.8 Disaster Recovery and Business Continuity

The submission must provide a detailed process that addresses the resumption of services after disaster occurrences in the hosting environment (e.g., server failure, loss of internet connectivity, data corruption) as well as the testing site (e.g., loss of internet connectivity). In addition, the process must describe the development of a detailed disaster recovery and business continuity plan that meets the minimum system requirements found in RFS Appendix A.

###### 7.3.2.B.9 Data Policy Retention and Destruction

The submission must provide a detailed procedure for data retention and destruction consistent with the minimum system requirements found in RFS Appendix A.

###### 7.3.2.B.10 Maintenance and Operations

The submission must describe the development of a detailed maintenance and operations plan that meets the minimum system requirements found in RFS Appendices A and B. The submission must provide detailed processes for system maintenance and operations that include the required components described below.

- How the bidder will maintain and operate the system during the contractual period when the system is partially and fully in production

- Coordination activities with the hosting provider that provide a clear definition of data center responsibilities and tasks

- Version control activities to manage production software

- Regular updates to system documentation

- A description of any required system downtimes, including purpose, timing, systems affected, and length of interruptions

- System monitoring activities

- System alerts

#### 7.3.3 System Enhancements

The submission must include a proposed system change management process for the bidder to address the need for ongoing system enhancements. This process must utilize a formal change request process capable of responding to system changes that arise from the following five sources:

- Problem reports that identify bugs that must be fixed, which form the most common source

- System enhancement requests from users

- Events in the development of other systems

- Changes in underlying structure and/or standards (e.g., in software development, this could be a new operating system)

- Changes in regulations or departmental policies

This submission must ensure that the process will work in an integrated way with the system release management process described in RFS Section 7.3.2.B.6.

### 7.4 TASK 4 – ASSESSMENT DEVELOPMENT AND ACCESSIBILITY

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 4 and must provide a description of the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge of the subjects and skills necessary to successfully complete the project as stated in Task 4.

The successful bidder must adhere to the Approval and Certification Process, as stated in RFS Section 7.1.6.A, for generating and delivering required deliverables.

#### 7.4.1 Assessment Design and Development

The submission must describe in detail the bidder’s knowledge of the subjects and skills necessary to successfully provide for the maintenance of current assessments and new development based on SBE-approved CAASPP and ELPAC summative or interim test designs and blueprints. This includes the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC. See RFS Table1.

The submission must describe in detail the design and development procedures to:

- Refresh and maintain the current practice and training tests for the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC. Development of items for use on these tests needs to complete the same new item development process as the summative assessment, including field test statistics.

- Produce and administer new interim assessments for the ELPAC to provide grade span assessments parallel to those for each domain of the summative ELPAC. Development of items to be field tested on the Summative ELPAC could be used to support new interim assessments once there is a sufficient number of items in the operational bank. Summative ELPAC test blueprints are located at https://www.cde.ca.gov/ta/tg/ep/documents/elpacsummativebluprt.pdf.

- Produce and administer performance tasks to support an innovative system for statewide summative science assessment.

The procedures will include the following:

- Conduct an initial analysis of how each standard (for the grades, content, and practices to be assessed) could be assessed in terms of item/task type and depth of knowledge to support test and item/task development experts.

- Conduct pilot testing and cognitive labs to support science assessment innovation development in accordance with an SBE-approved framework.

- Develop content specifications (claims, inferences, and evidence) for the tests, item/task development criteria, and sample item/task sets. Specifications are intended to support the development of test blueprints and test specifications.

- Develop item and task specifications to ensure that the items and tasks measure the adopted standards and ensure consistency across item/task writers and editors.

- Develop or propose edits to test specifications and blueprints that define test form components (number of items/tasks, breadth and depth of content coverage) necessary to consistently build valid and reliable test forms that reflect emphasis of adopted content standards.

- Determine appropriate item formats for each test (e.g., selected-response, constructed-response [short/extended], technology-enhanced, performance tasks, etc.).

- Research and explore innovative accessible item types that allow students to interact more fully with the assessment to show what they know and can do.

- Research, explore, and develop appropriate performance task formats to improve science assessment (e.g., student centered, curriculum embedded, formative, interactive, collaborative, etc.).

- Develop a TDS that allows for individualization, collaboration, and student-centered assessment.

- Develop and administer a multistage adaptive test to provide more specific scoring information for students. Provide all documentation for and support submissions of federal assessment peer review, as needed.

For each new assessment to be developed or current assessment to be maintained and improved, the submission must describe a comprehensive process to complete the activities for ongoing development and administration of the test, both computer- and paper-based, as defined in this RFS. The process must provide details of the assessment development process for each of these test formats. The submission must provide the details of how technology will be utilized or integrated in all of these activities, as appropriate.

The submission must ensure that all aspects of item development, review, field testing, and use will adhere to universal design principles for large-scale assessments as well as the Standards for Educational and Psychological Testing.

#### 7.4.2 Item and Task Development

The submission must describe and provide a detailed plan for developing, reviewing, and evaluating items and performance tasks for computer-based tests for the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC (including the Initial, Summative, and Alternate). The plan must include:

- CAASPP and ELPAC item counts are provided in RFS Appendix C. The tables display the number of operational items by content and grade by item type and the number of items available for field testing by content, grade, and item type that will be available to build test forms for the 2027–28 administration.

The submission must include information on developing and reviewing new items that reflects the bidder’s knowledge of all aspects of item design and item characteristics. This includes steps taken to maximize the number of items that will have the full complement of accessibility resources for each assessment and a process for twinning items that are not accessible to all populations.

The submission must ensure that the item and task development process will describe and demonstrate the following:

- Create an annual item development plan, with detailed schedules for each assessment.

- Contract for commissioned and authentic reading passages, stimuli, and phenomena.

  - Reading passages and items should be originally produced in the language they are being presented in.

  - Listening passages and items should be recorded by using a balanced approach of both AI and authentic human voices from native language speakers, based on the language being presented and the grade level being assessed.

- Process used to select and compensate California educators for development work (i.e., item review, and data review) and provide professional development to educators.

- Develop items to be administered by computer. Computer-based test items must be coded to comply with IMS Accessible Portable Item Protocol (APIP) and Question and Test Interoperability (QTI) standards for accessibility (or any other parallel or higher standards).

- Develop scoring rubrics for all test items.

- Review and edit the items internally for cognitive complexity (e.g., depth of knowledge [DOK]), linguistic complexity, alignment with standards/assessment targets, and bias and sensitivity; and prepare accessibility of items (e.g., identify and define terms for glossing, produce the translation of items and glossed terms to Spanish for the dual language designated support, and identify and prepare twinned items for items that are not accessible as originally written).

- Provide a secure online system to submit items to the CDE and capture CDE reviewers’ comments and ratings, using the mutually agreed upon criteria that will be used by educator content review panels for evaluation of the items (e.g., item content, bias and sensitivity, and accessibility).

- Conduct review meetings with California educators for content, bias and sensitivity, and accessibility. Describe a process for reporting educator ratings and comments and reconciling reviewed items with the CDE.

- Obtain final approval of the items from the CDE using mutually agreed upon criteria to be used for evaluation of the items.

- Embed field test items annually in operational forms.

- Conduct data review meetings of all flagged items, (for example, Differential Item Functioning [DIF]), with California educators.

##### 7.4.2.A Item Resting, Refresh, and Release Rates

The submission must describe and provide detailed plans for resting items, refreshing items, and releasing items for each of the non-Smarter Balanced assessments: the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC (including the Initial, Summative, and Alternate). The plans must include:

- Rules for resting items (i.e., temporary removal of the item from the operational cycle for a designated period of time that is mutually agreed upon by both the bidder and the CDE)

- Rules for retiring items (i.e., permanent removal of the item from the operational cycle; such items can be designated for use on practice and training tests, interim assessments or on a sample item and performance task bank website)

- Rules for refreshing assessment item banks to replace resting and retired items. Refresh refers to completely replacing items in a test form with a rested item or field test item.

The submission must provide a recommended approach, with a rationale that identifies the percentage of operational items to be reused annually. The plans must describe the reason and the date the items were rested or refreshed so that the status of each item is clear. The plans must describe how the bidder will provide an annual report of items available for release.

RFS Tables 8 and 9 document the current approach for the bidder to refer to in their submission.

Table 8. Annual CAASPP Item Rested, Refreshed, and Released Rates

| Assessment | Percentage of Operational Items to Be Rested1 | Percentage of Operational Items to Be Refreshed2 | Percentage of Operational Items to Be Released3 |
| --- | --- | --- | --- |
| CAA for ELA | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% |
| CAA for Mathematics | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% | Routing block = 20% Tier 1 = 20% Tier 2 = 20% Tier 3 = 10% |
| CAST Stand-alone 26–32 items 3 PTs | Stand-alone items = 20% 2 PTs | Stand-alone items = 20% 2 PTs | Stand-alone items = 20% 2 PT |
| CAA for Science | 3 PTs | 3 PTs | 2 PTs |
| CSA | Grades 3–8 = 20% High School = 50% | Grades 3–8 = 20% High School = 50% | Grades 3–8 = 10% High School = 20% |

1Resting rate = the percentage of items that are not used operationally for a period of one year before being reused.

2Refresh rate = the percentage of items replaced in an operational form each year.

3Release rate = the percentage of items released to the public each year through training and practice tests or through the sample items performance task web page.

Table 9. Annual ELPAC Item Rested, Refreshed, and Released Rates

| Assessment | Percentage of Operational Items to Be Rested1 | Percentage of Operational Items to Be Refreshed2 | Percentage of Operational Items to Be Released3 |
| --- | --- | --- | --- |
| Initial ELPAC | N/A | Refresh all tests within 4 years | N/A |
| Summative ELPAC | Items can be reused after 3 years resting | Over 4 domains = 30% | Refresh 20% of the practice test with released items over 2 years |
| Alternate ELPAC | Items can be reused after 3 years of resting | Over 4 domains = 30% | Refresh 20% of the practice with released Items over 3 years |

1Resting rate = the percentage of items that are not used operationally for a period of four years before being reused.

2Refresh rate = the percentage of items replaced in an operational form each year.

3Release rate = the percentage of items released to the public each year through training and practice tests or through the sample items performance task web page.

##### 7.4.2.B Embedded Field Test Items

The submission must provide a process for embedding field test items in the operational forms. In addition, the bidder will adhere to the requirements outlined in RFS Sections 7.4.6, and 7.6.2. The submission must propose a plan to maintain the equilibrium of the item bank for the life of the contract for each of the non-Smarter Balanced assessments: the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC (including the Initial, Summative, and Alternate).

The process must include the following criteria:

- Load and review test items in the TDS. Conduct UAT for all items, including accessibility supports.

- Conduct an item analysis and psychometric data review for the field test items. The data review must include the criteria to evaluate the field test items.

- Develop a plan to maximize field test items with accessibility resources (e.g., dual language, glossary, braille).

- Provide administration materials for embedded field test items.

- Provide field test training, binders, and videos for the ELPAC Speaking domain, showing student sample responses based on embedded field test items.

- Provide a description of the embedded field test administration, the embedded field test item scoring process, including range finding, human and AI scoring of constructed response items, and the psychometric and data review of the embedded field test items.

The following are specific requirements that must be addressed in the submission for the individual CAASPP assessments:

- For the Smarter Balanced Summative Assessments for ELA and mathematics, the bidder should anticipate including three to five field test items or one field test performance task in the operational computer-based tests to support ongoing test development activities.

- For the CAAs for ELA and mathematics, the submission must describe in detail how the bidder will develop a plan to ensure that embedded field test items are aligned with the California Common Core State Standards (CA CCSS) core content connectors (CCCs) and are appropriate to build the depth and breadth of the item bank and maintain a multistage adaptive test that follows the SBE-approved blueprint.

- For the CAST, the submission must describe in detail how the bidder will develop a plan to ensure that embedded field test items are appropriate to build the depth and breadth of the item bank and implement and maintain a multistage adaptive test that follows the SBE-approved blueprint. All performance expectations must be assessed over the course of three administration cycles. In addition, the bidder must acknowledge its commitment to the support of future assessment innovations that may apply to the CAST to provide authentic student assessment in science.

- For the CAA Science, the submission must describe in detail how the bidder will develop a plan to ensure that all CA NGSS core content connectors (CA NGSS connectors)-aligned embedded performance tasks that are developed follow the SBE-approved blueprint. All CA NGSS connectors identified in the SBE-approved blueprint must be assessed over the course of five years. The embedded field test performance tasks consist of a set of 15 items aligned with three CA NGSS connectors. These items must account for the cognitive complexity of skills by assigning items within the embedded performance task to low, medium, and high complexity. Each set of items per connector is preceded by a related orienting activity. This assessment is delivered online and administered one on one. The bidder will develop sufficient numbers of embedded performance tasks that will result in an item bank that prioritizes coverage of the SBE-approved blueprint.

- For the CSA, the submission must describe in detail how the bidder will develop a plan to ensure that embedded field test items are appropriate to build the depth and breadth of the item bank that follows the SBE-approved blueprint.

The following are specific requirements that must be addressed in the submission for the ELPAC assessments:

- For the Summative and Initial ELPAC, the submission must describe in detail how the bidder will develop a plan to ensure that embedded field test items are appropriate to build the depth and breadth of the item bank that follows the SBE-approved blueprint.

- For the Summative Alternate ELPAC, the submission must describe in detail how the bidder will develop a plan to ensure that embedded field test items are appropriate to build the depth and breadth of the item bank that follows the SBE-approved blueprint.

##### 7.4.2.C Test Form Construction

The submission must include a detailed description and process for the design and construction—for the 2028–29, 2029–30, 2030–31, 2031–32 and 2032–33 administration years—of paper and computer-based test forms for the assessments identified in RFS Table 10. Although all tests are computer-based, paper versions will continue to be needed for any the following:

- ELPAC K–2 Writing (all eligible students)

- Students with IEPs or Section 504 plans indicating the students cannot access the computer-based tests and require braille, large print, or regular print accommodations

- Schools that experience unexpected, temporary technology issues that are beyond the schools’ control that prevent online testing for an extended period

For the CAAs for ELA, mathematics, and science, there are two versions per grade. There will be one Initial Alternate ELPAC form and two Summative Alternate ELPAC forms (with field test items embedded) per grade and grade span.

Generally, test forms have been assigned at the LEA level, except in the case of the largest LEAs. The CDE expects that all field test items be administered to a representative subset of the population. CDE expects the contractor to propose a design for allocation of test forms as part of the planning process for test administration.

Table 10. Required Test Types by Assessment

| Assessment | Computer-Based Test | Paper Test |
| --- | --- | --- |
| Smarter Balanced ELA and Mathematics | Yes | Braille, Large Print, Regular Print (only for students with IEPs and/or 504 Plans who cannot access the online test or for long-term technical issues) |
| CAAs for ELA and Mathematics | Yes | None |
| CAST | Yes | Braille, Large Print, Regular Print (only for students with IEPs and/or 504 Plans who cannot access the online test or for long-term technical issues) |
| CAA for Science | Yes | None |
| CSA | Yes | None |
| Summative ELPAC | Yes | K–2 Writing (all eligible students), Braille, Large Print, and Regular Print (only for students with IEPs and/or 504 Plans who cannot access the online test or for long-term technical issues) |
| Initial ELPAC | Yes | K–2 Writing (all eligible students), Braille, Large Print, and Regular Print (only for students with IEPs and/or 504 Plans who cannot access the online test or for long-term technical issues) |
| Summative Alternate ELPAC | Yes | None |
| Initial Alternate ELPAC | Yes | None |

RFS tables 11 through 14 provide the number of paper and special forms ordered by assessment program in 2023–24.

Table 11. Number of Special Form Paper-Pencil Tests Ordered by Grade and Test Form Type for 2023–24 Smarter Balanced Summative Assessments for ELA and Mathematics

| Test Form | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 11 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ELA Braille | 8 | 3 | 8 | 13 | 3 | 8 | 4 |
| ELA Large Print | 9 | 16 | 12 | 9 | 5 | 8 | 3 |
| ELA Regular Print | 5 | 3 | 2 | 6 | 4 | 5 | 4 |
| Mathematics Braille | 8 | 3 | 8 | 14 | 3 | 8 | 4 |
| Mathematics Large Print | 9 | 16 | 12 | 9 | 5 | 8 | 3 |
| Mathematics Regular Print | 5 | 3 | 2 | 6 | 4 | 5 | 4 |

Table 12. Number of Special Form Paper-Pencil Tests Ordered by Grade and Test Form Type for 2023–24 California Science Test

| Test Form | Grade 5 | Grade 8 | High School |
| --- | --- | --- | --- |
| Braille | 8 | 13 | 7 |
| Large Print | 13 | 11 | 3 |
| Regular Print | 1 | 8 | 3 |

Table 13. Number of Special Form Paper-Pencil Tests Ordered by Grade/Grade Span and Test Form Type for 2023–24 Summative ELPAC

| Test Form | K* | Grade 1* | Grade 2* | Grades 3–5 | Grades 6–8 | Grades 9–10 | Grades 11–12 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Braille | 5 | 4 | 0 | 5 | 7 | 2 | 0 |
| Large Print | 10 | 3 | 5 | 3 | 3 | 0 | 0 |
| Regular Print | 0 | 1 | 0 | 5 | 2 | 1 | 1 |

*All eligible students in K–2 receive the Summative ELPAC Writing domain test as paper-pencil tests; therefore, the counts for the required K–2 Writing tests are not included in this table. The counts included in this table for these grades are for the counts of special forms for all four domains.

Table 14. Number of Special Form Paper-Pencil Tests Ordered by Grade/Grade Span and Test Form Type of 2023–24 Initial ELPAC

| Test Form | K | Grade 1 Writing Only | Grade 2 Writing Only | Grades 3–5 | Grades 6–8 | Grades 9–12 |
| --- | --- | --- | --- | --- | --- | --- |
| Braille | 14 | 10 | 10 | 0 | 0 | 1 |
| Large Print | 11 | 10 | 11 | 0 | 0 | 0 |
| Regular Print | 0 | 0 | 0 | 0 | 0 | 0 |

For CSA, the estimated test takers are based on the 2023–24 test taker counts in the Test Results for California’s Assessment website at https://caaspp-elpac.cde.ca.gov/caaspp/. The CDE anticipates an overall increase of 5,000 per year once testing circumstances return to normal and new testing components are added. There are no paper-pencil tests for CSA.

Braille code types are dependent on the assessment. For a sample of braille code types by assessment, please refer to the 2024–25 CAASPP ELPAC Accessibility Guide at: https://ca-toms-help.ets.org/accessibility-guide/requirements-for-visual-impairment/testing-students-requiring-braille/.

The submission must acknowledge that test forms for one additional administration must be provided to the subsequent California Assessment System contractor. Test forms must be developed by August 2032, with the exception of the Initial ELPAC and Initial Alternate ELPAC, which must be ready by March 2032 for administration on July 1, 2032, and the CAA for Science, which must be developed by May 2032 for administration beginning early September 2032.

Initial and Summative ELPAC K–2 students use a Writing Answer Book (paper test). Summative ELPAC Answer Books are returned to the contractor to be scored. Initial ELPAC Answer Books are scored locally based on rubrics and results are entered into a data entry interface or teacher hand scoring system depending on grade level or grade span. In addition, 10 percent of LEAs are selected annually to submit their student’s completed Initial ELPAC Answer Books for back scoring to produce item statistics for technical reports and provide targeted training or improvements to future administrations. As for the local scoring, LEAs are trained on how to score the writing prompts during the Administration and Scoring Training. Test Examiners are required to complete calibration quizzes (on a training platform) annually prior to administering the Speaking and Writing domains.

The submission must include the following requirements:

- Test forms must conform to the SBE-approved blueprints and adhere to the relevant content standards. Test forms are to be reviewed for key runs and clueing among items/performance tasks, including embedded field test items/performance tasks, and are to be evaluated for overall content, range of difficulty of items, and diversity of subject matter and approach as well as socioeconomic status, multicultural, and gender representation. Test forms must comply with universal design principles.

- How the bidder will explain the content and psychometric criteria used for item/performance task selection. The submission must also ensure that the test forms are assembled in accordance with the SBE-approved test design and psychometrically sound criteria.

- Describe a procedure for ensuring that the test length and composition reflect the SBE-approved blueprints and CDE-approved specifications and that they align with the relevant content standards.

- Describe the software and item selection process used for creating operational forms. The description must include the following:

- The criteria used for selecting anchor items and items/performance tasks through the use of classical item and item response theory (IRT) statistics; matching target test characteristics, test information, and test standard error curves; meeting content requirements and constraints; using statistics such as b-values, p-values, scoring reliability statistics, and point-biserial and polyserial correlations; using the SBE-approved blueprints; and using the complexity of the test items.

- An internal plan for the rotation of SBE-approved content standards on the assessments over time, as required by the SBE-approved blueprints. The plan must be designed to maintain a high degree of accuracy in the longitudinal test results across test forms.

- For CAASPP, a plan to provide for year-to-year comparability of scaled scores and achievement levels; for ELPAC, the plan must provide for year-to-year comparability of scaled scores and performance levels, including the development of vertically linked scales suitable for the measurement of student growth, where appropriate. The bidder is responsible for ensuring the integrity of retaining the existing vertical scale.

- Procedures for linking and equating test forms to maintain the integrity of the test scale over time.

- A process for selecting embedded field test items for CDE review and approval.

- A plan to ensure that the tests will include test items/performance tasks of differing levels of difficulty and DOK.

- Procedures and technical criteria used to maximize comparability of results from computer-administered and accessible test forms (e.g., braille) to inform the interpretation and use of scores. The submission must acknowledge that the results of the comparability study must be provided annually to the CDE.

Field test items must be embedded in all ELPAC forms, except Form 1, and placed with operational items of the same test component. The location of field test items may shift in different assessment editions as more or fewer items might need to be field-tested for different test components. For example, if the item bank shows that many items for certain task types have undesirable statistics, the bidder will be required to target that area during item development and field-test those items in the upcoming school year. Additionally, depending on need to refresh practice or training tests or develop new interims, the bidder will need to determine item development needs on an annual basis.

All test forms must adhere to the SBE-approved blueprints for each assessment. In addition, all test forms for the CAST must adhere to the three-year testing plan for the CAST, and all test forms for the CAA for Science must adhere to the five-year testing plan for the CAA for Science.

##### 7.4.2.D ELPAC Answer Books

The submission must describe, in sufficient detail, the process that will be used to annually review and revise the answer books. The submission must acknowledge and ensure that the bidder understands that the bidder is responsible for processing all paper-pencil answer books submitted for all administrations. This section of the submission must address, in detail, the following requirements:

- Answer books. All answer books for the Summative ELPAC must be returned to the bidder by LEAs for official scoring on a schedule determined by the CDE. Ten percent of the answer books for the Initial ELPAC will be returned to the potential contactor for analysis, as described in RFS Section 7.4.2.C.

- Demographic pages. All answer books that are returned to the potential contractor for scoring must have fillable student demographic pages as part of one document and must be scannable.

- Demographic data fields. The answer book must contain space to collect demographic and other data not collected by CALPADS or necessary for matching with CALPADS as well as information collected at the time of testing (e.g., date testing completed).

- Unique identifiers. Each answer book must have a Scannable Unique Identifier that is easily accessible. For purposes of security, the submission must describe a system for maintaining an up-to-date inventory of answer books at all times.

- Space for written responses. Answer books must provide sufficient space for responses to constructed-response items and notification made in the examiner’s manual that responses outside this space will not be scored.

- Annual update. The submission must describe in sufficient detail the process for the production of a new answer book for each school year during the contract period and the camera-ready forms for the transition year to the next contract. The same answer book must be used throughout the Initial and Summative ELPAC windows each school year during the contract period.

- Header sheets. The submission must acknowledge and ensure that header sheets are cover sheets submitted with completed answer books to organize test materials for processing by the bidder. Scannable header sheets must be produced for LEAs to batch answer books by grade. Header sheets must either be preprinted with LEA-identifying information, including county/district/school (CDS) code and LEA name, or a space must be provided for the LEA to fill in (i.e., using a grid format) such information.

#### 7.4.3 Standard Setting

The submission must describe in detail how the bidder will provide the CDE with a sound and defensible standard setting process, if needed. The submission must describe how the bidder will collaborate with the CDE and, as appropriate, with the TAG to provide the necessary plans and materials for approval. The submission must describe how the bidder will deliver reports in a timely manner to gain input from the CDE and the California public prior to the SBE’s approval. The submission must describe how the bidder will conduct the following standard setting activities for any new assessment development:

- Develop general Achievement Level Descriptors (ALDs) or Performance Level Descriptors (PLDs).

- Develop grade- or grade-span and content-specific descriptors, hereafter referred to as range ALDs or range PLDs.

- Recruit California educators with appropriate experience for range ALD or range PLD meetings and for standard setting.

- Develop reporting ALDs for use on score reports.

- Prepare data and materials and conduct standard setting.

- Develop technical reports on the standard setting.

- Prepare collateral materials such as introductory language and ALDs and PLDs in web-friendly formats that may be used to communicate with stakeholders. This includes a single ALD document for each assessment that provides information on the process used to develop ALDs and the purpose of the general ALDs, content and grade-specific range ALDs, and reporting ALDs.

#### 7.4.4 Test Administration System Familiarization

In order to provide opportunities for students, test administrators, test examiners, and other LEA staff to become familiar with the test content, TDS, and other related infrastructure used in the test administration process, the submission must describe how the bidder will continue to maintain and update practice and training tests for the CAASPP and ELPAC summative assessments. The current CAASPP and ELPAC Practice and Training Tests website can be accessed at https://www.caaspp-elpac.org/resources/preparation/practice-and-training-tests.

Training tests include small sets of sample test questions that allow students and test administrators to learn how to interact with the different item types, available accessibility features, and test administration instructions. Training tests are not necessarily grade-specific nor are they available as full-length tests. Practice tests generally mirror a full-length test and include a range of grade-level content. Like the training tests, practice tests include the available accessibility features and test delivery functionality. The submission must describe how the bidder will create scoring guides with rubric information for practice tests for use in local scoring.

The submission must describe how the bidder will ensure that updates to the practice and training tests will be reviewed and approved annually. Any new updates to be included in the upcoming test administration year must be approved by the CDE in accordance with the processes outlined in RFS Section 7.1.6. For the Smarter Balanced assessments, the bidder will work with Smarter Balanced to obtain access to the latest practice test and training test materials.

#### 7.4.5 User-Friendly Informational Content

The submission must describe how the bidder will collaborate and work with the CDE and Smarter Balanced to update and provide user-friendly information, accessible to parents/guardians, about each assessment in the California Assessment System. The materials will be interactive, easy to access and understand, and published on the CAASPP Starting Smarter website at https://ca.startingsmarter.org/ and the ELPAC Starting Smarter website at https://elpac.startingsmarter.org/.

#### 7.4.6 Analysis of Test Results

The submission must describe the proposed psychometric procedures and analyses to ensure that each computer-based test is aligned with the SBE-approved content standards and provide accurate, reliable, and valid scores. All developed assessments are subject to the same item- and test-level analyses specified for computer-based tests (refer to RFS Section 7.6.2). In addition, the submission must include a plan, which will be reviewed annually, that describes the scoring, scaling, and equating procedures that will ensure the comparability of test scores for the life of the contract.

The submission must describe the process used to conduct the analyses of field test items. All field-tested items must undergo the same analyses as those defined in the item analyses (refer to RFS Section 7.6.2). The analyses for statistical adequacy and the results of these analyses must be reported to the CDE.

The submission must acknowledge that within six weeks after conducting the analyses of field-test items, the bidder will deliver a report to the CDE containing, at a minimum, an analysis of each item as it appeared when it was field-tested, the standard to which the item is linked; the item key; IRT item statistics; DIF statistics; and, for each answer option, the classical item statistics, including the proportion responding correctly, and the point-biserial and polyserial correlations. The CDE will then have a minimum of 15 working days to review this report and provide feedback. The submission must describe how the bidder will facilitate a review of any items identified for statistical anomalies by a panel of California educators, as well as accessibility or group-level experts as needed. The CDE must approve each field-tested item before it can be used as an operational item.

#### 7.4.7 Item Banks

For the Smarter Balanced assessments, items are stored in the Smarter Balanced item bank. Smarter Balanced items will be packaged and delivered in test packages to the bidder from Smarter Balanced.

For the non-Smarter Balanced assessments, that is the CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC, the submission must describe and demonstrate that the bidder will provide a secure item bank that will serve as a repository for all non-Smarter Balanced items, their associated information (metadata), rubrics, scripts (as needed), and the functionality needed for test development tasks along with the item statistics required for item evaluation and test construction. The item bank will include the items from all of the CDE’s non-Smarter Balanced assessments used for CAASPP and ELPAC.

The submission must ensure and describe a procedure and process for the CDE, in real time, to access and review the following:

- Newly developed items

- Operational items

- Anchor items

- Stimuli, such as orienting activities, simulations, or reading passages

- Items designated for field testing

- Items, by accessibility tools

- Current item usage and status

- Current and historical item statistics

- All other items irrespective of status

All reading passages, set leaders and stimuli, orienting activities, artwork, stems, distractors, form identifiers, item keys, and scoring rubrics must be included in the item bank. All copyright permissions must be provided along with the date of expiration, if any, for usage. All copyright permissions must be reviewed and expiration dates reported to the CDE.

The item bank must follow the IMS APIP (https://www.imsglobal.org/apip/index.html), such that the contents of the item bank allow for the transition of the items to the subsequent contractor at the end of the contract period. The transfer of items must include the associated item metadata (e.g., translations, tools, supports) to maintain the functionality of the item and all item statistics linked to the item. The item bank must be delivered to the CDE within five days of request. All California Assessment System items of the item bank must be prepared and delivered, pending a transition, to the new contractor in 2032.

##### 7.4.7.A Item Bank of Test Questions Available for Educator Use

The submission must describe and demonstrate a process for K–12 California educators to access and use a site that allows test administration using released non-Smarter Balanced CAASPP and ELPAC items. This includes items that are on practice tests, training tests, and interim assessments. The site must include a system for searching and filtering items by grade level or grade band, standard or performance expectation, claim, target, or dimension, and item type (for example, constructed response) to choose individual items to combine into classroom assessments. The process also must provide rubrics and resources for educators to conduct the hand scoring of constructed-response items, including linking to the existing online hand scoring system, or provide automated scoring of constructed-response items. In addition, the plan must describe, in detail, how educators will be trained to interpret results, that is that scores from assessments created from the item bank are not scaled or comparable to interim or summative assessment scores. In addition, the submission must include a process to report raw scores to educators through a scoring key for hand scoring, dashboard, downloadable file, or other means.

For ELA and math interim assessments, the CDE uses the Interim Assessment Item Portal (IAIP) provided by the Smarter Balanced Assessment Consortium.

#### 7.4.8 Activities in Support of Future Assessment Development

The submission must acknowledge its commitment to the research, exploration, and support of future assessment development activities and innovations that may expand and improve the California Assessment System as directed by the SBE or should a need arise through legislative action or funding.

#### 7.4.9 Accessibility

The ESSA requires that all students (including students with disabilities and English learners) be tested with an assessment of state-adopted standards. To ensure that test results are a fair and accurate reflection of each student’s achievement, the submission must describe in detail how the test administration system will provide accessibility for all students. For this to be achieved, students must have access to appropriate accessibility resources, consisting of universal tools, designated supports, and accommodations, when needed. In addition, an alternate assessment must include, in all assessed content areas, accessibility resources for students with the most significant cognitive disabilities.

Universal tools are access features of the assessment that are available to all students on the basis of student preference and selection. Designated supports are those features that a student regularly uses in the classroom for instruction and/or assessment for whom the need has been indicated by an educator or group of educators, including an IEP or Section 504 team. Designated supports must be entered into the test engine prior to testing. Accommodations are changes in procedures or materials that increase equitable access during the assessments. Accommodations will be available only to students as specified in an IEP and/or Section 504 plan. Universal tools, designated supports, and accommodations are provided either as embedded or non-embedded supports. An embedded support is a universal tool, designated support, or accommodation that is part of the assessment technology platform for the computer-based tests. A non-embedded support is a universal tool, designated support, or accommodation that may be provided by LEA and is not part of the assessment technology platform for the computer-based tests.

The submission must acknowledge that the bidder is familiar with the accessibility resources available in the:

- UAAG at https://portal.smarterbalanced.org/library/en/usability-accessibility-and-accommodations-guidelines.pdf,

- California Assessment Accessibility Resources Matrix at https://www.caaspp-elpac.org/s/docs/CA-Accessibility-Matrix-25-26.docx, and

- Accessibility Guide at https://ca-toms-help.ets.org/accessibility-guide.

#### 7.4.10 Accessibility Plan for Computer-Based Tests and Special Forms

The submission must describe a detailed accessibility plan to provide students with access to the required embedded and non-embedded universal tools, designated supports, and accommodations for computer-based tests and special forms.

The submission also must describe a detailed plan to improve existing accessibility resources and integrate new, innovative accessibility resources and item types into the TDS annually. The UAAG document is updated annually, and the submission must provide detail on how the updates to the UAAG will be incorporated into the TDS. In addition, the submission must describe, in detail, how targeted feedback from California will be obtained annually to contribute to the updates to the UAAG.

The accessibility plan must include an annual report, provided by the successful bidder, that indicates both the assignment and usage of accessibility resources and includes a definition of usage by accessibility resource using the CDE approval process outlined in RFS Section 7.1.6.

##### 7.4.10.A Computer-Based Tests

The submission must describe a detailed accessibility plan to provide a TDS that is capable of including, at a minimum, the universal tools, designated supports, and accommodations available for the CAASPP and ELPAC assessments.

###### 7.4.10.A.1 Print on Demand

The submission must describe, in detail, how, for students with specific testing accessibility needs (i.e., a student’s IEP or Section 504 plan indicates administration of tests in paper-pencil format), the bidder’s test engine will support the ability to print on demand (i.e., the student’s test can be designated through the test engine and accompanying connection to a printer for the creation of hard copy versions of the items). The submission must describe how the print-on-demand resource may be combined with other existing resources (e.g., braille, print size, streamline, zoom).

Upon the student’s completion of the applicable print version of items, the test administrator or scribe would be expected to transcribe the student responses into the test engine interface. The submission must describe options for manual and automated processes for the inputting of student responses from print-on-demand tests into the test engine interface. Print versions of the test items must be securely destroyed immediately after that transcription.

The submission must provide detail on how the bidder will provide technical support to LEAs on the use of print on demand.

###### 7.4.10.A.2 Assistive Technology

The submission must acknowledge and ensure that the TDS will support external applications used for assistive technology (e.g., refreshable braille devices, vision-enhancing software, word prediction). The submission must describe the bidder’s collaboration with the CDE to explore the feasibility of supporting additional assistive technology, including assistive technology beyond that identified as existing universal tools, designated supports, and accommodations.

If the LEAs, through the unlisted resource request process (refer to RFS Section 7.4.11), request test access through a specific assistive technology device, the submission must describe how the bidder will make provisions to support the aforementioned assistive technology but would not be responsible for providing any needed hardware or software (such as refreshable braille devices) for LEAs or the CDE. The submission must describe options for manual and automated processes for inputting student responses from assistive technology into the test engine interface.

The submission must provide details on how the bidder will provide technical support to LEAs on the use of aforementioned assistive technology with the TDS.

###### 7.4.10.A.3 Translations

The submission must acknowledge and ensure that the TDS will support all means of translation access for CAASPP and ELPAC. The submission must describe, in detail, the TDS’s ability to restrict/disable translation access upon the direction of the CDE.

The CAASPP and ELPAC Accessibility Guide at https://ca-toms-help.ets.org/accessibility-guide/introduction/manual-content/ includes a list of translated glossaries and translated test directions in different languages made available for each of the assessments. Translated test directions provide directions only, not the stimulus or questions.

##### 7.4.10.B Special Forms

The submission must describe how the bidder will ensure that special version paper-pencil tests (braille, large print, or regular print) are made available for any of the following:

- ELPAC K–2 Writing (all eligible students)

- Students with IEPs or Section 504 plans indicating the students cannot access the computer-based tests and require braille, large print, or regular print accommodations

- Schools experiencing unexpected and prolonged technology issues that are beyond the schools’ control that prevents online testing for an extended period.

The submission must describe a detailed process to provide braille and large-print testing material for the CAASPP and ELPAC for students who require a special version for the assessment.

###### 7.4.10.B.1 Paper Tests

The submission must describe the process for producing and administering braille, regular print, and large print testing materials for all CAASPP and ELPAC assessments (refer to RFS Table 10). The submission must provide a process for LEAs to order braille, regular print, and large-print testing materials and shall distribute all such testing materials in a braille/large-print kit to the associated LEA. The submission must describe how the bidder’s braille and large-print kit will include braille response documents for braille assessments and appropriate response documents for large-print assessments. The bidder will not be required to produce paper pencil tests in any form; general, braille, or large print for any of the alternate assessments (i.e., ELA, math, science, and ELPAC).

Students being administered a large-print assessment will respond directly on a large-print test document unless the student’s IEP or Section 504 plan specifies a scribing accommodation. The submission must acknowledge and ensure that test administrators or scribes would be expected to transcribe student responses from braille and large-print test forms into the Data Entry Interface (DEI). The submission must describe options for manual and automated processes for inputting student responses from braille and large-print tests into the test engine interface.

The process must describe how the bidder will provide for the secure return of braille and large-print testing materials to the bidder’s facilities. The bidder’s braille/large-print kit shall include all materials (boxes, envelopes, and prepaid return shipping labels) for the schools to use to return the testing materials.

###### 7.4.10.B.2 Braille Hybrid Adaptive Test

The submission must include an online braille Hybrid Adaptive Test (HAT) that provides a secure summative assessment option for LEAs to make available to students who use braille. Currently, the braille HAT must be provided in English Braille American Edition or Unified English Braille paired with Nemeth mathematics code, contracted. The braille HAT option should include the following elements:

- Adaptive segment that includes only items that have no graphics

- Fixed form segment that includes items with graphics

- Pre-embossed graphic supplement

Currently, the braille HAT is only available for the Smarter Balanced Summative Assessment for mathematics. The braille HAT should provide access to an efficient online adaptive test that simplifies logistical burdens for educators and students. This online form serves as an alternative to the online adaptive and paper braille fixed-form options. The braille online HAT allows LEAs to order a set of preprinted embossed graphics for a student’s mathematics test in cases in which the student would not otherwise have access to an embossing printer that works with the Smarter Balanced mathematics assessment items. The student is then able to use the online TDS, including embedded accessibility resources, while also accessing the pre-embossed graphics.

The submission must also describe a process to provide braille forms for the CAST for students who require a specialized form for the assessment. At this time, the CAST is not an adaptive assessment; therefore, a HAT version is not necessary. If the CAST moves to a staged adaptive test during the course of this new contract, the successful bidder is expected to provide a braille HAT option for CAST.

#### 7.4.11 Unlisted Resources

Unlisted resources are accessibility resources that a student regularly uses in the classroom for instruction and assessment that are not identified as allowed universal tools, designated supports, or accommodations. Unlisted resources shall be available if specified in the student’s IEP or Section 504 plan.

Unlisted resources that change the construct being measured by a CAASPP test invalidate the test score and result in a score that cannot be compared with other CAASPP results. CAASPP scores for students’ tests with unlisted resources that change the construct being measured by an assessment will not be counted as the student having participated in statewide testing (and thereby will impact the accountability participation rate indicator). Unlisted resources that change the construct being measured by an ELPAC test will result in the lowest obtainable scale score for the domain. An individual score report will still be generated for both CAASPP and ELPAC. The student’s CAASPP score report will be reported with a message indicating that it may not represent a student's ability.

This approach is consistent with the emphasis that the CDE has placed on the validity of assessment results coupled with access.

The submission must describe the process for LEA CAASPP and ELPAC coordinators to securely submit, prior to the student’s first day of testing, electronic requests to the CDE for approval for the use of an unlisted resource. Requests must include: (1) LEA name, CDS code, and mailing address; (2) LEA coordinator’s name and contact information; (3) the LEA or site testing window, test, and grade; (4) the Statewide Student Identifier (SSID) for the student for whom the accessibility resource is requested; (5) the unlisted resource being requested; and (6) a description of the student’s need to be addressed by the unlisted resource.

The process must include the bidder’s provision of a log of requests and preparation of an annual report pertaining to the requests received for unlisted resources. The report of unlisted resources must include the requests for unlisted resources, sorted by assessment, and the CDE’s decisions. The portions of this report for ELA/literacy and mathematics will be provided to Smarter Balanced for review to determine which, if any, unlisted resources may be added to the Smarter Balanced approved universal tool, designated support, or accommodation list(s) in the next feasible administration, and to the California Accessibility Resources Matrix, as applicable.

The process must include the updating, by the bidder, of the student accessibility tool for California and the Student Access Data File to include a field to capture the student’s use of an unlisted resource (Refer to RFS Section 7.2.4).

### 7.5 TASK 5 – TEST ADMINISTRATION AND SECURITY

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 5 and must provide a description of the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge of the subjects and skills necessary to successfully complete the project as stated in Task 5.

The successful bidder must adhere to the Approval and Certification Requirements as stated in RFS Section 7.1.6.A for generating and delivering required reports/deliverables.

#### 7.5.1 Test Administration Requirements

The submission must describe and demonstrate a process for producing and distributing to LEAs paper and electronic formats of test administration manuals and post-test guides. The submission must include a contingency plan to improve the California Assessment Delivery System with enhancements to support multiple test administration modes (i.e., in-person and remote) should the in-person computer-based administration mode not be a viable option, while ensuring accurate and valid results.

##### 7.5.1.A Manuals and Context-Sensitive Help

The submission must describe how the bidder will produce high-quality manuals that provide California educators with the exact information needed in ways that are accurate and efficient. In addition, the submission must describe how the bidder will implement context-sensitive online help to provide the most appropriate test administration instructions to the user. Context-sensitive help offers guidance by providing specific information at the time the user is looking for help. It contains small pieces of information the user needs to understand at that point; it is not meant to be read as a whole, as opposed to user manuals. It is important to note that context-sensitive help does not make user manuals obsolete. For training purposes, the submission must describe how the bidder will provide detailed, step-by-step manuals with up-to-date system screenshots and explanations that will help the user gain a deeper understanding of the topic.

###### 7.5.1.A.1 Implementing Context-Sensitive Help

The submission must describe how the bidder will develop and implement a user-friendly, visually appealing interface to support document help pages in the California Assessment Delivery System. The context-sensitive help must utilize the California Access Management System to configure role-based permissions to secure information (e.g., test administration instructions that include test questions). The context-sensitive help must directly utilize the information provided in the manuals and other test administration materials and must be presented to the user in the smallest, most precise possible piece of information. In addition, the submission must describe how the bidder will include streaming videos, when available. For example, when a user selects a student’s test settings, the context-sensitive help must provide specific information about the test setting and, when available, provide a video about that test setting. The context-sensitive help also must provide direct access to the manuals posted at https://www.caaspp-elpac.org.

###### 7.5.1.A.2 General Specifications for Developing Manuals

The submission must describe how the bidder will conduct an intake meeting with the CDE prior to the start of the test administration cycle. This meeting must include discussion of all manuals and context-sensitive help and the proposed time frames of their releases. The submission must describe how the bidder will incorporate the guidelines from the intake meeting into the manual release plan and must deliver the manual release plan within 10 working days of the intake meeting for the CDE’s approval. The plan must allow sufficient time for a thorough review and approval of the manuals prior to their being posted or published. In addition, the submission must describe how the bidder will implement a process by which an editor will conduct inter-manual consistency checks to achieve consistent tone, language, and directions among the manuals. The production schedule for each manual will follow the Approval and Certification Process in RFS Section 7.1.6.A.

###### 7.5.1.A.3 Posting Manuals on CAASPP and ELPAC Website

The submission must describe how the bidder will convert all manuals to PDF or HTML files. The submission must describe how the bidder will update HTML versions of the manuals, as appropriate. The PDFs must include the appropriate accessibility tagging that meets the CDE Web, Document, and Accessibility Standards found at https://www.cde.ca.gov/re/di/ws/webstandards.asp. The submission must describe how the bidder will post only nonsecure materials, or materials that have been edited to remove secure sections, at https://www.caaspp-elpac.org based on the timeline agreed upon by the CDE for the given administration. Secure manuals must be posted within the California Assessment Delivery System requiring logon credentials.

For Smarter Balanced and CAST assessments, printing and shipping of manuals is only required for paper and pencil test situations. The latest manuals are available on the CAASPP and ELPAC Manuals Library website at https://ca-toms-help.ets.org/.

The high-level descriptions of some manuals required of the bidder are provided in RFS Table 15.

Table 15. California Assessment System Manuals

| Manual | Format | Assessments Included |
| --- | --- | --- |
| Accessibility Guide for the California Assessment System | Online | All assessments |
| Security Incidents and Appeals Procedure Guide | Online | All assessments |
| Technical Specifications and Configuration Guide | Online | All assessments |
| CERS User Guide | Online | All assessments |
| CERS Interpretive Guide | Online | All Assessments |
| Completion Status User Guide and Roster Management for the California Assessment System | Online | All assessments |
| Test Administration Manual—CAASPP Online Assessments | Online | All assessments |
| Smarter Balanced and CAST PPT Test Administration Manual (TAM) ELA/Mathematics | PPT | Smarter Balanced Summative ELA and Mathematics and CAST |
| Test Administration Planning Guides—CAA for Science | Online | CAA for Science |
| CAA practice and training tests Directions for Administration (DFAs) for the CAAs | Online | All CAAs |
| DFAs (secure materials) and Preparing for Administrations (not secure) | Online | All CAAs |
| Interim Assessment User Guide | Online | Smarter Balanced, CAST, and ELPAC Interim Assessments |
| CAASPP and ELPAC Scoring and Reporting Guide | Online | All CAASPP and ELPAC assessments |
| Summative and Initial ELPAC Online TAM | Online | Summative ELPAC and Initial ELPAC |
| Alternate ELPAC Online TAM | Online | Summative Alternate ELPAC and Initial Alternate ELPAC |
| Summative ELPAC Test Examiner’s Manual | Online | Summative ELPAC |
| Initial ELPAC Test Examiner’s Manual | Online | Initial ELPAC Assessment |
| Alternate ELPAC practice and training tests DFAs for Alternate ELPAC | Online | All Alternate ELPAC |
| DFAs—Initial Alternate ELPAC (secure materials) | Online | Initial Alternate ELPAC |
| DFAs—Summative Alternate ELPAC (secure materials) | Online | Summative Alternate ELPAC |

- Online Test Administration Manual. The Online TAM must include instructions for all available online assessments, including the CAASPP summative assessments: Smarter Balanced Summative Assessments; CAAs for ELA, mathematics, and science; CAST; and CSA; and the ELPAC. The submission must describe in detail how the bidder will ensure that for the TAM, California-specific revisions adhere to the Smarter Balanced test administration procedures and policies where appropriate. The following information must be included:

- Assessment overview

- Test administration resources

- Test security

- Administration preparation and planning

- Administering summative assessments

- Topic-Specific Guides and Manuals. Topic-specific manuals must include, but are not limited to, the following:

- Interim Assessment User Guide

- Completion Status User Guide for CAASPP Testing

- Accessibility Guide for CAASPP Testing

- Security Incidents and Appeals Procedure Guide

- Directions for Administration. DFAs, or examiner’s manuals, must include the following:

- Overview of the assessment and the various test management, registration, and delivery systems

- LEA coordinator responsibilities

- LEA responsibility and activity checklist

- Test site coordinator responsibility and activity checklist

- Test administrator or examiner responsibility and activity checklist

- Appropriate processes for handling accessibility and accommodations for computer-based tests

- Appropriate measures for protecting test security and confidentiality at the LEA level

- Estimated test duration charts for planning purposes and suggestions for LEA-level test scheduling

- Appropriate processes for including special populations of students in testing

- Important dates leading up to, during, and after the testing window(s)

- Supplementary Preparing for Administration documents may provide non-secure materials for public posting that include some of the above information.

- Technical Specifications and Configuration Guide for Online Testing. This manual provides information to LEAs about the system requirements network, hardware, and secure browser configurations for running various testing applications used in CAASPP and ELPAC testing. Scoring and Reporting Guides. A CAASPP and ELPAC Scoring and Reporting Guide must be developed each year to provide a single reference document for all reporting-related information, for all users. The submission must ensure that the manual will provide an overview of the assessments, a description and guide to both online reporting tools and paper reports, information on how tests are scored, and guidelines for interpreting reports.

The submission must include clear standards for interpreting the intended use of the test scores, clearly delimit the addressed population, and describe the constructs that the assessments should measure. The goal of this manual is to guide all CAASPP and ELPAC reporting stakeholders in understanding the scores provided, what they represent, and how they can be used to improve curricular programs in the schools.

##### 7.5.1.B Post-Test Surveys

The submission must describe how the bidder will annually develop and release a post-test survey for the CAASPP and ELPAC to gather information from LEA coordinators, site coordinators, test administrators, test examiners, and other LEA staff working within the California Assessment Delivery System about test administration. The survey must be designed to identify areas of strength and areas for improvement, both immediate and long term, to ensure the success of test administration by LEAs. The survey must focus on areas of actionable improvement. It must be developed and administered on an online platform and must open each year by May and close by July.

The submission must describe how the bidder will propose to the CDE how the information gathered from the annual post-test surveys will be used to inform the future development of test materials and training. The proposal will be subject to the CDE’s final approval for implementation.

#### 7.5.2 Paper Tests

The administration of paper–pencil tests will require systems for the delivery and collection of testing materials. Testing materials include answer books, test books (including braille and large print), test examiner’s manuals, and other materials necessary for the administration of tests. The submission must describe, in sufficient detail, how the bidder will:

- Provide for the secure packaging and distribution of testing materials to LEAs via a secure courier or freight company in a time frame that will allow sites to receive materials 10 working days before the first day of testing.

- Provide for the monthly collection of test materials via a secure courier or freight company no more than 10 working days after the last day of testing and return of the non-scannable materials to the contractor’s test processing center within 30 days of the last day of testing.

- Follow, in detail, the procedures to ensure the regular collection of completed answer books from LEAs participating in the Initial ELPAC 10 percent read-behind during the Initial ELPAC window and all K–2 Summative ELPAC Writing answer books. The procedures must include a detailed description of the process to be used by LEA ELPAC coordinators to inventory all materials before shipping to the bidder and a detailed description of the pickup and shipping procedures for all completed answer books. The submission must describe how the bidder will produce pre-identification labels to ensure the accuracy of student demographics and ease of scanning.

- Use, during the first year of this contract, unused Initial and Summative ELPAC test materials provided by the previous testing contractor.

- Develop a detailed process by which LEAs will return secure materials to the bidder for secure destruction or destroy secure materials locally. The process must include an inventory control procedure for the bidder to cross-reference LEAs’ test material orders with the number of test materials returned. The process must ensure the secure destruction of all remaining test materials and must include a communications plan to notify and follow up with any LEA that did not return all its secure materials for destruction. The plan must include a report to be prepared for the CDE at the end of each school year, with a list of all LEAs that failed to comply with the return of test materials for secure destruction.

##### 7.5.2.A Inventorying and Tracking Secure ELPAC Test Materials

The submission must describe, in sufficient detail, the inventory control procedures that will be implemented to ensure that shipping errors are quickly detected and remedied. All shipments to and from LEAs must be secure and traceable. The procedure must describe the process in detail to ensure the accounting of all boxes of secure test materials, including test books and answer books shipped, is in place. Each box shipped must be uniquely numbered, including a total box count (e.g., Box n of N). All shipping errors, including, but not limited to, missing boxes of test materials, must be reported to the CDE immediately. A search must be conducted to locate boxes not received at an LEA or at the successful bidder’s facilities. The process must ensure that a report describing a procedure for resolution is prepared and submitted to the CDE within five working days from the date of the shipping error.

The submission also must show, in detail, how a monthly retrieval of answer books from LEAs participating in the Initial ELPAC 10 percent read-behind and all K–2 Summative answer books will be implemented. These Initial ELPAC materials must be received from LEAs on a schedule determined by the CDE.

##### 7.5.2.B ELPAC Excessive Ordering Prevention

The submission must describe in sufficient detail a process to minimize the excessive ordering of testing materials by LEAs, including special test versions. The process must specifically describe the steps that will be taken to reduce the volume of excess orders placed by any LEA. The process must describe how detailed auditable records of the number of tests ordered and scored for each LEA will be maintained and describe, in sufficient detail, the bidder’s responsibility for writing and implementing procedures to bill LEAs for excess orders of materials. The process also must ensure a means for providing the CDE with an annual report of all excessive order charges, by total amount billed and received and broken down by LEA, no later than August 15 of each year. The description must include an outreach and administration communication plan to minimize excessive ordering.

##### 7.5.2.C ELPAC Pre-Identification Label Process

The submission must describe, in sufficient detail, the process for ensuring that pre-identification (Pre-ID) labels are provided to LEAs that submit answer books for scoring by the contractor. The submission must describe how the bidder will use CALPADS to populate the student demographic information on the Pre-ID labels.

##### 7.5.2.D Requests for Special Forms

The submission must describe how the bidder will annually work with the CDE to collect information on LEAs that need to administer the special forms due to at least one of the following factors:

- ELPAC K–2 Writing (all eligible students)

- Students with IEPs or Section 504 plans indicating the students cannot access the computer-based tests and require braille, large print, or regular print accommodations

- Schools experiencing unexpected, unexpected and prolonged technology issues that are beyond the schools’ control that prevents online testing for an extended period

During the annual update of LEA coordinators described in RFS Section 7.2.1, the submission must describe how the bidder will incorporate a request for CAASPP and ELPAC special forms survey, which must be released annually along with the Superintendent Designation Form, Security Affidavit, and Security Agreement. The submission must describe how the bidder will update and provide the request for CAASPP and ELPAC special forms survey to the CDE for the standard review and approval process described in RFS Section 7.1.6.A.

#### 7.5.3 Computer-Based Tests

The submission must describe and demonstrate a comprehensive process to administer all CAASPP and ELPAC computer-based tests in RFS Section 7.4.10.A. The process must detail how the CAASPP and ELPAC systems will be portrayed and administered as a seamless, integrated system, inclusive of Smarter Balanced Assessments and non-Smarter Balanced summative assessments.

##### 7.5.3.A Interim Assessments

The submission must describe and demonstrate a process to prepare K–12 educators to access and use the Smarter Balanced, CAST, and ELPAC Interim Assessments in a standardized manner and, to support classroom instruction, in a nonstandardized manner. The process also must prepare educators to conduct the hand scoring of constructed-response and performance task items, including providing and using an online hand scoring system. In addition, the plan must describe, in detail, how educators will be trained to interpret results from the interim assessments that are housed in CERS.

The submission must build on the implementation of the interim assessments for LEAs, to include the following:

- Create the capacity to limit the number of testing opportunities.

- Provide user-friendly educator access to all grade levels of the interim assessments.

- Develop visually distinct elements to differentiate the interim assessments from the summative assessments.

- Provide educator access to and support for the Interim Assessment Viewing System.

- Develop and provide training for classroom teachers on the scoring of student responses to constructed-response and performance task items (e.g., workshops, videos).

- Develop and provide training on the accurate interpretation of scores and the effective use of interim assessment results, including the use of CERS to access results.

- Develop a process to report scores to the Smarter Balanced data warehouse for reporting purposes.

The submission must describe how the bidder will provide services that will incorporate access to the interim assessments through the TDS. Access to the interim assessments must be available year-round and must be updated each year, by August 10. The submission must describe how the update will include materials provided by Smarter Balanced for the ELA and mathematics interim assessments, and any materials needed for the CAST and ELPAC Interim Assessments.

The interim assessments must share the same servers as the summative assessments. Approximately 6.2 million K–12 students will have access to the interim assessments. This estimate includes the students in grades three through eight and grade eleven who also must have access to the summative assessments. The submission must describe how the bidder will host a server infrastructure with sufficient bandwidth, hardware, and software to provide the interim assessments and tools to these students. It is estimated that more than 14 million interim assessments will be administered throughout California each school year.

###### 7.5.3.A.1 Training Educators in the Scoring of Student Responses to Constructed-Response Items

As part of the plan to improve educators’ understanding and use of the CAASPP and ELPAC interim assessments, the submission must describe how the bidder will use its expertise and provide opportunities for classroom teachers and other LEA staff to learn how to accurately and reliably score student responses to constructed-response and performance task items. The submission must describe how the bidder will provide training for educators statewide, with multiple offerings for each training.

###### 7.5.3.A.2 Reporting Interim Assessment Scores to the Smarter Balanced Data Warehouse

The submission must describe how, following the administration of an interim assessment, the bidder will securely transfer student demographic information and submitted interim assessments to the Smarter Balanced Data Warehouse for prompt reporting via CERS. Smarter Balanced implements a federated process for user authorizations. The submission must describe how the bidder will work with the California Access Management System to allow for single sign-on access to CERS to provide educators with seamless use of all components.

##### 7.5.3.B Test Security Incidents and Appeals for Computer-Based Tests

The submission must describe in detail how the TDS will provide an online method through which LEA CAASPP and ELPAC coordinators can submit a test security incident report and generate the corresponding appeal(s) for computer-based tests within the CAASPP and ELPAC systems for a seamless flow of appeals and incident reporting. The system must handle all of the current irregularities, breaches, appeal types, and conditions required by the CDE and Smarter Balanced. The submission must describe how the bidder will confirm the test security incidents and appeal types and conditions for each administration during the annual planning meetings.

The submission must describe how the bidder will provide a team of trained representatives, in conjunction with the CDE, to be responsible for monitoring and processing cases, including associated appeals, via the incident and appeal system. The monitoring and processing of the outstanding appeals must take place throughout the day, Monday through Friday, during the test administration period. The designated team must review each request and approve or deny the appeal, within two working days of submission, based on the requirements documented for each type of appeal.

The submission must describe how the bidder will work with the CDE on a mutually agreeable process for handling appeals authorized by 5 CCR Section 860, review this information annually with the CDE, and include it as part of maintaining and updating the Security Incidents and Appeals Procedure Guide. The types of test security and administration issues that can occur and the appeal applicable to that issue can be found in the Security Incidents and Appeals Procedure Guide at https://ca-toms-help.ets.org/stairs/overview/.

The submission must describe how the bidder will report weekly on the status of all appeals, whether they are approved, rejected, or outstanding appeals that are still in the queue to be processed. The bidder must be prepared to report daily or on demand, as needed by the CDE.

The submission must describe how the bidder will maintain a log of test security incidents and appeals that includes at least the following data elements:

- Date of test security incident

- CDS code of the LEA and the school

- Name of LEA

- Name of school

- Test name

- SSID of impacted student

- Grade level

- Test type/domain

- Comments from the LEA

- Email of the approver and the submitter

- Type of appeal

- Appeal decision

- Username of the submitter

#### 7.5.4 Test Security Plan Requirements

The submission must provide a detailed test security plan which describes the procedures that will be used to ensure the security of the following:

- Items under development and review

- Test development and construction

- Test administration, including pilot, field, and operational assessments

- Document processing

- Handling and storage of materials (to and from LEAs)

- Test scoring and reporting

- Cloud-based data storage

- All circumstances in which the security of tests and testing materials is required

- Special form processing, handling, and storage, including delivery and collection of materials to and from LEAs, and accounting for applicable test booklets and answer documents

In addition, the submission must describe detailed procedures that ensure the security of electronic files of items, including item banks, and electronic files of test results data. The procedures must ensure that only authorized staff with direct responsibilities for the tests have access to test materials, including manuals and secure test documents. Individuals with allowed access to secure testing materials must sign a confidentiality agreement or test security agreement or affidavit as specified in CAASPP and ELPAC regulations.

##### 7.5.4.A Test Administration Monitoring Plan

Test security violations can impact the fairness of testing and the validity of results. To ensure the fairness and validity of the CAASPP and ELPAC, the submission must describe, in detail, the proposed process to prevent, identify, investigate, and resolve potential compromises for all CAASPP and ELPAC administrations. The annual test administration monitoring plan must describe, in detail, a procedure to search social media sites for images or content of test questions and secure test materials for all CAASPP and ELPAC initial, summative, and interim assessments. The process must include an electronic system that will track all security breaches and communicate any breaches to the CDE and Smarter Balanced, if applicable, in a timely manner. The process must indicate the manner by which, if secure test questions or materials are found online, the breach will be reported to the CDE within one working day. The process also must ensure that the electronic transmittal of personally identifiable information (PII) to the CDE and LEA is secure.

The submission must provide a test administration monitoring plan detailing the process for the following:

- Selecting test sites for audit

- Determining audit type (online or in-person)

- Creating questions regarding pre-administration, administration, remote testing, security of materials, testing security and other topics to gain information on how LEAs are preparing for testing and maintaining test security

- Reviewing the responses to the audit questions and identifying any discrepancies or possible test security issues

- Identifying LEAs that may have possible test security issues and work with LEAs to correct and assist with any issues

- Scheduling audits and LEA notification

- Creating a communication confirming completion of the audit

The monitoring plan must also include the process for obtaining the CDE’s approval of proposed test site audits, process for notifying sites for audit how LEAs are to complete the audit process. The LEA superintendent and LEA Coordinator must be informed of the audit 10 working days in advance of an audit.

##### 7.5.4.B Test Administration Monitoring Instruments

The submission must include a monitoring plan which provides the development of two instruments designed to prepare LEAs for successful and secure administration of all CAASPP and ELPAC assessments, both of which are to be updated annually:

- Contractor monitoring instrument(s) specific to each of the CAASPP and ELPAC assessments. The plan must include a description of how the instrument(s) will be implemented by auditors.

- Self-monitoring instrument(s) for LEAs’ use that complement the content of the monitoring instrument(s) for use by auditors. The submission must include details for the development and distribution of the proposed instrument(s).

The monitoring plan must include as deliverables the following two annual reports:

- Test Administration Monitoring Report, which must include details on the content, means, frequency of reporting monitoring activities, a timeline for the audit results report back to the LEA, and an outline of the contents to be included in the audit results report.

- Test Administration Monitoring Summary Report, which must describe the detailed information and analysis of all monitoring activities and be provided within one month of the end of the academic year. This report must also include a final summary of findings with suggestions for any improvements in LEA trainings and communications, as well as improvements for the auditing program; and a list of any LEA or school that should be audited again in the following year.

##### 7.5.4.C Test Administration Monitor Training

The monitoring plan must set forth the processes to be followed for employing and training monitors and auditors. The monitoring plan must provide descriptions of how the monitors are employed and how quality training is provided to them prior to their interactions with LEA staff.

Auditors hired to monitor the security of the CAASPP and ELPAC must have a clear criminal background and a clear California Live Scan report on file and must possess appropriate identification prior to any monitoring visits. In addition, they must have an assessment administrative background or have administered the CAASPP or ELPAC. The annually updated plan must indicate the method for recruitment and hiring, mode of training, and the measurement tool used to confirm that auditors are prepared to represent the CDE as an assessment monitor.

The submission must include proposed training materials (e.g., PowerPoint, handbook, questionnaires) and any developed training evaluation materials to be delivered annually for CDE approval prior to recruiting.

##### 7.5.4.D Investigating Security Breaches

A security breach is anything that may compromise the test. Security breaches have external implications for the State and may result in a CDE decision to remove the test item(s) from the available secure item bank. The submission must describe, in detail, the procedure for conducting investigations of security breaches.

Examples of security breaches include the following:

- Students, or any individuals with access to testing materials, removing test materials from testing locations by any means, including through the use of electronic devices

- Posting test images on social media websites

- Test examiners sharing test questions

- Losing secure paper-pencil test materials

The plan’s approach and methodology must include the following guidelines:

- After discovering a breach, the LEA must investigate the security risk and alert the CDE immediately as specified in CAASPP and ELPAC regulations.

- The submission must acknowledge that, if the breach involves the Smarter Balanced summative or interim assessments, the bidder will alert the designated Smarter Balanced staff and follow up with a written notification. Smarter Balanced will contact the CDE and assist the CDE and the bidder in mitigating the risk.

- The submission must acknowledge that, if the breach involves non-Smarter Balanced computer-based summative tests or the ELPAC computer-based tests, the bidder will describe the breach, the impact of the breach, and the proposed resolution of the breach.

- The submission must describe how the bidder will investigate after the breach, which may require a site visit.

- The bidder’s approach to work with the LEAs to mitigate security breach issues (e.g., removing social media postings).

Within 10 working days of having received initial reporting of the breach, the selected bidder must provide a detailed report to the CDE regarding the investigation timeline, communications, and events that resulted in resolution of the breach. All breaches and mitigation efforts must also be described in an end of year Test Administration Monitoring Summary Report.

##### 7.5.4.E Security Log

The submission must describe how the bidder will establish a shared access location to maintain a log of all security notifications and status. The plan must describe the critical details of a security investigation that will be logged.

The bidder’s plan for investigating security breaches also must include as deliverables the following reports:

- Security Update Reports, which are weekly reports to provide communication regarding high-level information on active security investigations to the CDE.

- Summary Security Report, which is an annual report to the CDE describing the detailed information and analysis of all security breaches.

### 7.6 TASK 6 – SCORING AND REPORTING

#### REQUIREMENTS

This section of the submission must acknowledge the bidder’s commitment to completing all the requirements specified below in Task 6 and must provide a description of the approach and methodology by which the bidder will accomplish all the associated subtasks and activities. The submission must contain sufficient detail to convey the bidder’s knowledge of the subjects and skills necessary to successfully complete the project as stated in Task 6.

The successful bidder must adhere to the CDE approval requirements, as stated in RFS Section 7.1.6, for generating and delivering required reports/deliverables.

#### 7.6.1 Scoring

Depending on the test item format, tests may be scored by means of deterministic scoring (machine scoring), hand scoring, or AI scoring. Refer to RFS Appendix C for the item types within each assessment of the California Assessment System. The submission must describe the scoring process used for Smarter Balanced, non-Smarter Balanced (CAST; the CAAs for ELA, mathematics, and science; the CSA; and the ELPAC, including the Initial, Summative, and Alternate). computer-based tests and paper-pencil tests. This includes both summative and interim assessments for CAASPP and ELPAC.

##### 7.6.1.A Methods of Scoring

The submission must describe methods and processes for scoring items in the California Assessment System (exclusive of the interim assessment performance tasks and constructed-response items, which are scored locally). Items can be scored in three ways:

- Deterministic or machine scoring is used for test items that have an unambiguous definition of correctness that can be determined by an algorithm. Deterministic scoring applied to selected-response items, such as multiple-choice items, is a recognized application, but it can also be applied to a subset of constructed-response items, to which the answer is a mathematical formula, a number, a manipulation of an on-screen item, a keyword, and so forth.

- Hand scoring is for items that require human application of a rubric to assign the score.

- AI scoring uses statistical methods, usually from a sampling of hand-scored responses, to assign the score.

###### 7.6.1.A.1 Deterministic or Machine Scoring

The submission must describe a process for the machine scoring of CAASPP items (inclusive of summative and interim assessments) and ELPAC items (inclusive of Initial, Summative, and Alternate assessments, as well as interim assessments). The submission must include discussion of procedures used to ensure the accuracy of scoring processes.

###### 7.6.1.A.2 Summative and Initial ELPAC Paper Form Scanning and Scoring Process

The submission must describe the type of equipment, appropriate location, and security procedures that will be used for the scanning of both Summative and Initial ELPAC answer books and the scoring of student responses. The description must include a scanning system that must comply with the ISO 27000 series of standards and that fully meets state and federal requirements for privacy and student confidentiality.

The submission must describe in sufficient detail a test scanning system that is able to:

- Electronically scan answer books and store multiple-choice responses.

- Electronically scan answer books and store responses to constructed-response items for review by trained scorers.

The submission must describe in sufficient detail how the bidder will score the student responses to generate scale scores and identify students’ proficiency level on the basis of performance-level cut scores approved by the SBE.

###### 7.6.1.A.3 Hand Scoring or Artificial Intelligence Scoring

The submission must acknowledge that the summative assessment for each testing program has a subset of constructed-response items that require hand scoring. For all CAASPP and ELPAC items requiring hand scoring, the submission must provide details on how the bidder will ensure that the following criteria will be met:

- Prioritize recruitment and compensation for California educators.

- Participation of California educators is required and will comprise the majority of those selected.

- All hand scorers (i.e., raters) must possess, at a minimum, an undergraduate college degree.

- All hand scorers must reside in the United States.

- Technically sound methods of training and qualifying hand scorers, consistent with Smarter Balanced and CDE protocols, must be used.

- Unless otherwise specified, the monitoring of hand scoring processes must include a second scoring of at least 10 percent of performance tasks and constructed-response items as part of the process of monitoring hand scoring reliability. Where ratings of first and second scorers do not agree, a third scorer should score the item for adjudication purposes. “Do not agree” means two scores are more than one score point apart (i.e., nonadjacent).

- Ongoing checks and controls for scorer error must be performed.

- A secure, web-based distributed-scoring system to facilitate hand scoring must be provided.

- All training materials for all hand scoring activities must be prepared and provided to the CDE for review per RFS Section 7.1.6. (Smarter Balanced hand scoring training materials must be adapted from materials developed by the Smarter Balanced Assessment Consortium.)

- Weekly scoring reports must be provided to the CDE that document hand scoring inter-rater reliability (item level and scorer level with exact, adjacent, and non-adjacent rates); check-set (training) results; third scoring results; reports on item score-point frequencies by item and scorer (including non-scorable codes); item-level reports with mean scores; and rater drift data.

- For extended and brief writing responses, a process must be in place to detect, flag, and address student writing that indicates the student is in danger or distress. An “alert” flag must be assigned to these responses. The different types of alerts shall be: suicide; criminal activity; alcohol or drug use; extreme depression; violence; rape, sexual, or physical abuse; self-harm or intent to harm others; and neglect. The process must include the procedures to be used to notify LEA and school staff if the response indicates any of these alert conditions. The submission must describe this process in detail.

- Item condition codes (e.g., alerts, non-scorable, off topic) must be in place that are consistent with specifications and codes specified by Smarter Balanced and the CDE.

- Alerts should be provided for operational and field test extended and brief items (even though the contractor is responsible only for scoring operational items) to ensure that any student who describes an emergent crisis has an increased likelihood of receiving assistance.

- If proposing the use of AI scoring, the following must be provided:

- AI scoring method (e.g., AI single score of record, AI scoring used for the second reading for human scorers, hand scoring used to validate AI)

- Filtering process (i.e., business rules for filtering/flagging “gamed” responses)

- Modeling process (describe how the operational scoring model was developed)

- Framework for evaluating the correct functioning of the scoring model

- Scoring process (e.g., percent of items monitored by humans; resolution of discrepant reads between human and automated system, including condition code, alert, and “gamed” papers; detection of alert, “gamed” or condition code papers).

- Evidence regarding the degree to which the AI models have been validated for use on responses provided by students in traditionally underrepresented or specialized groups (e.g. ELs, students with disabilities, Spanish language responses)

###### 7.6.1.A.4 Smarter Balanced Summative Assessments

The submission must describe a process for scoring Smarter Balanced performance tasks and constructed-response items and clearly distinguish any differences in Smarter Balanced and non-Smarter Balanced hand scoring processes and procedures. The process must ensure and describe in detail how the bidder will conduct the handling of computer adaptive tests, which contain a wide variety of items that may be for hand scoring. Refer to RFS Table 16 and Table 17 for the estimated number of constructed-response items eligible for hand scoring. For Smarter Balanced assessments, the entire pool of hand scored items will be available for each administration with the possibility that each hand scored item may be administered to at least one student during each statewide administration.

For Smarter Balanced items, most training may be accomplished by task-model training instead of by item; however, some item-level training is required. Refer to RFS Table 18 for the task models for ELA items. For mathematics, Smarter Balanced will provide anchor items and training sets for the task models. Smarter Balanced will provide item-specific rubrics and item-specific validation sets for all mathematics items. The hand scoring process must describe in detail how the bidder will conduct scoring qualifications at the item level and how the scorer will check for scorer errors and scorer drift, inclusive of Smarter Balanced items.

Each student will be administered five short-answer (SA) text response items and one Writing Extended Response (WER or essay) item that will require hand scoring on the ELA assessment and up to four items requiring hand scoring on the mathematics performance task assessment, depending on grade.

Table 16. Estimated Constructed-Response Item Counts for Smarter Balanced Summative ELA Assessments

| Grade | ELA SA Items | ELA WER Items | ELA Total |
| --- | --- | --- | --- |
| 3 | 54 | 48 | 102 |
| 4 | 58 | 49 | 107 |
| 5 | 65 | 57 | 122 |
| 6 | 239 | 48 | 287 |
| 7 | 275 | 56 | 331 |
| 8 | 261 | 55 | 316 |
| 11 | 326 | 51 | 377 |
| Grand total | 1278 | 364 | 1642 |

Table 17. Estimated Constructed-Response Item Counts for Smarter Balanced Summative Mathematics Assessments

| Grade | Math EQ1 | Math GI2 | Math MI3 | Math SA4 | Math TI5 | Math Total |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | 2 | 3 | 2 | 94 | 16 | 117 |
| 4 | 3 | 4 | N/A | 104 | 11 | 122 |
| 5 | 9 | 1 | N/A | 121 | 15 | 146 |
| 6 | 9 | 2 | N/A | 91 | 14 | 116 |
| 7 | 9 | 11 | N/A | 68 | 8 | 96 |
| 8 | 18 | 13 | N/A | 86 | 2 | 119 |
| 11 | 23 | 16 | N/A | 92 | 4 | 135 |
| Grand total | 73 | 50 | 2 | 656 | 70 | 851 |

1Math EQ = equation response

2Math GI = grid item response

3Math MI = match interaction

4Math SA = short-answer text response

5Math TI = table interaction

Table 18. Smarter Balanced Item Types for ELA Constructed-Response and Performance Task Items

| Item Type | Subcategories |
| --- | --- |
| Claim 1 Reading (Computer adaptive test Short Text) | Training will occur at the grade-band level for the following subcategories: 1. Target 2 (Central Idea, Literary) 2. Target 9 (Central Idea, Informational) 3. Target 4 (Inference/evidence, Literary) 4. Target 11 (Inference/evidence, Informational) |
| Claim 2 Brief Writes (Computer adaptive test Short Text) | Training will occur at the grade-band level for the following subcategories: 1. Target 1a. Narrative a. Organization, Opening b. Organization, Conclusion c. Elaboration 2. Target 3a. Informational—Explanatory a. Organization, Introduction b. Organization, Conclusion c. Elaboration 3. Target 6a. Opinion—Argumentative a. Organization, Introduction b. Organization, Conclusion c. Elaboration |
| Claim 4 Research (Performance Task Short Text) | Training will occur at the grade-band level for the following subcategories: 1. Target 2 (Interpret and Integrate Information) 2. Target 3 (Evaluate Information/Sources) 3. Target 4 (Use Evidence) |

###### 7.6.1.A.5 California Science Test

The submission must describe in sufficient detail a process for hand scoring the CAST CR items. The submission also must describe how the bidder will conduct range finding meetings for field test CRs. Refer to RFS Section 7.6.1.A.9.

Refer to RFS Table 19 for the estimated number of operational and field test constructed-response item counts annually administered for the CAST. Refer to RFS Table 20 for the estimated machine and hand-scored constructed-response item counts for a CAST form. The entire pool of hand scored items will be available for each administration, with the possibility that each hand scored item may be administered to at least one student during each statewide administration.

Table 19. Estimated Constructed-Response Item Counts for CAST

| Grade | Operational CRs | Field Test CRs | Total |
| --- | --- | --- | --- |
| 5 | 8 to 10 | 13 | 21 to 34 |
| 8 | 8 to 10 | 11 | 21 to 34 |
| High school | 8 to 10 | 9 | 21 to 34 |
| Total | 24 to 30 | 33 | 63 to 102 |

Table 20. Estimated Machine-Scored and Hand-Scored Item Counts for a CAST Form

| Assessment | Item Counts |
| --- | --- |
| Machine scored | Discrete = 26 items for grade five, 28 items for grade eight, and 32 items for high school 3 PTs = 12-18 items for each grade Field test = 6 discrete items or 1 PT = 4-5 items for each grade |
| Hand scored | All grades = 9-13 each |

###### 7.6.1.A.6 California Spanish Assessment

The submission must describe in sufficient detail a process for the hand scoring of CSA constructed-response items. The submission also must describe how the bidder will conduct range finding meetings. Refer to RFS Section 7.6.1.A.9.

Refer to RFS Table 21 for the current machine scored item counts for the CSA and hand-scored constructed-response item counts for the CSA.

Table 21. Machine Scored and Hand-Scored Item Counts for the CSA

| Method | Item Counts |
| --- | --- |
| Machine scored | Grades 3 through 8 = 47 MC items High school = 47 items |
| Constructed response | Grades 3 through 8 = 1 CR by bidder High school = 9 CR by bidder |

###### 7.6.1.A.7 ELPAC Writing and Speaking Domains

The submission must describe in sufficient detail a process for scoring the ELPAC Writing and Speaking domains. Refer to RFS tables 22 through 25 for the estimated number of speaking and writing domain constructed-response items for hand scoring. The entire pool of hand-scored items will be available for each administration with the possibility that each hand-scored item may be administered to at least one student during each statewide administration.

Table 22. Estimated Constructed-Response Item Counts for Summative ELPAC Writing Domain

| Summative Grade(s) | Summative Writing Constructed-Response Items |
| --- | --- |
| Kindergarten | 8 |
| Grade 1 | 7 |
| Grade 2 | 7 |
| Grades 3–5 | 6 |
| Grades 6–8 | 6 |
| Grades 9–10 | 6 |
| Grades 11–12 | 6 |
| Total | 46 |

Table 23. Number of Constructed-Response Items Administered in the 2024–25 Summative ELPAC Speaking Domain

| Grade or Grade Span | Summative ELPAC Operational Constructed-Response Items | Summative ELPAC Field Test Constructed-Response Items | Total Constructed-Response Items for Summative ELPAC |
| --- | --- | --- | --- |
| K | 9 | 8 | 17 |
| 1 | 9 | 8 | 17 |
| 2 | 12 | 12 | 24 |
| 3–5 | 12 | 12 | 24 |
| 6–8 | 12 | 12 | 24 |
| 9–10 | 12 | 12 | 24 |
| 11–12 | 12 | 12 | 24 |
| Total | 78 | 76 | 154 |

Table 24. Estimated Constructed-Response Item Counts for Initial ELPAC Writing Domain

| Initial Grade(s) | Initial Writing Constructed-Response Items |
| --- | --- |
| Kindergarten | 8 |
| Grade 1 | 8 |
| Grade 2 | 6 |
| Grades 3–5 | 5 |
| Grades 6–8 | 2 |
| Grades 9–12 | 2 |
| Total | 31 |

Table 25. Number of Constructed-Response Items Administered in the 2024–25 Initial ELPAC Speaking Domain

| Grade or Grade Span | Initial ELPAC Operational Constructed-Response Items | Initial ELPAC Field Test Constructed-Response Items | Total Constructed-Response Items for Initial ELPAC |
| --- | --- | --- | --- |
| K | 8 | 14 | 23 |
| 1 | 8 | 15 | 22 |
| 2 | 8 | 14 | 22 |
| 3–5 | 9 | 14 | 24 |
| 6–8 | 9 | 15 | 23 |
| 9–12 | 9 | 14 | 24 |
| Total | 51 | 86 | 137 |

###### 7.6.1.A.8 California Alternate Assessment for ELA and Alternate ELPAC

The CAA for ELA and Alternate ELPAC have rubric-scored items that are scored locally by test examiners, who then enter the student scores into the scoring system. RFS tables 26 and 27 provide the approximate number of rubric-scored items on each of these assessments.

Approximately 20 percent of LEAs will be chosen annually for a second scoring of these items, to be conducted by a different trained test examiner. The submission must describe how the bidder will put in place the capability to gather and compare the submitted scores for analysis and future training opportunities.

Table 26. Estimated Rubric-Scored Item Counts for the Alternate ELPAC

| Assessment | Item Counts |
| --- | --- |
| Alternate ELPAC | Each grade level/grade span test will have approximately 7-10 rubric-scored items on the operational test which includes field test items. |

Table 27. Estimated Rubric-Scored Item Counts for the CAA for ELA

| Assessment | Item Counts |
| --- | --- |
| CAA for ELA | Tests for grades 6–8 and 11 will have approximately 2-3 rubric-scored items on the operational test which includes field test items. |

The submission must also describe and demonstrate a process and procedure to ensure that the minimum agreement rates consistent with industry standards are maintained as well as the ability to meet more stringent agreement rates for scoring accuracy as determined by the CDE.

Table 28. Minimum Exact Agreement Rates for the California Assessment System

| Score Point Range and Constructed-Response Item Types or Traits | Percent Exact Agreement |
| --- | --- |
| 0–1 short text, fill-in tables | 90% |
| 0–2 short text, fill-in tables Writing Conventions trait | 80% |
| 0–3 short text, fill-in tables | 80% |
| 0–4 short text, Writing traits 1 and 2 | 70% |

If the item types proposed in the submission differ from those in the table, the submission must propose minimum exact agreement rates that are consistent with industry standards.

###### 7.6.1.A.9 Range Finding

The submission also must describe how the bidder will ensure that range finding will be conducted to identify student responses that can be used as anchor sample responses (i.e., student responses representing the full range of each rubric score point), training sample responses (i.e., additional pre-scored student responses available to local scorers for practice), calibration sample responses (i.e., student responses used for the calibration of scorers), and validation sample response (i.e., student responses used for periodic evaluation of raters during a scoring session) for all California assessment programs. The description also must include the following:

  - Training materials for range finding meetings. The submission must ensure and acknowledge the bidder’s commitment to prepare and provide the necessary range finding training tasks and materials, including but not limited to, the following:

- Guidelines for the anchor selection process

- Development of training materials

- Training materials, prompts, scoring rubrics, score recording methodology, and student responses

  - Procedures for range finding meetings. The submission must describe in sufficient detail the procedures for conducting virtual range finding meetings, including, but not limited to, recruitment, schedule, facilitation, overall logistics, and meeting logistics. The procedures must ensure that the range finding meetings will include, for each assessed grade level, four to six participants who are California educators with experience scoring constructed-response items. Participants must review and score student responses for the purpose of recommending anchor, training, calibration, and validation responses for each assessed grade and score point. The meetings must be scheduled to allow the CDE staff to attend. The submission must acknowledge and ensure that the bidder will be responsible for all costs related to the range finding meetings.

To ensure that all constructed-response items are scored consistently and reliably, the submission must include details of the processes and materials that will be used in (1) the pre-scoring of items; and (2) the educators’ range finding meetings. The range-finding meetings must occur in advance of scoring and mutually agreed upon schedule for each assessment program.

The submission must acknowledge that the bidder’s staff will participate in the range finding meetings as facilitators, not scorers, ensuring that the process will lead to a fair, accurate, and reliable scoring of constructed-response items. Each facilitator will lead a small-group discussion among participants until consensus is reached on the score of each item.

##### 7.6.1.B Local Scoring

The assessments that require local scoring are the Smarter Balanced, CAST, and ELPAC Interim Assessments and the Initial and Summative ELPAC. For the Initial ELPAC, the writing and speaking domains are locally scored. For the Summative ELPAC, the speaking domain is locally scored.

While the scoring of these performance tasks and constructed-response items is the responsibility of LEA staff, the submission must describe a process to facilitate LEAs’ use of a hand scoring system for the local scoring of performance tasks and constructed-response items (e.g., training materials, directions, tools).

###### 7.6.1.B.1 Read-Behind Analyses and Comparison Report for the Initial ELPAC

For the computer-based Initial ELPAC, the local scores of student responses to all items result in official scores. LEAs will provide the official scores to parents/guardians within 30 days of a student’s enrollment in a California public school; however, the submission must describe how the bidder will ensure that 10 percent of LEAs, as approved by the CDE, return all of their answer books for scanning and read-behind analyses. The submission must describe in detail the procedures to scan and score the Initial ELPAC Answer Books returned for the purpose of producing item statistics for analysis. In addition, the submission must describe how the bidder will produce a comparison report that identifies discrepancies between the scores on the 10 percent read-behinds and each LEA’s corresponding scores in the TDS. The comparison report will be used to improve training and assist LEAs in identifying areas for improved administration. The read-behind analyses are only for the Writing domain. For training purposes only, the Speaking and Writing domain scores are bubbled into the back of the Answer Book and are scanned and compared.

###### 7.6.1.B.2 Local Scoring Training and Materials for the Initial and Summative ELPAC

The submission also must describe in sufficient detail the procedures and materials that will be developed for LEAs to locally score the Initial and Summative ELPAC. Materials must include, but are not limited to, specific instructions that allow LEAs to score locally, scoring rubrics, anchor samples, instructions for completing the demographic information, and performance level descriptors. All official scoring will require the use of CDE-approved rubrics to ensure the standardization of scores. The submission must ensure that LEAs will be provided with materials and procedures for calculating results and scale scores electronically. Refer to RFS Tables 22, 23, 24, and 25 for more information.

##### 7.6.1.C Cumulative Scores

The submission must describe and demonstrate a process for incorporating machine scoring, hand scoring, AI scoring, and local scoring into a cumulative score for each student.

For the CAA for Science, the three operational embedded performance tasks are equally weighted and the scores from the individual performance tasks are summed together to arrive at an overall raw score. This overall raw score is then converted to an equated scale score.

#### 7.6.2 Analysis of Test Results

The submission must describe a process for analyzing the performance of all the assessments of the California Assessment System. The submission must acknowledge that the bidder will use publicly available software for all item and test analyses to allow for replication by the CDE and to ease the transition to the next contractor. The submission must acknowledge that the bidder will not use any software that is not available to the general public for conducting statistical analyses. Results of all specified analyses must be included in each annual technical report for the year in which the assessment is administered (refer to RFS Section 7.6.7).

##### 7.6.2.A Item, Calibration, Equating, Scaling, and Test Analyses

The submission must describe in detail the analyses that will be conducted on an annual basis following the completion of the California Assessment System, excluding the Smarter Balanced assessments.

The submission must describe the bidder’s test analysis procedures which include the analysis of equating and scaling procedures to ensure the stability of reporting scales over time. Analyses will include comparisons of test characteristic curves (TCCs) from one year to another. For multistaged tests (CAA for ELA and CAA for Math), the TCCs and test information functions should be produced for each stage of the test and overall information function and compared to prior administrations to assess equating procedures. Analysis of tests that utilize a continuous scale across grade levels (Initial and Summative ELPAC) must include analyses designed to assess the consistency of the scale from one administration to another.

At a minimum, the submission must include item analyses which provide the following summary data for each test item presented to a student:

- Number of examinees presented with the item

- Total number of examinees responding per item

- Results by grade level and grade span

- Average, minimum, and maximum amount of time taken (as warranted) to respond to the item

- Average, minimum, and maximum latency prior to presentation of the item

- Classical item analysis: (1) the number and proportion of examinees selecting each correct response as well as number and proportion of examinees selecting each incorrect response option (distractor) for the multiple-choice items; (2) the proportion of examinees receiving each score point for constructed-response items; and (3) the point-biserial or polyserial correlation between all answer choices and their respective total-test-scores.

- Item-response theory (IRT) item analysis: (1) item difficulty (location) and discrimination (slope) parameters for all items (e.g., dichotomous multiple-choice, dichotomous constructed-response, and polytomous items); and (2) step parameters for polytomous items. For one-parameter logistic (Rasch) models, it is assumed that all item discrimination parameters equal unity and need not be reported.

- Item fit statistics for the IRT model

- DIF analyses using both Mantel-Haenszel and standardized mean difference procedures for gender and other variables

- Other analyses to evaluate the quality of items and reports, including appropriate statistics for the Writing and performance tasks (e.g., average item score of rubric scored items on Writing and Speaking domains)

- Classical item difficulties (p-values), biserial, and point-biserial correlation coefficients

- IRT item difficulties (b-parameters), item fit statistics, and test characteristic curves

- For pre-equated forms, or re-used test forms, cross plots of item difficulties as estimated for pretest and post-test

- As appropriate, raw score to scale score conversion tables with frequencies (distribution of student raw scores) and conditional standard errors of measurement

##### 7.6.2.B Summary Analyses

The submission must describe in detail a summary analysis process that provides evidence of test score validity and test score accuracy. The process must specify that the bidder shall conduct the following analyses for each computer-based assessment, and the results must be presented in a tabular or graphical format:

- Frequency distribution of test scores for all test takers, by grade level

- Frequency distribution of test scores for all test takers, by subgroups within each grade

- Indices of item completion rates

- Descriptive statistics, including the mean, standard deviation, minimum, and maximum for the total score, performance task score, and each domain or claim score

- Mean proportion correct and mean biserial and point-biserial correlations for each domain or claim score

- For variable-length assessments, maximum, minimum, and average number of items presented to students

- Maximum, minimum, and average time taken (as warranted) to complete the assessment

- Analysis of subgroup size changes at the LEA level of more than 10 percent from one year to the next

- Measures of accuracy, including internal consistency measures (reliability coefficients), standard errors of measurement, and misclassification probabilities for each domain score

- DIF analyses using both Mantel-Haenszel and standardized mean difference procedures for gender and other variables

- Other analyses to evaluate the quality of items and scores, including appropriate statistics for the constructed-response items

###### 7.6.2.B.1 Smarter Balanced and Non-Smarter Balanced Online Summative Assessments

The submission must include a detailed process for analyzing the performance of the assessments and assessment system. The summary analyses to be completed include: (1) item utilization rates analyses; (2) item response times; (3) latency of item presentation; (4) summary analyses of test score distributions; and (5) additional analyses to improve the interpretation and utility of test scores.

For the Initial and Summative ELPAC, the analyses must be conducted by composite and overall score. For the Alternate ELPAC, a minimum analysis will include the overall score due to the integrated domains with further analyses on receptive and expressive outcomes after three full administrations.

###### 7.6.2.B.2 Evidence of Test Score Reliability and Validity

The submission must describe in sufficient detail the procedures that will be used to assess the reliability and validity of the scores produced by the Initial and Summative Alternate ELPAC. Analyses for each assessment must include the following:

- Overall internal consistency and reliability of the assessment

- Standard errors of measurement and conditional standard errors of measurement for the assessment

- Rater consistency and reliability for hand-scored items

- Analysis of classification consistency and accuracy

- Item difficulty by person ability (Wright Map)

- Intercorrelations among domain scores

- Threshold validation study

##### 7.6.2.C Replication of Analyses

The submission must acknowledge that the bidder will provide all documentation and data needed for replication/auditing to the CDE within 10 working days of a request. The submission must acknowledge that the bidder will be prepared to consult with the CDE on the replication of analyses.

The submission must acknowledge that student data files for use in replicating item and summary analyses will be provided to the CDE in the format specified by the CDE. Formats for replication files will generally be either caret delimited or fixed length files depending on the analyses to be conducted. The files must include the following:

- SSID number

- Student demographic information

- Information on supports or accommodations assigned and used

- Test results, including computer adaptive test score, performance task score, and claim scores for the Smarter Balanced Assessments

- Overall scores for the CAAs for ELA, mathematics, and science

- Overall scores and science domain scores for the CAST

- Overall scores, composite scores, and domain performance levels for the CSA

- Test results, including overall scale score, oral language scale score, written language scale score, and domain performance levels, for ELPAC where applicable

- Identification of each item the student responded to, the student’s response, time to answer, and latency between items

- An explanation of how theta scores are converted into scale scores.

The submission must also ensure that the bidder will provide annual summative data files to the CDE containing raw scores, scale scores, sub-scores, and response vectors for each student along with all test administration and demographic data to be used in the replication of item analyses and test characteristics.

#### 7.6.3 Reporting Results to Local Educational Agencies

The submission must describe and demonstrate a process for a system that provides timely student and aggregate results to LEAs. The process must clearly describe when each of the various California Assessment System reports must be provided to the LEAs and must describe a system that is able to accomplish the following:

      - Integrate online summative student test data with demographic data from student registration information to produce individual and aggregate started/completion reports on a daily basis

      - Produce student roster reports of individual student results that can be downloaded or printed by the LEA for its use

      - Provide, by content area, the Smarter Balanced summative individual student results to LEAs via CERS. On average, individual student results must be delivered to the LEAs within three weeks, with a maximum of four weeks from the time the student completes all components (CAT and PT) of the test

      - Provide, by content area, the non-Smarter Balanced computer-based summative individual student results to LEAs via CERS. On average, individual student results must be delivered to the LEAs within three weeks, with a maximum of four weeks from the time the student completes all components (computer-based test, performance tasks, and/or domains) of the test

      - Provide LEAs access to customized aggregate reporting via CERS, allowing for the analysis of school- and LEA-level results. The content and format of reports are to be specified and approved by the CDE and must include a means for filtering any entity’s results to display the data for currently enrolled students, including students who tested outside of the school or LEA

      - Provide all operational assessments, electronic Student Score Reports (SSRs) (one for the parent/guardian, one for the school) that convey the overall individual student performance to LEAs. Provide electronic media files that report the overall individual student performance. The files must allow LEAs to transmit reports to their Student Information System and download and print out PDFs of the student reports. The content and format of student reports is to be specified and approved by the CDE.

The submission must include a description of the reporting of CAASPP and ELPAC interim assessment results to the CDE and LEAs via CERS. Results from the CAST and ELPAC Interim Assessments must be reported using procedures similar to the Smarter Balanced Interim Assessments.

California is a member of the Smarter Balanced Assessment Consortium, and Smarter Balanced developed CERS as the California instance of the Smarter Reporting System. The submission must acknowledge the requirement to work with the Smarter Balanced Assessment Consortium for the reporting of all CAASPP and ELPAC summative and interim assessment results that are housed in CERS as well as for the ongoing maintenance and development of CERS.

##### 7.6.3.A Electronic Student Score Reports

The submission must describe in sufficient detail a solution that must deliver electronic student score reports for LEAs to provide to Parents/Guardians as PDFs and HTML via an application programming interface (API).

The SSRs must be fully compliant and must adhere to CDE Web, Document, and Accessibility Standards and requirements as provided in RFS Section 7.1.5. An LEA or its authorized student information system (SIS) vendor must have the capability to use the API to download the SSR information directly into its SIS. The files must be transferred to the LEA using the same processes outlined in RFS Sections 7.6.3. and 7.6.4.

The submission must describe how the bidder will work collaboratively with the CDE to update the look and content of the SSRs, as required. The design process must incorporate feedback from parents/guardians obtained as part of a focus group process. The design process also must incorporate feedback from interest holders identified by the CDE. The submission must propose a schedule for the development of the SSRs and their approval by the CDE.

The submission must describe in detail how the bidder will provide for an SSR to be reproduced in the top 10 languages in California according to the most recent language report available on the DataQuest website at https://dq.cde.ca.gov/dataquest/. If an LEA indicates that the student comes from a home where Spanish, Vietnamese, Mandarin (simplified Chinese)/Cantonese (traditional Chinese), Filipino, Arabic, or Korean is primarily spoken, both the English SSR and the translated version must be provided in the electronic, downloadable format in the assessment management system.

#### 7.6.4 Reporting to the CDE—Public Reporting Websites

The submission must describe in detail how the bidder will plan for the development, delivery, and hosting of a test results public reporting website. The submission must describe in detail how the bidder will host a UAT version of the test results public reporting website for use by the CDE. In addition, the bidder must provide a preview version of the reporting website for LEAs to preview and verify results prior to public release.

The reporting website must present reports of aggregated results (grade, school, LEA, county, and state) and disaggregated results, including but not limited to, race/ethnicity, gender, economic status, parent education level, migrant status, foster status, homeless status, military status, disability status, English learners, English language fluency, English learners time in program, primary language, and race/ethnicity by economic status. The current public reporting website is available at https://caaspp-elpac.ets.org/.

EC Section 60641 requires the CDE to make statewide summative assessment results publicly available on or before October 15 each year. This data release beginning in 2026 will be in collaboration with the accountability results. The submission must describe in detail how the bidder will ensure that the process includes a schedule and plan that includes joint requirement sessions to capture and refine all public reporting requirements.

The process must ensure and describe in detail how the test results public reporting website will:

      - Be compatible with the California Assessment System environment.

      - Conform to the CDE design, accessibility, writing and content, and application standards specified in the CDE Web, Document, and Accessibility Standards located at https://www.cde.ca.gov/re/di/ws/webstandards.asp. (Note: The public reporting website must be submitted to the CDE WebART for annual review and approval.)

      - Be capable of reporting accurate and complete aggregate data.

      - Incorporate a dynamic, data-driven design that must allow for data update functionality and flexibility in report design.

      - Incorporate a data-visualization design approach.

      - Incorporate a design or display that facilitates the comparison of multiple entities (including schools, LEAs, and counties).

      - Incorporate the California Assessment System (that is, Initial ELPAC, Summative ELPAC, Smarter Balanced summative and non-Smarter Balanced online summative assessments and paper-pencil assessments) reporting into a single user interface.

      - Be designed in such a way that reports for each school year are integrated into a single site that builds on previous years. The site must incorporate results for all operational years for continuing assessments, even if those administrations were completed under a prior assessment contract.

      - Protect the security of individual student data by redacting data whenever 10 or fewer students are included in aggregate data per EC Section 60641. Specifically, an asterisk (*) will be displayed for total enrolled counts and total tested counts of fewer than 4 students and for assessment results for fewer than 11 students. "N/A" will be displayed instead of a number on test results where no data is found for the specific report.

      - Be capable of being protected by a user authentication system during the “LEA preview period” prior to releasing the data to the public.

The submission must ensure that the bidder meets the requirement of delivering the CAASPP and ELPAC reporting data to the CDE.

#### 7.6.5 Data Files

As described in RFS Section 7.3.2.A.9, the submission must describe a reporting solution that allows for the transfer of data to be used by CDE in its data and reporting systems as needed or required. The submission must describe that reporting solution, which must ensure that the bidder will produce and provide to the CDE, on a daily basis, electronic student data files containing results and other information for consumption by and incorporation into CERS and CALPADS.

The submission must describe and demonstrate a process to transmit data files containing testing results using a Secure File Transfer Protocol (SFTP) in a manner determined by the CDE. Data shall be in a fixed record length text file, XML file, and a character-delimited file, as specified by the CDE. The description must ensure that the data content shall be provided in accordance with the following CDE requirements:

      - Provide CAASPP and ELPAC data to CERS and CALPADS.

      - Cross-check editing, summary procedures, and accuracy.

      - Verify the accuracy of internet reports and other public reports.

      - Provide CAASPP and ELPAC data to AMARD to calculate measures for populating the California School Dashboard.

In addition, the submission must describe a reporting solution that allows for the transfer of historical, current, and future CAASPP and ELPAC summative assessment results and historical, current, and future CAASPP and ELPAC interim assessment results data to CERS. Test results must be delivered to CERS by the bidder in Test Results Transmission (TRT) format and using a representational state transfer (REST) protocol.

##### 7.6.5.A Growth Measure Reporting

The submission must describe and demonstrate a procedure for producing residual gain scores for each student record and aggregate the residual gain growth scores to the state, LEA, school, and student group levels (17 student groups at every level) using the methodology adopted by the SBE in accordance with the business rules determined by the CDE. Note: The CDE adopted the empirical best linear prediction (EBLP) methodology for aggregating scores.

The residual gain model will only be used for the Smarter Balanced assessments. They must be included in the same file in which the Smarter Balanced and CAA data are reported.

The submission must describe and demonstrate a process for developing data files containing the aggregate residual gain growth scores at the state, LEA, school, and student group levels.

The submission also must describe and demonstrate a detailed plan for effectively communicating the growth model results to LEA and school administrators as well as to the general public.

#### 7.6.6 Secure File Transfer System

The submission must describe and demonstrate a detailed procedure for performing secure file transfers to and from the CDE. The procedure must describe the method that the bidder will use to securely transfer files to and from the CDE. Given the range of files that must be transferred, the procedures and methods used to transfer data files must address not only California Assessment System results files, but all possible uses of file transfers, such as student-level files, which include registration information, preliminary results; and final student files, which contain all required administrative information, scores, and demographic, item, and record identification elements. The procedure must demonstrate the capacity to provide these files in a timely manner that conforms to file format requirements. The files must be encrypted using a REST protocol.

#### 7.6.7 Technical Report

The submission must describe and demonstrate a process for collecting and presenting the results of the analyses specified in RFS Section 7.6.2 in an annual technical report. Samples of previous technical reports are available at https://www.cde.ca.gov/ta/tg/ca/caaspprptstudies.asp, https://www.cde.ca.gov/ta/tg/ep/elpactechnicalreports.asp, and https://www.cde.ca.gov/ta/tg/ep/summativeelpac.asp. The process must ensure that the technical report is supplied initially as a Microsoft Word document, and the report must be organized and clearly labeled to facilitate cross-referencing with the Standards. The process must ensure that the bidder meets the requirement of preparing a technical report for each summative assessment administered and initial assessments, based on an agreed upon schedule with CDE (refer to RFS Table 1).

The technical reports are subject to the review and approval process and must ensure that the bidder meets the requirement of allowing 20 working days for the CDE’s initial review of each technical report. The reports are due each year by November 1 and at the termination of the contract. Each technical report must be submitted to the CDE in an electronic format.

The technical report documents all aspects of test administration and development. The submission must acknowledge that all narrative reports submitted by the bidder will include an executive summary, the full text, and appendices containing all relevant data tables. The executive summary must be written to stand alone as a document suitable for public distribution. All final narrative reports and all electronic deliverables must be provided in Microsoft Word, PDF, and HTML formats for distribution and posting on the CDE website. The submission must describe in detail how the bidder also will submit Microsoft Excel spreadsheet versions of all tables and technical appendices.

Note: The technical reports should not duplicate any requirements already supplied by the Smarter Balanced Assessment Consortium.

#### 7.6.8 Other Analyses or Reports

The submission must describe a process for collecting test results and test performance data to produce all other analyses or reports required by the CDE to ensure the validity of the assessments and to meet the requirements of state and federal law, including, but not limited to, special studies. The submission must ensure that special studies and research conducted by the bidder will adhere to the American Educational Research Association (AERA) Guidelines for Reporting on Empirical Social Science Research (2006). The following requirements are adapted from the guidelines and represent the basic expectations for reporting results of special studies and research projects contracted for by the CDE.

Overall, reports on special studies and research projects must be:

- Warranted; that is, adequate evidence should be provided to justify the results and conclusions.

- Transparent; that is, reporting should make explicit the logic of inquiry and activities that led from the development of the initial interest, topic, problem, or research question; through the definition, collection, and analysis of data or empirical evidence; to the articulated outcomes of the study.

All reports on empirical research submitted to the CDE should include:

- A problem formulation that provides a clear statement of the purpose and scope of the study. It should describe the question, problem, or issue the study addresses, situate it in context, and describe the approach taken to addressing it.

- A review of the relevant scholarship that bears directly on the topic of the report. It should include a clear statement of the criteria used to identify and select the relevant scholarship in which the study is grounded. The rationale for the conceptual, methodological, or theoretical orientation of the study should be described and explained with relevant citations to what others have written.

- A specific and unambiguous description of the design—the way the sources of evidence for data collection or data identification activities selected for and organized in the investigation. Significant developments or alterations in the research questions or design should be described and a rationale for the changes presented.

- A complete description of the data or empirical materials that were collected, the methods used to collect the data, and the source(s) of the data or materials collected. The means of selection of the sites, groups, participants, events, or other units of study should be described.

- A complete description of measurement instruments used or classification systems developed to analyze the data. The description must include evidence of the meaningfulness and appropriateness of the measure or classification system for capturing important characteristics of the groups or individuals being studied. With qualitative methods in particular, classification is integral to the data analysis process.

- The procedures used for analysis should be precisely and transparently described from the beginning of the study through presentation of the outcomes. Descriptive and inferential statistics should be provided for each of the statistical analyses essential to the interpretation of the results. Any considerations that arose in data collection or identified during data analysis and processing that might compromise the validity of the statistical analysis or inferences should be reported.

- For qualitative studies, the procedures used for analysis should be precisely and transparently described from the beginning of the study through presentation of the outcomes. Analytic techniques should be described in sufficient detail to permit understanding of how the data were analyzed and the processes and assumptions underlying specific techniques. Analysis and interpretation should include information about any intended or unintended circumstances that may have significant implications for interpretation of the outcomes, limit their applicability, or compromise their validity. If coding processes were used, the description should include, as relevant, information on the backgrounds and training of the coders; inter-coder reliability or outcomes of reviews by other analysts; and, where relevant, indications of the extent to which those studied (participants) agree with the classifications.

- For quantitative studies, reporting should clearly state what statistical analyses were conducted and the appropriateness of the statistical tests, linking them to the logic of design and any claims or interpretations based on them. For each of the statistical results that is critical to the logic of the design and analysis, there should be an indication of the uncertainty of the results such as a standard error or a confidence interval. When hypothesis testing is used, the test statistic and its associated significance level should be presented along with a qualitative interpretation of the meaningfulness of the results in terms of the questions the study was intended to answer.

- A presentation of conclusions and recommendations that provide a statement of the following: (a) how claims and interpretations address the research problem, question, or issue underlying the research; (b) show how the conclusions connect to support, elaborate, or challenge conclusions in earlier scholarship; and (c) emphasize the theoretical, practical, or methodological implications of the study.

The process must ensure the annual submission, by the bidder, of a brief description of special studies for review and approval by the CDE prior to conducting the studies. Some special studies identified for this contract are:

##### 7.6.8.A California Spanish Assessment: Threshold Validation Study

The bidder will conduct a threshold score validation study to evaluate the degree to which the threshold scores and achievement levels of the California Spanish Assessment consistently distinguish between levels of students’ achievement when compared to teacher ratings from a multistep process.

##### 7.6.8.B California Spanish Assessment: Spanish Lexile Alignment Study

The submission must describe in detail how the bidder will conduct a Spanish Lexile linking study based on the results of the CSA to determine the reading measure of how well a student reads and comprehends text written in Spanish based on the overall or subscores on the assessment. A result of this linking study could be used but not limited to the production of Spanish Lexile reading scores to be placed on the student score report to be used at minimum to select appropriate Spanish reading materials. More information on Spanish Lexiles is available at https://partnerhelp.metametricsinc.com/concept/spanish_lexile_reading_and_text_measures.html.

#### 7.6.9 Rescore Requests

The submission must describe in sufficient detail the process for hand scoring both online tests and submitted paper-pencil answer books if an LEA makes the request in writing within 30 working days of the receipt of the SSRs or, if the SSRs were not received during the summer when schools were closed, within the first 30 days of the LEA’s instructional year. The process must ensure that the LEA is provided with a form for requesting rescoring. The submission must acknowledge that, in the case that the rescoring indicates any anomalies, the bidder will verify the correct scores and issue the appropriate SSRs. In such a case, no charge will be made to the LEA. However, if no anomaly is determined, the bidder may charge for this service at a rate approved by the CDE. The rate may not exceed the actual cost to the bidder to rescore. The submission must describe how the bidder will also conduct rescoring requests by the CDE when a need is identified at no charge to the CDE.

## 8. BUDGET DETAIL AND PAYMENT PROVISIONS

### 8.1 Invoicing and Payment

For services satisfactorily rendered, and upon receipt and approval of the invoices, the CDE agrees to compensate the Contractor for actual expenditures incurred in performance of this Agreement not to exceed the amount budgeted in each FY. Should legislation subsequent to execution of the Agreement make a task or activity set forth in the Agreement unnecessary, the CDE will notify the Contractor of the change as soon as practicable. The Contractor will not be reimbursed for costs incurred after the relevant legislation becomes operative for the affected task or activity, or if such legislation is effective retroactively, the date that CDE issues a stop work order.

Payment of the invoice will not be made until the CDE accepts and approves the invoice. To be approved the invoice must include the level of detail described in the Budget for each task and for the FY in which the expense was incurred. The total costs invoiced for any FY may not exceed the amount for that FY in the Budget.

With each monthly invoice submitted for reimbursement, the Contractor must attach a written progress report containing the information set forth in RFS Section 7.1.7. The progress report must contain a detailed narrative so that the CDE staff can compare the invoice to the Budget contained herein. The progress report must be delivered as an original hard copy or electronic record, as directed by the CDE. In addition, the CDE will not approve an invoice for payment on this Agreement until it receives and approves the monthly progress report.

The Contractor must retain and update records and accounts, including original source records, necessary to support all costs and must be able to prepare and submit statistical, narrative, and/or financial and program reports and summaries related to this Agreement as requested by CDE or by the SBE.

Invoices shall be itemized per the Budget, using RFS Attachment 10B and 10C, and shall include the Contract Number—CN260003, dates of services, and shall be submitted in arrears. Each invoice shall contain a progress report outlining the costs being invoiced per task and subtask, by FY and by administrative test cycle. The tasks identified in the invoice must match the tasks set forth in the Budget. Invoices shall be sent, along with a progress report (refer RFS Section 7.1.7), not more frequently than monthly in duplicate to:

California Department of Education

Assessment Development and Administration Division

1430 N Street, Suite 4409

Sacramento, CA 95814

Attention: Chad Portney, CDE Contract Monitor

Email: cportney@cde.ca.gov

### 8.2 Budget Contingency Clause

A.	It is mutually understood between the parties that this Agreement may have been written before ascertaining the availability of federal and/or state funds, for the mutual benefit of both parties in order to avoid program and fiscal delays that would occur if the Agreement were executed after that determination was made.

B.	This Agreement is valid and enforceable only if sufficient funds are made available to the State by the United States Government and/or California State Legislature for the FYs covered by this Agreement for the purpose of this program. In addition, this Agreement is subject to any additional restrictions, limitations, or conditions, imposed by the federal or California government that may affect the provisions, terms or funding of this Agreement in any manner.

C.	It is mutually agreed that if the Congress or the State Legislature does not appropriate sufficient funds for the program or the federal or state executive branch does not disburse sufficient funds, the CDE has the option to void the Agreement under the 30-day termination clause set forth in RFS Section 10.4, Right to Terminate or to amend the Agreement to reflect any reduction of funds actually received by CDE. If the CDE terminates the Agreement, it agrees to pay the contractor for work completed based on the contractor’s actual final invoice of actual expenses incurred, up to and including the day of termination.

D.	Pursuant to GC Section 927.13(e), no late payment penalty shall accrue during any time period for which there is no Budget Act in effect, nor on any payment or refund that is the result of a federally mandated program or that is directly dependent upon the receipt of funds by a state agency.

E.	The Contractor shall comply with reporting requirements set forth in Office of Management and Budgets (OMB) Uniform Grants Guidance, subpart F commencing at Title 2 Code of Federal Regulations (CFR) Section 200.500. For purposes of this Agreement, the Contractor is considered a contractor and not a sub-recipient.

### 8.3 Travel

All travel costs shall be reimbursed at rates not to exceed those established for the State of California’s non-represented employees, computed in accordance with and allowable pursuant to applicable California Department of Human Resources regulations as specified on the CalHR website. For current rates, refer to https://www.calhr.ca.gov/employees/pages/travel-reimbursements.aspx.

### 8.4 Prior Approval of Out-of-State Travel

All out-of-state travel by the Contractor or subcontractor(s) for purposes of this Agreement is subject to prior written approval by the CDE contract monitor specified in this Agreement.

### 8.5 Excise Tax

The State of California is exempt from federal excise taxes, and no payment will be made for any taxes levied on the Contractor’s employees’ wages. California may pay any applicable sales and use tax imposed by another state.

### 8.6 Budget Adjustments

Per EC Section 60643(b)(1), the CDE, in consultation with the SBE, may make material amendments to the Agreement that do not increase the agreement cost. Agreement amendments that increase costs may only be made with the approval of the CDE, the SBE, and the Department of Finance.

### 8.7 Liquidated Damages

The Contractor shall pay liquidated damages in the amount of up to 10 percent of the

total cost of the Agreement for any component task per test administration that the

Contractor through its own fault or that of its subcontractors fails to substantially perform

by the date specified in the Agreement. (EC Section 60643[b][4])

### 8.8.	Prompt Payment Clause

Payment will be made in accordance with, and within the time specified in GC, Chapter 4.5, commencing with Section 927.

### 8.9 Payment Withhold for Separate and Distinct Tasks

In accordance with EC Section 60643(b)(3), the CAASPP and ELPAC contracts shall include provisions for progress payments to the Contractor(s) for work performed or costs incurred in the performance of the Agreement.

The CDE shall withhold not less than 10 percent of the amount budgeted for each separate and distinct component task per test administration provided for in each contract/Agreement pending final completion of all component tasks by the Contractor. Invoices will be paid upon satisfactory performance of each component task as determined by the SBE as described in Article 8.10. Those annual activities that are completed and repeated in their entirety each year shall be considered separate and distinct tasks that are to be paid following satisfactory completion in each year of the Agreement.

Final Payment is not a progress payment and is not subject to the 10 percent withholding.

### 8.10 Process for Release of Payment and Withhold

Pursuant to EC Section 60643(b)(5), the following establishes the process and criteria by which the successful completion of each component task shall be recommended by the CDE and approved by the SBE.

1. Process

- SBE Determination: During the term of the Agreement, based on the criteria set forth below, the SBE will consider at its November Board Meeting, or the next meeting thereafter if a November meeting is not held, whether the Contractor has successfully completed each component task for the prior FY. If the SBE determines the Contractor has not successfully completed each component task for the prior FY, it shall, within 10 business days of its determination, notify the Contractor and the CDE in writing which component tasks the SBE has determined that the Contractor has failed to successfully complete. The Contractor shall have 10 days from receipt of the notice to respond in writing, and the response shall be promptly delivered to the CDE Contract Monitor.

If the Contractor contests the decision of the SBE, the CDE and the Contractor will have an opportunity to discuss the issues before the SBE at the following SBE meeting. The SBE will, at that subsequent meeting, make its final determination based on the criteria set forth below, as to whether the contractor has successfully completed each task or component of a task for the prior FY and releases the withholding for those component tasks.

- Release: Once the SBE has determined that the Contractor has successfully completed a component task, the 10 percent withheld from invoices for the component task for the prior FY may be released by the CDE. The Contractor must submit an invoice to CDE for the withheld amounts for each component task which SBE authorized release. The Contractor must identify the prior invoice from which the money was withheld and the applicable component task in its invoice for the released withholding.

- Criteria

The criteria by which the CDE will recommend and the SBE will determine the successful completion of each separate and distinct component task for payment of the final 10 percent is set forth in the following table for each test administration covered in the Scope of Work of the Agreement.

If it is determined by the CDE that a certified deliverable submitted to the CDE by the Contractor does not meet all of the criteria for each task, the CDE reserves the right to use this information as part of the criteria by which the CDE will recommend, and the SBE will determine, successful completion of each separate and distinct component task for payment of the final 10 percent for each applicable test administration as set forth in RFS Table 29.

Table 29. California Assessment System Completion Criteria by Component Task

| Component Task | Criteria |
| --- | --- |
| Task 1: Comprehensive Plan and Schedule of Deliverables | - The Contractor provided all reports, plans and schedules required in the task as specified in the SOW. - All materials, documents, and/or deliverables developed in conjunction with this Agreement were submitted to the CDE for approval. - The Contractor provided the local educational agency (LEA) coordinators with all data, forms, and agreements as outlined in the SOW. - The Contractor provided and maintained a secure web-based project management system as specified in the SOW. - The Contractor delivered all electronic data files and documentation as specified in the SOW. - At the end of the Agreement, the Contractor will develop and implement a plan and schedule for transition to another vendor, including the delivery of all California-owned materials, developed specifically for the California Assessment System. This will not include any third party or previously developed, proprietary software embedded in the System. |
| Task 2: Program Support Services | - The Contractor provided all trainings, focus groups, workshops, and webcasts as specified in the SOW. - The Technical Assistance Center provided assistance to LEAs as specified, and within the response times specified, in the SOW. - The CDE and LEAs received electronic files and other reports as specified in the SOW. |
| Task 3: Technology Services | - The Assessment Technology Platform meets all system requirements as specified in the SOW. - The Contractor provided an access management system as detailed in the SOW. - The Contractor provided and maintained a Project Management Plan as detailed in the SOW. - The Assessment Technology Platform supported up to two million concurrent users as specified in the SOW. - The Assessment Technology Platform system supported at least 99.982 percent availability as specified in the SOW. |
| Task 4: Assessment Development and Accessibility | - The Contractor developed for all grades and subjects the number and types of items specified in the SOW. - The Contractor pilot tested or field tested the minimum required number of items as specified in the SOW. - The Contractor provided and followed high-level test design and blueprints for assessments as specified in the SOW. - A review of the scaling and equating processes showed items to meet or exceed industry standard. - The performance and achievement level settings generated results for all content areas and performance levels were reported to LEAs and the CDE. - The Contractor provided all documentation and supported submissions of federal assessment peer review, where applicable. - The Contractor provided all universal tools, designated supports, and accommodations as required in the SOW. - All items developed include all the embedded accessibility supports, functionality, and render within the TDS as specified in the SOW. |
| Task 5: Test Administration and Security | - All test materials required in the SOW were produced on time and in sufficient quantities. - All test materials were delivered to and retrieved from LEAs as specified in the SOW. - The Contractor hosted the Assessment Delivery System as specified in the SOW. - The hosting systems were operational and functioned as specified in the SOW, including the authentication of users. - Smarter Balanced Interim Assessments were hosted and scoring provided as specified in the SOW. - All test items, test materials, electronic files, data, (including student-identifiable data) were developed, used, transferred, delivered, and maintained in a secure manner as specified in the SOW. - The Contractor completed all monitoring (including but not limited to on-site visits, social media monitoring, inventorying of materials) of schools before, during, and after testing as specified in the SOW. - The Contractor conducted security breach investigations as specified in the SOW. - The Contractor provided the CDE with summary reports of the results of each security breach investigation. |
| Task 6: Scoring and Reporting | - All tests were correctly processed and scored within timelines specified in the SOW. - All data analysis were completed as specified in the SOW. - The Contractor delivered all electronic data files and documentation as specified in the SOW. - The Contractor provided accurate and complete reports of test results to LEAs that met all reporting requirements as specified in the SOW. - The Contractor provided accurate and complete data to the designated CDE vendor for CERS that met all requirements as specified in the SOW. - The Contractor provided accurate and complete reports of test results for the public reporting websites that met all reporting requirements as specified in the SOW. - The Contractor met all reporting requirements to the CDE as specified in the SOW. - The annual technical reports were received by the CDE as specified in the SOW. - The Contractor will propose and execute special studies as described in the SOW. |

## 9. GENERAL TERMS AND CONDITIONS

The General Terms and Conditions, GTC 02/2025 will be incorporated by reference and made part of the contract and also found at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language.

## 10. SPECIAL TERMS AND CONDITIONS

### 10.1 Information Technology Requirements

For agreements that require the Contractor to develop, modify, or maintain any type of web product (which includes but is not limited to a web page, web document, website, web application, or other web service), or agreements that include a web product as a deliverable or result, Contractor hereby agrees to adhere to the following CDE standards:

- All website and application pages or documents visible to users are subject to review and approval by the Contract Monitor or their authorized designee. If the Contract Monitor requires specific content to be reviewed before it is posted or made available, the Contractor must obtain approval prior to publishing that content. This requirement supersedes and replaces the Department’s DEAM 3900 policy for this Agreement.

- Websites and web applications must adhere to the CDE Web, Document, and Accessibility Standards, found at https://www.cde.ca.gov/re/di/ws/webstandards.asp. The Department’s DEAM 3900 policy does not apply to this Agreement.

- Contractor must provide the application and/or website source code (for all non-proprietary software systems or components paid for by the CDE), collected data, and project documentation for the Contractor and any subcontractor developed California-specific application only, in a form to be specified by the CDE according to the following time frame:

  - For California only new sites/applications: Within 30 days of implementation. For multi-year agreements, material must also be provided annually on the agreement date anniversary during the agreement period.

  - For existing sites/applications: Within 90 days of the contract renewal or amendment execution. For multi-year agreements, material must also be provided annually on the contract date anniversary during the contract period.

- Contractor shall monitor the website/application on a monthly basis (or more frequently if necessary) to identify and correct the following issues:

  - Broken links

  - Dated content

  - Usability issues

  - Circumstances where the contractual agreement is not followed

- Contractor agrees to not violate any proprietary rights or laws (i.e., privacy, confidentiality, copyright, commercial use, hate speech, pornography, software/media downloading, etc.). Also, the Contractor agrees to make all reasonable efforts to protect the copyright of CDE content and to obtain permission from the CDE Press to use any potentially copyrighted CDE material, or before allowing any other entity to publish copyrighted CDE content.

- Contractor agrees that any web applications, websites, data or other files which may be needed to restore the system in the event of disaster are backed up redundantly, and that a detailed, tested plan exists for such a restoration.

- Contractor shall provide the CDE with website usage reports on a monthly basis during the agreement period for each web page, document or file which can be viewed by users. Additionally, Contractor shall provide an easy mechanism for users to provide feedback on the site/application, such as a feedback form.

### 10.2 Data Management Requirements

  - Definitions: The following definitions apply for the purposes of this Agreement:

“Aggregated Data” means any data expressed in a summary form, for purposes such as statistical analysis to de-identify the Data and prevent unlawful or unauthorized disclosure of PII and/or Student or Individual-Level Data.

“Confidential Information” means information maintained by state agencies that is exempt from disclosure under the provisions of the California Public Records Act (Government Code Section 7920.000) or other applicable state or federal laws, whether or not marked “confidential,” “proprietary,” “privileged” or with similar markings. Confidential Information means Proprietary Information, PII, and Student or Individual-Level Data, as each are defined below.

“Data” means any digital or hard copy records or information, whether Confidential or publicly available.

“Personally Identifiable Information (PII)” means information about an individual, and includes but is not limited to information that, alone or in combination, is linked or linkable to a specific student or individual in a manner that would allow a reasonable person in the community, who does not have personal knowledge of the relevant circumstances, to identify the student or individual with reasonable certainty. PII includes, but is not limited to name, address, personal identifier (e.g., Social Security number, student number, biometric record), other indirect identifiers (e.g., date or place of birth, mother’s maiden name). “Biometric record” includes a fingerprint, retina, or iris pattern, voiceprint, DNA sequence, handwriting sample, facial geometry or other biological or behavioral characteristic used to identify an individual. PII are sensitive information that may occur in public and/or confidential records. Files and databases containing PII require special precautions to prevent inappropriate disclosure.

“Preferred Variation” means the particular variation of the name, definition, and format for a Data element or code set that is used by CDE to maintain order and consistency in its Data. To date, hundreds of common Data elements have been specified by the CDE (contact the EDMD for the most recent published list of Preferred Variations).

“Proprietary Information” means information contained in materials marked “confidential,” trade secrets, know-how, data and other information, in tangible and intangible form possessed by a party and having value by virtue of not being generally known or due to being obtained at significant effort or expense. Each party acknowledges that information supplied by a third-party to the other party under provisions of confidentiality shall be considered, for the purposes of this Agreement, to be the other party’s Proprietary Information.

“Student or Individual-Level Data” means demographic, performance, and other information that pertains to a single student or individual but cannot be attributed to a specific student or individual. Such Data is subject to compliance with applicable laws such as, but not limited to, the Family Educational Rights and Privacy Act (FERPA), the Pupil Protection Rights Amendment (PPRA), the Children’s Online Privacy Protection Act (COPPA), and the California Education Code (EC).

  - Confidentiality Conflicts and Public Record Act Requests: Notwithstanding any obligation of confidentiality or non-disclosure between the parties or any “confidential,” “proprietary,” or “privileged,” marking on documents provided by Contractor, any writing, regardless of form, containing information related to the conduct of the public’s business prepared, owned, used or retained by the CDE is subject to disclosure pursuant to the Public Records Act (PRA) (Govt. Code 7920.000 et. seq.) and other applicable law, unless an exemption from disclosure applies. Contractor shall immediately notify CDE of any request for documents and/or Data that it receives and shall further work cooperatively with CDE to allow CDE to respond correctly to Public Records Act requests in a timely manner.

  - Compliance with Statutory and Contractual Requirements: In the course of performing this Agreement, Contractor may gather or process or otherwise be intentionally or inadvertently exposed to Confidential Information, including personally identifiable educational records as defined in federal or California law. The Contractor must use, disclose, manage and protect Confidential Information in accordance with any terms of the Agreement, the contractual provisions set forth below, as well as all applicable federal and California law. Applicable laws may include, but are not limited to: the Family Educational Rights and Privacy Act of 1984 (FERPA; 20 U.S.C. Sec. 1232g), the Protection of Pupil Rights Amendment (PPRA; 20 U.S.C. Sec. 1232h), the Information Practices Act (California Civil Code Sec. 1798, et seq.), the Children’s Online Privacy Protection Act (COPPA; 15 U.S.C. Se 6501 et seq.), the California Education Code sections 49069.7 et. seq., and SAM sections 5300-5365.3. These obligations continue even after expiration of this Agreement.

  - Contractor as CDE Authorized Representative: Contractor agrees to serve as the CDE’s authorized representative in the event the Agreement provides for the Contractor to be exposed to, or provided with, PII pertaining to students or individuals in order to carry out an audit or evaluation of Federal- or state-supported education programs, or for the enforcement of or compliance with Federal legal requirements related to these programs.

  - Subcontractors: CDE must, at its discretion, approve in writing each of Contractor’s proposed subcontractors who may be exposed to CDE Confidential Information.  Contractor shall request any such approval in advance and provide CDE with: i) a copy of the proposed subcontract; ii) background information about the subcontractor and its executives; and iii) any other information reasonably requested by the CDE.

  - Use and Disclosure/Data Security: Contractor shall only allow those employees, agents, and subcontractors to have access to Confidential Information as necessary to perform any duties or functions associated with the Agreement. The Contractor, its employees, agents, and subcontractors shall protect from unauthorized disclosure all PII, sensitive information, or Confidential Information. The Contractor, its employees, agents, and subcontractors promise not to copy, give or otherwise redisclose such PII, sensitive information, or Confidential Information to any other person or entity unless the redisclosure is permitted by federal and state law, the CDE has approved of the redisclosure, and the CDE has on file a CDE confidentiality agreement that is signed by the party to whom the information has been disclosed.

The Contractor fully understands that any unauthorized disclosure made by the contractor, its employees, agents, or subcontractors may be a basis for civil or criminal penalties and/or disciplinary action (including dismissal for State employees). The Contractor will immediately inform the CDE Contract Monitor in the event that the Contractor, its employees, agents, or subcontractors either learns or has reason to believe that any person who has access to confidential information has or intends to disclose that information in violation of this agreement.

Contractor and its subcontractors shall exercise all reasonable security measures, including any additional security precautions that have been approved by the CDE’s EDMD and TSD to prevent unauthorized use, access, modification or disclosure/re-disclosure of any Confidential Information. Such security precautions shall include, at a minimum (and without limiting the generality of the use and disclosure restrictions set forth above):

- Securely encrypting and otherwise complying with best practices in order to securely protect Confidential Information that is transmitted electronically or stored on portable electronic devices;

- Securely locking any repository for Confidential Information;

- Provide appropriate levels of security (confidentiality, integrity, and availability) for the data based on data categorization and classification and FIPS Publication 199 protection levels;

- Properly maintaining security of any and all computer systems (hardware and software applications) used to store or process Confidential Information, including installing all security patches, upgrades, and anti-virus updates;

- Designating a Security Officer to oversee such Party’s Data security program, carry out privacy programs and to act as the principal point of contact responsible for communicating on security matters with the CDE;

- Immediately reporting (within two hours of discovery) to the CDE any breach of security, per California Civil Code section 1798.29(d), to:

Matthew Mellow, Chief Information Security Officer

California Department of Education

Technology Services Division – Information Security and Privacy Office

1430 N Street, Suite 3712

Sacramento, CA 95814-5901

Office phone: 916-327-3852

Email: ISO@cde.ca.gov

- Promptly taking corrective action to cure any such breach of security. Contractor shall investigate such breach and provide a written report of the investigation to the CDE via email and within 30 working days of the discovery of the breach to address the above.

- Implementing any other reasonable security protocols for PII or Student or Individual-Level Data that may be prescribed by the CDE’s TSD in a written notice to Contractor.

- Making and distributing copies of Data only as necessary to perform the obligations hereunder in full compliance with the other terms hereof, keeping accurate records of any such copies (including any back-ups), and legally and physically controlling such copies in a manner that prevents unauthorized duplication, use or disclosure.

The Contractor shall retain and provide CDE upon written request with a copy of any compliance agreements required pursuant to the Scope of Work, which include signed confidentiality statements, training certifications, and other documentation necessary to demonstrate compliance with this provision.

  - Data Formatting and Delivery: All PII or Student or Individual-Level Data to be delivered from one party to the other hereunder shall i) be in a format, ii) use nomenclature, iii) be delivered in compliance with security protocols, and iv) meet any other specifications, all as set forth in Data delivery and file layout specifications approved by the CDE EDMD. As early as reasonably possible in the Data delivery process, but in no event less than 12 weeks prior to Data delivery to CDE or 6 weeks prior to Data delivery to Contractor, Contractor shall submit for CDE approval its proposed Data delivery and file layout specifications, including the proposed secure file transfer protocols, formatting, nomenclature and other specifications to be used. The scope of work may specify additional requirements for the proposed data delivery and file layout specifications, such as additional time between the proposed Data Delivery and file layout specification and Data delivery for those cases where a data reporting structure needs to be built, where special provisions are needed for working with other CDE Contractors, etc.

- Data Delivered to CDE: Unless otherwise agreed by the CDE in writing, the Contractor shall use CDE’s Preferred Variation of each data element in the proposed file layout specification for data delivery to the CDE. In the event that the CDE has not yet formulated a Preferred Variation for a particular Data element, the Contractor shall consult with the CDE to reach a resolution. The Contractor shall cooperate with CDE and shall make each change to the proposed Data delivery and file layout specification that is requested by the CDE in order to gain written approval. Thereafter, all PII and Student or Individual-Level Data shall be delivered in a file conforming to the approved Data delivery and file layout specifications, as they may be revised from time-to-time. In addition, all PII and Student-Level Data deliveries to the CDE shall be accompanied by a complete Data Dictionary that describes and defines in detail the meaning of all symbols, abbreviations, codes and other descriptors contained in the file provided by Contractor to the CDE.

- Data Delivered to Contractor: If a scope of work specifies the delivery of PII or Student or Individual-Level Data from the CDE to Contractor, Contractor shall specify its requested Data delivery and file layout specifications in a submission to the CDE for approval. The CDE will review the requested specifications for inconsistencies, data definitions that do not align with CDE’s preferred variations and for data elements that do not yet exist or need extraction, redaction, compilation, aggregation or the like. The CDE will indicate to Contractor whether the request can be met and CDE’s estimated costs to meet such requirements. The parties shall revise the Data delivery and file layout specifications until mutually acceptable. Unless otherwise agreed in writing in advance, CDE may charge Contractor for its reasonable costs, including staff time, computing time and materials, in order to meet Contractor’s requested specifications.

Contractor acknowledges that CDE maintains and uses Data collected from a variety of diverse sources and that compliance with these Data formatting and delivery provisions is necessary to maintain Data order and for the consistent and effective use of Data by the CDE, regardless of the source of the Data and regardless of how the Data has been collected, developed, matched, aggregated, linked, connected or otherwise generated for use by CDE.

  - De-Identification of PII: Contractor may not attempt to create, use or disclose Aggregated Data or other forms of de-identified Data, except as CDE may expressly authorized in writing in the scope of work. Any Aggregated Data that is authorized by CDE shall be created in compliance with best practices to minimize disclosure risk (e.g., those outlined in the NCES SLDS Technical Brief “Statistical Methods for Protecting Personally Identifiable Information in Aggregate Reporting”) and shall be aggregated using a methodology approved in writing in advance by the CDE. The NCES SLDS Technical Brief is located at https://nces.ed.gov/pubs2011/2011603.pdf.

  - Data Destruction: Contractor shall return or destroy in accordance with the CDE’s instructions any and all CDE Data, including, without limitation, Data: i) provided by CDE hereunder, ii) developed by Contractor for CDE hereunder, or iii) otherwise owned by CDE. Such return or destruction shall occur i) immediately upon CDE’s request, ii) immediately upon termination of this Agreement, or iii) prior to any merger, combination, acquisition, or other change in control of the Contractor, unless CDE, at its sole discretion, gives prior written consent to the change in control and the appropriate parties execute any additional documents CDE specifies in order to preserve or extend the obligations hereunder. Unless otherwise agreed to in writing by the CDE, such destruction shall include Data that is publicly available; however, nothing herein shall prevent the Contractor from thereafter obtaining such Data from publicly available sources. Contractor agrees to submit a letter to the CDE within 30 calendar days of the destruction of the Data attesting to the destruction of all Data obtained from the CDE under this Agreement.

  - Data Ownership and Possession: Contractor acknowledges that any and all Data that are collected, developed and/or generated by Contractor at CDE’s expense are the sole and exclusive Proprietary Information of the CDE and may not be used or disclosed by Contractor except as expressly permitted by the CDE in writing. CDE acknowledges that software and Data previously developed by Contractor at Contractor’s sole expense, without contribution or reimbursement from the CDE, is Contractor Proprietary Information.

  - Subsequent Data Disclosures: Notwithstanding any other provision of this Agreement, any future disclosure of PII or Student or Individual-Level Data by the CDE is subject to CDE’s internal approval processes and applicable law.

### 10.3 Resolution of Disputes

If the Contractor disputes any action by the CDE Contract Monitor arising under or out of the performance of this agreement, the Contractor shall notify the CDE Contract Monitor of the dispute in writing and request a claims decision. The CDE Contract Monitor shall issue a decision within 30 days of the Contractor's notice. If the Contractor disagrees with the CDE Contract Monitor’s claims decision, the Contractor shall submit a formal claim to the Superintendent of Public Instruction or the Superintendent's designee. The decision of the Superintendent shall be final and conclusive on the claim unless the decision is arbitrary or capricious. The decision may encompass facts, interpretations of the agreement, and determinations or applications of law. The decision shall be in writing following an opportunity for the Contractor to present oral or documentary evidence and arguments in support of the claim. Contractor shall continue with the responsibilities under this Agreement during any dispute.

### 10.4 Right to Terminate

Only the CDE has the right to terminate this Agreement subject to 30 working days written notice to the Contractor. Contractor may submit for approval a written request to the CDE to terminate this Agreement if CDE substantially fails to perform its responsibilities provided under the Agreement upon 30 working days written notice.

The Agreement can be immediately terminated by the CDE for cause. The term “for cause” shall mean that the Contractor fails to meet the terms, conditions, and/or responsibilities of the agreement. In this instance, the agreement termination shall be effective as of the date indicated on the State’s notification to the Contractor.

This Agreement may be suspended or cancelled without notice, at the option of the Contractor or the CDE, if the Contractor or CDE’s premises or equipment are destroyed by fire or other catastrophe, or so substantially damaged that it is not reasonably possible to continue service, or in the event the Contractor determines or the CDE finds that the contractor is unable to render all services as a result of any action by any governmental authority. The CDE is not responsible for payment for any work conducted by the contractor during any period of suspension or after the date of cancellation.

### 10.5 Termination for Targets of Economic Sanctions; Executive Order N-6-22 – Russia Sanctions

On March 4, 2022, Governor Gavin Newsom issued Executive Order N-6-22 (the EO) regarding Economic Sanctions against Russia and Russian entities and individuals. “Economic Sanctions” refers to sanctions imposed by the U.S. government in response to Russia’s actions in Ukraine, as well as any sanctions imposed under state law. In compliance with the EO, Bidder and/or Contractor represents that it is not a target of Economic Sanctions. Should the State determine Bidder and/or Contractor is a target of Economic Sanctions or is conducting prohibited transactions with sanctioned individuals or entities, that shall be grounds for rejection of the Bidder’s proposal any time prior to contract execution, or, if determined after Agreement execution, shall be grounds for termination by the State.

### 10.6 Information and Communications Technology Accessibility Requirements (05/2018)

Unless the scope of work expressly provides that the CDE shall be responsible for all 508 compliance:

- Contractor shall, in accordance with California GC Section 7405 (which requires state agencies to comply with Section 508 of the federal Rehabilitation Act of 1973 [Section 508]), ensure that any and all Information and Communications Technology (ICT) deliverables developed, procured, or maintained as a result of this Agreement shall comply with state and federal accessibility requirements, including: (i) the Web Content Accessibility Guidelines (WCAG) 2.1 at the conformance level of AA found at https://www.w3.org/TR/WCAG20/, (ii) the CDE’s Web, Document, and Accessibility Standards found at https://www.cde.ca.gov/re/di/ws/webstandards.asp, and (iii) the CDE’s WebART review process found at: https://www.cde.ca.gov/re/di/ws/webartproc.asp.

- The definition of “Information and Communications Technology” or “ICT” includes but is not limited to: computer hardware, software, cloud services, websites, web content, web or mobile application, office documents (e.g., MS Word, MS Excel, MS PowerPoint, PDF), multimedia, social media, email, and electronic devices.

- Contractor shall employ a section 508 compliance expert with qualifications and experience acceptable to the CDE to: (i) advise Contractor during ICT deliverable development, and (ii) certify in writing on behalf of Contractor that the ICT deliverables are fully compliant with the standards in subsection A above and Section 508 prior to submission to, or use by, the CDE.  Such certification shall also include a statement describing precise methods by which compliance was determined, along with the results of testing.  The Contractor is responsible for any costs associated with breach of such certification.

- Upon CDE’s request, the Contractor must provide to the CDE all source files for ICT deliverables to the CDE for the purpose of improving accessibility. This may include non-proprietary code, unedited pictures and video, and original documents prior to PDF conversion among others.

### 10.7 Prohibition of Discrimination

In addition to the non-discrimination requirements in RFS Section 9 General Terms and Conditions, Contractor and its subcontractors shall comply with Education Code Section 220, which prohibits discrimination on the basis of disability, gender, gender identity, gender expression, nationality, race or ethnicity, religion, sexual orientation, or any other characteristic that is contained in the definition of hate crimes set forth in Section 422.55 of the Penal Code, including immigration status, in any program or activity conducted in connection with this Agreement.

### 10.8 Health and Safety

Contractors are required to, at their own expense, comply with all applicable health and safety laws and regulations. Upon notice, Contractors are also required to comply with the state agency’s specific health and safety requirements and policies. Contractors agree to include in any subcontract related to performance of this Agreement, a requirement that the subcontractor comply with all applicable health and safety laws and regulations, and upon notice, the state agency’s specific health and safety requirements and policies.

## 11. ADDITIONAL PROVISIONS

### 11.1 Contract Amendment

Per EC Section 60643(b)(1), the CDE, in consultation with the SBE, may make material amendments to the contract that do not increase the contract/Agreement cost. Contract amendments that increase contract costs may only be made with the approval of the CDE, the SBE, and the DOF.

No changes or variation of the terms of any Agreement between the CDE and the Contractor shall be valid unless formally amended in writing, signed by the parties and approved as required. No oral understanding or agreement not incorporated in the written agreement between the parties is binding on any of the parties.

### 11.2 Contractor Evaluation

Within sixty (60) days after the completion of this Agreement, the CDE Contract Monitor shall complete a written evaluation of Contractor’s performance under this Agreement. If the Contractor did not satisfactorily perform the work, a copy of the evaluation will be sent to the State Department of General Services, Office of Legal Services, and to the Contractor within 15 working days of the completion of the evaluation. (PCC Section 10369)

### 11.3 Contractor’s Rights and Obligations

PCC sections 10335 through 10353.51 contains language describing the Contractor's duties, obligations and rights under this Agreement. By signing this Agreement, the Contractor certifies that they have been fully informed and agrees to abide by these provisions of the PCC as applicable.

### 11.4 Insurance Requirements

1.	Contractor, at their own expense, shall maintain the following insurance coverage for the term of this Agreement:

        - General Liability:

General liability with limits of not less than $1,000,000 per occurrence for both injury and property damage combined. The policy should include coverage for liabilities arising out of premises, operations, independent contractors, products completed operations, personal and advertising injury and liability assumed under an insured agreement. This insurance shall apply separately for each insured against whom claim is made or suit is brought subject to the Contractor’s limit of liability. If the policy contains an annual aggregate, this should be at least double the per occurrence limit.

        - Automobile Liability:

Motor vehicle liability with limits not less than $1,000,000 per accident. Such insurance shall cover liability arising out of a motor vehicle accident including owned, hired, and non-owned motor vehicles. The Contractor shall insure that any subcontracts include the same provisions as stated herein.

        - Workers Compensation and Employers Liability:

Contractor shall maintain statutory workers compensation and employer’s liability coverage for all its employees who will engage in the performance of the Agreement. Employer’s liability limits of $1,000,000 are required. Contractor shall furnish a certificate for Workers’ Compensation Insurance in the State of California, including the name of the carrier and the date of expiration of insurance, or a Certificate of Consent to Self-Insure issued by the Department of Industrial Relations.

        - Professional Liability:

Professional liability with limits no less than $1,000,000 per claim and $3,000,000 aggregate. The policy retro date must be shown on the certificate and must be no later than the date of the Agreement or the date work under the Agreement begins.

2.	The insurance required above shall cover all Contractor-supplied personnel and equipment used in the performance of the Agreement. If subcontractors performing work under this Agreement do not have insurance equivalent to the above, Contractor liability shall provide such coverage for the subcontractor, except for coverage for error, mistake omissions, or malpractice, which shall be provided by the subcontractor if such insurance is required by the State.

3.	The Contractor agrees that the insurance herein provided for shall be in effect at all times during the term of this Agreement. In the event said insurance coverage expires at any time or times during the term of the Agreement, the Contractor agrees to provide at least 30 working days before said expiration date, a new certificate of insurance evidencing insurance coverage as provided herein for not less than one year.

4.	The certificate(s) of insurance must include the following provisions stating that:

- The insurer will not cancel the insured’s coverage without 30 working days prior written notice to the State; and

- The State of California, its officers, agents, employees, and servants are included as additional insured, but only with respect to work performed for the State of California under this Agreement.

5.	Certificates evidencing Contractor’s insurance coverage shall be filed with the CDE prior to execution of this Agreement.

### 11.5 Computer Software Copyright Compliance

By signing this Agreement, the Contractor certifies that it has appropriate systems and controls in place to ensure that state funds will not be used in the performance of this contract/Agreement for the acquisition, operation or maintenance of computer software in violation of copyright laws.

### 11.6 Contracts Funded by the Federal Government (Rev. 04/2025)

It is mutually understood between the parties that this contract/Agreement may have been written before ascertaining the availability of congressional appropriation of funds, for the mutual benefit of both parties, in order to avoid program and fiscal delays which would occur if the contract/Agreement were executed after that determination was made.

This contract/Agreement is valid and enforceable only if sufficient funds are made available to the State by the United States Government for FY(s) covered by this Agreement for the purposes of this program. In addition, this contract/Agreement is subject to any additional restrictions, limitations, or conditions enacted by the Congress or imposed by the federal government, which may affect the provisions, terms, or funding of this contract in any manner.

It is mutually agreed that if Congress does not appropriate sufficient funds for the program or the federal government does not disburse sufficient funds for this program, this contract/Agreement shall be amended to reflect any reduction in funds.

The CDE has the option to void the contract under the 30-day cancellation clause or to amend the contract/Agreement to reflect any reduction of funds.

The recipient shall comply with the reporting requirements set forth in Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards, 2 CFR Part 200.

### 11.7 Prohibition Against Outside Agreements

Except as expressly provided in the scope of work, the Contractor or subcontractor(s) must not enter into agreements related to products and/or services developed specifically for the CDE under this Agreement without the prior approval by the CDE of a work proposal and budget for the work proposed.

The Contractor shall not enter into agreements specifically for product and/or services developed under the terms of this Agreement or any predecessor agreements and paid for with CDE funds with any out-of-state agency or organization. The CDE reserves the right to review such materials referenced above that the Contractor intends to sell during the duration of this Agreement to ensure that those products and/or services are outside the terms of this Agreement. Any out-of-state agency or organization shall negotiate with the CDE for products and/or services developed under to this Agreement or any predecessor agreements.

### 11.8 Disclosures of Information

The Contractor shall not disclose CDE data or documents or disseminate the contents of documents or reports without express written permission from the CDE Contract Monitor.

The Contractor shall not comment publicly to the press or any other media regarding the CDE data or documents, or CDE actions on the same, except as may be required at a public hearing, or in response to questions from a legislative committee or a judge in court of law pursuant to a judicial subpoena.

The Contractor must immediately notify the CDE Contract Monitor if a third party requests or subpoenas documents or information related to this Agreement.

### 11.9 Disclosure of Financial Interests

The Contractor must disclose any financial interests that may allow any individual or organization to materially benefit from the state’s adoption of a course of action.

During the performance of this Agreement, should the Contractor become aware of a financial conflict of interest that may foreseeably allow an individual or organization involved in this Agreement to materially benefit from this Agreement, the Contractor must inform the CDE in writing within 10 working days. If, in the CDE’s judgment, the financial interest will jeopardize the objectivity of the recommendations, the CDE shall have the option of terminating the Agreement.

Failure to disclose a relevant financial interest on the part of the Contractor or any subcontractors will be deemed grounds for termination of the contract/Agreement with all associated costs to be borne by the Contractor and, in addition, the Contractor may be excluded from participating in the State’s bid processes for a period of up to 36 months in accordance with PCC Section 12102.2(i).

Contractor should also be aware of the following provisions of GC Section 1090(a):

“Members of the Legislature, state, county district, judicial district, and city officers or employees shall not be financially interested in any contract made by them in their official capacity, or by any body or board of which they are members. Nor shall state, county district, judicial district, and city officers or employees be purchasers at any sale or vendors at any purchase made by them in their official capacity.”

### 11.10 Correspondence

Correspondence, including emails prepared by the Contractor relating to the logistics of tasks to be performed by the Contractor under the scope of work of this Agreement or correspondence of an informational nature related to the program supported by this Agreement which is prepared by the Contractor must be reviewed by CDE prior to mailing or distribution.

As a standard business practice, unless otherwise provided for in this agreement, the Contractor must "copy" CDE Contract Monitor on each final letter, email, and memorandum prepared by the Contractor under the scope of work of this Agreement.

### 11.11 News Releases

The Contractor must not issue any news releases or make any statement to the news media in any way pertaining to this Agreement without the prior written approval by the CDE, and then only in cooperation with the CDE.

### 11.12 CDE Approval of Deliverables

All approvals, orders for correction, or disapprovals from CDE must be in writing. If the CDE deems a deliverable or product as unacceptable, the Contractor shall make required corrections within the timeframe required by the CDE as referenced in RFS Section 7.1.6.

Failure of the Contractor to obtain prior CDE approval of deliverables or products shall not relieve the Contractor of performing the related contract responsibilities and providing related required deliverables or products to the CDE. The Contractor must accept financial responsibility for failure to meet agreed-upon timelines and quality standards, provided that delays in deliverables or failure in quality are not directly caused by the CDE. The Contractor is not responsible however for delays in deliverables or failure in quality caused by other CDE contractors (e.g., Smarter Balanced). The CDE shall have no liability for payment of any work, of any kind whatsoever, which commences without prior CDE approval.

### 11.13 Representational Conflicts of Interest

Contractor personnel and subcontractor personnel shall not advise, consult, or voluntarily testify on behalf of a party whose interests are adverse to the CDE or SBE. A party has interests adverse to the CDE or SBE when the party is contemplating taking legal action against the CDE or SBE or has taken legal action against the CDE or SBE for issues other than breach of Agreement by the CDE or SBE. The Contractor must disclose to the CDE Contract Monitor any known activities by Contractor or subcontractor personnel involving representation of parties, or provision of consultation services to parties, whose interests are known to be adverse to those of the CDE or SBE. The CDE may immediately terminate this Agreement if the CDE is not satisfied that any conflicts of interest have been resolved.

### 11.14 Unlawful Denial of Services (GC Section 11135)

No person in the State of California shall, on the basis of sex, race, color, religion, ancestry, national origin, ethnic group identification, age, mental disability, physical disability, medical condition, genetic information, marital status, or sexual orientation, be unlawfully denied full and equal access to the benefits of, or be unlawfully subjected to discrimination under, any program or activity that is conducted, operated, or administered by the state or by any state agency, is funded directly by the state or receives any financial assistance from the state.

With respect to discrimination on the basis of disability, programs and activities that are funded directly by the state or receive financial assistance from the State shall meet the protections and prohibitions contained in Section 202 of the Americans with Disabilities Act of 1990 (42 U.S.C. Sec. 12132), and the federal rules and regulations adopted in implementation thereof, except that if the laws of this state prescribe stronger protections and prohibitions, the programs and activities funded by the State or receiving financial assistance from the state shall be subject to the stronger protections and prohibitions.

### 11.15 Material Developed Under the Terms of This Agreement

All materials developed under the terms of this Agreement shall be considered a work made for hire. The State, therefore, reserves the exclusive right to copyright and publish, disseminate, and otherwise use the material developed under the terms of this Agreement in whatever way it deems appropriate.

Any material that is not acceptable to the state may be rejected by the State at its discretion. Notice of such a rejection shall be given to the Contractor by the State within 10-days of receipt of the materials, and final payment shall not be made for such material until substantial compliance has been obtained within the time and manner determined by the State.

### 11.16 Subcontracting

The Contractor is responsible for any work it subcontracts. Subcontracts must include all applicable terms and conditions of this Agreement. Any subcontractors, outside associates, or consultants required by the Contractor in connection with the services covered by this Agreement shall be limited to such individuals or firms as were specifically identified in the submission or agreed to during negotiations for this Agreement, or as are specifically authorized in writing by the CDE and the SBE Executive Director during the performance of this Agreement. Any substitutions in, or additions to, such subcontractors, associates or consultants shall be subject to prior written approval of the CDE. Contractor warrants, represents, and agrees that it and its subcontractors, employees and representatives shall at all times comply with all applicable laws, codes, rules and regulations in the performance of this Agreement. Should the CDE or the SBE determine that the work performed by a subcontractor is substantially unsatisfactory and is not in substantial accordance with the agreement terms and conditions, or that the subcontractor is substantially delaying or disrupting the process of work, the CDE or the SBE may demand substitution of the subcontractor.

### 11.17 Subcontractors

Nothing contained in this Agreement resulting from this RFS or otherwise, shall create any contractual relation between the CDE and any subcontractors, and no subcontract shall relieve the Contractor of their responsibilities and obligations hereunder. The Contractor agrees to be as fully responsible to the CDE for the acts and omissions of its subcontractors and of persons either directly or indirectly employed by any of them as it is for the acts and omissions of persons directly employed by the Contractor. The Contractor's obligation to pay its subcontractors is an independent obligation from the CDE's obligation to make payments to the Contractor. As a result, the CDE shall have no obligation to pay or to enforce the payment of any moneys to any subcontractor.

### 11.18 Staff Replacements

Changes to any of the Contractor’s professional project management team (e.g., project manager, fiscal manager, technology manager, or key personnel, etc.) require formal written approval by the CDE Contract Monitor. The staffing change may not occur until the Contractor receives written approval of the change by the CDE Contract Monitor. The CDE shall not arbitrarily withhold approval or withhold approval for reasons that would constitute unlawful discrimination.

### 11.19 Ownership of Materials

All materials developed under the terms of this Agreement, or any predecessor agreement, and paid for using CDE funds, are the property of the CDE. The Contractor acknowledges that the rights to any report, computer program, documentation for programs, exams, exam items or other material developed or modified by the Contractor or its subcontractors and paid for with CDE funds under the terms of this Agreement or the terms of predecessor agreements shall belong to the CDE. The CDE reserves the exclusive right to copyright such material, and to publish, disseminate, and otherwise use materials developed under the terms of this Agreement and paid for using CDE funds. No contractor or subcontractor staff may participate in any meeting or activity without prior written permission from the CDE Contract Monitor.

Copyright for the CDE must be noted on all materials produced for the purposes of this Agreement. The CDE acknowledges that any materials and proprietary computer programs previously developed by the Contractor or its subcontractors shall belong to the Contractor or its subcontractors, not paid for with CDE funds under the terms of this Agreement or the terms of the predecessor agreements, shall belong to the Contractor or its subcontractors. Unless otherwise stated in the Scope of Work, any materials and proprietary computer programs previously developed by the Contractor or its subcontractors shall be owned by and remain the property of the Contractor or its subcontractors.

### 11.20 Retention of Records

The Contractor shall maintain accounting records and other evidence pertaining to costs incurred, with the provision that they shall be kept available by the Contractor during the agreement period and thereafter for five full years from the date of the final payment. The CDE must be permitted to audit, review, and inspect the Contractor's activities, books, documents, papers and records during progress of the work and for five years following final payment.

### 11.21 Ownership and Disposition of Equipment

The purchasing of equipment is not allowed without approval of the CDE. Equipment purchased under the provisions of this Agreement is the property of the State and shall be used for its intended purpose during the term of this Agreement. An inventory of all equipment purchased under this Agreement shall be maintained. After the term of this Agreement, the equipment shall be disposed of in accordance with instructions from the CDE.

### 11.22 Follow-on Contracts

No contractor, subcontractor, person, firm, or subsidiary thereof who has been awarded a consulting services agreement, or an agreement which includes a consulting component, (refer to PCC Section 10335.5) may be awarded an agreement for the provision of services, delivery of goods or supplies, or any other related action, which is required, suggested, or otherwise deemed appropriate as an end product of the consulting services agreement (PCC Section 10365.5[a]).

### 11.23 Rights/Licenses

The Contractor warrants that it has secured, or shall have secured, any and all necessary rights, clearances, and/or licenses with respect to all materials and elements embodied in or used in connection with the performance of this Agreement, and that all included material shall neither violate nor infringe upon the copyright, service mark, trademark, privacy, creative, or other rights of any person, firm, corporation, or other third party. The Contractor must provide CDE with documentation indicating a third party’s permission for CDE’s use, for a period of eight years, of the third party’s materials, such as a reading passage excerpted from a book or short story or artwork, or for such term that the third party is willing to negotiate. Contractor agrees to defend the CDE against any third-party claims and to fully indemnify CDE for any and all losses sustained or for any damages or losses suffered as a result of any violation of this clause.

## APPENDIX A—Minimum System Requirements

The following table consists of the minimum system requirements for the California Assessment Delivery System (CADS).

| # | Type | Requirement |
| --- | --- | --- |
| ARC- 01.01 | Architecture | The contractor must provide a data dictionary that utilizes the CDE’s preferred variation for each data element collected or stored. |
| ARC- 01.02 | Architecture | The contractor must provide dataflow diagrams. |
| ARC- 01.03 | Architecture | The contractor must provide an Entity Relationship Diagram (ERD) in the format determined by the CDE. |
| ARC- 01.05 | Architecture | The CADS must be scalable to accommodate new and modified consortium and California-specific assessments. |
| INT- 02.00 | Interface | The CADS must accept test packages (both Smarter Balanced and non-Smarter Balanced) in the Smarter Balanced test package format (Refer to https://www.smarterapp.org/) and accurately deliver tests and applicable tools, supports, and accommodations to students with authenticity (inclusive of the adaptive algorithm), collect responses, score responses, and deliver scores to the Data Warehouse. |
| INT- 02.01 | Interface | The CADS must successfully and completely process a daily electronic student registration information file, containing up to 6.5 million records, by 6 a.m. PST of the same day of the file availability. The CDE will make the student registration information file available by 2 a.m. PST, Monday through Friday. All current student registration information must be available within the CADS immediately after processing of the student registration information file. |
| INT- 02.02 | Interface | The CADS must successfully identify and process all student information changes (e.g., new, modified, deleted, including student ID changes) contained in CALPADS electronic student registration information file within 24 hours. |
| INT- 02.03 | Interface | The CADS must be able to complete the processing of electronic data student registration information files received from CALPADS without impacting any of its other nightly batch processing or maintenance windows. |
| INT- 02.04 | Interface | The CADS must generate and deliver to the CDE daily electronic student data files (final specifications will be determined during joint requirement sessions) for CALPADS in a location designated by the CDE. |
| INT- 02.05 | Interface | The CADS must accept and process daily (Monday through Friday) Student Access Data Files from LEAs that specify accessibility tools, designated supports, and accommodations that the student must be provided during summative and/or interim testing, the specifications of which are to be derived during the joint requirement sessions. |
| INT- 02.06 | Interface | The CADS must provide students with access to the accessibility tools, supports, and accommodations specified in the Student Access Data File within 24 hours of the contractor receiving the data file from the LEA. |
| INT- 02.07 | Interface | The CADS must be able to accommodate annual changes to the Student Access Data File to coincide with the use of new tools, designated supports, and accommodations as they become available. |
| INT- 02.08 | Interface | The contractor must provide a document describing the solution’s application programming interfaces and Web services. |
| INT- 02.09 | Interface | The CADS must be able to deliver assessments using the minimum technology standards (e.g., network connections, student devices, operating systems) established (and annually updated) by the Smarter Balanced Consortium in the Technology Strategy Framework and Testing Device Requirements. |
| INT- 02.10 | Interface | The CADS must not require the use of any additional software beyond the Secure Browser (e.g., use HTML5 and JavaScript as the means to render items and submit responses). |
| INT- 02.11 | Interface | The CADS must support the use of all embedded accessibility supports (refer to the Accessibility Guide at https://ca-toms-help.ets.org/accessibility-guide and the California Accessibility Resource Matrix at https://www.caaspp-elpac.org/s/docs/CA-Accessibility-Matrix-25-26.docx). |
| INT- 02.12 | Interface | The CADS must use either the Smarter Balanced Assessment Item Packaging Format as described in the Smarter Balanced Assessment Item Format Specification or, if available, another format consistent with the Smarter Balanced Assessment Item Packaging Format. |
| INT- 02.13 | Interface | The CADS must support the scoring of selected-response and constructed-response items using machine scoring, hand scoring, and AI (AI applicable only if the contractor is using AI scoring). |
| INT- 02.14 | Interface | The contractor must download the electronic data student registration information file, extracted from CALPADS by the CDE, once a day Monday through Friday, from a CDE- designated location. |
| INT- 02.15 | Interface | The CADS must successfully and completely process a daily electronic school and associated LEA information file by 6 a.m. PST of the same day of the file availability. The school and associated LEA information file will be extracted from CALPADS and made available by 2 a.m. PST the same day. |
| SEC- 3.00 | Security | The contractor must provide security policy and governance, including: - information security program policies; - information security governance; - use of human-resource policy and practice security controls related to employees and contractors with potential access to sensitive information; - physical security of facilities hosting sensitive information resources; - organization’s security audit policy and practice including internal audits, independent audits, the audit scope, the audit frequency, and the exposure/reporting of audit results; - The contractor’s system administrator roles and access levels and related controls. |
| SEC- 03.01 | Security | The CADS must provide hosted and delivered system access control features consistent with required user roles and permissions, including: - system-level access controls; - feature/function access controls; - information/data access controls; - system’s incorporation of role based, group-based, and specific user-based access controls. |
| SEC- 03.02 | Security | The CADS must provide authentication of users using industry-standard user authentication methods. Access control features will restrict access to information that is outside the responsibility of the assigned user role when the user has numerous, different roles. |
| SEC- 03.03 | Security | The CADS must provide the ability to set and enforce password strength and reset policies. |
| SEC- 03.04 | Security | The CADS, including secondary storage, must implement strong encryption (in transit and at rest) consistent with encryption guidelines published by the National Institute of Standards and Technology (NIST), an equivalent, or better, to protect confidential information handled by the system. This information includes student registration information, student identifiable results information, test items, and other information as identified by applicable Federal, State of California, and CDE laws, regulations, or policies. Whenever feasible, cryptographic modules shall be validated to the Federal Information Processing Standard (FIPS) 140-2. In rare instances where encryption cannot be implemented, compensating control(s) or alternatives to encryption must be in place. Compensating controls and alternatives to encryption must be reviewed on a case-by-case basis and approved in writing by the state entity ISO, after a thorough risk analysis. |
| SEC- 03.05 | Security | The CADS must purge, dispose, and/or archive sensitive information securely. |
| SEC- 03.06 | Security | The CADS must employ integrity, controls such as source authentication, checksums, and message authentication methods to ensure that the secure information, such as student information, test content, answers, and scores, are unaltered and reliable. |
| SEC- 03.07 | Security | The CADS must provide availability controls, such as protections against denial of service attacks. |
| SEC- 03.08 | Security | The CADS must provide logging and audit controls available in the system to identify all user and system access of all data and functions and provide such information as necessary in the course of a security incident investigation. |
| SEC- 03.09 | Security | The contractor must provide a security plan that follows the NIST Special Publication 800-18 at https://csrc.nist.gov/pubs/sp/800/18/r1/final. |
| SEC- 03.10 | Security | The contractor shall provide storage administration that includes the strict control and accessibility of all storage media. |
| SEC- 03.11 | Security | The contractor must ensure that all storage media is inventoried on an annual basis, or sooner as dictated by the CDE, regulatory, or other contractual agreements. |
| SEC- 03.12 | Security | The contractor must ensure all portable storage devices, including backup tapes, are encrypted using a FIPS 140-2 validated solution. (SAM 5350.1) |
| SEC- 03.15 | Security | The contractor must ensure physical media containing PII is maintained in a secure environment prior to its transfer offsite. |
| SEC- 03.16 | Security | The contractor must ensure physical media containing PII is monitored during the internal shipping process and must never be left unattended before handoff to the shipper. |
| SEC- 03.17 | Security | The contractor must ensure that physical media containing PII is shipped in locked containers with no special markings or other indications of the sensitive nature of the contents. |
| SEC- 03.18 | Security | The contractor must ensure shipping procedures include a positive acknowledgement of receipt of encrypted backup files at the destination. |
| SEC- 03.19 | Security | If a Cloud Service Provider is used as part of the CADS, the cloud system must be listed as a FedRAMP Compliant Cloud System (refer to https://www.fedramp.gov/cloud-service-providers/). |
| SEC- 03.20 | Security | The contractor must ensure data remains within the continental United States. |
| SEC- 03.21 | Security | If a Cloud Service Provider is used as part of the CADS, the data maintained by the Cloud Service Provider shall be consistent with encryption guidelines published by the National Institute of Standards and Technology (NIST), an equivalent, or better, to protect confidential information handled by the system. |
| SEC- 03.22 | Security | The contractor must ensure that data will not be converted into a proprietary format which will render the data non- portable. |
| SEC- 03.23 | Security | The contractor must deploy a secure browser (that supports Operating Systems as dictated by Smarter Balanced) annually in order to create a secure interface for students to access only the CAASPP summative tests without any other online-enabled utility (i.e., students may only access the exam). Refer to the Secure Browser Requirements and Specifications at https://www.smarterapp.org/specs/SecureBrowserSpecificati on.html. |
| SEC- 03.24 | Security | The solution proposed for implementing paperless reporting must also adhere to the security requirements in this section. |
| SEC- 03.25 | Security | The contractor must allow the CDE to perform annual security audits of system activities when requested except in the case a breach. Costs for a CDE or third-party auditor to conduct the annual review will be outside of this contract. Notification of the audit will be provided to the contractor two (2) weeks prior to the requested audit date. The contractor must allow the CDE or authorized third-party auditor the right to inspect artifacts discovered in the audit. Contractor- owned data or shared systems may not kept by the auditor. In the event that nonconformance to contract requirements is found as a result of the annual audit, the contractor must address the issue to be consistent with the applicable contract requirements. In the case of a breach, the contractor must allow the CDE to perform security audits upon demand in the area in which the breach occurred. The contractor must coordinate with the CDE to complete the audit related to a breach. Costs for an audit related to a breach will be negotiated between the contractor and the CDE according to applicable contract provisions. |
| SDP- 04.00 | System Development Process | The CADS must provide real-time progress reporting to LEA CAASPP coordinators, site coordinators, and the CDE pertaining to aggregate test administration information by LEA, school, course/grade, or content area consistent with the roles and permissions established during joint requirement sessions. The specifications of the progress reporting are to be finalized during joint requirement sessions but may include such information as number of tests scheduled (by date or session and test type), number of tests being administered, number of tests completed, and the number of scoreable tests completed. |
| SDP- 04.01 | System Development Process | The contractor must have an established, repeatable Unit/Functional testing process for which evidence can be given if requested. The contractor must develop System/Functional, Integration, and User Acceptance Test Plans that describe, at a minimum: - Roles and responsibilities - Scope - System test phases and schedule - System test approach, methodology, and tools - System test entry and exit criteria - System test pass/fail criteria - System test data and metrics - System test reporting - System test scenarios, cases, and scripts - System test defect management processes and procedures |
| SDP- 04.02 | System Development Process | The contractor must provide system test environment(s) for each system test phase, including System/Functional, Integration, and User acceptance. |
| SDP- 04.03 | System Development Process | The contractor must provide functional testing, including test environment(s), test data, and test to requirements/feature coverage. |
| SDP- 04.04 | System Development Process | The CADS must have the ability to limit interim assessment usage (i.e., restrict interim usage) within one hour of receiving the direction from the CDE to do so. |
| SDP- 04.05 | System Development Process | The CADS must create unique test session IDs that ensure secure test administration. |
| SDP- 04.06 | System Development Process | The CADS must allow for functionality to process approved appeals (i.e., test reset, invalidation, reopen, and restore). |
| SDP- 04.07 | System Development Process | The CADS must allow all students to review their answers for certain sections or sets of questions before moving on to the next section or completing the exam. |
| SDP- 04.08 | System Development Process | The CADS must have controls to prevent a student from prematurely exiting an assessment or from being inadvertently exited from an assessment. |
| SDP- 04.09 | System Development Process | The CADS must default to human voice when both human and machine voice options are available as a feature of accessibility supports, tools, or accommodations. |
| SDP- 04.10 | System Development Process | The CADS must save student responses to selected-response items (both linked to common stimuli and not) upon selection by the student. |
| SDP- 04.11 | System Development Process | The CADS must save student responses to constructed-response items and technology- enhanced (e.g., drag/drop, graphing) items. |
| SDP- 04.12 | System Development Process | The CADS must allow test administrators to start, stop, pause, and resume a test session. |
| SDP- 04.13 | System Development Process | For the Smarter Balanced Interim Assessments only, the CADS must allow test administrators to specify a limited set (number) of questions for testing. |
| SDP- 04.14 | System Development Process | The CADS must allow test administrators to monitor student progress during testing, which includes but is not limited to, having the ability to determine which item a student is currently working on without showing the item or student response. |
| SDP- 04.15 | System Development Process | The CADS must provide a user interface (accessible to user roles consistent with those established during joint requirement sessions) to activate and deactivate accessibility tools, supports, and accommodations. The activations/deactivations made via the user interface must be made prior to a student taking a test and must be immediately available to the student once he or she begins testing. |
| SDP- 04.16 | System Development Process | The CADS must retain previously saved student responses when a test is paused or restarted. |
| SDP- 04.17 | System Development Process | The CADS must save student responses and end a test session when there is no activity on the test for a specified period established during joint requirement sessions. |
| SDP- 04.18 | System Development Process | For the CAASPP and ELPAC interim assessments only, the CADS must allow for out-of-level testing (i.e., administration of tests that are not consistent with the student’s enrolled grade). |
| SDP- 04.19 | System Development Process | For the CAASPP and ELPAC interim assessments only, the CADS must allow an unlimited number of interim tests to be administered to any one student. |
| SDP- 04.20 | System Development Process | Provide a training instance of the teacher hand scoring system to allow CDE staff and LEA staff members to provide training and demonstrations of the teacher hand scoring system to California stakeholders and LEA staff. The training site is to be a standalone (independent of the teacher hand scoring system/production environment) instance of the teacher hand scoring system that provides a local mirror, or context, of the functionality of the production environment, but has no effect on the functioning of the production environment. Updated regularly to reflect each assessment with results in the teacher hand scoring system, the training site is to contain ‘dummy’ data and will include a full range of functions. |
| SIM- 05.00 | System Implementation | The contractor must develop a System Implementation Plan that describes how the Assessment Technology Platform will be deployed, installed, and transitioned into an operational system. The plan shall include, at a minimum: - an overview of the hosting system; - system implementation readiness assessment methodology and schedule; - implementation schedule, including field tests and pilots; - description of the major tasks involved in the implementation; - overall resources needed to support the implementation effort, including hardware, software, facilities, materials, and staff; - security features associated with the system when it is implemented, including security during implementation; - description of performance monitoring tools and techniques; - any site-specific implementation requirements; - description of process for validating the implementation was successful; - description of system acceptance and sign-off process. |
| UEP- 06.00 | User Experience | The CADS must conform to a consistent look and feel for each class of user for all components of the system, including Smarter Balanced and non-Smarter Balanced components. |
| UEP- 06.01 | User Experience | The CADS must display (on the workstation screen) the name of the student who is testing. |
| UEP- 06.02 | User Experience | The Assessment Technology Platform must be presented as a cohesive, single system with a single sign-on and seamless navigation. |
| UEP- 06.03 | User Experience | The CADS must adhere to industry best practice user interface standards and use industry best practice user interface controls in accordance with the supported end-user devices (e.g., W3C, Microsoft). |
| UEP- 06.04 | User Experience | The CADS must comply with all applicable accessibility standards set forth in California Government Code Section 11135 as well as policy set forth in the CDE Web Accessibility Standards located at https://www.cde.ca.gov/re/di/ws/accessibility2017.asp (excluding vendor-specific proprietary systems). |
| UEP- 06.05 | User Experience | The CDE web-based systems must provide online, context- sensitive help for each class of user. The specific features requiring online help shall be identified during joint requirement sessions. |
| UEP- 06.06 | User Experience | The user interfaces (both administrators and students) of the CADS must be identical except for required deviations due to differences between Smarter Balanced and non-Smarter Balanced tests (e.g., skip item functionality would only be available on non-Smarter Balanced tests). |
| TAC- 07.00 | Technical Assistance Center | The contractor must provide Tier 1, 2, and 3 supports for technical issues. |
| TAC- 07.01 | Technical Assistance Center | The contractor must provide an escalation to Tier 2 and 3 support for unresolved Tier 1 issues consistent with RFS Section 3.2.3. |
| TAC- 07.02 | Technical Assistance Center | The contractor must provide a process for working with user-sponsored technical support organizations (i.e., LEA and the CDE information technology groups). |
| TAC- 07.03 | Technical Assistance Center | The contractor must provide system support ticket tracking, resolution, and reporting. |
| SRM- 08.00 | System Delivery Release Management | The contractor must provide a System Delivery Release Management Plan that includes, at a minimum: - scope; - roles and responsibilities; - Release Management approach and methodology; - processes and procedures for solution maintenance and upgrade as it relates to participation in, and implementation of, subsequent versions of the open- source Smarter Balanced code base, as well as proprietary modifications and independently developed components (only applicable if the CADS uses the Smarter Balanced open-source code); - process and procedures for communications and coordination with internal and external partners; - description of release artifacts, including release notes and reports; - inputs to Release Management; - description of release types, including maintenance and emergency releases; - processes and procedures for performing scheduled and unscheduled releases; - system outage management; - processes and procedures for performing scheduled and unscheduled releases; - release testing procedures, including regression and integration testing with CALPADS and other external partners; - production readiness procedures; - production deployment procedures; - production validation procedures; - processes and procedures for system delivery acceptance; - release rollback/back-out procedures. |
| SRM- 08.01 | System Delivery Release Management | The contractor must provide a process for scheduled and unscheduled releases. |
| SRM- 08.02 | System Delivery Release Management | The contractor must comply with the system delivery acceptance process as defined by the CDE for the initial, and each subsequent, system delivery release. |
| PER- 09.00 | Performance | The CADS has dedicated support for 750,000 concurrent users, with expandable capacity to support over 2,000,000 concurrent users using shared services. These users are inclusive of student test takers and test administrators between the hours of 6 a.m. and 8 p.m. PST Monday through Friday. |
| PER- 09.01 | Performance | The CADS must provide an adequate number of concurrent web sessions to support the number of concurrent users at any given time. |
| PER- 09.02 | Performance | The CADS must deliver 100% of the test questions with no more than five seconds of latency while serving a simulated peak concurrent user load as tested from a series of test devices connected to a test lab. Performance testing results will be provided to the CDE annually prior to the launch of testing in January. The performance testing results will provide details on the number of concurrent users tested and associated latency with test delivery. |
| PER- 09.03 | Performance | The contractor must conduct performance/load/stress testing that addresses, at a minimum, the following objectives: - To verify the reliability of the application under stress. - To determine application’s behavior under extreme load conditions. - To discover application bugs that occur only under high load conditions. These can include such things as synchronization issues, race conditions, and memory leaks. - To determine the application's robustness in terms of extreme load and help application administrators to determine if the application will perform sufficiently if the current load goes well above the expected maximum. |
| PER- 09.04 | Performance | The CADS must demonstrate performance and stress requirements compliance through rigorous performance testing prior to the opening of the summative testing window. |
| PER- 09.05 | Performance | The contractor must provide a performance, load, and stress testing environment that utilizes the same code base as the production environment and is capable of simulating peak transaction and user loads as well as data creation/storage/transfer capacities. |
| PER- 09.06 | Performance | The contractor must work with the CDE during joint requirement development sessions to define performance thresholds that include, but are not limited to, network utilization, component latency/processing time, screen refresh rates, test item delivery latency, and test answer submission latency. |
| PER- 09.07 | Performance | The contractor must conduct performance/load/stress testing that identifies, at a minimum: - the hardware and/or the system's configurations/communication bottlenecks and their causes; - application’s response times; - application’s throughput; - maximum concurrent users that application can bear in a system; - resource (e.g., CPU, RAM, network I/O, and disk I/O) utilizations that application consumes during the test; - behavior of the system under various workload types including normal load and peak load; - at what parameter levels beyond the minimum the system performance degrades below acceptable performance thresholds; - symptoms and causes of application failure under stress conditions; - weak points in the application (e.g., an increase in the number of users, amount of data, or application activity might cause an increase in stress). |
| PER- 09.08 | Performance | The contractor must instrument and monitor the production hosted and delivered system to ensure the production implementation remains compliant with performance requirements and service level agreements. |
| PER- 09.09 | Performance | The CADS will comply with the interoperability standards in terms of performance/capacity and written confirmation of complete compliance. Confirmation will be provided to the CDE yearly prior to January’s summative testing window. |
| PER- 09.10 | Performance | The contractor must provide a process for monitoring and reporting production system performance, the specifics of which will be determined through joint requirement sessions. |
| PER- 09.11 | Performance | The contractor must provide production system health reporting capabilities that include, but are not limited to, the ability for the CDE to monitor in real-time, or through reports, the number of test takers, number of in-progress tests (interim and summative counts), number of administrative users, and other technical system health and use parameters to be determined through joint requirement sessions. |
| PER- 09.12 | Performance | The contractor must obtain a network peering agreement (or functionally similar agreement) with the K12HSN to enable efficient routing of messages. |
| PER- 09.13 | Performance | The CADS must maintain an availability rate of 99.9 percent during summative testing as defined by California Education Code, and availability rate of 99 percent outside of the summative testing window, exclusive of the California school holidays, planned system release outages, and approved maintenance windows. The availability rate will be calculated between the hours of 6 a.m. and 6 p.m. PST Monday through Friday. |
| DRC- 10.00 | Disaster Recovery and Business Continuity | A disaster recovery results from a catastrophic impairment of a facility. A disaster will be declared as soon as reasonable expectation indicates the disrupted processes and/or facility will not be able to resume near normal operation within an acceptable time period. If a disaster occurs and systems/infrastructure are offline, they will be recovered at an alternate location based on business- defined Recovery Time Objectives (RTO). Once systems are up and running at the alternate facility, systems will be subject to normal processing Service Level Agreements (SLAs). Unless there is specific agreement to the contrary, the RTO will be defined by the recovery tiers. |
| DRC- 10.01 | Disaster Recovery and Business Continuity | The CADS must be at a Tier 3 data center. A Tier 3 data center is defined as a facility consisting of multiple active power and cooling distribution paths; however, only one path is active. For post disaster recovery, the facility has redundant components and is concurrently maintainable providing 99.982% availability. |
| DRC- 10.02 | Disaster Recovery and Business Continuity | The CADS must provide sufficient information on student progress or state of the application with sufficient detail necessary for system recovery, including saving the state of partially completed answers to multi-part items. |
| DRC- 10.03 | Disaster Recovery and Business Continuity | The CADS must have the ability to recover from end-user device failure while minimizing the loss of information, progress, and state. |
| DRC- 10.04 | Disaster Recovery and Business Continuity | The CADS must have the ability to recover from network failure while minimizing the loss of information, progress, and state. |
| DRC- 10.05 | Disaster Recovery and Business Continuity | The CADS must have the ability to recover from a web server/application server/database server failure while minimizing the loss of information, progress, and state. |
| DRC- 10.06 | Disaster Recovery and Business Continuity | The CADS must ensure the maintenance of test integrity during outage events that occur while test administration is in process. |
| DRC- 10.07 | Disaster Recovery and Business Continuity | The CADS must have robust data backup and recovery process and architecture that adhere to industry best practices. |
| DRC- 10.08 | Disaster Recovery and Business Continuity | The contractor must provide a Disaster Recovery and Business Continuity Plan that provides for the CADS to stay functional in a disastrous state. The plan must include, at a minimum: - Scope - Approach and methodology - Roles and responsibilities - Backup and restore strategies and policies for data, database, and code - Business continuity planning activities - Disaster recovery process, procedures, and timeframes - Ongoing testing, updates, and maintenance of the plan |
| DRD- 11.00 | Data Policy Retention and Destruction | The Assessment Delivery Component must securely store and transmit student-level data in accordance with the requirements of the SAM Section 5305.8 for highly sensitive data. Data must be accessed only by authorized staff and securely destroyed after the termination of the contract. |
| DRD- 11.01 | Data Policy Retention and Destruction | The contractor must adhere to the DEAM, sections 10120, 10600, and 10601 with regards to data security, retention, and destruction. |
| DRD- 11.02 | Data Policy Retention and Destruction | The contractor must adhere to EC 60607 and to the FERPA of 1974, Section 1232g in Part 4 of Title 20 of the Code of Federal Regulations (20 C.F.R. § 1232g) with regard to the access and destruction of PII information and/or confidential data. |
| MAO- 12.00 | Maintenance and Operation | The contractor must develop a maintenance and operation plan that describes, at a minimum: - process for system maintenance and upgrades (e.g., implementation of subsequent versions of the open-source Smarter Balanced code base; implementation of proprietary modifications and independently developed components); - process for scheduled and unscheduled releases; - process for release testing and coordination; - release notes, communications, and coordination processes. |

## APPENDIX B—CERS Minimum System Requirements

| Rqt # | Type | Requirement |
| --- | --- | --- |
| ARC-01r | Architecture | CERS must use an open-source architecture that is transferrable to and allows operation, maintenance and enhancements by other third-party providers at the end of the contract period. |
| ARC-02r | Architecture | CERS must be extensible to allow for adding other assessments in the future. |
| ARC-03r | Architecture | CERS must subscribe to the same SSO service as used for all other assessment services in California, including Tools for Teachers. |
| ARC-04r | Architecture | CERS must be accessible (at a minimum Section 508- and WCAG 2.1 AA-compliant). |
| ARC-05r | Architecture | CERS must support 35,000 concurrent users. The successful bidder will notify CDE when concurrent users hit the 20,000 mark. |
| INT-01a | Interface | Work with the CDE and Smarter Balanced to participate in a SSO authorization solution that includes logons and support for the user base. This requirement will need to be reconsidered if the SSO design changes. |
| INT-02a | Interface | The authentication solution must accept security permissions from the contractor system: using Security Assertion Markup Language (SAML) or Open Authorization (OAuth) standards to accept identity packages and encrypted authentication as “payloads.” This requirement will need to be reconsidered if the SSO design changes. |
| SEC-01a | Security | Meet California published standards for system security, back-up, disaster recovery, availability, performance, and capacity. California’s published information security standards are provided in the California State Administrative Manual located at https://www.dgs.ca.gov/Resources/SAM, section 5300 – Information Technology – Office of Information Security The specific sections are as follows: - System Security - Minimum Security Controls – 5300.5 located at https://www.dgs.ca.gov/Resources/SAM/TOC/5300/5300-5 - Information Security Program – 5305 located at https://www.dgs.ca.gov/Resources/SAM/TOC/5300/5305 - Back-up - Information System Backups – 5325.6 located at https://www.dgs.ca.gov/Resources/SAM/TOC/5300/5325-6 - Disaster Recovery - Technology Recovery Plan – 5325.1 located at https://www.dgs.ca.gov/Resources/SAM/TOC/5300/5325-1 - Availability, performance, and capacity - Introduction – 5300 located at https://www.dgs.ca.gov/Resources/SAM/TOC/5300/5300. |
| SD-01r | System development | Allow authorized users to download student test-level results in CSV format with test statistics, including domain (e.g., Listening, Speaking, Reading, Writing, the equivalent of a Smarter Balanced claim). With the exception of scheduled system downtimes, the successful bidder must also conduct a match daily to link student results so they display in a single place in the reporting system. |
| SD-02r | System development | Provide an authorized user with the ability to obtain/download an electronic version of score results data by: - Statewide Student Identifier (SSID) - Grade level - School - LEA (District) - Primary Language Code Users will not be able to view summative assessment items or student responses. Assessments shall have no more than 6 sub-scores (equivalent to Smarter Balanced claims scores). Assessments shall have no more than 6 performance/achievement levels. |
| SD-03r | System development | Provide for the printing capability of individual student test results (generated by data, including domain). |
| SD-04r | System development | Provide aggregate reporting at the state, LEA, school, grade, and student group levels (including student demographic data and filtering), using Common Education Data Standards (CEDS.ed.gov) demographic categories plus Filipino ethnicity, Primary Language Code, and English Language Acquisition Status (ELAS) date. |
| SD-05r | System development | Store and maintain all received finalized test results (including test results revised as a result of successful rescores/appeals) in historical raw data files for the duration of the Agreement. Each FY, historical data files may be archived in a secure off-line format. Corrected or revised records will override previous test results. |
| SD-06r | System development | Support a minimum of five years of historical data that are accessible to educators. Data older than five years may be archived in a secure off-line format for the life of the Agreement. |
| SD-07r | System development | Develop a process for annual maintenance, including the loading of test definitions for each new school year while preserving previous years’ data. The CDE and the successful bidder will collaborate on a solution if test design changes cause new test definitions to be incompatible with previous years’ data. |
| SD-08r | System development | Provide CDE authorized users with access to CERS for analytical purposes. CDE and the successful bidder will agree to a process to minimize any interruption to operational services that may result from these analyses. |
| SD-09r | System development | Accept and store test results. Test results will be delivered in a Test Results Transmission (TRT) format and use a Representative State Transfer (REST) protocol. |
| SD-10r | System development | Provide a training instance of CERS (i.e., CERS sandbox) to allow CDE staff and LEA staff members to provide training and demonstrations of the CERS to California stakeholders and LEA staff. The Sandbox is to be a standalone (independent of CERS) instance of CERS that provides a local mirror, or context, of the functionality of the CERS, but has no effect on the functioning of the CERS. Updated regularly to reflect each assessment with results in CERS, the Sandbox is to contain ‘dummy’ data and will include a full range of functions. |
| SD-11r | System development | CERS must maintain an availability rate of 99 percent, exclusive of the California school holidays, planned system release outages, and approved maintenance windows. The availability rate will be calculated between the hours of 6 a.m. and 6 p.m. PT Monday through Friday. |
| UE-01r | User experience | Apply responsive web design principles to improve the user experience when accessing the reporting site from a variety of form-factors including, but not limited to, tablets and smart phones. |

## APPENDIX C—CAASPP and ELPAC Item Counts

CAASPP and ELPAC Item Counts as of October 2, 2025

Number of CAA for ELA Items—Operational

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 11 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Composite | 9 | 0 | 2 | 3 | 1 | 4 | 1 | 20 |
| MatchMS | 8 | 15 | 9 | 11 | 7 | 5 | 9 | 64 |
| MatchSS | 3 | 2 | 5 | 7 | 3 | 1 | 0 | 21 |
| MCMA | 9 | 5 | 7 | 4 | 8 | 8 | 6 | 47 |
| MCMS | 10 | 4 | 11 | 5 | 13 | 10 | 13 | 66 |
| MCSS | 66 | 81 | 63 | 54 | 79 | 45 | 53 | 441 |
| MCSS Partial Credit | 7 | 5 | 4 | 6 | 7 | 5 | 3 | 37 |
| ZoneMS | 16 | 28 | 38 | 31 | 31 | 45 | 31 | 220 |
| ZoneSS | 8 | 2 | 1 | 2 | 1 | 0 | 0 | 14 |
| Grand Total | 136 | 142 | 140 | 123 | 150 | 123 | 116 | 930 |

Number of CAA for ELA Items—Field Test

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 11 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Composite | 2 | 2 | 1 | 0 | 1 | 1 | 1 | 8 |
| MatchMS | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 5 |
| MatchSS | 2 | 0 | 1 | 4 | 0 | 0 | 0 | 7 |
| MCMS | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 8 |
| MCSS | 11 | 22 | 10 | 11 | 9 | 13 | 6 | 82 |
| MCSS Partial Credit | 1 | 1 | 0 | 1 | 1 | 2 | 1 | 7 |
| ZoneMS | 3 | 4 | 3 | 2 | 2 | 5 | 2 | 21 |
| ZoneSS | 2 | 2 | 0 | 0 | 1 | 0 | 2 | 7 |
| Grand Total | 23 | 33 | 17 | 21 | 15 | 23 | 13 | 145 |

Number of CAA for Mathematics Items—Operational

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 11 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BarPicturegraphMS | 3 | 4 | 0 | 0 | 0 | 0 | 2 | 9 |
| Composite | 12 | 12 | 26 | 10 | 17 | 7 | 8 | 92 |
| Graph | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 |
| InLineChoicelistMS | 4 | 2 | 4 | 4 | 8 | 7 | 4 | 33 |
| InLineChoicelistSS | 1 | 1 | 3 | 4 | 2 | 3 | 1 | 15 |
| MatchMS | 2 | 4 | 1 | 0 | 1 | 1 | 5 | 14 |
| MatchSS | 1 | 0 | 1 | 2 | 2 | 4 | 0 | 10 |
| MCMA | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 8 |
| MCMS | 1 | 1 | 0 | 2 | 0 | 5 | 1 | 10 |
| MCSS | 32 | 19 | 18 | 28 | 17 | 17 | 21 | 152 |
| Numeric | 0 | 0 | 4 | 2 | 1 | 5 | 4 | 16 |
| ZoneMS | 1 | 4 | 4 | 3 | 3 | 0 | 3 | 18 |
| ZoneSS | 8 | 10 | 3 | 5 | 1 | 10 | 7 | 44 |
| Grand Total | 65 | 57 | 66 | 60 | 53 | 62 | 60 | 423 |

Number of CAA for Mathematics Items—Field Test

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | Grade 11 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BarPicturegraphMS | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 3 |
| Composite | 4 | 6 | 7 | 5 | 6 | 5 | 6 | 39 |
| MatchMS | 2 | 0 | 0 | 0 | 1 | 1 | 3 | 7 |
| MatchSS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| MCMS | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 4 |
| MCSS | 10 | 17 | 11 | 12 | 10 | 4 | 4 | 68 |
| Numeric | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| ZoneMS | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 4 |
| ZoneSS | 2 | 2 | 0 | 2 | 1 | 5 | 1 | 13 |
| Grand Total | 20 | 28 | 18 | 23 | 20 | 16 | 15 | 140 |

Number of CSA Items—Operational

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AudioResponse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Composite | 1 | 3 | 0 | 4 | 0 | 0 | 2 | 10 |
| Composite-Discrete | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 4 |
| ExtendedText | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 24 |
| ExtendedText-Discrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| GridMS | 3 | 3 | 1 | 5 | 4 | 2 | 1 | 19 |
| GridMS-Discrete | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |
| GridSS-Discrete | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |
| InLineChoicelistMS | 9 | 9 | 8 | 13 | 7 | 4 | 2 | 52 |
| InLineChoicelistMS-Discrete | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 6 |
| InLineChoicelistSS | 15 | 7 | 9 | 4 | 13 | 11 | 7 | 66 |
| InLineChoicelistSS-Discrete | 2 | 2 | 2 | 1 | 0 | 1 | 0 | 8 |
| InlineTextChoices | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 5 |
| InlineTextChoices-Discrete | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 |
| InlineTextChoicesMS | 0 |  | 1 |  | 2 | 3 | 0 | 6 |
| MatchMS | 2 | 3 | 2 | 2 | 1 | 0 | 1 | 11 |
| MatchMS-Discrete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| MatchSS | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 4 |
| MatchSS-Discrete | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 4 |
| MCMS | 27 | 29 | 27 | 22 | 27 | 29 | 32 | 193 |
| MCMS-Discrete | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 9 |
| MCSS | 78 | 54 | 56 | 67 | 49 | 52 | 51 | 407 |
| MCSS-Discrete | 4 | 4 | 5 | 9 | 5 | 4 | 8 | 39 |
| ZoneMS | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 |
| ZoneSS | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 6 |
| ZoneSS-Discrete | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |
| ZonesSS | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 3 |
| Grand Total | 155 | 124 | 121 | 136 | 114 | 114 | 120 | 884 |

Number of CSA Items—Field Test

| Item Type | Grade 3 | Grade 4 | Grade 5 | Grade 6 | Grade 7 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AudioResponse | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |
| Composite | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 8 |
| ExtendedText | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 12 |
| GridMS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 6 |
| InLineChoicelistMS | 2 | 7 | 2 | 1 | 3 | 6 | 8 | 29 |
| InLineChoicelistSS | 3 | 3 | 7 | 2 | 4 | 11 | 12 | 42 |
| InlineTextChoicesMS | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |
| MatchMS | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 5 |
| MatchSS | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 5 |
| MCMS | 9 | 12 | 9 | 8 | 11 | 15 | 30 | 94 |
| MCSS | 17 | 23 | 19 | 14 | 17 | 25 | 56 | 171 |
| ZoneMS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |
| ZoneSS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |
| Grand Total | 34 | 52 | 42 | 31 | 38 | 64 | 116 | 377 |

Number of CAST Items—Operational

| Item Type | Grade 5 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- |
| Bar-PicturegraphMS | 3 | 0 | 0 | 3 |
| Composite | 16 | 18 | 23 | 57 |
| ExtendedText | 57 | 55 | 53 | 165 |
| GridMS | 34 | 42 | 44 | 120 |
| InlineChoiceListMS | 133 | 136 | 177 | 446 |
| InlineChoiceListSS | 19 | 3 | 4 | 26 |
| InLineChoicelistSS-Member | 10 | 3 | 3 | 16 |
| MatchMS | 37 | 33 | 25 | 95 |
| MatchSS | 2 | 1 | 3 | 6 |
| MCMS | 37 | 43 | 44 | 124 |
| MCSS | 255 | 241 | 247 | 743 |
| ZoneMS-Discrete | 13 | 7 | 0 | 20 |
| ZoneSS-Discrete | 9 | 8 | 0 | 17 |
| ZonesSS | 1 | 0 | 0 | 1 |
| Grand Total | 626 | 590 | 623 | 1839 |

Number of CAST Items—Field Test

| Item Type | Grade 5 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- |
| Composite | 4 | 6 | 2 | 12 |
| ExtendedText | 4 | 10 | 7 | 21 |
| FillInBlank | 0 | 1 | 0 | 1 |
| GridMS | 15 | 9 | 18 | 42 |
| InlineChoiceListMS | 26 | 28 | 19 | 73 |
| InlineChoiceListSS | 4 | 0 | 0 | 4 |
| MatchMS | 3 | 0 | 1 | 4 |
| MCMS | 11 | 9 | 15 | 35 |
| MCSS | 35 | 35 | 37 | 107 |
| Numeric | 0 | 0 | 1 | 1 |
| ZoneMS-Discrete | 0 | 1 | 0 | 1 |
| Grand Total | 102 | 99 | 100 | 301 |

Number of Interim CAST Items—Operational

| Item Type | Grade 5 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- |
| Composite | 6 | 4 | 4 | 14 |
| ExtendedText | 6 | 6 | 6 | 18 |
| GridMS | 13 | 6 | 4 | 23 |
| InlineChoiceListMS | 16 | 24 | 31 | 71 |
| InlineChoiceListSS | 6 | 1 | 0 | 7 |
| InLineChoicelistSS-Member | 2 | 0 | 0 | 2 |
| MCMS | 6 | 9 | 7 | 22 |
| MCSS | 34 | 39 | 44 | 117 |
| Grand Total | 89 | 89 | 96 | 274 |

Number of CAA for Science Performance Tasks (and Items)—Operational

| Item Type | Grade 5 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- |
| Composite Objective | 37 | 42 | 33 | 112 |
| GridMS | 1 | 1 | 1 | 3 |
| MatchMS | 8 | 10 | 11 | 29 |
| MatchSS | 5 | 2 | 3 | 10 |
| MCMS | 24 | 9 | 12 | 45 |
| MCSS | 203 | 196 | 197 | 596 |
| Grand Total | 278 | 260 | 257 | 795 |

Number of CAA for Science Performance Tasks (and Items)—Field Test

| Item Type | Grade 5 | Grade 8 | HS | Totals |
| --- | --- | --- | --- | --- |
| Composite Objective | 8 | 9 | 14 | 31 |
| MatchMS | 6 | 3 | 4 | 13 |
| MatchSS | 1 | 0 | 0 | 1 |
| MCMS | 6 | 6 | 2 | 14 |
| MCSS | 41 | 47 | 48 | 136 |
| Grand Total | 62 | 65 | 68 | 195 |

Number of Initial ELPAC Items—Operational

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | Grades 9–10 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MCSS | 4 | 13 | 6 | 29 | 12 | 12 | 76 |
| AudioResponse | 2 | 0 | 0 | 8 | 0 | 7 | 17 |
| ExtendedText | 24 | 12 | 7 | 1 | 2 | 0 | 46 |
| Grand Total | 30 | 25 | 13 | 38 | 14 | 19 | 139 |

Number of Summative ELPAC Items—Operational

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | Grades 9–10 | Grades 11–12 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AudioResponse | 54 | 64 | 71 | 72 | 86 | 85 | 80 | 512 |
| Composite Objective | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |
| ExtendedText | 40 | 43 | 45 | 12 | 12 | 18 | 14 | 184 |
| InlineChoiceListMS | 14 | 3 |  | 0 | 0 | 0 | 0 | 17 |
| MCSS | 114 | 184 | 226 | 210 | 215 | 255 | 231 | 1435 |
| Grand Total | 230 | 294 | 342 | 294 | 313 | 358 | 325 | 2156 |

Number of Summative ELPAC Items—Field Test

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | Grades 9–10 | Grades 11–12 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AudioResponse | 3 | 2 | 11 | 14 | 7 | 15 | 12 | 64 |
| ExtendedText | 28 | 18 | 13 | 3 | 3 | 2 | 0 | 67 |
| InlineChoiceListMS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |
| InlineTextChoices | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |
| MCSS | 13 | 17 | 16 | 44 | 45 | 49 | 29 | 213 |
| Totals | 47 | 37 | 41 | 61 | 55 | 66 | 41 | 348 |

Number of Interim ELPAC Items—Operational

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | Grades 9–10 | Grades 11–12 | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AudioResponse | 8 | 6 | 9 | 14 | 14 | 9 | 7 | 67 |
| Composite Objective | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |
| ExtendedText | 0 | 0 | 0 | 7 | 6 | 4 | 6 | 23 |
| MCSS | 26 | 36 | 35 | 26 | 29 | 26 | 33 | 211 |
| Grand Total | 36 | 42 | 44 | 47 | 49 | 39 | 46 | 303 |

Number of Summative ALT ELPAC Items—Operational

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | HS | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- |
| InlineChoiceListSS | 15 | 13 | 14 | 18 | 16 | 5 | 81 |
| MatchSS | 0 | 1 | 1 | 0 | 1 | 0 | 3 |
| MCSS | 31 | 28 | 25 | 37 | 41 | 19 | 181 |
| Grand Total | 46 | 42 | 40 | 55 | 58 | 24 | 265 |

Number of Summative ALT ELPAC Items—Field Test

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | HS | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- |
| InlineChoiceListSS | 8 | 9 | 4 | 5 | 0 | 20 | 46 |
| MatchSS | 1 | 0 | 0 | 1 | 0 | 2 | 4 |
| MCMS | 2 | 0 | 0 | 0 | 0 | 0 | 2 |
| MCSS | 33 | 23 | 25 | 9 | 10 | 48 | 148 |
| MCSSPartialCredit | 1 | 0 | 1 | 0 | 1 | 0 | 3 |
| Totals | 45 | 32 | 30 | 15 | 11 | 70 | 203 |

Number of Initial ALT ELPAC Items—Operational

| Item Type | Grade K | Grade 1 | Grade 2 | Grades 3–5 | Grades 6–8 | HS | Totals |
| --- | --- | --- | --- | --- | --- | --- | --- |
| InlineChoiceListSS | 5 | 6 | 4 | 4 | 6 | 6 | 31 |
| MCSS | 17 | 18 | 17 | 17 | 18 | 18 | 105 |
| Grand Total | 22 | 24 | 21 | 21 | 24 | 24 | 136 |

Glossary of Item Types

| Item Type | Description |
| --- | --- |
| AudioResponse | Requires the student to speak their response |
| Bar-PictureGraphMS, Bar-PictureGraphSS | These items present a bar graph to the student to manipulate the bar height to represent an answer. - Multiple Select (MS)—The student manipulates two or more graph bars. - Single Select (SS)—The student manipulates one graph bar. |
| Composite, Composite Objective | These items require a test taker to respond to a stimulus by using multiple item types in a single item with multiple response portions. Scoring is dependent on which item type combination is selected, and the raw weights for each part are combined to give an item score. |
| Extended Text | Essay/Writing Extended Response (WER) — A multiparagraph written response or essay; also referred to as the writing extended response (WER). |
| Graph | These items allow students to plot points, lines, multisegmented lines, or any combination of these on a graph. A Graph may have points or lines that appear when the graph first displays that the student cannot manipulate, or it may be interactive, and the student must manipulate them to respond. |
| GridMS, Grid SS | These items consist of a table with descriptions or characteristics, which the student then selects a box in a column or row for true-and-false or yes-or-no type of questions. - Multiple Select (MS)—The student marks two or more cells in a table. The question might only allow one selection per row or column, but it might also have no restrictions in the number of cells a student can mark. Single Select (SS)—The student marks a single cell in a table for credit. |
| InlineChoiceListMS, InlineChoiceListSS | These items consist of questions with a drop-down list of choices to fill in the blank. - Multiple Select (MS)—The student must fill multiple blanks from a drop-down list for credit. - Single Select (SS)—The student must fill a single blank from a drop-down list for credit. |
| InlineTextChoices, InlineTextChoicesMS | These items present a short passage or a paragraph that contains underlined words or phrases. These underlined words or phrases represent the choices a student can select. - Multiple Select (MS)—The student selects two or more terms or phrases. - Single Select (SS)—The student selects one term or phrase. |
| Interactive | These items require the student to manipulate a set of inputs within an interactive stimuli to provide custom output that students use to respond to multiple items or to keyboard entry their responses into table cells. |
| MatchMS, MatchSS | These items require the student to move objects such as words or images by selecting and dragging the objects into a specific order or to a specific location in a table, passage, or image. - Multiple Select (MS)—The student drags and drops two or more choices into the appropriate locations. - Single Select (SS)—The student drags and drops a single choice into the appropriate location. |
| MCMA, MCMS, MCSS, MCSS Partial Credit | These items consist of a question and list of choices; they may also include a stimulus or subset of a passage as the stimulus. - Multiple Attempt (Try-2) (MA)—The student makes an initial selection, and, if the response is incorrect, one option is removed leaving two remaining options from which to choose for a second attempt. - Multiple Select (MS)—The student must select all correct choices to receive credit. - Single Select (SS)—The student must select the one correct choice to receive credit. - Partial Credit—The student must respond to a stimulus by providing a direct response to the test examiner who then rates the response by assigning a weighted score, using the rubric provided in the DFA. |
| Numeric | The student responds by selecting a single-entry box with a numeric value. The numeric value may contain decimals or a slash line to represent a fraction. |
| ZoneMS, Zone SS | These items have answer choices that are predefined “hotspots” on an image, word, or phrase within a sentence. When the student selects a spot, the selection is highlighted, shaded, or outlined in red. - Multiple Select (MS)—The student selects two or more zones for credit. - Single Select (SS)—The student selects one zone for credit. |

## APPENDIX D—Scoring Guide

For Use by the Evaluation Team for RFS CN260003

### Overview

The California Department of Education (CDE) is issuing the Request for Submissions (RFS) to procure its next assessment contract for five administrations of the California Assessment of Student Performance and Progress (CAASPP) and English Language Proficiency Assessments for California (ELPAC) systems, collectively known as the California Assessment System, beginning March 1, 2027, and continuing through December 31, 2032. The purpose of this RFS is to identify a successful bidder with the capacity and expertise to successfully implement the California Assessment System. The submission consists of a scope of work with a transition plan, and the cost submission with a proposed budget.

This scoring guide describes the complete evaluation process—Phases I through III—including the evaluation and scoring criteria. Each submission will be evaluated to determine its responsiveness to the general requirements and components, as well as format and content requirements, as described in the RFS. This scoring guide will assist the CDE and the evaluation team in the process of fairly and accurately reviewing all eligible submissions to the RFS.

### Evaluation Process

The evaluation process is designed to determine the quality of the submissions in response to the RFS. That determination will be accomplished by the evaluation team’s participation in the evaluation process described in this scoring guide.

#### Phase I: Requirements Checklist

At the time of the submission opening, each submission will be checked for the presence or absence of required information in conformance with the requirements of the RFS. Submissions that do not provide requested information may be rejected as non-responsive at the discretion of the CDE.

Submissions that contain false or misleading statements, or that provide references that do not support an attribute or condition claimed by the proposer, shall be rejected at the discretion of the CDE.

In Phase I, the CDE will use the following checklist to verify that each of the requirements is included in the bidder’s submission. Submissions will be rated on a Yes/No basis. Receipt of a “No” on any of the requirements on the checklist may result in elimination of the submission from further consideration and review at the discretion of the CDE.

Within Phase I, the CDE reserves the right to require a bidder to remedy any obvious clerical or incidental errors on a submission. Bidders will be required to initial corrections. Submissions that fail to provide any of the required documentation will not advance to Phase II. One completed checklist for each bidder will be saved as documentation of Phase I of the evaluation process.

##### Requirements Checklist

Bidder: ___________________________________ Date Received: _____________

- Intent to Submit Delivery to the California Department of Education

  - Intent to Submit (Attachment 1) was received by the date and time specified in RFS Section 2.3, in accordance with RFS Section 2.6.

- Submission Delivery to the California Department of Education

  - One clearly marked ORIGINAL hardcopy submission (marked as “Original Copy”), ten (10) hard copies, and one electronic copy on a portable USB drive packaged and received by the specified deadline, February 12, 2026, by 1 p.m. PST at the California Department of Education as specified in RFS Section 3.

- Scope of Work – Each task identified in RFS Section 7, Scope of Work, must be addressed in the submission, including timelines provided for the accomplishment of each task.

  - Table of Contents

  - Task 1 – Comprehensive Plan and Schedule of Deliverables

  - Task 2 – Program Support Services

  - Task 3 – Technology Services

  - Task 4 – Assessment Development and Accessibility

  - Task 5 – Test Administration and Security

  - Task 6 – Scoring and Reporting

- Management and Staffing – As specified in RFS Section 3.1.3, the submission contains an Organization Structure and Personnel Resources section. The submission must:

  - Identify a management team that includes:

    - Project Manager

    - Fiscal Manager

    - Technology Manager

    - All other Key Personnel identified by the eligible bidder

  - Include résumés for:

    - Project Manager

    - Fiscal Manager

    - Technology Manager

    - Any other Key Personnel identified by the eligible bidder

  - Include the following requirements for any subcontractor(s):

    - A clear description of the proposed work for each subcontractor

    - Résumés for subcontractor key staff

    - A commitment letter for each proposed subcontractor

  - Include staff/subcontractor labor hours and organizational chart:

    - Staff Labor Hours by FY

    - Subcontractor Labor Hours by FY

    - Organization Chart

- Capacity and Experience – As specified in RFS Section 3.1.4, the submission contains a Capacity section. The submission must:

  - Acknowledge the bidder has at least three years, within the last five years, of full-time experience.

  - Describe the bidder’s capacity and experience.

  - Describe subcontractors’ capacity and ability to perform the work in which it is involved.

- Facilities and Resources – As specified in RFS Section 3.1.5, the submission contains a Facilities and Resources section. The submission must:

  - Describe the prime bidder’s company/business and its ownership structure.

  - Describe the prime bidder’s facilities, equipment, and technical capacity.

  - Describe the subcontractor’s facilities, equipment, and technical capacity.

  - Describe the location(s) and office(s) from which primary contract work will be performed.

  - Describe the software/ hardware that will be used in performance of the work outlined in RFS Section 7

  - Describe the facility and the staff to be located in Sacramento.

- Required Attachments/Forms – As specified in RFS sections 3.2 and 3.3, the submission must include the following correctly completed attachments and forms:

  - Attachment Checklist (RFS Attachment 2)

  - Bidder Certification Sheet (RFS Attachment 3)

  - Federal Certifications (RFS Attachment 4)

  - Iran Contracting Act Certification (RFS Attachment 5)

  - California Civil Rights Laws Certification (RFS Attachment 6)

  - Bidder References (RFS Attachment 7)

  - Subcontractor Commitment Letter(s)

  - Contractor Certification Clauses CCC 04/2017

  - Payee Data Record (STD. 204)

    - Payee Data Record Supplement (STD. 205), if applicable

  - Certificate of Good Standing or a separate paragraph that clearly states the eligible bidder’s legal status and evidence that it is legally constituted and qualified to do business with the State of California

  - GenAI Disclosure Notification, if applicable

  - Staffing Labor Hours (RFS Attachment 10A)

  - Cost Submission Summary by FY (RFS Attachment 10B)

  - Cost Submission Task Detail (RFS Attachment 10C)

- Results of Phase I: Requirements Checklist

  - Submission meets all Phase I requirements and may advance to Phase II. If “No” is selected, indicate which of the following conditions applies:

    - The requirements marked “No” in checklist above were not provided by the bidder as required by the RFS and as a result the bidder’s submission has been eliminated from further consideration.

    - The requirements marked “No” in checklist above were not correctly completed by the bidder as required by the RFS and as a result the bidder’s submission has been eliminated from further consideration.

#### Phase II: Submission and Cost Evaluation

Phase II consists of the following sequence: 1) submission evaluation; 2) cost evaluation review; and 3) scoring total. The details of these processes are set forth in the sections below.

##### Submission Evaluation

An evaluation panel will convene to evaluate the submissions using a consensus scoring process. A minimum of 240 out of 300 is required for a submission to advance to the cost evaluation.

###### RFS Section 7. Scope of Work, Task 1 – Comprehensive Plan and Schedule of Deliverables

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 1 including all subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 1.1	Schedule of Deliverables, Narrative Schedule and Timeline

- 1.2	Meetings

- 1.3	Coordination and Continuous Improvement

- 1.4	Records and Minutes

- 1.5	Web, Document, and Accessibility Standards

- 1.6	CDE Notification and Approval Requirements

- 1.7	Monthly Written Progress Reports

- 1.8	Transition of Contracts Plan

Task 1 Consensus score: <Your Score> out of 15 points possible

###### RFS Section 3.1. Submission Requirements, Task 1 – Comprehensive Plan and Schedule of Deliverables

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions below and the information requirements contained in Task 1 including subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 1 Consensus score: <Your Score> out of 10 points possible

Task 1 Combined consensus score: <Your Score> out of 25 points possible

###### RFS Section 7. Scope of Work, Task 2 – Program Support Services

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 2 including all subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 2.1	Coordinators

- 2.2	Administration Management System

- 2.3	Technical Assistance Center

- 2.4	Student Accessibility Tool

- 2.5	Internet Resource Sites

- 2.6	Trainings

- 2.7	Local Assessments: Interim Assessments and Formative

Assessment Tools

- 2.8	Data-Driven Improvement

Task 2 Consensus score: <Your Score> out of 25 points possible

###### RFS Section 3.1. Submission Requirements, Task 2 – Program Support Services

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 2 including all subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 2 Consensus score: <Your Score> out of 10 points possible

Task 2 Combined consensus score: <Your Score> out of 35 points possible

###### RFS Section 7. Scope of Work, Task 3 – Technology Services

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 3 including subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 3.1	California Assessment System Long-Term Technology Plan

- 3.2	California Assessment Delivery System

- 3.3	System Enhancements

Task 3 Consensus score: <Your Score> out of 25 points possible

###### RFS Section 3.1. Submission Requirements, Task 3 – Technology Services

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 3 including subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 3 Consensus score: <Your Score> out of 10 points possible

Task 3 Combined consensus score: <Your Score> out of 35 points possible

###### RFS Section 7. Scope of Work, Task 4 – Assessment Development and Accessibility

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 4 including all subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 4.1	Assessment Design and Development

- 4.2	Item and Task Development

- 4.3	Standard Setting

- 4.4	Test Administration System Familiarization

- 4.5	User-Friendly Informational Content

- 4.6	Analysis of Test Results

- 4.7	Item Banks

- 4.8	Activities in Support of Future Assessment Development

- 4.9	Accessibility

- 4.10	Accessibility Plan for Computer-Based Tests and Special Forms

- 4.11	Unlisted Resources

Task 4 Consensus score: <Your Score> out of 25 points possible

###### RFS Section 3.1. Submission Requirements, Task 4 – Assessment Development and Accessibility

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 4 including subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 4 Consensus score: <Your Score> out of 10 points possible

Task 4 Combined consensus score: <Your Score> out of 35 points possible

###### RFS Section 7. Scope of Work, Task 5 – Test Administration and Security

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 5 including all subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 5.1 	Administration Requirements

- 5.2 	Paper Tests

- 5.3 	Computer-Based Tests

- 5.4 	Test Security Plan Requirements

Task 5 Consensus score: <Your Score> out of 40 points possible

###### RFS Section 3.1. Submission Requirements, Task 5 – Test Administration and Security

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 5 including all subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 5 Consensus score: <Your Score> out of 10 points possible

Task 5 Combined consensus score: <Your Score> out of 50 points possible

###### RFS Section 7. Scope of Work, Task 6 – Scoring and Reporting

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 6 including all subtasks before assigning the consensus score.

- How well does the bidder’s submission address the requirements of the RFS?

- How well does the bidder’s submission meet the minimum requirements of and demonstrate its capability to meet the specifications of the requirements in the following subtasks:

- 6.1 	Scoring

- 6.2 	Analysis of Test Results

- 6.3 	Reporting Results to Local Educational Agencies

- 6.4 	Reporting to the CDE—Public Reporting Websites

- 6.5 	Data Files

- 6.6 	Secure File Transfer System

- 6.7 	Technical Report

- 6.8 	Other Analyses or Reports

- 6.9	Rescore Requests

Task 6 Consensus score: <Your Score> out of 50 points possible

###### RFS Section 3.1. Submission Requirements, Task 6 – Scoring and Reporting

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in Task 5 including subtasks before assigning the consensus score.

- To what extent do the proposed project staff have the organization, management capability, competency and expertise, and related experience to perform the task?

- To what extent do the proposed project staff have the personnel resources (e.g. hours) by fiscal year to perform the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, have the facilities, resources, equipment, technical capacity, and experience to perform the work required by the task?

- To what extent do the bidder and the bidder’s proposed subcontractor(s), if any, possess sufficient professional qualifications and experience for the task?

Section 3.1, Task 6 Consensus score: <Your Score> out of 10 points possible

Task 6 Combined consensus score: <Your Score> out of 60 points possible

###### RFS Section 3.1.3 Organization Structure and Personnel Resources

When evaluating the bidder’s submission for this section, please carefully consider the following questions and the requirements contained in Section 3.1.3 in relation to the overall submission before assigning the consensus score.

How well does the bidder’s submission:

- Include and meet the specifications of the requirements in RFS Section 3.1.3 Organization Structure and Personnel Resources?

- Identify, describe, and demonstrate that the assigned Project Manager meets or exceeds the requirements?

- Identify, describe, and demonstrate that the assigned Fiscal Manager meets or exceeds the requirements?

- Identify, describe, and demonstrate that the assigned Technology Manager meets or exceeds the requirements?

- Identify by name and position title all Key Personnel?

- Describe and demonstrate how the Key Personnel meet or exceed the requirements?

- Specify that the bidder will comply with the Changes to Key Personnel requirements?

- Provide resumes for the Project Manager, Fiscal Manager, Technology Manager, and all Key Personnel?

- Address the Subcontractor requirements?

- Describe and demonstrate that the proposed Key Personnel and Subcontractors possess the qualifications and experience to perform the work required by this project?

- Provide for allocation of sufficient labor hours per position per task and per fiscal year?

- Demonstrate a clear connection between proposed activities, by task/subtask, and labor hours?

- Provide an organization chart?

Section 3.1.3 Consensus score: <Your Score> out of 30 points possible

###### RFS Section 3.1.4 Capacity and Experience

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the requirements contained in RFS Section 3.1.4 in relation to the overall submission before assigning the consensus score.

How well does the bidder’s submission:

- Include and meet the specifications of the requirements in RFS Section 3.1.4 Capacity and Experience?

Section 3.1.4 Consensus score: <Your Score> out of 15 possible points

###### RFS Section 3.1.5 Facilities and Resources

When evaluating the bidder’s submission for this section, please consider carefully the following guiding questions and the information requirements contained in RFS Section 3.1.5 in relation to the overall submission before assigning the consensus score.

How well does the bidder’s submission:

- Include and meet the specifications of the requirements in RFS Section 3.1.5 Facilities and Resources?

Section 3.1.5 Consensus score: <Your Score> out of 15 possible points

After the completion of the submission evaluation, the evaluation team will enter the combined consensus scores for each task or section in the associated column on the Submission Scoring Sheet in Table 1.

Table 1. Submission Scoring Sheet

Bidder Name: _____________________________________________

| RFS Section | Requirement | Submission Possible Points | Submission Consensus Score |
| --- | --- | --- | --- |
| 7.1 | Comprehensive Plan and Schedule of Deliverables (Task 1) | 25 | TBD |
| 7.2 | Program Support Services (Task 2) | 35 | TBD |
| 7.3 | Technology Services (Task 3) | 35 | TBD |
| 7.4 | Assessment Development and Accessibility (Task 4) | 35 | TBD |
| 7.5 | Test Administration and Security (Task 5) | 50 | TBD |
| 7.6 | Scoring and Reporting (Task 6) | 60 | TBD |
| 3.1.3 | Organization Structure and Personnel Resources | 30 | TBD |
| 3.1.4 | Capacity and Experience | 15 | TBD |
| 3.1.5 | Facilities and Resources | 15 | TBD |
| N/A | Submission Total | 300 | TBD |

A maximum score of 300 points is possible on the submission evaluation. The required minimum points needed to advance to the cost evaluation is 240 (80%). Those submissions receiving less than the required minimum points will not receive further consideration. During this evaluation phase, the CDE reserves the right, at its sole discretion, to request clarification on any aspect of the submissions.

##### Cost Evaluation

For the cost evaluation review, the evaluation team will identify the total cost for the submission in RFS Attachment 10B.

The bidder with the lowest total cost gets 100% of the 150 points. Bidders with higher costs will receive fewer points based on their cost relative to the lowest cost.

For example, if the cost is worth 150 points and bidder A bids $1,000, bidder B bids $1,500, and bidder C bids $2,000, then bidder A will receive 100% of the 150 points possible. Bidder A’s cost is 67% of bidder B’s cost, so bidder B will receive 67% of 150 points which equals 100 points. Bidder A’s cost is 50% of bidder C’s cost, so bidder C will receive 50% of 150 points which equals 75 points. Table 2 presents this example with corresponding calculations.

Table 2. Cost Evaluation Calculation Example

| Eligible Bidder | Task X Low Bid/ Bidder Bid | Percent x Task X Points | Task X Points Earned |
| --- | --- | --- | --- |
| A | 1000/1000 | 1 x 150 | 150 |
| B | 1000/1500 | 0.67 x 150 | 100 |
| C | 1000/2000 | 0.5 x 150 | 75 |

##### Scoring of Submissions

The bidders’ submission scores will be added to the cost scores to calculate an overall score for each bidder. The bidder with the highest overall score, in accordance with this scoring guide, will be recommended by the CDE to the California State Board of Education (SBE), at a publicly noticed meeting, to participate in Phase III, negotiations of a contract.

Table 3. List of Submission Scores

| Submitter | Submission Score— 300 points possible | Cost Score—150 points possible | Overall Score | Submission Ranking |
| --- | --- | --- | --- | --- |
| Submitter Name | TBD | TBD | TBD | TBD |
| Submitter Name | TBD | TBD | TBD | TBD |
| Submitter Name | TBD | TBD | TBD | TBD |

#### Phase III: Recommendation and Contract Negotiations

The CDE will request approval from the SBE to begin contract negotiations with the successful bidder who passed the submission evaluations with the highest overall score. It is anticipated that this request will occur at the May 2026 SBE meeting.

Once the CDE receives approval from the SBE, staff from the CDE, SBE, and Department of Finance will commence contract negotiations. It is anticipated that contract negotiations will begin on June 3, 2026 (tentative) in Sacramento, California. The CDE reserves the right to conduct contract negotiations via teleconference or video conference. If, after such negotiations, the bidder fails to accept the state’s best and final offer, negotiations may be conducted with the bidder with the next highest score.

It is anticipated that the CDE will bring a recommendation to the SBE for approval of negotiated contract documents at the September 2026 SBE meeting.