recommended

recommended

recommended

and

or

District prepares Initial Study,  if DEIR needed, circulates Notice of Prep. (or if CEQA doc. previously approved decide if further CEQA doc. is nec. based upon avail. PhaseI/PEA info.)

Dist. prepares Draft Neg. Dec. or Draft EIR on Project-may include Response Action, (or if nec. subsequent, supplement or addendum to prior CEQA doc.) or DTSC is lead agency on separate Response Action CEQA doc.,  includes Phase I, PEA & DTSC infor.

Dist. provides notice of draft CEQA doc. availability & public comment Period/Intent to adopt Neg. Dec. or Notice of Completion of Draft EIR pursuant to CEQA

Dist. conducts draft CEQA Public Review/ Comment Period & State Clearinghouse circ. of CEQA doc. (30 days for Neg. Dec. 45 days  for DEIR), Dist. responds to DEIR comments

Dist. may conduct public Hearing on draft CEQA doc.

& may Approve* Neg. Dec. or Certify Final EIR

DTSC reviews PEA/ comments & w/in 30 cal. days of close of Dist.’s  PEA public review period DTSC  shall approve  PEA or disapprove PEA & inform Dist. of actions nec. to secure  PEA approval. Dist. takes such actions

DTSC approves PEA, determines No Further Action or Investigation

is required

DTSC approves PEA, determines Response Action/Further  Investigation is required

District may Approve* Project any time after CEQA doc. approval & File Notice of Determination w/in 5 working days

DTSC PEA PROCESS (may be done before, at the same time, or after project’s CEQA doc. approval*)

# CEQA PROCESS (may be done before, at the same time, or after DTSC’s PEA approval*)

## AB972  OPTION ‘A’   SEPARATE  PEA / CEQA PROCESS

# Per Ed. Code Section 17213.1 and California Department of Education Policies

Note that not all DTSC, CDE, CEQA or Education Code requirements or policies are shown on this chart, Districts may elect not to pursue a site at any time, and projects may be approved in phases

### CDE/SFPD interpretation of AB972, Ed Code 17213.1, italics indicate suggestions only, not in code

11/30/01

District implements Response Action under DTSC oversight

DTSC

certifies Response Action is completed

Dist. prepares cost est./ financial analysis of response action, assesses site benefits/suitability, obtains CDE Contingent Site Approval, prepares Response Action for approval under DTSC Voluntary Cleanup Agrmt., conducts Public Participation Plan, Dist. or DTSC completes CEQA for Resp. Action. DTSC notifies DSA if any design conditions are nec. to protect resp.action If nec. Dist. acquires site

Dist. may seek CDE final approvals after PEA is approved and CEQA (& if nec. Response Action) is/are completed

* When possible the district may wish to obtain DTSC’s PEA approval prior to

approving CEQA and  the project, or if the PEA is disapproved/modified, consider

if a subsequent or supplemental CEQA doc. and circulation  is necessary

Dist. provides

DTSC format Notice to immed. area residents prior to starting PEA field work & prepares  PEA

District  submits PEA to DTSC & at same time publishes newspaper notice & posts school site stating  PEA submittal  to DTSC & District  determination to make PEA available for review/ comment via Option ‘A’,

Notice offers to receive written comments for at least 30 cal. days starting on date published. Hearing notice shall include date/ location of public hearing & location where public may review PEA docs. (District should submit notice w/PEA to DTSC or otherwise advise DTSC of selection  of Option A)

Prior to receipt of public comments, DTSC informs Dist. if it is likely to disapprove PEA & any District action required to secure DTSC approval

Dist. may take action required for DTSC to approve the PEA during or after PEA comment period or hearing

Through the time of public hearing District makes available to the public the PEA, DTSC requested changes  & any DTSC  PEA correspondence

Dist. conducts PEA Public Hearing,

receives further comments

Dist. transmits copy of all PEA comments received to DTSC

Dist. should notify DTSC of close of review period

Dist. makes any PEA revisions made after the District’s PEA hearing available to the public