## Title Page
California Preschool Data Collection (CAPSDAC) Team Template & Responsible, Accountable, Consulted, and Informed (RACI) Chart
California Department of Education
June 2025
Notes: 1. The Contacts are an example of personnel that could comprise an agencies CAPSDAC data team. 2. The compiled Definitions and Quick Tips are tools to support an agency in developing their CAPSDAC data team and assigning roles for the RACI. 3. The RACI is a project management tool that suggests who fills what role for each task involved in developing a CAPSDAC Data Team and local CAPSDAC Data governance policy. An example is provided but each agency may choose their own tools or assign different tasks and roles based on the needs of their organization.

## Contacts
Example CAPSDAC Data Team Contacts
Name | Title | Organization | Email Address | Phone | Notes
Contact 1 | Executive Director/ Superintendent | Local Educational Agency (LEA) | contact1@example.com | 2025550100
Contact 2 | Program Director | LEA | contact2@example.com | 2025550200
Contact 3 | Legal | LEA | contact3@example.com | 2025550300
Contact 4 | Information Technology Specialist | LEA | contact4@example.com | 2025550400
Contact 5 | Student Information System (SIS) Data Steward | LEA | contact5@example.com | 2025550500
Contact 6 | Child Education Data Steward | LEA | contact6@example.com | 2025550600
Contact 7 | Early Education Program Staff | LEA | contact7@example.com | 2025550700
Contact 8 | SIS Coordinator | LEA | contact8@example.com | 2025550800
Contact 9 | Curriculum Coordinator | LEA | contact9@example.com | 2025550900
Contact 10 | Incident Result Coordinator | LEA | contact10@example.com | 2025551000
Contact 11 | Attendance Coordinator | LEA | contact11@example.com | 2022551100
Contact 12 | SIS Support | Vendor | contact12@example.com | 2025551200

## Definitions - T1
RACI Roles and Responsibilities (Table 1)
In general, the data coordinators and data stewards manage the data. Roles and responsibilities for these and other staff members are detailed in Tables 1 and 2.
Table 1: RACI definitions - Responsible, Accountable, Consulted and Informed
Role | Role Code | Definition
Responsible | R | This role completes the actual work and owns the problem; this role is the “Doer.” There can be multiple R’s.
Accountable | A | This role delegates, reviews, and approves the completed work and is held accountable for it; this role is the "final decision maker". There should only be one A.
Consulted | C | This role has information and/or feedback to complete the work; this role is “in the loop” as two-way communication occurs, usually between the “C” and the “R”. There can be multiple C’s.
Informed | I | This role is to be informed of progress and results. This role receives one-way communication, usually from the R; this role is "apprised" but is not involved in creating it. There can be multiple I’s.

## Definitions - T2
RACI Roles and Responsibilities (Table 2)
In general, the data coordinators and data stewards manage the data. Roles and responsibilities for these and other staff members are detailed in Tables 1 and 2.
Table 2: Definitions of Roles for CAPSDAC Data Team
Roles | Definition
Superintendent (Early Childhood Education (ECE) Executive Director) | These individuals are responsible for 1) communicating the importance of making local data governance a priority and 2) providing final approval of any policies and procedures related to student-level data for children receiving California State Preschool Program (CSPP) services.
Administrators (may be ECE Program Director) | These individuals are responsible for 1) communicating the importance of making local data governance a priority and 2) providing final approval of any policies and procedures related to student-level data for children receiving CSPP services.
Legal Staff | These individuals are responsible for providing legal advice regarding areas such as student data
Information Technology Specialists | These individuals provide technical expertise on system security and the Student Information System (SIS) and or child data systems (e.g., Aeries, Hubbe, KinderSystems, etc.)
Student Information System (SIS) Data Stewards | These individuals are the staff most familiar with child enrollment and demographic information in the SIS.
Child Education Data Stewards | These individuals are the staff most familiar with children in preschool through Kindergarten interconnectivity in data systems (e.g., SEIS, Migrant, CPARIS)
Early Education Program Staff | These individuals provide expertise on the CSPP data (e.g., current data collection methods and interconnectability)
Student Information System (SIS) Coordinator | These individuals are responsible for the coordination of the SIS for the agency
Student Information System (SIS) Support (e.g. Vendor) | These individuals are contracted personnel, such as software vendors, who support the data input into the SIS for the agency
Curriculum Coordinator | These individuals are staff who coordinate curriculum for any grade level for the agency
Incident Result Coordinator | These individuals are staff whose responsibility is tracking incidents and incident results, including those that do and do not result in suspension or expulsion, for the agency
Attendance Coordinator | These individuals are staff whose responsibility is tracking attendance at any grade level for the agency

## Quick Tips
Quick Tips for Optimizing your RACI Chart
How to Build a RACI Chart: (See Example)
1. Enter all project roles or team member names across the top row.
2. List all tasks, milestones, and decisions down the left column.
3. For each task, assign a responsibility value to each role or person on the team.
In a best-case scenario, the Data Team would meet to walk through the role assignments on each task.
Make sure all staff represented on your RACI chart have acknowledged and agreed to the roles and responsibilities you’ve laid out.
More importantly, you want to check that your matrix eliminates any further project confusion.
Recommendations for Meeting Efficiency
- Align the tasks in your RACI chart with your project plan so there is no confusion about details and due dates.
- Be sure to assign the proper team members to the task and send calendar reminders.
- Keep RACI definitions in your document or local calendar
Once your RACI chart is complete, review it to be sure it follows these simple rules:
1. Every task has at least one Responsible person.
2. There is only one Accountable party assigned to each task to allow for clear decision-making.
3. No team members are overloaded with too many Responsible tasks.
4. Every team member has a role on each task. (It is not uncommon for some folks to be Informed on most tasks.)

## RACI Chart 1.0
EXAMPLE CAPSDAC RACI CHART
1.0 Planning for Transition to Updated CAPSDAC
Roles/Steps Involved in CAPSDAC Submission | Executive Director/ Superintendent | Program Director | Legal | Information Technology Specialists | Student Information System Data Stewards | Child Education Data Stewards | Early Education Program Staff | Student Information System Coordinator | Curriculum Coordinator | Incident Result Coordinator | Attendance Coordinator | Student Information System Support (Vendor)
1.1 Develop a high-level system governance plan that includes ethically responsible and legally compliant steps for data gathering, data management, data security, system management, system access, and risk management. | A | R | C | C | C | C | I | I | I | I | I | I
1.2 Communicate the plan as a priority | A | R | I | C | I | I | I | I | I | I | I | I
1.3 Approve policies and procedures to be implemented by the Local Educational Agency (LEA) | A | C | R | C | I | C | I | I | I | I | I | I
1.4 Provide administrative support (designate staff and financial resources) to implement, enforce and maintain these policies and procedures | A | R | R | C | I | R | I | I | I | I | I | I
1.5 Review LEA data privacy and security policies to ensure compliance with state and federal privacy laws | A | C | R | R | I | R | R | R | I | I | I | I
1.6 Provide technical support to implement an effective security plan | A | C | C | R | I | R | I | I | I | I | I | I
1.7 Ensure protocols are established for data security and privacy | A | R | C | R | I | C | I | C | I | I | I | I
1.8 Provide expertise on specific data that should be submitted to the system | I | A | I | C | C | R | C | C | C | C | C | C
1.9 Provide details on the existing process for student data maintenance | A | C | I | I | R | R | C | C | C | C | C | C
1.10 Contribute to the development of a collaborative process for student data maintenance. | A | C | I | I | R | R | C | C | R | R | R | C
1.11 Provide data security training for all staff who interact with early childhood education staff, child, and family data and the Student Information System (SIS). | A | R | I | I | I | R | C | C | I | I | I | I

## RACI Chart 2.0
EXAMPLE CAPSDAC RACI CHART
2.0 Preparing for System Integration
Roles/Steps Involved in CAPSDAC Submission | Executive Director/ Superintendent | Program Director | Legal | Information Technology Specialists | Student Information System Data Stewards | Child Education Data Stewards | Early Education Program Staff | Student Information System Coordinator | Curriculum Coordinator | Incident Result Coordinator | Attendance Coordinator | Student Information System Support (Vendor)
2.1 Form a cross-functional team representing both the early education and student information systems that meets on a regular basis | A | R | I | C | I | C | C | C | I | I | I | I
2.2 Ensure that the data in each system are well defined and understood to ensure exchanging like data | A | R | I | R | C | R | C | R | C | C | C | C
2.3 Decide which data needs to be exchanged between the systems for local use and state and federal reporting. | A | R | R | R | C | C | C | R | C | C | C | C
2.4 Define source system for different data that need to be exchanged. | A | I | I | R | C | C | C | R | C | C | C | C
2.5 Document the current processes that each system uses to update any shared data. | A | R | I | R | C | R | C | R | C | C | C | C
2.6 Analyze and refine current processes and identify any redundant processes, or processes that should change to make the process more efficient. | A | R | I | R | C | C | C | R | C | C | C | C
2.7 Develop a new, collaborative process for maintaining data for students in early education between the TK-12 SIS staff and CSPP data stewards. | A | R | I | C | I | I | I | C | I | I | I | I
2.8 Ensure all staff understand their roles and responsibilities in the new process and are properly trained. | A | R | I | I | I | I | I | I | I | I | I | I

## RACI Chart 3.0
EXAMPLE CAPSDAC RACI CHART
3.0 Child Education Stewards
Roles/Steps Involved in CAPSDAC Submission | Executive Director/ Superintendent | Program Director | Legal | Information Technology Specialists | Student Information System Data Stewards | Child Education Data Stewards | Early Education Program Staff | Student Information System Coordinator | Curriculum Coordinator | Incident Result Coordinator | Attendance Coordinator | Student Information System Support (Vendor)
3.1 Contribute to the development of a collaborative process for student data maintenance. | I | A | I | C | C | R | C | R | C | C | C | C
3.2 Provide expertise on child education business rules (laws, regulations, or local policies) that may affect the population of student data for children in CSPP. | A | I | R | I | C | C | R | C | C | C | C | C
3.3 Schedule training sessions and set up meetings. | I | A | I | C | I | R | R | R | I | I | I | I